## Sheet2
IPMC ¦ All Questions
No. | Questions | Answer A | Answer B | Answer C | Answer Correct | Feedback | Questions Ar | Answer A Ar | Answer B Ar | Answer C Ar | Answer Correct Ar | Feedback Ar | Chapter | Process Group | Free Quiz | Exam No. | Column1
1 | You have been appointed as a project manager for a new project. After several months, you find that the accounting department has reject all charges because the project was not approved. What should the project manager have done to prevent this? | Obtained the fund needed to start the project | Planned the resources necessary to start the project | Verified that the business case was authorized by the project initiator | Get the project charter approval from the project sponsor | The sponsor or initiator of the project Is responsible to establish (approve and issue) the charter and can take the help of the prospect project manager to develop it. The project manager should obtain the project charter approval from the project sponsor because the project charter is a document that formally authorizes the existence of a project al d provides the project manager with the authority to apply organizational resources to project activities. [PMBOK 6th edition page, 75]. | لقد تم تعيينك كمدير مشروع لمشروع جديد. بعد عدة أشهر ، تجد أن قسم المحاسبة قد رفض جميع المطالبات المالية لأن المشروع لم تتم الموافقة عليه. ما الذي كان يجب على مدير المشروع فعله لمنع ذلك؟ | الحصول على الأموال اللازمة لبدء المشروع | تخطيط الموارد اللازمة لبدء المشروع | التحقق من اعتماد مستند حالة اعمال المشروع من قبل بادئ المشروع | الحصول على موافقة ميثاق المشروع من راعي المشروع | يكون الراعي أو البادئ بالمشروع مسؤولاً عن إنشاء (الموافقة وإصدار) الميثاق ويمكنه الاستعانة بمدير المشروع المحتمل لتطويره. يجب أن يحصل مدير المشروع على موافقة ميثاق المشروع من الجهة الراعية للمشروع لأن ميثاق المشروع هو مستند يصرح رسميًا بوجود مشروع ، وهو ما يمنح مدير المشروع السلطة لتطبيق الموارد التنظيمية على أنشطة المشروع. [PMBOK الطبعة السادسة ، الصفحة 75] | 140 | 2 | False | "17" | Ahmad
2 | A project progressing on time and within budget is 40 days away from achieving its main milestone. The project manager then learns that a key component to achieve this milestone will be unavailable for 60 days. What should the project manager do? | Send an amended progress report to all stakeholders. | Notify stakeholders at the next project status meeting. | Revise the risk management plan. | Update the issue log. | Because ( milestone will be unavailable for 60 days.) This Is an example of an issue and should be documented In the issue log. The Issue log will help the project manager effectively track and manage Issues, ensuring that they are investigated and resolved. [PMBOK 6th edition Page, 96] | يتقدم المشروع في الوقت المحدد وفي حدود الميزانية على بعد 40 يومًا من تحقيق احد الاحداث الرئيسية بالمشروع. يعلم مدير المشروع بعد ذلك أن المكون الرئيسي لتحقيق هذا الإنجاز لن يكون متاحًا لمدة 60 يومًا. ماذا يجب أن يفعل مدير المشروع؟ | إرسال تقرير مرحلي معدل إلى جميع أصحاب المصلحة. | إخطار أصحاب المصلحة في اجتماع حالة المشروع التالي. | مراجعة خطة إدارة المخاطر. | القيام بتحديث سجل المشكلة. | بسبب (لن تكون المرحلة الرئيسية متاحة لمدة 60 يومًا.) هذا مثال على مشكلة ويجب توثيقها في سجل الأحداث. سيساعد سجل الأحداث مدير المشروع على تتبع المشكلات وإدارتها بشكل فعال ، مما يضمن التحقيق فيها وحلها. [PMBOK الطبعة السادسة ، الصفحة 96] | 140 | 4 | False | "16" | Ahmad
3 | You are a project manager in an Construction project. During the work, an unexpected resource shortage occurs. What should the project manager do? | Perform a qualitative risk analysis | Risk categorization | Risk probability and impact assessment | Refer to the risk register and inform key stakeholders | As an unexpected power outage occurs, the project manager should first Refer to the risk register and inform key stakeholders to handle this scenario. Risk categorization and Risk probability and Impact assessment are Tools & Techniques in Perform a qualitative risk analysis process, therefore they can be excluded. [PMBOK 6th edition Page, 453] | أنت مدير مشروع في مشروع بناء. أثناء العمل ، يحدث نقص غير متوقع في الموارد. ماذا يجب أن يفعل مدير المشروع؟ | القيام بإجراء تحليل نوعي للمخاطر | تصنيف المخاطر | تقييم احتمالية المخاطر الأثر | الرجوع إلى سجل المخاطر وإبلاغ أصحاب المصلحة الرئيسيين | عند حدوث انقطاع غير متوقع للتيار الكهربائي ، يجب على مدير المشروع الرجوع أولاً إلى سجل المخاطر وإبلاغ أصحاب المصلحة الرئيسيين للتعامل مع هذا السيناريو. تصنيف المخاطر واحتمالية المخاطر وتقييم الأثر هي أدوات وتقنيات في إجراء عملية تحليل مخاطر نوعية ، وبالتالي يمكن استبعادها. [PMBOK الطبعة السادسة ، الصفحة 453] | 147 | 5 | False | "20" | Ahmad
4 | The customer wants to remove certain characteristics from the product. The project manager submits a change request which is approved by the change control board (CCB). What should the project manager do next? | Update the risk register. | Update the project charter. | Update the issue log. | Update the project management plan. | The project management plan should be updated after a change request takes approval by CCB. [PMBOK 6th edition Page, 120] | يريد العميل إزالة خصائص معينة من المنتج. يقدم مدير المشروع طلب التغيير الذي تمت الموافقة عليه من قبل لجنة التحكم في التغيير (CCB). ماذا يجب أن يفعل مدير المشروع بعد ذلك؟ | تحديث سجل المخاطر. | تحديث ميثاق المشروع. | قم بتحديث سجل المشكلة. | تحديث خطة إدارة المشروع. | يجب تحديث خطة إدارة المشروع بعد أن يأخذ طلب التغيير موافقة لجنة التحكم في التغيير. [PMBOK الطبعة السادسة ، الصفحة 120] | 140 | 5 | False | "16" | Ahmad
5 | A project manager wants to recruit another team member to replace an engineer who retired. What document should capture this change? | Ground rules | Organizational process Assets. | Project management plan. | Responsibility assignments matrix (RAM) | Responsibility assignments matrix RAMS are used within the group to designate roles, responsibilities, and levels of authority for specific activities. The matrix format shows all activities associated with one person and alt people associated with one activity. This also ensures that there is only one person accountable for each task to avoid confusion about who is ultimately in charge or has authority for the work. [PMBOK 6th edition Page, 317] | يريد مدير المشروع تعيين عضو آخر في الفريق ليحل محل مهندس متقاعد. ما هي الوثيقة التي يجب أن تلتقط هذا التغيير؟ | القواعد الأساسية | أصول العمليات التنظيمية. | خطة إدارة المشروع. | مصفوفة تعيين المسؤوليات (RAM) | مصفوفة تعيين المسؤوليات تُستخدم داخل المجموعة لتعيين الأدوار والمسؤوليات ومستويات السلطة لأنشطة محددة. يُظهر تنسيق المصفوفة جميع الأنشطة المرتبطة بشخص واحد وأشخاص بديل مرتبطين بنشاط واحد. يضمن هذا أيضًا أن يكون هناك شخص واحد فقط مسؤول عن كل مهمة لتجنب الالتباس حول من هو المسؤول في النهاية أو الذي لديه السلطة على العمل. [PMBOK الطبعة السادسة ، الصفحة 317] | 145 | 3 | False | "19" | Ahmad
6 | While creating the probability and impact matrix, what should the project manager and his team consider to support the project risk analysis? | Project scope and project deliverables. | Project quality and resources. | Contingency reserve for budget and schedule. | Possible effects on the objectives of the project. | The most important element that should the team and project manager consider while creating the probability and Impact matrix Is the Possible effects on the objectives of the project by taking the highest priority level regardless of which objective Is affected. [PMBOK 6th edition page, 425] | أثناء إنشاء مصفوفة الاحتمالات والتأثير ، ما الذي يجب على مدير المشروع وفريقه النظر فيه لدعم تحليل مخاطر المشروع؟ | نطاق المشروع وتسليمات المشروع. | جودة المشروع والموارد. | احتياطي الطوارئ للميزانية والجدول الزمني. | التأثيرات المحتملة على أهداف المشروع. | أهم عنصر يجب على الفريق ومدير المشروع مراعاته أثناء إنشاء مصفوفة الاحتمالات والأثر هو التأثيرات المحتملة على أهداف المشروع من خلال اتخاذ أعلى مستوى من الأولوية بغض النظر عن الهدف المتأثر. [PMBOK الطبعة السادسة ، الصفحة 425] | 144 | 3 | False | "16" | Ahmad
7 | You are a project manager in a construction project. The project is ahead of schedule and under budget. A key stakeholder suggests a change to include a value-added feature that wouldn't impact project schedule and cost. What should you do next? | Advise the stakeholder that, since the project is under budget. the feature will be added | Advise the stakeholder that changes shouldn't be implemented when a project is behind schedule. | Update the project management plan to include the new feature. | Evaluate the change's impact with the project team. | The change does not Impact the schedule and cost but the project manager should evaluate the change's impact on the other constrains with the project team. [PMBOK 6th edition page, 90] | أنت مدير مشروع في مشروع بناء. المشروع متقدم بالجدول الزمني وتحت الميزانية المحددة. يقترح أحد أصحاب المصلحة الرئيسيين إجراء تغيير ليشمل ميزة ذات قيمة مضافة لن تؤثر على جدول المشروع وتكلفته. ماذا يجب ان تفعل بعد ذلك؟ | إبلاغ أصحاب المصلحة بأنه ، بما أن المشروع تحت الميزانية. ستتم إضافة الميزة | أخبر أصحاب المصلحة بأنه لا ينبغي تنفيذ التغييرات عندما يتأخر المشروع عن الجدول الزمني. | القيام بتحديث خطة إدارة المشروع لتضمين الميزة الجديدة. | القيام بتقييم تأثير التغيير مع فريق المشروع. | لا يؤثر التغيير على الجدول الزمني والتكلفة ولكن يجب على مدير المشروع تقييم تأثير التغيير على القيود الأخرى مع فريق المشروع. [PMBOK الطبعة السادسة ، الصفحة 90] | 140 | 4 | False | "17" | Ahmad
8 | If the project deliverables didn't meet the agreed-upon acceptance criteria. What should the project manager reference to verity this with the contractor? | Quality log | Request for proposal (RFP). | Procurement management plan | Statement of work (SOW). | The SOW Include 1. Description of the procurement item, 2. Specifications, quality requirements and performance metrics, 3. Description of collateral services required, and 4. Acceptance methods and criteria. [PMBOK 6th edition page. 481] | إذا كانت مخرجات المشروع لا تلبي معايير القبول المتفق عليها. ما الذي يجب أن يشير إليه مدير المشروع بصدق هذا مع المقاول؟ | سجل الجودة | مستند طلب مقترح (RFP). | خطة إدارة المشتريات | بيان العمل بالمشروع (SOW). | يتضمن بيان العمل 1. وصف بند الشراء ، 2. المواصفات ومتطلبات الجودة ومقاييس الأداء ، 3. وصف الخدمات الإضافية المطلوبة ، و 4. طرق ومعايير القبول. [PMBOK الطبعة السادسة ، الصفحة 481] | 148 | 3 | False | "18" | Ahmad
9 | In your project, the Schedule Performance Index SPI is 0.7, and Cost Performance Index CPI 1.1. You analyzed the baseline and decided to return the schedule back to meet the baseline. You will: | Terminate the project. | Check with your sponsor. | Check tasks which can be removed from baseline. | Check options of crashing or fast-tracking the project. | SPI = 0.7 and CPI = 1.1 mean that the [Project is behind schedule and under budget. In this case, the project manager should Crash the project to meet the baseline. [PMBOK 6th edition page.263] | في مشروعك ، مؤشر أداء الجدول الزمني SPI هو 0.7 ، ومؤشر أداء التكلفة CPI 1.1. لقد قمت بتحليل خط الأساس وقررت إرجاع الجدول الزمني مرة أخرى ليتوافق مع خط الأساس. سوف: | إنهاء المشروع. | تحقق مع الراعي الخاص بك. | تحقق من المهام التي يمكن إزالتها من الأساس. | تحقق من خيارات حشد الموارد أو التتبع السريع للمشروع. | SPI = 0.7 و CPI = 1.1 يعني أن [المشروع متأخر عن الجدول الزمني وتحت الميزانية المحددة. في هذه الحالة ، يجب على مدير المشروع حشد موارد المشروع لتلبية خط الأساس المرجعي المعتمد. [الطبعة السادسة ، الصفحة 263 PMBOK] | 142 | 5 | False | "17" | Ahmad
10 | An experienced engineer is hired to supervise a subcontractor hired for a project. The experienced engineer uses an effective cost control technique, but it is not the agreed-upon technique for the project. This causes conflicts with the integration group reconciling the monthly reports. What should the project manager do? | Force the new employee to follow the agreed-upon technique. | Initiate a change request to resolve the issue. | Search for solutions that are similar to the existing technique. | Emphasize the advantage of the new method and change the technique with which costs are managed. | The experienced engineer uses an effective cost control technique, so the project manager should emphasize the advantage of the new method and change the technique with which costs are managed. The option (initiate a change request to resolve the issue) not correct because no need to issue a change request to solve this issue. The option (Search for solutions that are similar to the existing technique) not correct because the experienced engineer uses an effective cost control technique. The option (Force the new employee to follow the agreed upon technique) will Increase the conflict and will not solve the issue. [PMBOK 6th edition. Page 257] | يتم تعيين مهندس متمرس للإشراف على مقاول من الباطن تم تعيينه لمشروع. يستخدم المهندس المتمرس تقنية فعالة للتحكم في التكلفة ، ولكنها ليست التقنية المتفق عليها للمشروع. يتسبب هذا في حدوث تعارض مع مجموعة التكامل التي تقوم بتسوية التقارير الشهرية. ماذا يجب أن يفعل مدير المشروع؟ | اجبار الموظف الجديد على اتباع الأسلوب المتفق عليه. | البدء في طلب التغيير لحل المشكلة. | البحث عن حلول مشابهة للتقنية الحالية. | التأكيد على ميزة الطريقة الجديدة وتغيير التقنية التي تدار بها التكاليف. | يستخدم المهندس المتمرس تقنية فعالة للتحكم في التكلفة ، لذلك يجب على مدير المشروع التأكيد على ميزة الطريقة الجديدة وتغيير التقنية التي تدار بها التكاليف. خيار (بدء طلب تغيير لحل المشكلة) غير صحيح لأنه لا داعي لإصدار طلب تغيير لحل هذه المشكلة. خيار (البحث عن حلول مشابهة للتقنية الحالية) غير صحيح لأن المهندس المتمرس يستخدم تقنية فعالة للتحكم في التكلفة. سيؤدي خيار (إجبار الموظف الجديد على اتباع الأسلوب المتفق عليه) إلى زيادة التعارض ولن يحل المشكلة. [PMBOK الطبعة السادسة ، الصفحة 257] | 143 | 5 | False | "18" | Ahmad
11 | A project manager updating a dashboard monthly with information on the project's performance using project management information system (PMIS). Which of the following communication methods describes this? | Manual communication | Interactive Communication. | Informal communication. | Pull Communication. | Dashboards help the Internal and external stakeholders to get project information any time. its example of pull communication. [PMBOK 6th edition. Page 374] | يقوم مدير المشروع بتحديث لوحة القيادة شهريًا بمعلومات عن أداء المشروع باستخدام نظام معلومات إدارة المشروع (PMIS). أي من طرق الاتصال التالية تصف هذا؟ | الاتصال اليدوي | التواصل التفاعلي. | التواصل غير الرسمي. | سحب الاتصال. | تساعد لوحات المعلومات أصحاب المصلحة الداخليين والخارجيين في الحصول على معلومات المشروع في أي وقت. مثاله على سحب الاتصال. [PMBOK الطبعة السادسة ، الصفحة 374] | 146 | 3 | False | "16" | Ahmad
12 | During project closure and transferring of the completed project deliverables to the operation department, the project manager discovers that an audit report from an early project phase is missing. What should the project manager do? | Remove the audit report from the required project documents and update the project management plan. | Ask the operation department representative to accept the project without the audit report. | Complete project closure and update the OPA | Inform the operation department representative about the missing audit report. | Ethically, the project manager must Inform the operation department representative about the missing audit report. [PMBOK 6th edition. Page 121] | أثناء إغلاق المشروع ونقل تسليمات المشروع المكتملة إلى قسم التشغيل ، يكتشف مدير المشروع أن تقرير تدقيق من مرحلة مبكرة من المشروع مفقود. ماذا يجب أن يفعل مدير المشروع؟ | القيام بإزالة تقرير المراجعة من مستندات المشروع المطلوبة وقم بتحديث خطة إدارة المشروع. | الطلب من ممثل قسم العمليات قبول المشروع بدون تقرير المراجعة. | استكمال إغلاق المشروع وتحديث اصول العمليات التنظيمية | إبلاغ ممثل إدارة العمليات بتقرير التدقيق المفقود. | أخلاقياً ، يجب على مدير المشروع إبلاغ ممثل إدارة العمليات بتقرير التدقيق المفقود. [PMBOK الطبعة السادسة ، الصفحة 121] | 140 | 6 | False | "16" | Ahmad
13 | A project manager has received reports from a supplier that he is over capacity, which may delay his delivery. What should the project manager update next? | Schedule Baseline. | Stakeholder engagement plan. | Issue log. | Risk register. | Since the report show that the delivery may delayed, so the project manager should update the risk register then perform analysis to assess the impact of this delay on the project. [PMBOK 6th edition. Page 453] | تلقى مدير المشروع تقارير من أحد الموردين تفيد بتجاوز طاقته ، مما قد يؤخر تسليمه. ما الذي يجب على مدير المشروع تحديثه بعد ذلك؟ | اعادة جدولة خط الأساس المرجعي المعتمد للجدول الزمني. | خطة إشراك أصحاب المصلحة. | سجل المشكلة. | سجل المخاطر. | نظرًا لأن التقرير يوضح أن التسليم قد يتأخر ، لذلك يجب على مدير المشروع تحديث سجل المخاطر ثم إجراء تحليل لتقييم تأثير هذا التأخير على المشروع. [PMBOK الطبعة السادسة ، الصفحة 453] | 147 | 5 | False | "19" | Ahmad
14 | During the kick-off meeting, who should present the executing strategy of the project? | Project Management Team | Project Sponsor | Directive PMO | Project manager | The project manager is the responsible to presents the executing strategy of the project, and the sponsor responsible to present the organization strategy. | خلال الاجتماع الافتتاحي لإنطلاق المشروع ، من يجب أن يقدم الإستراتيجية التنفيذية للمشروع؟ | فريق إدارة المشروع | راعي المشروع | مكتب ادارة المشاريع الموجه | مدير المشروع | مدير المشروع هو المسؤول عن تقديم الاستراتيجية التنفيذية للمشروع ، والراعي المسؤول عن تقديم استراتيجية المنظمة. | 140 | 4 | False | "18" | Ahmad
15 | You are managing a project that is in its first month of execution. In one of the meetings, a key stakeholder asks for some changes to be made in the ongoing work. The stakeholder is asking for the changes to be implemented immediately. You realize that the changes being asked for will require update the Project Management Plan and the Scope baseline, which have already been baselined. As a Project manager, which is the best course of action? | Make the changes as they are being asked for by a key stakeholder | Refuse to make the changes as it is a deviation from approved | Scope Analyze the impact of the changes on triple constraints | Generate a change request and submit it to Integrated change control | Any changes being asked for or requested to any approved plan need to be formally reviewed by the Change Control Board. [PMBOK 6th edition. Page 113] | أنت تدير مشروعًا في أول شهر من تنفيذه. في أحد الاجتماعات ، طلب أحد أصحاب المصلحة الرئيسيين إجراء بعض التغييرات في العمل الجاري. يطلب صاحب المصلحة تنفيذ التغييرات على الفور. أنت تدرك أن التغييرات المطلوبة ستتطلب تحديث خطة إدارة المشروع وخط الأساس للنطاق ، اللذين تم تحديدهما بالفعل. كمدير مشروع ، ما هو أفضل مسار للعمل؟ | القيام بإجراء التغييرات كما يطلبها أحد أصحاب المصلحة الرئيسيين | رفض إجراء التغييرات لأنه يعد انحرافًا عن الموافقة | تحليل تأثير التغييرات بالنطاق على القيود الثلاثية | إنشاء طلب تغيير وإرساله إلى عملية التحكم المتكامل في التغيير | يجب مراجعة أي تغييرات يتم طلبها أو طلبها على أي خطة معتمدة رسميًا من قبل لجنة التحكم في التغيير. [PMBOK الطبعة السادسة ، الصفحة 113] | 140 | 5 | False | "17" | Ahmad
16 | After stakeholders in a company's sales department examined all the deliverables, they state that there has been a change in the company strategy. Therefore, important changes must be made to the requirements. The project manager believes that these changes make the deliverables unstable. What should the project manager do? | Evaluate and incorporate the changes to the project management plan to start executing them. | Request the details about the new requirements. evaluate them with the project team. and recommend whether to continue or close the project. | Evaluate the impact on the project. coordinate with the sponsor and close the project. | Request that the stakeholders specify the new requirements and present them to the change control board (CCB). | Since the changes are Important and MUST be made to the requirements so the PM need to make it. Any changes In project requirement can impact the baseline will require formal change request to take the approval from CCB. The project manager should request the stakeholders to specify the new requirements and present them to the change control board (CCB). Options of implement the changes without the approval of CCB are not correct . Also close the project after evaluate the Impact on project is not correct. [PMBOK 6th edition. Page. 167] | بعد أن قام أصحاب المصلحة في قسم مبيعات الشركة بفحص جميع التسليمات ، ذكروا أنه كان هناك تغيير في استراتيجية الشركة. لذلك ، يجب إجراء تغييرات مهمة على المتطلبات. يعتقد مدير المشروع أن هذه التغييرات تجعل النواتج غير مستقرة. ماذا يجب أن يفعل مدير المشروع؟ | تقييم ودمج التغييرات في خطة إدارة المشروع للبدء في تنفيذها. | طلب تفاصيل المتطلبات الجديدة. تقييمها مع فريق المشروع. والتوصية بالمتابعة أو إغلاق المشروع. | تقييم الأثر على المشروع. التنسيق مع الراعي وإغلاق المشروع. | اطلب من أصحاب المصلحة تحديد المتطلبات الجديدة وتقديمها إلى لجنة التحكم في التغيير (CCB). | نظرًا لأن التغييرات مهمة ويجب إجراؤها وفقًا للمتطلبات ، لذلك يحتاج مدير المشروع إلى إجرائها. أي تغييرات في متطلبات المشروع يمكن أن تؤثر على خط الأساس المرجعي المعتمد سيتطلب طلب تغيير رسمي لأخذ الموافقة من لجنة التحكم في التغيير. يجب على مدير المشروع أن يطلب من أصحاب المصلحة تحديد المتطلبات الجديدة وتقديمها إلى لجنة التحكم في التغيير (CCB). خيارات تنفيذ التغييرات دون موافقة لجنة التحكم في التغيير غير صحيحة. كما أغلق المشروع بعد تقييم الأثر على المشروع غير صحيح. [PMBOK الطبعة السادسة ، الصفحة 167] | 141 | 5 | False | "18" | Ahmad
17 | You are in the execution phase of a project to build a building. The project team develops a new response for an existing risk that will reduce the schedule by 20 days. What document should the project manager update? | Schedule management plan. | Risk breakdown structure (PBS). | Risk management plan. | Risk register. | The risk register Is updated when appropriate risk responses are chosen and agreed upon. [PMBOK 6th edition. Page. 448] | أنت في مرحلة تنفيذ مشروع لبناء مبنى. يطور فريق المشروع استجابة جديدة لمخاطر قائمة من شأنها تقليل الجدول الزمني بمقدار 20 يومًا. ما هي الوثيقة التي يجب على مدير المشروع تحديثها؟ | خطة إدارة الجدول. | هيكل توزيع المخاطر (RBS). | خطة إدارة الخطر. | سجل المخاطر. | يتم تحديث سجل المخاطر عند اختيار الاستجابات المناسبة للمخاطر والاتفاق عليها. [PMBOK الطبعة السادسة ، الصفحة 448] | 147 | 4 | False | "18" | Ahmad
18 | A change request has been approved to add additional scope to a project. The change will increase the project duration by one month and will increase the budget by $50,000. What should the project manager do next? | Add resources to bring the schedule back on track. | Implement the approved change by following the project management plan. | Use management reserves to cover the cost of the change. | Communicate the change to the relevant stakeholders. | In this case, the decision has been made (the change request has been approved); therefore, the decision should be communicated to the relevant stakeholders. Typically, the decisions are communicated in accordance with the guidelines specified in the project's communications management plan which establishes how, when, and by whom information about the project will be administered and disseminated [PMBOK 6th edition., Page 120]. | تمت الموافقة على طلب تغيير لإضافة نطاق إضافي إلى مشروع. سيؤدي التغيير إلى زيادة مدة المشروع بمقدار شهر واحد وزيادة الميزانية بمقدار 50000 دولار أمريكي. ماذا يجب أن يفعل مدير المشروع بعد ذلك؟ | أضافة موارد لإعادة الجدول إلى المسار الصحيح. | تنفيذ التغيير المعتمد باتباع خطة إدارة المشروع. | استخدم احتياطيات الإدارة لتغطية تكلفة التغيير. | إبلاغ التغيير لأصحاب المصلحة المعنيين. | في هذه الحالة ، تم اتخاذ القرار (تمت الموافقة على طلب التغيير) ؛ لذلك ، ينبغي إبلاغ القرار لأصحاب المصلحة المعنيين. عادةً ، يتم إبلاغ القرارات وفقًا للمبادئ التوجيهية المحددة في خطة إدارة اتصالات المشروع التي تحدد كيف ومتى ومن سيتم إدارة ونشر المعلومات حول المشروع [PMBOK الطبعة السادسة ، الصفحة 120]. | 140 | 5 | False | "18" | Ahmad
19 | You are managing a project with a budget of $9,000, and $1,500 has been spent. However, you only completed $1,000 worth of work. Your schedule says that you should have completed 50% of the work. What is the estimate at completion (EAC)? | $13,500 (Based on original project Budget). | $9,000 (Based on original project Budget). | $9,000 (Based on performance data). | $13,500 (Based on performance data). | The used formulas: EAC = BAC/CPI and CPI = EV/AC CPI = 1000/1500 = 0.66 So, EAC = 9000 / 0.66 = 13,500 (Based on performance data). [PMBOK 6th edition., Page 263] | أنت تدير مشروعًا بميزانية 9000 دولار ، وقد تم إنفاق 1500 دولار. ومع ذلك ، لقد أكملت فقط 1000 دولار من العمل. يشير جدولك إلى أنه كان يجب عليك إكمال 50٪ من العمل. ما هو التقدير عند الانتهاء (EAC)؟ | 13500 دولار (على أساس ميزانية المشروع الأصلية). | 9000 دولار (على أساس ميزانية المشروع الأصلية). | 9000 دولار (بناءً على بيانات الأداء). | 13500 دولار (بناءً على بيانات الأداء). | المعادلات المستخدمة: EAC = BAC / CPI و CPI = EV / AC CPI = 1000/1500 = 0.66 لذلك ، EAC = 9000 / 0.66 = 13500 (بناءً على بيانات الأداء). [الطبعة السادسة ، الصفحة 263 PMBOK] | 143 | 5 | False | "16" | Ahmad
20 | You are managing a IT project. After identifying risks, you start the qualitative risk analysis process and now you are going to prioritize them. Which of the following techniques you are going to use? | Tornado diagram. | Scatter diagram. | Sensitive analysis. | Probability and impact matrix. | After Identifying risks, your next step will be to prioritize them. To do so you will use the probability and impact matrix. [PMBOK 6th edition. Page 408] | أنت تدير مشروع تكنولوجيا المعلومات. بعد تحديد المخاطر ، تبدأ في عملية التحليل النوعي للمخاطر ، وستقوم الآن بتحديد أولوياتها. أي من الأساليب التالية ستستخدمها؟ | مخطط الاعصار. | مخطط التشتت. | تحليل الحساسية. | مصفوفة الاحتمالات والأثر. | بعد تحديد المخاطر ، ستكون خطوتك التالية هي ترتيب أولوياتها. للقيام بذلك سوف تستخدم مصفوفة الاحتمالات والتأثير. [PMBOK الطبعة السادسة ، الصفحة 408] | 147 | 3 | False | "16" | Ahmad
21 | During the planning phase of your project, the project and product requirements have been identified by the project team. Which of the following tools and techniques will be used to accomplish this? | Network diagram, benchmarking, and project scope statement. | Mind mapping, affinity diagram, and brainstorming. | Observations conversations, trend analysis, and work breakdown structure (WBS). | Observations conversations, benchmarking, and affinity diagram. | You can easily remove two options that include Network Diagram and WBS. Also, Mind mapping and Brainstorming both used to generate new ideas so not a good choice. So tools to Identify the project and product requirements are Observations Conversations, Benchmarking, and Affinity Diagram. [PMBOK 6th edition page, 142] | أثناء مرحلة التخطيط لمشروعك ، حدد فريق المشروع متطلبات المشروع والمنتج. أي من الأدوات والتقنيات التالية سيتم استخدامها لإنجاز ذلك؟ | مخطط الشبكة والقياس المعياري وبيان نطاق المشروع. | رسم الخرائط الذهنية ومخطط التقارب والعصف الذهني. | محادثات الملاحظات ، وتحليل الاتجاهات ، وهيكل تجزئة العمل (WBS). | ملاحظات المحادثات ، قياس الأداء ، ومخطط التقارب. | يمكنك بسهولة إزالة خيارين يتضمنان مخطط الشبكة و هيكل تجزئة العمل . أيضًا ، يتم استخدام كل من تخطيط العقل والعصف الذهني لتوليد أفكار جديدة لذلك ليس اختيارًا جيدًا. لذا فإن أدوات تحديد متطلبات المشروع والمنتج هي محادثات الملاحظات وقياس الأداء ومخطط التقارب. [PMBOK الطبعة السادسة ، الصفحة 142] | 141 | 3 | False | "16" | Ahmad
22 | Task B is dependent upon task A which is delayed. Resource for task B have limited availability and you must begin task B on time. What should you do to replan the schedule so that the deadline not changed? | Fast track task A and move task B's start date. | Fast track task B and immediately begin work. | Replan task B start date so it begins after the completion of task A | Crash task A and start task B at the planned time. | The relation between task A and B is (FS) and the task A Is delayed, so you should focus on crashing task A and start task B at the planned time so that the deadline not changed. Option (Fast track task B and immediately begin work) not correct because resources for task B have limited availability. Option (Fast track task A and move task B's start date.) not correct because the deadline will change. Option (Replan task B's start date so It begins after the completion of task A.) not correct because the deadline will change. [PMBOK 6th edition page, 215] | يعتمد النشاط "ب" على النشاط A التي تم تأخيره. مورد المهمة B وقته محدود ويتعين عليك بدء النشاط B في الوقت المحدد. ما الذي يجب عليك فعله لإعادة جدولة الجدول الزمني بحيث لا يتغير الموعد النهائي؟ | تطبيق تقنية التتبع السريع في النشاط A ونقل تاريخ بدء النشاط B. | تطبيق تقنية التتبع السريع في النشاط B وبدء العمل على الفور. | تاريخ بدء إعادة تخطيط النشاط B بحيث تبدأ بعد الانتهاء من النشاط A | حشد الموارد في النشاط A والبدء في النشاط B في الوقت المخطط له. | العلاقة بين النشاط A و B هي (FS) النشاط A مؤجلة ، لذا يجب التركيز على حشد الموارد في النشاط A وبدء النشاط B في الوقت المخطط لها حتى لا يتغير الموعد النهائي. الخيار (تقنية التتبع السريع النشاط B وبدء العمل فورًا) غير صحيح لأن موارد النشاط B محدودة التوفر. الخيار (تقنية التتبع السريع في النشاط A ونقل تاريخ بدء النشاط B) غير صحيح لأن الموعد النهائي سيتغير. الخيار (تاريخ بدء إعادة تخطيط النشاط ب بحيث يبدأ بعد الانتهاء من النشاط A) غير صحيح لأن الموعد النهائي سيتغير. [PMBOK الطبعة السادسة ، الصفحة 215] | 142 | 3 | False | "16" | Ahmad
23 | You are a project manager in an IT project. You and key stakeholders start conducting a project benefit analysis. Because of the solutions that have not been identified, an engineer from another department has informed you that there are affected systems. As a project manager, what should you do? | Update the risk register | Identify all stakeholders | Review the project benefit analysis to consider the additional impact | Document the issue in the issue log. | The Issue log is a project document used to Identify and monitor issues that occur In the project. The issue log can be updated with any new issues found during the project and described In the scenario because of the solutions that have not been identified causing the system are affected. This choice "Document the issue in the issue log" is the best answer. [PMBOK 6th edition page, 453] | أنت مدير مشروع في مشروع تكنولوجيا المعلومات. تبدأ أنت وأصحاب المصلحة الرئيسيين في إجراء تحليل فوائد المشروع. بسبب الحلول التي لم يتم تحديدها ، أبلغك مهندس من قسم آخر بوجود أنظمة متأثرة. كمدير مشروع ، ماذا يجب أن تفعل؟ | تحديث سجل المخاطر | تحديد جميع أصحاب المصلحة | القيام بمراجعة تحليل فوائد المشروع للنظر في التأثير الإضافي | القيام بتوثيق المشكلة في سجل الأحداث. | سجل الأحداث هو مستند مشروع يُستخدم لتحديد المشكلات التي تحدث في المشروع ومراقبتها. يمكن تحديث سجل الأحداث بأي مشكلات جديدة يتم العثور عليها أثناء المشروع ووصفها في السيناريو بسبب الحلول التي لم يتم تحديدها والتي تتسبب في تأثر النظام. هذا الخيار "توثيق المشكلة في سجل المشاكل" هو أفضل إجابة. [PMBOK الطبعة السادسة ، الصفحة 453] | 147 | 5 | False | "18" | Ahmad
24 | You are working in a matrix organization and managing a construction project. The functional manager moved some resources you need from your project to another project. What should you do next? | Update stakeholder engagement plan | Escalate this problem to the sponsor | Complete the project without this resources | Negotiate with functional manager to assign a new resources | In matrix organizations environment the project manager should effectively negotiate and influence others who are in a position to provide the required team and physical resources for the project. [PMBOK 6th edition, Page 329]. | أنت تعمل في منظمة مصفوفة وتدير مشروع بناء. نقل المدير الوظيفي بعض الموارد التي تحتاجها من مشروعك إلى مشروع آخر. ماذا يجب ان تفعل بعد ذلك؟ | تحديث خطة إشراك أصحاب المصلحة | تصعيد هذه المشكلة إلى الراعي | اكمال المشروع بدون هذه الموارد | تفاوض مع المدير الوظيفي لتعيين موارد جديدة | في بيئة المنظمات المصفوفة ، يجب على مدير المشروع أن يتفاوض بشكل فعال وأن يؤثر على الآخرين الذين هم في وضع يسمح لهم بتوفير الفريق المطلوب والموارد المادية للمشروع. [PMBOK الطبعة السادسة ، الصفحة 329]. | 145 | 4 | False | "18" | Ahmad
25 | A change request has been approved by the change control board CCB. You want to make sure that this change has been implemented correctly. Which process will ensure this? | Direct and Manage Project Work. | Mange Quality. | Monitor and Control Project Work. | Control Quality. | As part of the Perform Integrated Change Control process, a change log update Indicates that some changes are approved and some are not. Approved change request may include modification such as defect repairs, revised work methods, and revised schedules. Partial change completion may result in inconsistencies and later delays due to incomplete steps or corrections, The implementation of approved changes should be verified, confirmed for completeness, retested, and certified as correct. [PMBOK 6th edition, Page 301] | تمت الموافقة على طلب التغيير من قبل لجنة التحكم في التغيير CCB. تريد التأكد من تنفيذ هذا التغيير بشكل صحيح. ما هي العملية التي ستضمن ذلك؟ | تنفيذ وإدارة أعمال المشروع. | ادارة الجودة | المراقبة والتحكم لاعمال المشروع. | التحكم بالجودة | كجزء من عملية تنفيذ التحكم المتكامل في التغيير ، يشير تحديث سجل التغيير إلى الموافقة على بعض التغييرات والبعض الآخر غير مقبول. قد يتضمن طلب التغيير المعتمد تعديلات مثل إصلاحات العيوب وأساليب العمل المنقحة والجداول الزمنية المنقحة. قد يؤدي إكمال التغيير الجزئي إلى حدوث تناقضات وتأخيرات لاحقة بسبب عدم اكتمال الخطوات أو التصحيحات ، يجب التحقق من تنفيذ التغييرات المعتمدة ، وتأكيد اكتمالها ، وإعادة اختبارها ، واعتمادها على أنها صحيحة. [PMBOK الطبعة السادسة ، الصفحة 301] | 144 | 5 | False | "16" | Ahmad
26 | As part of earned value management (EVM), The budget at completion (BAC) for the project is SAR 100,000 and the estimate at completion (EAC) is SAR 130,000. If the schedule performance index (SPI) is equal to 1.0. What is the cost performance index (CPI)? | Equal to 1.2 | Greater than 1.0 | Equal to 1.0 | Less than 1.0 | EAC = BAC / CPI So: CPI = BAC / EAC CPI = 100,000/130,000 = 0.77 CPI Less than 1.0 [PMBOK 6th edition, Page 267] | كجزء من إدارة القيمة المكتسبة (EVM) ، تبلغ الميزانية عند الانتهاء (BAC) للمشروع 100،000 ريال سعودي والتقدير عند الانتهاء (EAC) هو 130،000 ريال سعودي. إذا كان مؤشر أداء الجدول (SPI) يساوي 1.0. ما هو مؤشر أداء التكلفة (CPI)؟ | يساوي 1.2 | أكبر من 1.0 | يساوي 1.0 | أقل من 1.0 | EAC = BAC / CPI لذلك: CPI = BAC / EAC CPI = 100،000 / 130،000 = 0.77 CPI أقل من 1.0 [PMBOK الطبعة السادسة ، الصفحة 267] | 143 | 5 | False | "17" | Ahmad
27 | As the project manager of a large project, you are determining the accuracy of the deliverables before closing a project. What process should be used to determine this and is an input to formalizing acceptance? | Accepted deliverables | Manage quality | Control scope | Control quality | Validate Scope is the process of formalizing acceptance of the completed project deliverables. The verified deliverables obtained from the Control Quality process are reviewed with the customer or sponsor to ensure they are completed satisfactorily and have received formal acceptance of the deliverables by the customer or sponsor. Verified deliverables is the key inputs of validate scope process and outputs of Control quality process. [PMBOK 6th edition, Page 164]. | بصفتك مدير مشروع لمشروع كبير ، فأنت تحدد دقة التسليمات قبل إغلاق المشروع. ما هي العملية التي يجب استخدامها لتحديد ذلك وهل تعتبر مدخلاً لإضفاء الطابع الرسمي على القبول؟ | التسليمات المقبولة | إدارة الجودة | نطاق التحكم | التحكم بالجودة | التحقق من النطاق هو عملية إضفاء الطابع الرسمي على قبول نواتج المشروع المكتملة. تتم مراجعة التسليمات التي تم التحقق منها والتي تم الحصول عليها من عملية مراقبة الجودة مع العميل أو الراعي للتأكد من اكتمالها بشكل مرض وتلقيها قبولًا رسميًا للنواتج من قبل العميل أو الراعي. التسليمات التي تم التحقق منها هي المدخلات الرئيسية لعملية التحقق من النطاق ونواتج عملية التحكم في الجودة. [الطبعة السادسة من PMBOK ، صفحة 164]. | 141 | 5 | False | "16" | Ahmad
28 | Which of the following statements is correct regarding the kickoff meeting? | Just to inform and engage stakeholders | Just to get the commitment | Just to inform | Kickoff meeting is conducted not only to inform but also to engage and gain commitment from stakeholders | The kickoff meeting is conducted to communicate the start of the project, the key milestones, and other information to inform and engage stakeholders and gain their commitment. [PMBOK 6th edition, Page 86 | أي من العبارات التالية صحيحة فيما يتعلق باجتماع الافتتاحي لانطلاق المشروع؟ | فقط لإعلام وإشراك أصحاب المصلحة | فقط للحصول على الالتزام | فقط للإبلاغ | يتم عقد اجتماع البداية ليس فقط للإبلاغ ولكن أيضًا للمشاركة والحصول على الالتزام من أصحاب المصلحة | يتم عقد الاجتماع الافتتاحي لانطلاق المشروع للإبلاغ عن بداية المشروع ، والمعالم الرئيسية ، وغيرها من المعلومات لإعلام أصحاب المصلحة وإشراكهم وكسب التزامهم. [الطبعة السادسة من PMBOK ، الصفحة 86] | 140 | 3 | False | "16" | Ahmad
29 | You are calculates the amount of float on various paths in the network diagram to determine the minimum project duration. Which tool or technique you are using to do this? | Three-point estimating | Critical chain method | Parametric estimating | Critical path method | The critical path method is used to estimate the minimum project duration and determine the amount of schedule flexibility on the logical network paths within the schedule model. A critical path is normally characterized by zero total floats on the critical path. [PMBOK 6th edition, Page 210] | أنت تحسب مقدار التعويم على مسارات مختلفة في الرسم التخطيطي للشبكة لتحديد الحد الأدنى لمدة المشروع. ما الأداة أو التقنية التي تستخدمها للقيام بذلك؟ | ثلاث نقاط تقدير | طريقة السلسلة الحرجة | التقدير الاحصائي (استخدام المعادلات الرياضية) | طريقة المسار الحرج | تُستخدم طريقة المسار الحرج لتقدير الحد الأدنى لمدة المشروع وتحديد مقدار مرونة الجدول الزمني على مسارات الشبكة المنطقية ضمن نموذج الجدول. يتميز المسار الحرج عادة بصفر إجمالي عوامات على المسير الحرج. [الطبعة السادسة من PMBOK ، الصفحة 210] | 143 | 5 | False | "19" | Ahmad
30 | As part of a strategy to handle negative risk, a project manager decided to do less complex processes, add more tests, and deal with more stable supplier. What strategy would this be classified as? | Acceptance | Avoidance | Transference | Mitigation | Actions such as doing less complex processes, add more test, or dealing with more stable supplier would be considered mitigation. These actions reduce the probability and impact of risks. [PMBOK 6th edition, Page 443] | كجزء من استراتيجية للتعامل مع المخاطر السلبية ، قرر مدير المشروع القيام بعمليات أقل تعقيدًا وإضافة المزيد من الاختبارات والتعامل مع مورد أكثر استقرارًا. ما هي الاستراتيجية التي يمكن تصنيفها؟ | قبول | تجنب | نقل | تخفيف | إجراءات مثل القيام بعمليات أقل تعقيدًا ، أو إضافة المزيد من الاختبارات ، أو التعامل مع مورد أكثر استقرارًا يمكن اعتباره بمثابة تخفيف. تقلل هذه الإجراءات من احتمالية وتأثير المخاطر. [الطبعة السادسة من PMBOK ، صفحة 443] | 147 | 4 | False | "18" | Ahmad
31 | Which of the following components of a project scope statement is useful in reducing scope creep? | Acceptance criteria | Deliverables | Scope description | Exclusions | Project exclusions identifies what is excluded from the project. Explicitly stating what is out of scope for the project helps manage stakeholders’ expectation and can reduce scope creep. Other choices cannot help more in this regard. [PMBOK 6th edition, Page 154] | أي من المكونات التالية لبيان نطاق المشروع مفيد في تقليل زحف النطاق؟ | معايير القبول | المخرجات | وصف النطاق | الاستثناءات | تحدد استثناءات المشروع ما هو مستبعد من المشروع. يساعد التوضيح الصريح لما هو خارج نطاق المشروع على إدارة توقعات أصحاب المصلحة ويمكن أن يقلل من زحف النطاق. لا يمكن أن تساعد الخيارات الأخرى أكثر في هذا الصدد. [الطبعة السادسة من PMBOK ، الصفحة 154] | 141 | 3 | False | "17" | Ahmad
32 | Which of the following statements most accurately describes a project scenario? | Changes in project scope during the initial phases of the project are very expensive | The influence of the stakeholders is the same all through the project | The next phase of a project should never start until the deliverables for the previous phase are completely reviewed and approved | Staffing peaks are in the execution phase of a project | Staffing is typically highest during the execution phase of the project. The other three responses may not hold true. Projects can move forward into subsequent phases without the deliverables of the prior phase being completely approved; this is known as fast tracking. Changes during the initial phases of the project are the least expensive. The influence of the stakeholders is highest during the start of the project and declines as the project moves to completion. [PMBOK 6th edition, Page 549] | أي من العبارات التالية يصف سيناريو المشروع بدقة أكبر؟ | تعتبر التغييرات في نطاق المشروع خلال المراحل الأولية للمشروع باهظة الثمن | تأثير أصحاب المصلحة هو نفسه طوال المشروع | يجب ألا تبدأ المرحلة التالية من المشروع أبدًا حتى تتم مراجعة مخرجات المرحلة السابقة والموافقة عليها بالكامل | ذروة التوظيف في مرحلة تنفيذ المشروع | عادة ما يكون التوظيف هو الأعلى خلال مرحلة تنفيذ المشروع. قد لا تكون الردود الثلاثة الأخرى صحيحة. يمكن للمشاريع المضي قدمًا في المراحل اللاحقة دون الموافقة الكاملة على مخرجات المرحلة السابقة ؛ يُعرف هذا بالتتبع السريع. التغييرات خلال المراحل الأولى من المشروع هي الأقل تكلفة. يكون تأثير أصحاب المصلحة على أعلى مستوى خلال بداية المشروع وينخفض ​​مع انتقال المشروع إلى الاكتمال. [PMBOK الطبعة السادسة ، الصفحة 549] | 145 | 4 | False | "16" | Ahmad
33 | Which of these types of precedence relationships is least commonly used in the Precedence Diagramming Method? | Start to Start | Finish to Finish | Finish to Start | Start to Finish | Start to Finish relationships indicate that the next task cannot be completed until the one preceding it has started. This type is not commonly used. [PMBOK 6th edition, Page 190] | أي من هذه الأنواع من علاقات الأسبقية هو الأقل استخدامًا في طريقة رسم مخطط الأسبقية؟ | البداية الى البداية | النهاية الى النهاية | النهاية الى البداية | البداية الى النهاية | تشير علاقات البدء إلى الانتهاء إلى أنه لا يمكن إكمال المهمة التالية حتى تبدأ المهمة التي تسبقها. هذا النوع غير مستخدم بشكل شائع. [الطبعة السادسة من PMBOK ، الصفحة 190] | 142 | 3 | False | "17" | Ahmad
34 | A contractor is currently constructing a new building for your organization on a cost-plus-incentive contract. You just received the project status report from the contractor’s project manager. According to the report, the project’s CPI is 1.5. You are shocked because you believe the project costs are out of control. Upon investigation, you learn the $1 million advance payment (20 percent of the estimated project cost) given to the contractor at the start of the project was included in the project’s earned value. Further, the cost of the inventory at the project site was excluded from the total actual costs. According to the contract, your company reimburses only the costs for the completed deliverables and not for the supplies in the project’s inventory. In this scenario, the reported project’s CPI is incorrect because: | Actual cost is understated | Earned value is overstated, and actual cost is understated | Both the earned value and the actual cost are overstated | Earned value is overstated. | In this scenario the earned value has been overstated while the reported actual cost is ok. Earned value should be the sum of PVs of all completed activities. The initial 20% advance should not be part of this. Further, since the buyer is not liable for the inventory cost and only reimburses the costs associated with completed deliverables, the cost of the inventory does not become part of the actual cost until that inventory is consumed during the construction process. The inventory is an asset for the contactor until it is consumed on the project and at that time it becomes a cost for the project. [PMBOK 6th edition, Page 267] | يقوم المقاول حاليًا ببناء مبنى جديد لمؤسستك بموجب عقد التكلفة بالإضافة إلى الحوافز. لقد تلقيت للتو تقرير حالة المشروع من مدير مشروع المقاول. وفقًا للتقرير ، يبلغ مؤشر اداء التكلفة للمشروع 1.5. لقد صدمت لأنك تعتقد أن تكاليف المشروع خارجة عن السيطرة. عند التحقيق ، علمت أن الدفعة المقدمة البالغة 1 مليون دولار (20 في المائة من تكلفة المشروع المقدرة) الممنوحة للمقاول في بداية المشروع قد تم تضمينها في القيمة المكتسبة للمشروع. علاوة على ذلك ، تم استبعاد تكلفة المخزون في موقع المشروع من إجمالي التكاليف الفعلية. وفقًا للعقد ، تسدد شركتك فقط تكاليف التسليمات المكتملة وليس الإمدادات الموجودة في مخزون المشروع. في هذا السيناريو ، مؤشر اداء التكلفة للمشروع المبلغ عنه غير صحيح للأسباب التالية: | التكلفة الفعلية أقل من قيمتها الحقيقية | القيمة المكتسبة مبالغ فيها ، والتكلفة الفعلية أقل من قيمتها الحقيقية | كل من القيمة المكتسبة والتكلفة الفعلية مبالغ فيها | القيمة المكتسبة مبالغ فيها. | في هذا السيناريو ، تم المبالغة في القيمة المكتسبة في حين أن التكلفة الفعلية المبلغ عنها لا بأس بها. يجب أن تكون القيمة المكتسبة هي مجموع PVs لجميع الأنشطة المكتملة. يجب ألا تكون الدفعة الأولى البالغة 20٪ جزءًا من هذا. علاوة على ذلك ، نظرًا لأن المشتري غير مسؤول عن تكلفة المخزون ولا يقوم إلا بسداد التكاليف المرتبطة بالنواتج المنجزة ، فإن تكلفة المخزون لا تصبح جزءًا من التكلفة الفعلية حتى يتم استهلاك هذا المخزون أثناء عملية البناء. يعد المخزون أحد الأصول لجهة الاتصال حتى يتم استهلاكه في المشروع وفي ذلك الوقت يصبح تكلفة للمشروع. [الطبعة السادسة من PMBOK ، الصفحة 267] | 143 | 5 | False | "20" | Ahmad
35 | Increasing the number of resources in order to crash a project schedule does not always cut the time by the same factor. In worst cases, too many resources assigned to an activity may actually increase the activity duration. This is because: | Decrease in cost budget | Funding limit reconciliation | Additional risk introduced due to crashing | Required additional coordination | Increasing the number of resources in order to crash a project schedule does not always cut the time by the same factor. In worst cases, too many resources to the activity may actually increase the duration due to required additional coordination. Other choices are either not applicable or do not directly influence the project schedule. [PMBOK 6th edition, Page 197] | إن زيادة عدد الموارد من أجل تسريع جدول المشروع لا يؤدي دائمًا إلى تقليل الوقت بنفس المعامل. في أسوأ الحالات ، قد يؤدي عدد كبير جدًا من الموارد المخصصة لنشاط ما إلى زيادة مدة النشاط بالفعل. هذا بسبب: | انخفاض في ميزانية التكلفة | الحد من التمويل | مخاطر إضافية مقدمة بسبب الاصطدام | التنسيق الإضافي المطلوب | إن زيادة عدد الموارد من أجل تعطل جدول المشروع لا يؤدي دائمًا إلى قطع الوقت بنفس العامل. في أسوأ الحالات ، قد يؤدي وجود موارد كثيرة جدًا للنشاط إلى زيادة المدة الفعلية بسبب التنسيق الإضافي المطلوب. الخيارات الأخرى إما غير قابلة للتطبيق أو لا تؤثر بشكل مباشر على الجدول الزمني للمشروع. [PMBOK الطبعة السادسة ، الصفحة 197] | 142 | 3 | False | "18" | Ahmad
36 | The Requirements Traceability Matrix helps in tracing all the following except: | Requirements to project objectives | Requirements to project scope | Requirements to test strategy | Requirements to project risk | Requirements Traceability Matrix is an output of the Collect Requirements process. It is used for tracing requirements to project scope, objectives, and test strategy. Tracing requirements to project risk is not a valid use. [PMBOK 6th edition, Page 149] | تساعد مصفوفة تتبع المتطلبات في تتبع كل ما يلي باستثناء: | متطلبات أهداف المشروع | متطلبات نطاق المشروع | متطلبات اختبار الإستراتيجية | متطلبات مخاطر المشروع | مصفوفة تتبع المتطلبات هي أحد مخرجات عملية تجميع المتطلبات. يتم استخدامه لتتبع المتطلبات لنطاق المشروع والأهداف واستراتيجية الاختبار. متطلبات التعقب لمخاطر المشروع ليست استخداما صالحا. [الطبعة السادسة من PMBOK ، الصفحة 149] | 141 | 3 | False | "18" | Ahmad
37 | The Control Procurements process receives a very important input from the Direct and Manage Project Work process. Which one is it? | Approved change requests | Procurement documents | Agreements | Work performance data | Work performance data is provided to the Control Procurements process by the Direct and Manage Project Work process. [PMBOK 6th edition, Page 493] | تتلقى عملية مشتريات التحكم مدخلات مهمة للغاية من عملية مباشرة وإدارة عمل المشروع. أي واحد هو؟ | طلبات التغيير المعتمدة | وثائق المشتريات | الاتفاقيات | بيانات أداء العمل | يتم توفير بيانات أداء العمل لعملية مشتريات التحكم من خلال عملية Direct and Manage Work Work. [الطبعة السادسة من PMBOK ، صفحة 493] | 148 | 5 | False | "16" | Ahmad
38 | Julia is currently recruiting her project team. She has carried out various interviews and has shortlisted potential candidates. Now, according to the project communication management plan, she has to submit the shortlisted profiles to the project client (customer) for approval. Only then, can she formally hire the approved candidates for the project. The submission of the profiles to the client will go through which of the following processes? | Manage Stakeholder Engagement | Acquire Resources | Plan Resource Management | Manage Communications | Manage Communications is the process of distributing project information in accordance to the communications management plan. The interviews and shortlisting was carried out during the Acquire Resources and so will be the hiring once the approvals come in. However, the profiles submission to the client will be done through the Manage Communications process. [PMBOK 6th edition, Page 379] | تقوم جوليا حاليًا بتجنيد فريق المشروع الخاص بها. لقد أجرت العديد من المقابلات وقامت باختيار المرشحين المحتملين. الآن ، وفقًا لخطة إدارة اتصالات المشروع ، يتعين عليها تقديم الملفات الشخصية المختصرة إلى عميل المشروع (العميل) للموافقة عليها. عندها فقط ، يمكنها تعيين المرشحين المعتمدين للمشروع رسميًا. أي من العمليات التالية ستتم بتقديم الملفات الشخصية إلى العميل؟ | إدارة إشراك أصحاب المصلحة | اكتساب الموارد | خطة إدارة الموارد | إدارة الاتصالات | إدارة الاتصالات هي عملية توزيع معلومات المشروع وفقًا لخطة إدارة الاتصالات. تم إجراء المقابلات والقائمة المختصرة أثناء اكتساب الموارد ، وبالتالي سيكون التوظيف بمجرد وصول الموافقات. ومع ذلك ، سيتم إرسال الملفات الشخصية إلى العميل من خلال عملية إدارة الاتصالات. [الطبعة السادسة من PMBOK ، صفحة 379] | 146 | 4 | False | "16" | Ahmad
39 | What does a Cost Performance Index (CPI) of more than 1.0 indicate? | The project is over budget | The project is right on budget | The project is ahead of schedule | The project is under budget | The CPI is calculated as the earned value divided by the actual cost. An index of greater than one indicates that you have spent less than you forecasted to this point. [PMBOK 6th edition, Page 263] | ماذا يشير مؤشر أداء التكلفة (CPI) الذي يزيد عن 1.0؟ | المشروع تجاوز الميزانية | المشروع الحق في الميزانية | المشروع قبل الموعد المحدد | المشروع اقل من الميزانية | يتم حساب مؤشر اداء التكلفة CPI على أنه القيمة المكتسبة مقسومة على التكلفة الفعلية. يشير الفهرس الأكبر من واحد إلى أنك أنفقت أقل مما توقعته حتى هذه النقطة. [الطبعة السادسة من PMBOK ، الصفحة 263] | 143 | 5 | False | "19" | Ahmad
40 | Which of the following is a tool or technique of the Develop Team process? | Organizational charts | Acquisition | Influence diagrams | Co-location | Colocation is a tool and technique of the Develop Team process. The other choices are not valid responses. [PMBOK 6th edition, Page 336] | أي مما يلي يعتبر أداة أو تقنية لعملية تطوير الفريق؟ | المخططات التنظيمية | استحواذ | مخططات التأثير | موقع مشترك | الموقع المشترك هي أداة وتقنية لعملية تطوير الفريق. الخيارات الأخرى ليست استجابات صالحة. [PMBOK الطبعة السادسة ، الصفحة 336] | 145 | 4 | False | "17" | Ahmad
41 | A project manager must stress the importance of collecting and documenting lessons learned through the project lifecycle. One good way to collect this information is during weekly status meetings. Usually, weekly status meetings, if not managed properly, end up in firefighting since most of the time, attention goes to the burning issues. How can you ensure that the lessons-learned gathering does not get missed in such a situation? | Record the minutes of the meeting | Do not discuss burning issues in weekly status meetings | Replace status update meetings with one-on-one meetings with the team members | Add a lessons-learned agenda item | A good approach is to add a lessons-learned agenda item to the meeting. As the meeting progresses to the point where you’re ready to collect lessons-learned information, ask each team member about his or her positive and negative experiences for the week. Don’t mention the words “lessons learned” to them; just capture what went right and wrong from every team member. Do your best to prevent this part of the meeting from devolving into a complaint session. [PMBOK 6th edition, Page 379] [PMI best practice] | يجب أن يؤكد مدير المشروع على أهمية جمع وتوثيق الدروس المستفادة خلال دورة حياة المشروع. إحدى الطرق الجيدة لجمع هذه المعلومات هي أثناء اجتماعات الحالة الأسبوعية. عادةً ما تنتهي اجتماعات الحالة الأسبوعية ، إذا لم تتم إدارتها بشكل صحيح ، بمكافحة الحرائق نظرًا لأن الاهتمام يتجه في معظم الأحيان إلى القضايا الملتهبة. كيف يمكنك التأكد من عدم تفويت مجموعة الدروس المستفادة في مثل هذه الحالة؟ | سجل محضر الاجتماع | لا تناقش القضايا الملتهبة في اجتماعات الحالة الأسبوعية | استبدال اجتماعات تحديث الحالة باجتماعات فردية مع أعضاء الفريق | اضافة بند جدول أعمال الدروس المستفادة | من الأساليب الجيدة إضافة بند جدول أعمال الدروس المستفادة إلى الاجتماع. مع تقدم الاجتماع إلى النقطة التي تكون فيها على استعداد لجمع معلومات الدروس المستفادة ، اسأل كل عضو في الفريق عن تجاربه الإيجابية والسلبية لهذا الأسبوع. لا تذكر الكلمات "الدروس المستفادة" لهم. ما عليك سوى التقاط ما حدث بشكل صحيح وما هو خطأ من كل عضو في الفريق. بذل قصارى جهدك لمنع هذا الجزء من الاجتماع من التحول إلى جلسة شكوى. [الإصدار السادس من PMBOK ، الصفحة 379] [أفضل ممارسات PMI] | 146 | 4 | False | "17" | Ahmad
42 | Which document describes the project's deliverables and the work required to create those deliverables? | Project authorization document | Project scope management plan | Project charter | Project scope statement | The project scope statement is the correct response. This document describes the project's deliverables in detail and the work that is required to create those deliverables. It also forms the baseline for evaluating whether requests for changes are within or outside the project's boundaries. [PMBOK 6th edition, Page 154] | ما المستند الذي يصف مخرجات المشروع والعمل المطلوب لإنشاء تلك المخرجات؟ | وثيقة تفويض المشروع | خطة إدارة نطاق المشروع | ميثاق المشروع | بيان نطاق المشروع | بيان نطاق المشروع هو الاستجابة الصحيحة. يصف هذا المستند مخرجات المشروع بالتفصيل والعمل المطلوب لإنشاء تلك المخرجات. كما أنها تشكل الأساس لتقييم ما إذا كانت طلبات التغييرات داخل أو خارج حدود المشروع. [الطبعة السادسة من PMBOK ، الصفحة 154] | 141 | 3 | False | "19" | Ahmad
43 | The term Progressive Elaboration incorrectly represents which of the following? | Rolling wave planning | Detailing out the product requirements developed during the initiation process | Production of fabrication and construction drawings from the design drawings for a chemical plant. | Changes to project scope | The distinction between progressive elaboration and scope creep needs to be understood since the two terms are different. The changes to scope (especially in an uncontrolled manner) are called scope creep. In contrast, progressive elaboration involves building on or elaborating the output of a previous phase. [PMBOK 6th edition, Page 185] | يشير مصطلح التفصيل التدريجي بشكل غير صحيح إلى أي مما يلي؟ | تخطيط الموجة المتداولة | تفصيل متطلبات المنتج التي تم تطويرها أثناء عملية البدء | إنتاج رسومات التصنيع والبناء من رسومات التصميم لمصنع كيماويات. | التغييرات في نطاق المشروع | يجب فهم التمييز بين التفصيل التدريجي وتسلل النطاق لأن المصطلحين مختلفان. التغييرات على النطاق (خاصة بطريقة غير خاضعة للرقابة) تسمى زحف النطاق. في المقابل ، يتضمن التفصيل التدريجي البناء على ناتج المرحلة السابقة أو تطويره. [الطبعة السادسة من PMBOK ، الصفحة 185] | 142 | 3 | False | "19" | Ahmad
44 | While analyzing a project, the project manager calculated the ratio of the Earned Value (EV) to the Actual Costs (AC) and obtained a value of 1.2. The project manager decided this was an unfavorable condition for the project and decided to take corrective action. What is your view? | The project manager is correct. The ratio of EV to AC is the Cost Performance Index and a ratio greater than 1 is unfavorable to the project | The project manager is not correct. The ratio of EV to AC is the Cost Variance and a ratio greater than 1 is favorable to the project | The project manager is correct. The ratio of EV to AC is the Cost Variance and a ratio greater than 1 is unfavorable to the project | The project manager is not correct. The ratio of EV to AC is the Cost Performance Index and a ratio greater than 1 is favorable to the project | The project manager is not correct. Cost Performance Index (CPI) is the ratio of EV to AC. A value greater than one represents a favorable condition for the project. The project manager has misinterpreted the situation. [PMBOK 6th edition, Page 263] | أثناء تحليل المشروع ، قام مدير المشروع بحساب نسبة القيمة المكتسبة (EV) إلى التكاليف الفعلية (AC) وحصل على قيمة 1.2. قرر مدير المشروع أن هذا كان شرطًا غير مواتٍ للمشروع وقرر اتخاذ إجراء تصحيحي. ما هو رأيكم؟ | مدير المشروع على صواب. نسبة EV إلى AC هي مؤشر أداء التكلفة ونسبة أكبر من 1 غير مواتية للمشروع | مدير المشروع غير صحيح. نسبة EV إلى AC هي تباين التكلفة ونسبة أكبر من 1 مواتية للمشروع | مدير المشروع على صواب. نسبة EV إلى AC هي تباين التكلفة ونسبة أكبر من 1 غير مواتية للمشروع | مدير المشروع غير صحيح. نسبة EV إلى AC هي مؤشر أداء التكلفة ونسبة أكبر من 1 مواتية للمشروع | مدير المشروع غير صحيح. مؤشر أداء التكلفة (CPI) هو نسبة EV إلى AC. تمثل القيمة الأكبر من واحد شرطًا مناسبًا للمشروع. أساء مدير المشروع تفسير الموقف. [الطبعة السادسة من PMBOK ، الصفحة 263] | 143 | 5 | False | "20" | Ahmad
45 | As a project manager, you are responsible for determining and delivering the required levels of both grade and quality. Select which of the following statements you disagree with. | Grade relates to the product's characteristics | Quality relates to the customer requirements | Quality and grade of a product must be carefully managed | Grade relates to the customer requirements | The grade of a product relates to the technical characteristics of the product. [PMBOK 6th edition, Page 274] | بصفتك مدير مشروع ، فأنت مسؤول عن تحديد المستويات المطلوبة وتقديمها لكل من الدرجة والجودة. حدد العبارات التالية التي لا توافق عليها. | الدرجة تتعلق بخصائص المنتج | الجودة تتعلق بمتطلبات العميل | يجب أن تدار جودة ودرجة المنتج بعناية | الدرجة تتعلق بمتطلبات العميل | ترتبط درجة المنتج بالخصائص التقنية للمنتج. [الطبعة السادسة من PMBOK ، الصفحة 274] | 144 | 3 | False | "17" | Ahmad
46 | Ahmad has worked for a retail company as a project manager. With his positive thinking and strong managerial skills, he turned many potentially disastrous projects into successes. Because of his expertise, his employer’s senior executives offered him a group project manager position for a newly started environmental project. However, Ahmad learned that, in his newly assigned project, he might have to offer bribes to obtain government licenses. What should Ahmad do in such a situation? | Accept the offer because project managers must obey their higher-ups | Accept the position and offer bribes because project managers must complete projects on time and within budget | Investigate to find out if it is customary to offer bribes in that part of the country | Reject the offer because project managers should not engage in an unethical conduct | Project managers must adhere to the code of ethics and professional conduct. They must maintain fairness and honesty. Since the new job requires some illegal and unethical activities, Ahmad must reject the offer. [PMI code of Ethics and Professional Conduct] [Prof. Responsibility][PMBOK 6th edition, Page 3] | عمل أحمد في شركة بيع بالتجزئة كمدير مشروع. بفضل تفكيره الإيجابي ومهاراته الإدارية القوية ، حول العديد من المشاريع التي يحتمل أن تكون كارثية إلى نجاحات. بسبب خبرته ، عرض عليه كبار المديرين التنفيذيين في صاحب العمل منصب مدير مشروع جماعي لمشروع بيئي بدأ حديثًا. ومع ذلك ، علم أحمد أنه في مشروعه الجديد ، قد يضطر إلى تقديم رشاوى للحصول على تراخيص حكومية. فماذا يفعل أحمد في مثل هذه الحالة؟ | اقبل العرض لأن مديري المشروع يجب أن يطيعوا رؤسائهم | اقبل المنصب وعرض رشاوى لأن مدراء المشاريع يجب أن يكملوا المشاريع في الوقت المحدد وفي حدود الميزانية | التحقق لمعرفة ما إذا كان من المعتاد تقديم رشاوى في ذلك الجزء من البلاد | ارفض العرض لأن مديري المشروع يجب ألا ينخرطوا في سلوك غير أخلاقي | يجب أن يلتزم مديرو المشاريع بمدونة الأخلاق والسلوك المهني. يجب أن يحافظوا على الإنصاف والصدق. نظرًا لأن الوظيفة الجديدة تتطلب بعض الأنشطة غير القانونية وغير الأخلاقية ، يجب على أحمد رفض العرض. [مدونة الأخلاق والسلوك المهني لدى معهد إدارة المشاريع] [المسؤولية المهنية] [PMBOK الطبعة السادسة ، الصفحة 3] | 140 | 2 | False | "18" | Ahmad
47 | Nada is managing a complex industrial process reengineering project. She has identified all her key project stakeholders and has conducted individual interviews with them to identify other project stakeholders, as well. However, Nada is still not satisfied with her project’s stakeholders list; she believes there may be more key external stakeholders missing from the list. What can help Nada in this situation? | Use stakeholder register templates from the organizational process assets | Conduct more meetings with the key stakeholders | Get over her fear and finalize the project stakeholder register | Seek expert judgment from subject matter experts | The stakeholder register template does not contain stakeholders information; it only helps the project manager produce the project's stakeholder register. If Nada is not satisfied with the list, she needs to identify more stakeholders until she is satisfied. Interviewing the identified key stakeholders again might not resolve the issue. The best option is to seek an expert's opinion. [PMBOK 6th edition, Page 511] | ندى تدير مشروع إعادة هندسة العمليات الصناعية المعقدة. لقد حددت جميع أصحاب المصلحة الرئيسيين في المشروع وأجرت مقابلات فردية معهم لتحديد أصحاب المصلحة الآخرين في المشروع أيضًا. ومع ذلك ، لا تزال ندى غير راضية عن قائمة أصحاب المصلحة في مشروعها. إنها تعتقد أنه قد يكون هناك المزيد من أصحاب المصلحة الخارجيين الرئيسيين المفقودين من القائمة. ما الذي يمكن أن يساعد ندى في هذه الحالة؟ | استخدم قوالب تسجيل أصحاب المصلحة من أصول العملية التنظيمية | عقد المزيد من الاجتماعات مع أصحاب المصلحة الرئيسيين | تغلب على مخاوفها واستكمل سجل أصحاب المصلحة في المشروع | اطلب رأي الخبراء من الخبراء المتخصصين | لا يحتوي نموذج سجل أصحاب المصلحة على معلومات أصحاب المصلحة ؛ إنه يساعد مدير المشروع فقط في إنتاج سجل أصحاب المصلحة في المشروع. إذا لم تكن ندى راضية عن القائمة ، فعليها تحديد المزيد من أصحاب المصلحة حتى تشعر بالرضا. قد لا تؤدي مقابلة أصحاب المصلحة الرئيسيين المحددين مرة أخرى إلى حل المشكلة. الخيار الأفضل هو البحث عن رأي خبير. [PMBOK الطبعة السادسة ، الصفحة 511] | 149 | 2 | False | "16" | Ahmad
48 | There are several communication methods used to share and distribute information to stakeholders, team members, and management. Which of the following communication methods is used when you notify the public about environmental effects from your project after implementation by posting reports on the project's website? | Interactive communication | Informal communication | Push communication | Pull communication | Push communication is used to send information to specific recipients who need to know. Push communication is done using letters, faxes, memos, etc. Pull communication is used for large volumes of information. The methods for this type of communication include internet sites and blogs. Since you want to notify the general public about environmental effects by posting reports on the project's website, this is an example of pull communication methods. [PMBOK 6th edition, Page 374] | هناك العديد من طرق الاتصال المستخدمة لمشاركة المعلومات وتوزيعها على أصحاب المصلحة وأعضاء الفريق والإدارة. أي من طرق الاتصال التالية تُستخدم عندما تُخطر الجمهور بالتأثيرات البيئية لمشروعك بعد التنفيذ عن طريق نشر التقارير على موقع الويب الخاص بالمشروع؟ | التواصل التفاعلي | التواصل غير الرسمي | دفع التواصل | سحب التواصل | يتم استخدام اتصال الدفع لإرسال المعلومات إلى مستلمين محددين يحتاجون إلى المعرفة. يتم إجراء اتصالات الدفع باستخدام الرسائل والفاكسات والمذكرات وما إلى ذلك. يتم استخدام اتصال السحب لأحجام كبيرة من المعلومات. تشمل طرق هذا النوع من الاتصال مواقع الإنترنت والمدونات. نظرًا لأنك تريد إخطار عامة الناس بالتأثيرات البيئية عن طريق نشر التقارير على موقع الويب الخاص بالمشروع ، فهذا مثال على طرق الاتصال. [الطبعة السادسة من PMBOK ، صفحة 374] | 146 | 3 | False | "16" | Ahmad
49 | Ali is in the execution phase of his project. He is getting unexpected requests from his stakeholders about the project’s progress. Ali can use all the following to respond to their requests except: | Communications management plan | Organizational process assets | Work performance reports | Business case | Since Ali is in the execution phase and stakeholders are requesting project information, he must respond through the Manage Communications process. The communications management plan, organizational process assets and work performance reports are inputs to this process. Ali can use any of these documents to respond to their requests. The project's business case is not of much help at this stage. [PMBOK 6th edition, Page 379] | علي في مرحلة تنفيذ مشروعه. إنه يتلقى طلبات غير متوقعة من أصحاب المصلحة حول تقدم المشروع. يمكن لعلي استخدام كل ما يلي للرد على طلباتهم باستثناء: | خطة إدارة الاتصالات | أصول العمليات التنظيمية | تقارير أداء العمل | مسوغ المشروع | نظرًا لأن علي في مرحلة التنفيذ ويطلب أصحاب المصلحة معلومات عن المشروع ، يجب عليه الرد من خلال عملية إدارة الاتصالات. تعتبر خطة إدارة الاتصالات وأصول العملية التنظيمية وتقارير أداء العمل من المدخلات في هذه العملية. يمكن لعلي استخدام أي من هذه المستندات للرد على طلباتهم. مسوغ المشروع لا يساعد كثيرًا في هذه المرحلة. [الطبعة السادسة من PMBOK ، صفحة 379] | 146 | 4 | False | "18" | Ahmad
50 | Salwa has to brief her key project stakeholders on the recent approved changes to the project scope. Which of the following project documents will provide essential input to Salwa for preparing her presentation? | Change request form | Change control procedures | Issue management procedures | Change log | The change control procedure and the issue management procedure are organizational process assets. They do not document the details of the recently approved project changes. Lucy can find all the essential inputs for her presentation in the project change log. [PMBOK 6th edition, Page 120] | يتعين على سلوى إطلاع أصحاب المصلحة الرئيسيين في المشروع على التغييرات المعتمدة الأخيرة في نطاق المشروع. أي من وثائق المشروع التالية ستوفر المدخلات الأساسية لسلوى لإعداد عرضها التقديمي؟ | تغيير استمارة الطلب | تغيير إجراءات الرقابة | إصدار إجراءات الإدارة | سجل التغيير | يعتبر إجراء التحكم في التغيير وإجراءات إدارة المشكلة من أصول العملية التنظيمية. لا يوثقون تفاصيل تغييرات المشروع التي تمت الموافقة عليها مؤخرًا. يمكن أن تجد لوسي جميع المدخلات الأساسية لعرضها التقديمي في سجل تغيير المشروع. [الطبعة السادسة من PMBOK ، الصفحة 120] | 140 | 5 | False | "19" | Ahmad
51 | You have recently taken over a troubled automobile project, which has gone out of control. The project team missed many deadlines, and stakeholders were displeased with the project’s progress. As an experienced project manager, your first priority is to align the schedule with the project plan. You would like to use what-if scenario analysis to see how various factors affected the project schedule so you can develop a plan to reduce the impact of adverse conditions on the project schedule in the future. What would be your next course of action be, once you determine the factors that created schedule overruns? | Prepare a resource breakdown structure to identify resources used | Update activity lists to incorporate new activities into the schedule | Develop project schedule network diagrams to determine the total slack | Generate change requests for a corrective action | You are in the process of determining the status of the project schedule and investigating the factors that caused schedule changes. From this scenario, you are currently in the Control Schedule process. What-if analysis is used in the Control Schedule process to see how various factors influence the schedule. One output of this process is to generate change requests to correct the schedule. Hence, you should generate a change request for the required corrective action. [PMBOK 6th edition, Page 229] | لقد استلمت مؤخرًا مشروع سيارات متعثر ، وخرج عن السيطرة. فات فريق المشروع العديد من المواعيد النهائية ، وكان أصحاب المصلحة غير راضين عن تقدم المشروع. بصفتك مدير مشروع ذي خبرة ، فإن أولويتك الأولى هي مواءمة الجدول الزمني مع خطة المشروع. قد ترغب في استخدام تحليل سيناريو ماذا لو لمعرفة كيف أثرت العوامل المختلفة على الجدول الزمني للمشروع حتى تتمكن من وضع خطة لتقليل تأثير الظروف المعاكسة على الجدول الزمني للمشروع في المستقبل. ماذا سيكون مسار العمل التالي ، بمجرد تحديد العوامل التي أدت إلى تجاوز الجدول الزمني؟ | القيام بإعداد هيكل توزيع الموارد لتحديد الموارد المستخدمة | القيام بتحديث قوائم الأنشطة لدمج الأنشطة الجديدة في الجدول | القيام بتطوير مخططات شبكة جدول المشروع لتحديد إجمالي فترة السماح | توليد طلبات التغيير لإجراء تصحيحي | أنت بصدد تحديد حالة جدول المشروع والتحقيق في العوامل التي تسببت في تغييرات الجدول. من هذا السيناريو ، أنت حاليًا في عملية جدول التحكم. تم استخدام تحليل ماذا لو في عملية جدول التحكم لمعرفة كيف تؤثر العوامل المختلفة على الجدول. يتمثل أحد مخرجات هذه العملية في إنشاء طلبات التغيير لتصحيح الجدول. وبالتالي ، يجب عليك إنشاء طلب تغيير للإجراء التصحيحي المطلوب. [الطبعة السادسة من PMBOK ، الصفحة 229] | 142 | 5 | False | "18" | Ahmad
52 | You are in the Validate Scope process of your electronic goods manufacturing project. While reviewing some products, you have noticed that the tolerance for one product is 0.01 percent less than what was listed in the requirements documentation. This deviation may not be a problem for the customers, and it may not impair the product’s operation. What is your best immediate action in such a situation? | Change the project management plan to allow for small deviation | Reject all products and restart the project | Discuss with your team about the quality testing | Notify the stakeholders about the deviation | When you find a defective product, you must notify stakeholders immediately even if the deviation may not affect customers. As a project manager, you must maintain honesty and should not hide facts. After notifying the stakeholders, the project manager must discuss the issue with the team and change the project management plan based on the stakeholders’ inputs. [PMI Code of Ethics and Professional Conduct] [Prof. Responsibility] | أنت في عملية التحقق من النطاق لمشروع تصنيع السلع الإلكترونية. أثناء مراجعة بعض المنتجات ، لاحظت أن التفاوت المسموح به لمنتج واحد أقل بنسبة 0.01 بالمائة مما تم سرده في وثائق المتطلبات. قد لا يمثل هذا الانحراف مشكلة للعملاء ، وقد لا يضر بتشغيل المنتج. ما هو أفضل إجراء فوري في مثل هذه الحالة؟ | قم بتغيير خطة إدارة المشروع للسماح بانحراف بسيط | ارفض جميع المنتجات وأعد تشغيل المشروع | ناقش مع فريقك حول اختبار الجودة | إبلاغ أصحاب المصلحة عن الانحراف | عندما تجد منتجًا معيبًا ، يجب عليك إخطار أصحاب المصلحة على الفور حتى إذا كان الانحراف قد لا يؤثر على العملاء. بصفتك مدير مشروع ، يجب عليك الحفاظ على الصدق وعدم إخفاء الحقائق. بعد إخطار أصحاب المصلحة ، يجب على مدير المشروع مناقشة المشكلة مع الفريق وتغيير خطة إدارة المشروع بناءً على مدخلات أصحاب المصلحة. [مدونة الأخلاق والسلوك المهني لدى معهد إدارة المشاريع] [المسئوليةالمهنية] | 141 | 5 | False | "17" | Ahmad
53 | A project manager has just started planning his project. If he has only limited information about the project, he should use the following technique to estimate the duration for each activity using historical data from a similar project: | Four-point estimating | Three-point estimating | Parametric estimating | Analogous estimating | When there is a limited amount of information available about a project, analogous estimating is used to estimate the activity durations. This estimating technique uses parameters such as budget, complexity and size from previous projects to estimate the duration. [PMBOK 6th edition, Page 200] | بدأ مدير المشروع للتو في التخطيط لمشروعه. إذا كان لديه معلومات محدودة فقط عن المشروع ، فعليه استخدام التقنية التالية لتقدير المدة لكل نشاط باستخدام البيانات التاريخية من مشروع مماثل: | أربع نقاط تقدير | ثلاث نقاط تقدير | التقدير الاحصائي (استخدام المعادلات الرياضية) | تقدير مماثل | عندما يكون هناك قدر محدود من المعلومات المتاحة حول المشروع ، يتم استخدام تقدير مماثل لتقدير مدد النشاط. تستخدم تقنية التقدير هذه معلمات مثل الميزانية والتعقيد والحجم من المشاريع السابقة لتقدير المدة. [الطبعة السادسة من PMBOK ، الصفحة 200] | 142 | 3 | False | "20" | Ahmad
54 | You just completed the first phase of a multi-phase project. You have calculated earned value measurements and found that the current CPI is 0.79 and the current SPI is 0.98. Your next phase plan should focus first on which element of the project: | Quality | Resources | Schedule | Cost | A Schedule Performance Index (SPI) of less than one indicates that less work has completed than planned, and a Cost Performance Index (CPI) of less than one indicates a cost overrun for the work completed. In this scenario, the cost overrun is more severe than the schedule delay. Therefore, you should focus on reducing the cost of the project. [PMBOK 6th edition, Page 263] | لقد أكملت للتو المرحلة الأولى من مشروع متعدد المراحل. لقد قمت بحساب قياسات القيمة المكتسبة ووجدت أن مؤشر أسعار المستهلك الحالي هو 0.79 ومؤشر SPI الحالي هو 0.98. يجب أن تركز خطة المرحلة التالية أولاً على عنصر المشروع: | جودة | مصادر | جدول | كلفة | يشير مؤشر أداء الجدول (SPI) الذي يقل عن واحد إلى أنه تم إكمال عمل أقل مما هو مخطط له ، ويشير مؤشر أداء التكلفة (CPI) الذي يقل عن واحد إلى تجاوز تكلفة العمل المكتمل. في هذا السيناريو ، يكون تجاوز التكلفة أكثر حدة من تأخير الجدول. لذلك ، يجب التركيز على تقليل تكلفة المشروع. [الطبعة السادسة من PMBOK ، الصفحة 263] | 143 | 5 | False | "19" | Ahmad
55 | Which document defines how the project is to be executed, monitored, controlled, and closed? | Project scope | Project charter | Project management information system | Project management plan | The project management plan defines how the project is executed, monitored, controlled, and closed. [PMBOK 6th edition, Page 83] | ما المستند الذي يحدد كيفية تنفيذ المشروع ومراقبته والتحكم فيه وإغلاقه؟ | نطاق المشروع | ميثاق المشروع | نظام معلومات إدارة المشروع | خطة إدارة المشروع | تحدد خطة إدارة المشروع كيفية تنفيذ المشروع ومراقبته والتحكم فيه وإغلاقه. [الطبعة السادسة من PMBOK ، الصفحة 83] | 140 | 3 | False | "19" | Ahmad
56 | Which of the following is neither an input to nor an output of the Develop Project Charter process? | A project charter | A business case | Benefits management plan | Expert Judgment | A project statement of work and a business case are inputs to the Develop Project Charter process. A project charter is an output of the Develop Project Charter process. Expert judgment is a tool and technique of this process. [PMBOK 6th edition, Page 75] | أي مما يلي لا يعتبر مدخلاً أو ناتجًا لعملية تطوير ميثاق المشروع؟ | ميثاق المشروع | مستند حالة اعمال المشروع | خطة إدارة الفوائد | حكم خبير | بيان عمل المشروع ودراسة الجدوى هي مدخلات لعملية تطوير ميثاق المشروع. ميثاق المشروع هو نتيجة لعملية تطوير ميثاق المشروع. حكم الخبراء هو أداة وتقنية لهذه العملية. [الطبعة السادسة من PMBOK ، الصفحة 75] | 140 | 2 | False | "20" | Ahmad
57 | Your project team has recently identified a risk in the software development project and decided not to change the project management plan to deal with the risk. The risk response strategy that your team used in this scenario is an example of: | Mitigate | Transfer | Avoid | Acceptance | When risks cannot be handled or managed in a project, it is advisable to accept them. In this scenario, your team is unable to devise a suitable response strategy. Hence, risk acceptance is the correct strategy to employ. [PMBOK 6th edition, Page 443] | حدد فريق المشروع مؤخرًا أحد المخاطر في مشروع تطوير البرامج وقرر عدم تغيير خطة إدارة المشروع للتعامل مع المخاطر. استراتيجية الاستجابة للمخاطر التي استخدمها فريقك في هذا السيناريو هي مثال على: | تخفيف | نقل | تجنب | قبول | عندما لا يمكن التعامل مع المخاطر أو إدارتها في مشروع ما ، فمن المستحسن قبولها. في هذا السيناريو ، يتعذر على فريقك وضع استراتيجية استجابة مناسبة. ومن ثم ، فإن قبول المخاطر هو الاستراتيجية الصحيحة للاستخدام. [الطبعة السادسة من PMBOK ، صفحة 443] | 147 | 3 | False | "17" | Ahmad
58 | All the following activities are performed in the Close Project or Phase process except: | Activities that fulfill the exit criteria of the project | Activities that are needed to transfer the completed products to operations | Documenting the reasons for terminating the projects early | Sending the deliverables to the customer for acceptance | Sending the deliverables to the customer for acceptance is an activity of the Validate Scope process. The other choices are activities related to the Close Project or Phase process. [PMBOK 6th edition, Page 123] | يتم تنفيذ جميع الأنشطة التالية في عملية إغلاق المشروع أو المرحلة باستثناء: | الأنشطة التي تستوفي معايير الخروج من المشروع | الأنشطة اللازمة لنقل المنتجات المكتملة إلى العمليات | توثيق أسباب إنهاء المشاريع مبكراً | إرسال التسليمات إلى العميل للقبول | يعد إرسال التسليمات إلى العميل للقبول نشاطًا لعملية التحقق من النطاق. الخيارات الأخرى هي الأنشطة المتعلقة بإغلاق المشروع أو عملية المرحلة. [الطبعة السادسة من PMBOK ، صفحة 123] | 140 | 6 | False | "17" | Ahmad
59 | You are working as a project manager for a high-yield crop development project. Data from the weather agency shows an unfavorable weather pattern for the next few months. As a senior project manager, you want to assess the schedule’s feasibility under adverse conditions and provide some insights to your team. That way, your team can prepare some reserves and plan risk responses if unfavorable conditions exist during execution. Which of the following techniques should you use to simulate risks and other sources of uncertainty to calculate possible schedule outcomes? | Pareto charts | Variance analysis | Crashing | Monte Carlo analysis | Modeling techniques are used to prepare a schedule under various scenarios. These techniques help assess the feasibility of the project schedule if adverse conditions exist. The Monte Carlo technique employs simulation to calculate multiple project durations, each with a different set of activity assumptions using a probability distribution. [PMBOK 6th edition, Page 213] [Project Schedule Management] | أنت تعمل كمدير مشروع لمشروع تنمية المحاصيل عالي الإنتاجية. تُظهر البيانات الواردة من وكالة الأرصاد الجوية نمط طقس غير مواتٍ للأشهر القليلة القادمة. بصفتك مدير مشروع أول ، فأنت تريد تقييم جدوى الجدول الزمني في ظل ظروف معاكسة وتقديم بعض الأفكار لفريقك. بهذه الطريقة ، يمكن لفريقك إعداد بعض الاحتياطيات والتخطيط للاستجابات للمخاطر في حالة وجود ظروف غير مواتية أثناء التنفيذ. أي من الأساليب التالية يجب أن تستخدمه لمحاكاة المخاطر ومصادر عدم اليقين الأخرى لحساب نتائج الجدول الزمني المحتملة؟ | مخططات باريتو | تحليل التباين | حشد الموارد | تحليل مونت كارلو | تُستخدم تقنيات النمذجة لإعداد جدول في ظل سيناريوهات مختلفة. تساعد هذه التقنيات في تقييم جدوى الجدول الزمني للمشروع في حالة وجود ظروف معاكسة. تستخدم تقنية مونت كارلو المحاكاة لحساب مدد متعددة للمشروع ، لكل منها مجموعة مختلفة من افتراضات النشاط باستخدام توزيع الاحتمالات. [الإصدار السادس من PMBOK ، صفحة 213] [إدارة جدول المشروع] | 142 | 3 | False | "16" | Ahmad
60 | You are managing a heavy equipment manufacturing project that involves many mechanical, electrical, and IT staff. Your team prepared a schedule network diagram using duration estimates with dependencies and constraints. Your team also calculated the critical path for the project using late and early values. Today, your project office has indicated to you that some of the resources you had planned for the project will be unavailable. To deal with this, you explore the possibility of modifying the schedule to account for limited resources. What is your best possible step in such a situation? | Perform Resource Leveling to account for limited resources | Use crashing or fast tracking to level resources across the project | Apply leads and lags to develop a viable schedule | Recalculate critical path after applying the resource constraints | The critical path method is used to prepare a schedule network diagram. A network diagram is prepared initially, and the critical path is then calculated. Availability of resources is entered, and a resource limited schedule is prepared. Hence, recalculating the critical path using the critical path method after applying the resource constraints is the next best step. [PMBOK 6th edition, Page 210] | أنت تدير مشروعًا لتصنيع المعدات الثقيلة يتضمن العديد من موظفي الميكانيكا والكهرباء وتكنولوجيا المعلومات. أعد فريقك مخططًا لشبكة الجدول الزمني باستخدام تقديرات المدة مع التبعيات والقيود. قام فريقك أيضًا بحساب المسار الحرج للمشروع باستخدام القيم المتأخرة والمبكرة. اليوم ، أوضح لك مكتب مشروعك أن بعض الموارد التي خططت لها للمشروع لن تكون متاحة. للتعامل مع هذا الأمر ، يمكنك استكشاف إمكانية تعديل الجدول لمراعاة الموارد المحدودة. ما هي أفضل خطوة ممكنة في مثل هذه الحالة؟ | قم بإجراء "تسوية الموارد" لحساب الموارد المحدودة | استخدم حشد الموارد أو التتبع السريع لتسوية الموارد عبر المشروع | تطبيق اداة الاستباق والتخلف لتطوير جدول زمني | إعادة حساب المسار الحرج بعد تطبيق قيود الموارد | تُستخدم طريقة المسار الحرج لإعداد مخطط شبكة جدولة. يتم إعداد مخطط الشبكة في البداية ، ثم يتم حساب المسار الحرج. يتم إدخال توفر الموارد ، ويتم إعداد جدول زمني محدود الموارد. ومن ثم ، فإن إعادة حساب المسار الحرج باستخدام طريقة المسار الحرج بعد تطبيق قيود الموارد هي الخطوة التالية الأفضل. [الطبعة السادسة من PMBOK ، الصفحة 210] | 142 | 3 | False | "17" | Ahmad
61 | You are working with your customers on completing deliverables in your electronic parts manufacturing project. Since these parts will be exported to other countries, they will need more testing before your customers accept them. In this scenario, which of the following statements about the completed deliverables is correct? | Completed deliverables not accepted by customers must be forwarded to the close project or phase process. | Deliverables formally accepted by customers must be moved to organizational process assets. | Deliverables formally accepted by customers are forwarded to the validate scope process. | Completed deliverables not accepted by customers must require a change request for defect repair. | Validate Scope is the process of formalizing the acceptance of finished deliverables. In this process, stakeholders or customers give formal acceptance of the completed deliverables. The accepted deliverables are forwarded to the Close Project or Phase process. If there are any completed deliverables that they do not accept, a change request for defect repair must be initiated. [PMBOK 6th edition, Page 166] | أنت تعمل مع عملائك على إكمال التسليمات في مشروع تصنيع الأجزاء الإلكترونية. نظرًا لأنه سيتم تصدير هذه الأجزاء إلى بلدان أخرى ، فستحتاج إلى مزيد من الاختبارات قبل أن يقبلها عملاؤك. في هذا السيناريو ، أي من العبارات التالية حول المخرجات المكتملة صحيحة؟ | يجب إعادة توجيه التسليمات المكتملة التي لم يقبلها العملاء إلى عملية إغلاق المشروع أو المرحلة. | يجب نقل التسليمات المقبولة رسميًا من قبل العملاء إلى أصول العملية التنظيمية. | يتم إرسال التسليمات المقبولة رسميًا من قبل العملاء إلى عملية التحقق من النطاق. | يجب أن تتطلب التسليمات المكتملة التي لم يقبلها العملاء طلب تغيير لإصلاح العيب. | التحقق من النطاق هو عملية إضفاء الطابع الرسمي على قبول التسليمات النهائية. في هذه العملية ، يعطي أصحاب المصلحة أو العملاء قبولًا رسميًا للنتائج المكتملة. يتم إرسال التسليمات المقبولة إلى عملية إغلاق المشروع أو المرحلة. إذا كانت هناك أي مخرجات مكتملة لا يقبلونها ، فيجب بدء طلب تغيير لإصلاح العيب. [الطبعة السادسة من PMBOK ، الصفحة 166] | 141 | 5 | False | "18" | Ahmad
62 | All the following are tools of the Control Schedule process except: | Critical Path Method | Schedule compression | Leads and lags | Parametric estimating | Leads and lags, schedule compression and critical path method are tools in the Control Schedule process. Parametric estimating is not a tool of this process. [PMBOK 6th edition, Page 222] | كل ما يلي عبارة عن أدوات لعملية جدول التحكم باستثناء: | طريقة المسار الحرج | ضغط الجدول الزمني | الاستباق والتخلف | التقدير الاحصائي (استخدام المعادلات الرياضية) | تعتبر الاستباق والتخلف وضغط الجدول الزمني وطريقة المسار الحرج أدوات في عملية جدول التحكم. التقدير البارامترى ليس أداة لهذه العملية. [الطبعة السادسة من PMBOK ، صفحة 222] | 142 | 5 | False | "20" | Ahmad
63 | No matter how good you are in communicating, information distribution to stakeholders as planned is a challenging task. Many tools and techniques are used during the Manage Communications process except: | Project reporting | Communication technologies | Communication skills | Work performance reports | The work performance reports are inputs to the Manage Communications process. The other choices are the valid tools and techniques of the Manage Communications process. [PMBOK 6th edition, Page 379] | بغض النظر عن مدى براعتك في التواصل ، فإن توزيع المعلومات على أصحاب المصلحة كما هو مخطط يعد مهمة صعبة. يتم استخدام العديد من الأدوات والتقنيات أثناء عملية إدارة الاتصالات باستثناء: | تقارير المشروع | تكنولوجيات الاتصال | مهارات التواصل | تقارير أداء العمل | تعد تقارير أداء العمل بمثابة مدخلات لعملية إدارة الاتصالات. الخيارات الأخرى هي الأدوات والتقنيات الصالحة لعملية إدارة الاتصالات. [الطبعة السادسة من PMBOK ، صفحة 379] | 146 | 4 | False | "18" | Ahmad
64 | You are managing a project for a customer that has just gone bankrupt and is subject to liquidation proceedings. There are several outstanding invoices this customer has not paid to your company. What should you do now? | Go into alternate dispute resolution | Do nothing | Send the invoices to the bankruptcy attorneys | Contact the appropriate management at your company for advice how to proceed | You are responsible for finding the right way to handle this situation. Contact your management for advice on how to proceed. Your company may already have plans in place for this scenario; if not, they will develop a path forward. [PMI Code of Ethics and Professional Conduct] [Prof. Responsibility] | أنت تدير مشروعًا لعميل أفلس للتو ويخضع لإجراءات التصفية. هناك العديد من الفواتير المعلقة التي لم يدفعها هذا العميل لشركتك. ماذا عليك ان تفعل الان؟ | انتقل إلى حل النزاع البديل | لا تفعل شيئا | إرسال الفواتير لمحامي الإفلاس | اتصل بالإدارة المناسبة في شركتك للحصول على المشورة بشأن كيفية المتابعة | أنت مسؤول عن إيجاد الطريقة الصحيحة للتعامل مع هذا الموقف. اتصل بإدارتك للحصول على المشورة بشأن كيفية المتابعة. قد يكون لشركتك بالفعل خطط جاهزة لهذا السيناريو ؛ إذا لم يكن الأمر كذلك ، فسوف يطورون طريقًا إلى الأمام. [مدونة الأخلاق والسلوك المهني لدى معهد إدارة المشاريع] [المسئولية المهنية] | 140 | 4 | False | "19" | Ahmad
65 | _______________ is the authorized budget for the work scheduled to be completed on an activity or WBS component. | Earned value | Midpoint cost | Interim cost | Planned value | Planned value is the budgeted cost of the work scheduled to be completed on an activity or WBS component up to a given point in time. [PMBOK 6th edition, Page 261] | _______________ هي الميزانية المصرح بها للعمل المجدول لاستكمال نشاط أو مكون WBS. | القيمة المكتسبة | تكلفة نقطة المنتصف | التكلفة المؤقتة | القيمة المخططة | القيمة المخططة هي التكلفة المدرجة في الميزانية للعمل المجدول لإكماله في نشاط أو مكون هيكل تجزئة العمل حتى نقطة زمنية معينة. [الطبعة السادسة من PMBOK ، الصفحة 261] | 143 | 5 | False | "20" | Ahmad
66 | The RACI chart is an example of a responsibility assignment matrix (RAM). The letters R and C in “RACI” stand for: | Resource and consultant | Responsible and categorize | Resource and consult | Responsible and consult | The responsibility assignment matrix (RAM) describes the relationship between resources and work packages. An RACI chart is an example of a RAM. The letters in “RACI” stand for Responsible, Accountable, Consult, and Inform. [PMBOK 6th edition, Page 317] | مخطط RACI هو مثال على مصفوفة تعيين المسؤولية (RAM). يرمز الحرفان R و C في "RACI" إلى: | الموارد والاستشاري | المسؤولية والتصنيف | الموارد والاستشارة | مسؤول واستشارة | تصف مصفوفة تعيين المسؤولية (RAM) العلاقة بين الموارد وحزم العمل. مخطط RACI هو مثال على ذاكرة الوصول العشوائي. تشير الأحرف الموجودة في "RACI" إلى "مسئول ومسؤول واستشارة وإعلام". [الطبعة السادسة من PMBOK ، صفحة 317] | 145 | 3 | False | "20" | Ahmad
67 | Project costs are estimated for all project activities and are aggregated to establish a cost baseline. Which of the following statements about the cost baseline is not true? | The project cost performance is measured against the cost baseline. | The cost baseline is an output of the determine budget process. | The cost baseline is in the form of an ‘S’ curve. | The cost baseline includes all authorized budgets, including management reserves. | The project cost baseline includes all authorized budgets excluding management reserves. Management reserves are not included to measure the cost performance of a project. [PMBOK 6th edition, Page 248] | يتم تقدير تكاليف المشروع لجميع أنشطة المشروع ويتم تجميعها لإنشاء خط أساس للتكلفة. أي من العبارات التالية حول خط أساس التكلفة غير صحيح؟ | يتم قياس أداء تكلفة المشروع مقابل خط الأساس المرجعي للتكلفة المعتمد . | يعتبر خط الأساس المرجعي للتكلفة المعتمد ناتجًا عن عملية تحديد الموازنة. | يتخذ خط الأساس المرجعي للتكلفة المعتمد شكل منحنى "S". | يشمل خط الأساس المرجعي للتكلفة المعتمد جميع الميزانيات المصرح بها ، بما في ذلك احتياطيات الإدارة. | يتضمن خط الأساس لتكلفة المشروع جميع الميزانيات المصرح بها باستثناء احتياطيات الإدارة. لا يتم تضمين احتياطيات الإدارة لقياس أداء تكلفة المشروع. [الطبعة السادسة من PMBOK ، الصفحة 248] | 143 | 3 | False | "16" | Ahmad
68 | The project you are working on has received an invoice from a vendor for US$17,500. However, your team believes the correct total due is US$15,300. When you notify the vendor, the vendor still insists on US$17,500. What is the best course of action now? | Pay $15,300 | File a lawsuit | Pay $17,500 | Negotiate with the vendor | Negotiate with the vendor. Making a unilateral decision is counter to the PMI Code of Ethics, which mandates good faith negotiations. Failing to negotiate will not be in the best interest of either the project or the vendor. [PMBOK 6th edition, Page 498; PMI Code of Ethics and Professional Conduct] [Prof. Responsibility] | تلقى المشروع الذي تعمل عليه فاتورة من بائع بمبلغ 17500 دولار أمريكي. ومع ذلك ، يعتقد فريقك أن المبلغ الإجمالي الصحيح المستحق هو 15300 دولار أمريكي. عند إخطار البائع ، لا يزال البائع يصر على 17500 دولار أمريكي. ما هو أفضل مسار للعمل الآن؟ | ادفع 15300 دولار | رفع دعوى قضائية | ادفع 17500 دولار | تفاوض مع البائع | تفاوض مع البائع. إن اتخاذ قرار من جانب واحد يتعارض مع مدونة الأخلاق الخاصة بمعهد إدارة المشاريع ، التي تنص على إجراء مفاوضات بحسن نية. لن يكون الفشل في التفاوض في مصلحة المشروع أو البائع. [PMBOK 6th edition، Page 498؛ مدونة الأخلاق والسلوك المهني لدى معهد إدارة المشاريع] [المسئولية المهنية] | 148 | 5 | False | "17" | Ahmad
69 | A team member in your project is constantly providing incomplete deliverables and not performing well. What should you do first? | Discuss the issue with the team member in the presence of the project sponsor | Discuss the issue with the team member in the presence of other team members | Discuss the issue with the team member in the presence of the company's HR manager | Discuss the issue with the team member in private | Discuss the issue with the team member in private. Conflicts should be first addressed in private, using a direct and collaborative approach. [PMBOK 6th edition, Page 348] | يقدم أحد أعضاء الفريق في مشروعك باستمرار مخرجات غير مكتملة ولا يؤدي أداءً جيدًا. ما الذى ينبغى عليك فعله اولا؟ | ناقش الموضوع مع عضو الفريق بحضور راعي المشروع | ناقش المشكلة مع عضو الفريق بحضور أعضاء الفريق الآخرين | ناقش المشكلة مع عضو الفريق بحضور مدير الموارد البشرية بالشركة | ناقش المشكلة مع عضو الفريق على انفراد | ناقش المشكلة مع عضو الفريق على انفراد. يجب أولاً معالجة النزاعات على انفراد ، باستخدام نهج مباشر وتعاوني. [الطبعة السادسة من PMBOK ، الصفحة 348] | 145 | 4 | False | "18" | Ahmad
70 | The method used in the Manage Quality process to identify the factors that may influence specific characteristics of a product under development is: | The forecasting technique | The control chart | The statistical sampling | Design for X | Design for X is a set of technical guidelines that may be applied during the design of a product for the optimization of a specific aspect of the design. Daft can control or even improve the product's final characteristics. [PMBOK 6th edition, Page 295] | الطريقة المستخدمة في عملية إدارة الجودة لتحديد العوامل التي قد تؤثر على خصائص معينة لمنتج قيد التطوير هي: | تقنية التنبؤ | مخطط التحكم | أخذ العينات الإحصائية | تصميم من اجل التميز | التصميم من اجل التميز عبارة عن مجموعة من الإرشادات الفنية التي يمكن تطبيقها أثناء تصميم منتج ما لتحسين جانب معين من التصميم. يمكن لـ المسودة التحكم في الخصائص النهائية للمنتج أو حتى تحسينها. [الطبعة السادسة من PMBOK ، الصفحة 295] | 144 | 4 | False | "16" | Ahmad
71 | You have just received notice that the organization you have worked for as a project manager has gone bankrupt. All employees have 72 hours’ notice of termination. What is the best course of action for the two projects you are managing? | Conduct a project closeout meeting | Leave the office today | Raise a claim for and on behalf of all the employees and contractors who were participating in the project | Follow company directives | Follow all company directives. The organization’s management is responsible for developing these directives, which may include specific instructions on closing out work in progress. [PMI Code of Ethics and Professional Conduct] [Prof. Responsibility] | لقد تلقيت للتو إشعارًا بأن المؤسسة التي عملت بها كمدير مشروع قد أفلست. جميع الموظفين لديهم إشعار 72 ساعة من الإنهاء. ما هو أفضل مسار عمل للمشروعين اللذين تديرهما؟ | عقد اجتماع ختام المشروع | اترك المكتب اليوم | رفع دعوى لصالح ونيابة عن جميع الموظفين والمقاولين الذين كانوا يشاركون في المشروع | اتبع توجيهات الشركة | اتبع جميع توجيهات الشركة. إدارة المنظمة مسؤولة عن تطوير هذه التوجيهات ، والتي قد تتضمن تعليمات محددة بشأن إغلاق العمل الجاري. [مدونة الأخلاق والسلوك المهني لدى معهد إدارة المشاريع] [المسئولية المهنية] | 140 | 4 | False | "20" | Ahmad
72 | Which of the following is an output of the Create WBS process? | Project scope statement | Decomposition | Requirements documentation | Scope baseline | The scope baseline is an output of the Create WBS process. The other choices are either inputs or tools and techniques of the process. [PMBOK 6th edition, Page 156] | أي مما يلي يعد ناتجًا عن عملية إنشاء هيكل تنظيم العمل؟ | بيان نطاق المشروع | تقسيم | مستندات المتطلبات | خط الاساس المرجعي المعتمد للنطاق | يعتبر النطاق الأساسي ناتجًا عن عملية إنشاء هيكل تنظيم العمل. الخيارات الأخرى هي إما مدخلات أو أدوات وتقنيات للعملية. [الطبعة السادسة من PMBOK ، الصفحة 156] | 141 | 3 | False | "18" | Ahmad
73 | Mervat an IT project manager, is in the planning phase of a shopping website development project. A junior project manager, who has worked under her authority, started developing procedures for maintaining the integrity of cost and schedule performance baselines in the project. Where should the junior project manager store these procedures? | In the project resource management plan | In the project scope statement | In the project communications management plan | In the project management plan | The baselines change only when a change request is generated. A project management plan documents the procedures for making changes to performance baselines. These baselines include scope, cost and schedule baselines. Therefore, the junior project manager must store these procedures in the project management plan. [PMBOK 6th edition, Page 88] | ميرفت ، مديرة مشروع تكنولوجيا المعلومات ، في مرحلة التخطيط لمشروع تطوير موقع إلكتروني للتسوق. بدأت مديرة مشروع مبتدئة ، والتي عملت تحت سلطتها ، في تطوير إجراءات للحفاظ على سلامة التكلفة وجدولة خطوط الأساس في المشروع. أين يجب على مدير المشروع المبتدئ تخزين هذه الإجراءات؟ | في خطة إدارة موارد المشروع | في بيان نطاق المشروع | في خطة إدارة اتصالات المشروع | في خطة إدارة المشروع | تتغير الخطوط الأساسية فقط عند إنشاء طلب التغيير. توثق خطة إدارة المشروع إجراءات إجراء تغييرات على خطوط أساس الأداء. تتضمن خطوط الأساس هذه الخطوط الأساسية للنطاق والتكلفة والجدول الزمني. لذلك ، يجب على مدير المشروع المبتدئ تخزين هذه الإجراءات في خطة إدارة المشروع. [الطبعة السادسة من PMBOK ، صفحة 88] | 140 | 3 | False | "17" | Ahmad
74 | Fatimah can bid on two projects. Project A has a 50 percent return on investment while Project B has a 20 percent return on investment. Project A’s scope of work is complex, and Fatimah’s organization does not have the necessary skills and experience to do this project. However, Project B’s scope of work falls within the strengths of Fatimah’s organization. Which project must Fatimah bid on? | None as this is a conflict of interest situation | Both since the overall profit will be higher | Project A since the return on investment is the highest | Project B since the organization has the required skills | Fatimah must not bid on Project A since her organization lacks the required skills and experience. This leaves her with only Project B to bid on. Project managers are mandated by the PMI's code of ethics and professional conduct to accept only those assignments that are consistent with their background, experience, skills and qualifications. [PMI Code of Ethics & Professional Conduct] [Prof. Responsibility] | يمكن أن تقدم فاطمة العطاء على مشروعين. يتمتع المشروع (أ) بعائد استثمار بنسبة 50 في المائة بينما يتمتع المشروع (ب) بعائد استثمار بنسبة 20 في المائة. نطاق عمل المشروع (أ) معقد ، ومنظمة فاطمة لا تمتلك المهارات والخبرة اللازمة للقيام بهذا المشروع. ومع ذلك ، فإن نطاق عمل المشروع ب يقع ضمن نقاط القوة في مؤسسة فاطمة. ما هو المشروع الذي يجب على فاطمة تقديم العطاء فيه؟ | لا شيء لأن هذا هو حالة تضارب في المصالح | كلاهما لأن الربح الإجمالي سيكون أعلى | المشروع (أ) حيث أن العائد على الاستثمار هو الأعلى | المشروع B حيث أن المنظمة لديها المهارات المطلوبة | يجب ألا تقدم فاطمة عرضًا على المشروع "أ" لأن مؤسستها تفتقر إلى المهارات والخبرة المطلوبة. هذا يترك لها فقط المشروع ب للمزايدة عليه. يتم تكليف مديري المشاريع بموجب مدونة الأخلاقيات والسلوك المهني لمعهد إدارة المشاريع بقبول تلك المهام التي تتوافق مع خلفيتهم وخبراتهم ومهاراتهم ومؤهلاتهم فقط. [مدونة الأخلاق والسلوك المهني PMI] [المسئولية المهنية] | 140 | 2 | False | "19" | Ahmad
75 | Analysis of project spending against project budget and calculation of the percentage complete of tasks currently underway are examples of: | Control Chart | PERT analysis | Expert judgment | Performance reviews | Performance reviews compare performance over time and funds needed to complete the work in progress. [PMBOK 6th edition, Page 712] | تحليل إنفاق المشروع مقابل ميزانية المشروع وحساب النسبة المئوية لإكمال المهام الجارية حاليًا هي أمثلة على: | مخطط التحكم | تحليل بيرت | حكم خبير | استعراضات الأداء | تقارن مراجعات الأداء الأداء بمرور الوقت والأموال اللازمة لإكمال العمل الجاري. [الطبعة السادسة من PMBOK ، الصفحة 712] | 143 | 5 | False | "18" | Ahmad
76 | Organizations evaluate whether to buy products or make the items themselves. Which of the following is not a factor that influences make-or-buy decisions: | Core capabilities of the organization | Value delivered by vendors meeting the need | Risk associated with meeting the need in a cost-effective manner | Total duration of the project | A make-or-buy analysis results in a decision as to whether particular work can best be accomplished by the project team or needs to be outsourced. The total duration of the project does not (and should not) influence this analysis. The other choices are rational considerations during this analysis. [PMBOK 6th edition, Page 479] | تقوم المنظمات بتقييم ما إذا كانت ستشتري المنتجات أو تصنع العناصر بنفسها. أي مما يلي لا يُعد عاملاً يؤثر على قرارات الشراء أو الشراء: | القدرات الأساسية للمنظمة | القيمة التي يقدمها البائعون الذين يلبون الحاجة | المخاطر المرتبطة بتلبية الحاجة بطريقة فعالة من حيث التكلفة | المدة الإجمالية للمشروع | ينتج عن تحليل الشراء أو الشراء اتخاذ قرار بشأن ما إذا كان فريق المشروع يمكن أن ينجز عملًا معينًا على أفضل وجه أو يحتاج إلى الاستعانة بمصادر خارجية. لا تؤثر المدة الإجمالية للمشروع (ولا ينبغي) على هذا التحليل. الخيارات الأخرى اعتبارات منطقية خلال هذا التحليل. [PMBOK الطبعة السادسة ، الصفحة 479] | 148 | 3 | False | "16" | Ahmad
77 | A project manager is spending most of the project funding in the current phase of the project. The manager is also managing various resources in the project. What is the stakeholder influence on the project now compared to earlier phases? | Cannot be determined | More | Same | Less | Since the project manager is spending most of the money and managing resources, he or she is currently in the execution phase of the project. Spending levels reach a maximum in the execution phase. Stakeholder influences on the project decrease over the life of the project. Hence, stakeholder influence is now less than in previous phases. [PMBOK 6th edition, Page 549] | ينفق مدير المشروع معظم تمويل المشروع في المرحلة الحالية من المشروع. يقوم المدير أيضًا بإدارة الموارد المختلفة في المشروع. ما هو تأثير أصحاب المصلحة على المشروع الآن مقارنة بالمراحل السابقة؟ | لا يمكن تحديدها | أكثر | نفسه | أقل | نظرًا لأن مدير المشروع ينفق معظم الأموال وإدارة الموارد ، فهو حاليًا في مرحلة تنفيذ المشروع. تصل مستويات الإنفاق إلى الحد الأقصى في مرحلة التنفيذ. تقل تأثيرات أصحاب المصلحة على المشروع على مدى عمر المشروع. ومن ثم ، فإن تأثير أصحاب المصلحة الآن أقل مما كان عليه في المراحل السابقة. [PMBOK الطبعة السادسة ، الصفحة 549] | 149 | 4 | False | "20" | Ahmad
78 | Haitham is managing a software development project. The buyer of the product is an external entity. During the project’s execution, Haitham finds that a new operations manager was hired in the customer organization. The new manager is now a key stakeholder. Which of the following documents is least likely to be updated because of the addition of this new stakeholder? | Stakeholder register | Risk register | Stakeholder engagement plan | Issue log | The stakeholder register must be updated since a new project stakeholder has joined the project. Changes to the stakeholder engagement plan might also be required to ensure that the new key stakeholder is properly engaged with the project. Addition of a new key stakeholder might bring some additional uncertainty to the project; this should be recorded in the risk register. The issue log is least likely to be updated in this case since no new issue has emerged. [PMBOK 6th edition, Page 507] | يدير هيثم مشروع تطوير البرمجيات. مشتري المنتج كيان خارجي. أثناء تنفيذ المشروع ، وجد هيثم أنه تم تعيين مدير عمليات جديد في منظمة العملاء. المدير الجديد هو الآن أحد أصحاب المصلحة الرئيسيين. أي من المستندات التالية أقل احتمالًا للتحديث بسبب إضافة صاحب المصلحة الجديد هذا؟ | سجل أصحاب المصلحة | سجل المخاطر | خطة إشراك أصحاب المصلحة | سجل المشكلة | يجب تحديث سجل أصحاب المصلحة منذ انضمام صاحب مشروع جديد إلى المشروع. قد تكون هناك حاجة أيضًا لإجراء تغييرات على خطة إشراك أصحاب المصلحة لضمان مشاركة صاحب المصلحة الرئيسي الجديد بشكل صحيح في المشروع. قد تؤدي إضافة صاحب مصلحة رئيسي جديد إلى مزيد من عدم اليقين في المشروع ؛ يجب تسجيل ذلك في سجل المخاطر. من غير المرجح أن يتم تحديث سجل الأحداث في هذه الحالة نظرًا لعدم ظهور مشكلة جديدة. [PMBOK الطبعة السادسة ، الصفحة 507] | 149 | 3 | False | "20" | Ahmad
79 | You are a certified PMP, and the PMI has contacted you as part of an investigation it is conducting into allegations of improper conduct by your manager, who is also a PMP. A complaint has been filed stating your manager has received bribes related to a large procurement contract on another project. PMI has asked whether you could provide information regarding this situation. What should you do? | Confront your manager | Send PMI project documentation and emails related to the allegations to assist with their investigation | Do nothing, citing a conflict of interest | Notify the appropriate management immediately | Notifying the appropriate management of the PMI investigation and their request for your assistance is the best choice. Sharing confidential information with an outside party without approval from your management is a violation of the PMI Code of Ethics and Professional Conduct. Once the appropriate management have been notified, they will let you know the best way to proceed with this investigation. [PMI Code of Ethics and Professional Conduct] [Prof. Responsibility] | أنت PMP معتمد ، وقد اتصلت PMI بك كجزء من التحقيق الذي تجريه في مزاعم السلوك غير اللائق من قبل مديرك ، وهو أيضًا PMP. تم تقديم شكوى تفيد بأن مديرك قد تلقى رشاوى تتعلق بعقد شراء كبير في مشروع آخر. سأل PMI عما إذا كان يمكنك تقديم معلومات بخصوص هذا الموقف. ماذا عليك ان تفعل؟ | مواجهة مديرك | إرسال وثائق مشروع الى معهد ادارة المشاريع ورسائل البريد الإلكتروني المتعلقة بالادعاءات للمساعدة في التحقيق | لا تفعل شيئًا ، بحجة تضارب المصالح | القيام بإخطار الإدارة المناسبة على الفور | إخطار الإدارة المناسبة لتحقيق معهد ادارة المشاريع وطلبهم للمساعدة هو الخيار الأفضل. تعد مشاركة المعلومات السرية مع طرف خارجي دون موافقة من إدارتك انتهاكًا لمدونة قواعد الأخلاق والسلوك المهني الخاصة بمعهد إدارة المشاريع. بمجرد إخطار الإدارة المناسبة ، سيعلمونك بأفضل طريقة لمتابعة هذا التحقيق. [مدونة الأخلاق والسلوك المهني لدى معهد إدارة المشاريع] [المسئولية المهنية] | 148 | 4 | False | "18" | Ahmad
80 | As part of the Estimate Costs process, a project manager obtained access to certain commercially available databases to get resource cost rate information. Such published commercial information is considered what type of input? | Historical information | Organizational process asset | HR Input | Enterprise environmental factor | Such published commercial information is considered part of enterprise environmental factors that influence the Estimate Costs process. [PMBOK 6th edition, Page 243] | كجزء من عملية تقدير التكاليف ، حصل مدير المشروع على حق الوصول إلى بعض قواعد البيانات المتاحة تجاريًا للحصول على معلومات معدل تكلفة الموارد. تعتبر هذه المعلومات التجارية المنشورة أي نوع من المدخلات؟ | معلومات تاريخية | أصول العمليات التنظيمية | مدخلات الموارد البشرية | العامل البيئي للمؤسسة | تعتبر هذه المعلومات التجارية المنشورة جزءًا من العوامل البيئية للمؤسسة التي تؤثر على عملية تقدير التكاليف. [الطبعة السادسة من PMBOK ، الصفحة 243] | 143 | 3 | False | "17" | Ahmad
81 | A project needed to monitor the technical performance of the project and capture data related to how many errors or defects had been identified and how many remained uncorrected. Which of the following techniques should the project use? | Scatter diagram | Flowchart | Control chart | Histogram | Histograms are bar charts that are used to graphically show numeric data. [PMBOK 6th edition, Page 293] | يحتاج المشروع إلى مراقبة الأداء الفني للمشروع والتقاط البيانات المتعلقة بعدد الأخطاء أو العيوب التي تم تحديدها وعدد الأخطاء التي لم يتم تصحيحها. أي من الأساليب التالية يجب أن يستخدمها المشروع؟ | مخطط التشتت | المخطط الانسيابي | مخطط التحكم | الرسم البياني التوزيعي | المدرجات التكرارية هي مخططات شريطية تُستخدم لعرض البيانات الرقمية بيانياً. [الطبعة السادسة من PMBOK ، الصفحة 293] | 144 | 4 | False | "17" | Ahmad
82 | Which of the following is not an example of parametric estimating? | Activity duration estimated based on the number of drawings multiplied by the number of labor hours per drawing. | Activity duration estimated based on the number of labor hours per meter for cable installation. | Activity duration estimated based on the square footage in construction. | Activity duration estimated based on the actual duration of a similar, previous project. | Estimated activity duration based on the actual duration of a previous similar project is an instance of analogous estimating. The other three choices are examples of parametric estimating. [PMBOK 6th edition, Page 200] | أي مما يلي ليس مثالاً على التقدير البارامترى (الاحصائي)؟ | مدة النشاط المقدرة بناءً على عدد الرسومات مضروبًا في عدد ساعات العمل لكل رسم. | تقدر مدة النشاط بناءً على عدد ساعات العمل لكل متر لتركيب الكابلات. | مدة النشاط المقدرة على أساس القدم المربع في البناء. | مدة النشاط المقدرة على أساس المدة الفعلية لمشروع سابق مماثل. | مدة النشاط المقدرة على أساس المدة الفعلية لمشروع سابق مماثل هي مثال على تقدير مماثل. الخيارات الثلاثة الأخرى هي أمثلة لتقدير البارامترية. [الطبعة السادسة من PMBOK ، الصفحة 200] | 142 | 3 | False | "18" | Ahmad
83 | Which of the following is not an example of a work performance report? | Status report | Progress report | Project dashboard | Project charter | The project charter is a high-level document that authorizes a project. It is not a work performance report. The other choices are valid examples of work performance reports. [PMBOK 6th edition, Page 112] | أي مما يلي ليس مثالاً على تقرير أداء العمل؟ | تقرير الحالة | تقرير التقدم | لوحة تحكم المشروع | ميثاق المشروع | ميثاق المشروع هو مستند عالي المستوى يصرح بالمشروع. إنه ليس تقرير أداء العمل. الخيارات الأخرى هي أمثلة صالحة لتقارير أداء العمل. [PMBOK الطبعة السادسة ، الصفحة 112] | 140 | 5 | False | "20" | Ahmad
84 | A project charter that formally authorized a project was created. The project charter documented the initial requirements to satisfy stakeholders' needs and expectations. How often should the project charter be revised? | At the beginning, middle, and end of a project | Once a month | As required by the PMO | Project charter is usually not updated during the course of the project. | The project charter is a high-level document that authorizes a project. It documents a broad understanding of the project and does not need to be updated during the course of the project. [PMBOK 6th edition, Page 75] | تم إنشاء ميثاق المشروع الذي أجاز مشروعًا رسميًا. وثق ميثاق المشروع المتطلبات الأولية لتلبية احتياجات وتوقعات أصحاب المصلحة. كم مرة يجب مراجعة ميثاق المشروع؟ | في بداية المشروع ووسطه ونهايته | مرة في الشهر | كما هو مطلوب من قبل مكتب إدارة المشاريع | عادة لا يتم تحديث ميثاق المشروع أثناء سير المشروع. | ميثاق المشروع هو مستند عالي المستوى يصرح بالمشروع. يوثق فهمًا واسعًا للمشروع ولا يحتاج إلى تحديث أثناء سير المشروع. [الطبعة السادسة من PMBOK ، الصفحة 75] | 140 | 2 | False | "20" | Ahmad
85 | Which of the following techniques focuses on identifying non-value-added activities in a project? | Pareto charting | Root cause analysis | Affinity diagrams | Process analysis | Process analysis examines problems experienced, constraints experienced, and non-value-added activities identified during process operation. [PMBOK 6th edition, Page 292] | أي من الأساليب التالية يركز على تحديد الأنشطة غير ذات القيمة المضافة في المشروع؟ | مخطط باريتو | تحليل السبب الجذري | مخططات التقارب | تحليل العمليات | يفحص تحليل العملية المشكلات التي تمت مواجهتها والقيود التي تمت مواجهتها والأنشطة غير ذات القيمة المضافة التي تم تحديدها أثناء تشغيل العملية. [الإصدار السادس من PMBOK ، الصفحة 292] | 144 | 4 | False | "18" | Ahmad
86 | Nancy's project is in execution. Nancy is currently planning to execute the Manage Stakeholder Engagement process. She has gathered the project documents such as the issue log, the change log, the stakeholder register, the lessons learned register and the necessary organizational process assets. Which of the following is a key input to this process that is still missing from this list? | Expert Judgment | Communication Skills | Change requests | Project Management Plan | The missing input is the project management plan. [PMBOK 6th edition, Page 523] | مشروع نانسي قيد التنفيذ. تخطط نانسي حاليًا لتنفيذ عملية إدارة مشاركة أصحاب المصلحة. لقد جمعت مستندات المشروع مثل سجل الأحداث وسجل التغيير وسجل أصحاب المصلحة وسجل الدروس المستفادة وأصول العملية التنظيمية الضرورية. أي مما يلي يعد أحد المدخلات الرئيسية لهذه العملية التي لا تزال مفقودة من هذه القائمة؟ | حكم خبير | مهارات التواصل | تغيير الطلبات | خطة إدارة المشروع | المدخلات المفقودة هي خطة إدارة المشروع. [الطبعة السادسة من PMBOK ، الصفحة 523] | 149 | 4 | False | "17" | Ahmad
87 | A project manager needed to shorten a project schedule and decided to employ crashing, a schedule compression technique. Which of the following activities would not be an example of crashing? | Paying to expedite delivery activities | Bringing in additional resources | Approving overtime | Reducing project scope | Schedule compression techniques such as crashing and fast tracking shorten the project schedule without changing the project scope. Approving overtime, bringing in additional resources and paying to expedite delivery activities are valid examples of crashing. Reducing project scope is not a valid example of crashing. [PMBOK 6th edition, Page 215] | احتاج مدير المشروع إلى تقصير الجدول الزمني للمشروع وقرر استخدام أسلوب حشد الموارد. أي من الأنشطة التالية لن يكون مثالاً على الانهيار؟ | الدفع لتسريع أنشطة التسليم | جلب موارد إضافية | اعتماد العمل الإضافي | تقليص نطاق المشروع | تعمل تقنيات ضغط الجدول مثل حشد الموارد والتتبع السريع على تقصير جدول المشروع دون تغيير نطاق المشروع. تعد الموافقة على العمل الإضافي وجلب موارد إضافية والدفع لتسريع أنشطة التسليم أمثلة لحشد الموارد. إن تقليل نطاق المشروع ليس مثالاً صالحًا على الانهيار. [الطبعة السادسة من PMBOK ، الصفحة 215] | 142 | 3 | False | "19" | Ahmad
88 | A project can be authorized by any of the following except: | The PMO | The sponsor | The portfolio steering committee | The project manager | Projects are authorized by someone external to the project such as a project sponsor, project management office (PMO), or portfolio steering committee. A project manager does not authorize the project. [PMBOK 6th edition, Page 77] | يمكن أن يرخص المشروع من قبل أي مما يلي باستثناء: | مكتب إدارة المشاريع | الراعي | اللجنة التوجيهية للحقيبة | مدير المشروع | تمت الموافقة على المشاريع من قبل شخص خارج المشروع مثل راعي المشروع أو مكتب إدارة المشروع (PMO) أو لجنة توجيه المحفظة. مدير المشروع لا يأذن بالمشروع. [PMBOK الطبعة السادسة ، الصفحة 77] | 140 | 2 | False | "18" | Ahmad
89 | A first-time project manager created a Work Breakdown Structure (WBS) where the deliverables had different levels of decomposition. What would your comment on this be? | This is incorrect. All deliverables need to have the same level of decomposition. | This is incorrect. Only deliverables under different branches can have different levels of decomposition. | This is fine. The focus of the WBS is not the deliverables but the tasks involved. | This is fine. Different deliverables can have different levels of decomposition, depending on the work involved. | This is acceptable. Deliverables need not all have the same level of decomposition. This will depend on the work involved and degree of control required. [PMBOK 6th edition, Page 158] | أنشأ مدير مشروع لأول مرة هيكلًا لتقسيم العمل (WBS) حيث كان للتسليمات مستويات مختلفة من التحلل. ماذا سيكون تعليقك على هذا؟ | هذا غير صحيح. يجب أن يكون لجميع المخرجات نفس مستوى التحلل. | هذا غير صحيح. يمكن أن يكون للمخرجات تحت الفروع المختلفة مستويات مختلفة من التحلل. | هذا جيد. لا ينصب تركيز هيكل تجزئة العمل على المخرجات بل على المهام المعنية. | هذا جيد. يمكن أن تحتوي المخرجات المختلفة على مستويات مختلفة من التحلل ، اعتمادًا على العمل المطلوب. | هذا مقبول. لا تحتاج جميع النواتج إلى نفس مستوى التحلل. سيعتمد هذا على العمل المطلوب ودرجة التحكم المطلوبة. [الطبعة السادسة من PMBOK ، الصفحة 158] | 141 | 3 | False | "20" | Ahmad
90 | Decision tree analysis is used to calculate the average outcome when the future includes scenarios that may or may not happen. What are a decision node’s inputs and outputs? | Input: Cost of each decision; Output: Probability of occurrence | Input: Scenario probability; Output: Expected Monetary Value (EMV) | Input: Cost of each decision; Output: Payoff | Input: Cost of each decision; Output: Decision made | Decision tree analysis is used to calculate the average outcome when the future includes scenarios that may or may not happen. In a decision node, the input is the cost of each decision and the output is a decision made. [PMBOK 6th edition, Page 435] | يستخدم تحليل شجرة القرار لحساب متوسط ​​النتيجة عندما يتضمن المستقبل سيناريوهات قد تحدث أو لا تحدث. ما هي مدخلات ومخرجات عقدة القرار؟ | المدخلات: تكلفة كل قرار ؛ المخرجات: احتمالية الحدوث | الإدخال: احتمالية السيناريو ؛ المخرجات: القيمة النقدية المتوقعة (EMV) | المدخلات: تكلفة كل قرار ؛ الإخراج: مردود | المدخلات: تكلفة كل قرار ؛ المخرجات: القرار المتخذ | يستخدم تحليل شجرة القرار لحساب متوسط ​​النتيجة عندما يتضمن المستقبل سيناريوهات قد تحدث أو لا تحدث. في عقدة القرار ، المدخل هو تكلفة كل قرار والمخرجات هي قرار تم اتخاذه. [الطبعة السادسة من PMBOK ، صفحة 435] | 147 | 3 | False | "18" | Ahmad
91 | Which of the following is neither an input nor an output of the Direct and Manage Project Work process? | Approved change requests | Change requests | Deliverables | Approved deliverables | Approved deliverables are neither an input nor an output of the Direct and Manage Project Work process. Approved or accepted deliverables are outputs of the Validate Scope process and are the inputs of the Close Project or Phase process. [PMBOK 6th edition, Page 90] | أي مما يلي ليس مدخلاً أو ناتجًا لعملية مباشرة وإدارة عمل المشروع؟ | طلبات التغيير التي تمت الموافقة عليها | طلبات التغيير . | المخرجات | المخرجات المعتمدة | التسليمات المعتمدة ليست مدخلاً أو مخرجات لعملية مباشرة وإدارة عمل المشروع. التسليمات المعتمدة أو المقبولة هي مخرجات عملية التحقق من النطاق وهي مدخلات عملية إغلاق المشروع أو المرحلة. [الطبعة السادسة من PMBOK ، صفحة 90] | 140 | 4 | False | "16" | Ahmad
92 | Which of the following is true about risks? | A risk usually has a single cause and, if it occurs, may have one or more effects. | A risk usually has a single cause and, if it occurs, usually has a single effect. | A risk usually has more than one cause, and if it occurs, usually has a single effect. | A risk may have one or more causes, and, if it occurs, may have one or more effects. | A project risk is an uncertain event or condition whose occurrence may affect the objectives of the project. A risk may have one or many causes, and if it occurs, it may have one or more impacts. [PMBOK 6th edition, Page 417] | أي مما يلي ينطبق على المخاطر؟ | عادة ما يكون للمخاطر سبب واحد ، وإذا حدثت ، فقد يكون لها تأثير واحد أو أكثر. | عادة ما يكون للمخاطر سبب واحد ، وإذا حدثت ، فعادة ما يكون لها تأثير واحد. | عادة ما يكون للمخاطر أكثر من سبب واحد ، وإذا حدثت ، فعادة ما يكون لها تأثير واحد. | قد يكون للمخاطر سبب أو أكثر ، وفي حالة حدوثها ، فقد يكون لها تأثير واحد أو أكثر. | مخاطر المشروع هي حدث أو حالة غير مؤكدة قد يؤثر حدوثها على أهداف المشروع. قد يكون للمخاطر سبب أو عدة أسباب ، وإذا حدثت ، فقد يكون لها تأثير واحد أو أكثر. [الطبعة السادسة من PMBOK ، صفحة 417] | 147 | 3 | False | "19" | Ahmad
93 | You have just taken over a project from another project manager about six months into a 12-month project. As you get to know the staff on the project, you become aware that five staff members are relatives of the previous project manager. What do you do? | Check recruitment records of all employees | Report the HR manager to PMI | Interview these five employees | Notify your project stakeholders there is a possibility that nepotism was behind some of the staffing decisions made on your project | Notify your project stakeholders of the situation. Once they are aware of the circumstances, a plan of action can be developed. It is possible the stakeholders may already be aware of the situation and had actually approved the hiring of these resources. Therefore, you should involve your stakeholders to resolve this issue. [PMI Code of Ethics and Professional Conduct] [Prof. Responsibility] | لقد تسلمت للتو مشروعًا من مدير مشروع آخر لمدة ستة أشهر تقريبًا في مشروع مدته 12 شهرًا. عندما تتعرف على الموظفين في المشروع ، تدرك أن خمسة موظفين هم أقارب مدير المشروع السابق. ماذا تعمل؟ | تحقق من سجلات التوظيف لجميع الموظفين | القيام بإبلاغ مدير الموارد البشرية إلى PMI | مقابلة هؤلاء الموظفين الخمسة | ابلاغ أصحاب المصلحة في مشروعك أن هناك احتمال أن المحسوبية كانت وراء بعض قرارات التوظيف التي تم اتخاذها في مشروعك | قم بإخطار أصحاب المصلحة في المشروع بالموقف. بمجرد أن يدركوا الظروف ، يمكن وضع خطة عمل. من الممكن أن يكون أصحاب المصلحة على علم بالفعل بالوضع ووافقوا بالفعل على توظيف هذه الموارد. لذلك ، يجب عليك إشراك أصحاب المصلحة لحل هذه المشكلة. [مدونة الأخلاق والسلوك المهني لدى معهد إدارة المشاريع] [المسئولية المهنية] | 145 | 4 | False | "19" | Ahmad
94 | The Actual Cost (AC) is the total cost actually incurred and recorded in accomplishing work performed for an activity or work breakdown structure component. What is the upper limit for the AC? | 50 percent over and above the Planned Value (PV) | The Actual Cost (AC) is limited to the Planned Value (PV) | 100 percent over and above the Planned Value (PV) | There is no upper limit for the Actual Cost (AC) | There is no limit to the Actual Cost (AC). Whatever is spent to achieve the Earned Value (EV) is measured as the Actual Cost. [PMBOK 6th edition, Page 261] [Project Cost Management] | التكلفة الفعلية (AC) هي التكلفة الإجمالية المتكبدة والمسجلة بالفعل في إنجاز العمل المنجز لنشاط أو مكون هيكل تقسيم العمل. ما هو الحد الأعلى لمكيف الهواء؟ | 50 في المائة فوق القيمة المخططة (PV) | التكلفة الفعلية (AC) تقتصر على القيمة المخططة (PV) | 100 في المائة فوق القيمة المخططة (PV) | لا يوجد حد أعلى للتكلفة الفعلية (AC) | لا يوجد حد للتكلفة الفعلية (AC). كل ما يتم إنفاقه لتحقيق القيمة المكتسبة (EV) يتم قياسه على أنه التكلفة الفعلية. [الإصدار السادس من PMBOK ، الصفحة 261] [إدارة تكاليف المشروع] | 143 | 5 | False | "17" | Ahmad
95 | A project manager planning the risk responses for his project. He ask the project team to perform more tests on some of the critical applications being developed to minimize the problems during the user acceptance testing phase. This Risk Response is an example of: | Risk Avoidance | Risk Transference | Risk Acceptance | Risk Mitigation | Performing more tests is one way to mitigate the risk.[PMBOK 6th edition, Page 443] | مدير مشروع يخطط لاستجابات المخاطر لمشروعه. طلب من فريق المشروع إجراء المزيد من الاختبارات على بعض التطبيقات الهامة التي يتم تطويرها لتقليل المشكلات أثناء مرحلة اختبار قبول المستخدم. هذه الاستجابة للمخاطر هي مثال على: | تجنب المخاطر | تحويل المخاطر | قبول المخاطر | تخفيف المخاطر | يعد إجراء المزيد من الاختبارات إحدى الطرق لتقليل المخاطر. [PMBOK الطبعة السادسة ، الصفحة 443] | 147 | 3 | False | "20" | Ahmad
96 | You are preparing two documents for risk management. One contains sources of overall project risk and also summary information on individual risks. The second describes individual risks identified. What name should you give to the first document? | Requirements traceability matrix | Risk register | Risk management plan | Risk report | The risk report presents the current level of overall risk exposure of the project that will inform the selection of the risk response strategy. The risk report may also list individual project risks in priority order and provide additional analysis of the distribution of individual project risks that may inform risk response selection. [PMBOK 6th edition, Page 440] | أنت تعد وثيقتين لإدارة المخاطر. يحتوي أحدهما على مصادر المخاطر الكلية للمشروع وكذلك معلومات موجزة عن المخاطر الفردية. يصف الثاني المخاطر الفردية المحددة. ما الاسم الذي يجب أن تطلقه على المستند الأول؟ | مصفوفة تتبع المتطلبات | سجل المخاطر | خطة إدارة الخطر | تقرير المخاطر | يعرض تقرير المخاطر المستوى الحالي للتعرض العام للمخاطر للمشروع الذي سيوجه اختيار استراتيجية الاستجابة للمخاطر. قد يسرد تقرير المخاطر أيضًا مخاطر المشروع الفردية في ترتيب الأولويات ويوفر تحليلًا إضافيًا لتوزيع مخاطر المشروع الفردية التي قد تساعد في اختيار الاستجابة للمخاطر. [الإصدار السادس من PMBOK ، الصفحة 440] | 147 | 3 | False | "16" | Ahmad
97 | A project manager managing a project with extreme weather expected soon. The project is over budget, and the project sponsor can not provide additional funding. To achieve the milestone before the extreme weather begins, which of the following techniques should the project manager use? | Resource leveling | Crashing | What-if scenario analysis | Fast-tracking | Because the project is over budget and the project sponsor can not provide additional funding, you can not use crashing in this case. The project manager should use Fast Tracking to achieve the milestone before the extreme weather begins. [PMBOK 6th edition, Page 215] | مدير مشروع يدير مشروعًا مع طقس قاس متوقع قريبًا. تجاوز المشروع الميزانية ولا يمكن لراعي المشروع تقديم تمويل إضافي. لتحقيق المعلم قبل بدء الطقس القاسي ، أي من التقنيات التالية يجب أن يستخدمها مدير المشروع؟ | تسوية الموارد | حشد الموارد | تحليل سيناريو ماذا لو | تتبع سريع | نظرًا لأن المشروع تجاوز الميزانية ولا يستطيع راعي المشروع توفير تمويل إضافي ، فلا يمكنك استخدام حشد الموارد في هذه الحالة. يجب على مدير المشروع استخدام التتبع السريع لتحقيق المعلم قبل بدء الطقس القاسي. [الطبعة السادسة من PMBOK ، الصفحة 215] | 142 | 3 | False | "19" | Ahmad
98 | The total budget of a 12 month project is SAR 2 million. The project's first three months indicates a cost to date of SAR 500,000 and the earned value is SAR 525,000, and the total amount spent till now is SAR 550,000. What is the project status? | Ahead of schedule and under budget. | Behind schedule and over schedule. | On schedule and on budget. | Ahead of schedule and over budget. | A cost to date (PV) = SAR 500,000 Earned value (EV) = SAR 525,000. Actual cost (AC) = SAR 550,000 CV = EV - AC = 525,000 - 550,000 = -25,000 (Negative) PV = EV - PV = 525,000 - 500,000 = 25,000 (Positive) SO, the project is ahead of schedule and over budget [PMBOK 6th edition Page 262] | الميزانية الإجمالية لمشروع 12 شهر 2 مليون ريال سعودي. تشير الأشهر الثلاثة الأولى من المشروع إلى أن التكلفة حتى تاريخه 500،000 ريال سعودي والقيمة المكتسبة 525،000 ريال سعودي ، والمبلغ الإجمالي الذي تم إنفاقه حتى الآن هو 550،000 ريال سعودي. ما هي حالة المشروع؟ | قبل الموعد المحدد وتحت الميزانية. | تأخر عن الجدول الزمني وجدول أكثر. | في الموعد المحدد وعلى الميزانية. | قبل الجدول الزمني وعلى الميزانية. | التكلفة حتى تاريخه (PV) = 500،000 ريال سعودي القيمة المكتسبة (EV) = 525،000 ريال سعودي. التكلفة الفعلية (AC) = 550،000 ريال سعودي CV = EV - AC = 525،000 - 550،000 = -25،000 (سلبي) PV = EV - PV = 525،000 - 500،000 = 25،000 (إيجابي) SO ، المشروع متقدم على الجدول الزمني ويفوق الميزانية [PMBOK الطبعة السادسة الصفحة 262] | 143 | 5 | False | "18" | Ahmad
99 | A project scope statement is defined with project deliverables, constraints, and assumptions associated with the project objectives. What should the project manager do next? | Take a formal acceptance of the completed project deliverables. | Monitoring the status of the project and product scope and managing changes to the scope baseline. | Determine the products, services, and results to be delivered. | Establish a hierarchical breakdown of the total scope to be carried out by the project team. | A project scope statement is defined, So, "Define scope" process is completed. Therefor the next process is "Create WBS". Create webs is the process of establish a hierarchical breakdown of the total scope to be carried out by the project team to comply with the project objectives. [PMBOK 6th edition Page 157] | يتم تعريف بيان نطاق المشروع مع مخرجات المشروع والقيود والافتراضات المرتبطة بأهداف المشروع. ماذا يجب أن يفعل مدير المشروع بعد ذلك؟ | خذ قبولًا رسميًا لنواتج المشروع المكتملة. | مراقبة حالة المشروع ونطاق المنتج وإدارة التغييرات على خط الأساس للنطاق. | تحديد المنتجات والخدمات والنتائج المراد تسليمها. | إنشاء تقسيم هرمي للنطاق الإجمالي الذي يتعين على فريق المشروع تنفيذه. | يتم تحديد بيان نطاق المشروع ، لذلك ، يتم إكمال عملية "تحديد النطاق". لذلك فإن العملية التالية هي "إنشاء هيكل تجزئة العمل". إنشاء شبكات هو عملية إنشاء تقسيم هرمي للنطاق الإجمالي الذي يتعين على فريق المشروع تنفيذه للامتثال لأهداف المشروع. [PMBOK الطبعة السادسة ، الصفحة 157] | 141 | 3 | False | "16" | Ahmad
100 | You are administering a contract on your project. Your sponsor asks you to give him the list of paid invoices to the seller. He wants a report containing information about the total amount collected by the seller as part of project execution. What documentation would you review in order to provide your sponsor with the report? | Performance Reports | Project Management Plan | Statement of Work | Work Performance Data | Work Performance Data contain raw observations and measurements during activities performed to carry out the project work. Seller paid invoices are part of work performance data used as input to the "Control Procurements" process. You review, analyze, and integrate the seller invoice data into work performance information (for example total amount collected by the seller comparing to the planned amount), which you can then use to create the report requested by your sponsor. [PMBOK 6th edition Page 496] | أنت تدير عقدًا على مشروعك. يطلب منك كفيلك أن تقدم له قائمة الفواتير المدفوعة للبائع. إنه يريد تقريرًا يحتوي على معلومات حول المبلغ الإجمالي الذي جمعه البائع كجزء من تنفيذ المشروع. ما هي الوثائق التي ستراجعها لتزويد الراعي بالتقرير؟ | تقارير الأداء | خطة إدارة المشروع | بيان العمل | بيانات أداء العمل | تحتوي بيانات أداء العمل على ملاحظات وقياسات أولية أثناء الأنشطة المنجزة لتنفيذ عمل المشروع. فواتير البائع المدفوعة هي جزء من بيانات أداء العمل المستخدمة كمدخل لعملية "مراقبة المشتريات". تقوم بمراجعة وتحليل ودمج بيانات فاتورة البائع في معلومات أداء العمل (على سبيل المثال المبلغ الإجمالي الذي يجمعه البائع مقارنة بالمبلغ المخطط له) ، والتي يمكنك استخدامها بعد ذلك لإنشاء التقرير الذي طلبه الراعي. [PMBOK الطبعة السادسة ، الصفحة 496] | 148 | 5 | False | "19" | Ahmad
101 | Which of the following business documents that Justify why the project is authorized? | Project management plan | Project charter | Scope statement of work | Business case | The business need and the cost-benefit analysis are contained in the business case to justify and establish boundaries for the project. [PMBOK 6th edition, Page 77] | أي من مستندات الأعمال التالية تبرر سبب بدء المشروع؟ | خطة إدارة المشروع | ميثاق المشروع | بيان نطاق العمل | مسوغ الأعمال | يتم تضمين حاجة العمل وتحليل التكلفة والمنفعة في مسوغ الأعمال لتبرير ووضع حدود للمشروع. [PMBOK الطبعة السادسة ، الصفحة 496] | 140 | 2 | False | "18" | Ahmad
102 | You and your team have compiled your project's activity list, determined how the activities should be performed, and analyzed the schedule. You are preparing information for the project sponsor to highlight the identified activities that may create a delay in the overall project schedule. Which of the following would be most useful in this situation? | Project calendars | Activity attributes | Duration estimates | Project schedule network diagrams | In this question, project network diagrams would best serve to provide information concerning activities that would possibly create schedule delays. A project network diagram is one of three suggested project schedule models. At a minimum, a project schedule should include planned start dates and planned finished dates for each activity. Network diagrams which include activity date information and critical path activities, display has those activities logically relate to other activities and overall project timeline. A detailed network diagram that includes critical path activities, durations, milestones, and resources could be useful in this situation to highlight the activities that may create a delay in the overall project schedule. [PMBOK 6tha edition, Page 194] | قمت أنت وفريقك بتجميع قائمة أنشطة مشروعك وتحديد كيفية تنفيذ الأنشطة وتحليل الجدول الزمني. أنت تقوم بإعداد معلومات لراعي المشروع لتسليط الضوء على الأنشطة المحددة التي قد تؤدي إلى تأخير في الجدول الزمني العام للمشروع. أي مما يلي سيكون أكثر فائدة في هذه الحالة؟ | تقويمات المشروع | سمات النشاط | تقديرات المدة | مخطط الشبكة للجدول الزمني للمشروع | في هذا السؤال ، من الأفضل استخدام مخطط الشبكة للجدول الزمني للمشروع لتوفير المعلومات المتعلقة بالأنشطة التي قد تؤدي إلى تأخيرات في الجدول الزمني. مخطط شبكة المشروع هو واحد من ثلاثة نماذج مقترحة للجدول الزمني للمشروع. كحد أدنى، يجب أن يتضمن جدول المشروع تواريخ البدء المخطط لها والتواريخ النهائية المخططة لكل نشاط. الرسوم البيانية للشبكة التي تتضمن معلومات تاريخ النشاط وأنشطة المسار الحرج، والعرض يحتوي على تلك الأنشطة مرتبطة منطقيًا بالأنشطة الأخرى والجدول الزمني العام للمشروع. يمكن أن يكون مخطط الشبكة التفصيلي الذي يتضمن أنشطة المسار الحرج، والمدد الزمنية، والمعالم الرئيسية، والموارد مفيدًا في هذه الحالة لتسليط الضوء على الأنشطة التي قد تؤدي إلى تأخير في الجدول الزمني الإجمالي للمشروع. [PMBOK الطبعة السادسة ، الصفحة 194] | 142 | 3 | False | "20" | Ahmad
103 | Ahmad is a project manager working for a construction company. As part of his current project, he oversees the inspection of deliverables, measuring them against documented requirements and acceptance criteria for obtaining the stakeholders' formal acceptance of the project deliverables. What project management process is he performing? | Control Quality | Manage Quality | Control Scope | Validate Scope | Inspection activities such as measuring, examining and validating to determine whether work and deliverables meet requirements and product acceptance criteria is a tool used in "Validate Scope" process. Inspections are sometimes called reviews, product reviews, and walkthroughs. In some application areas, these different terms have unique and specific meanings. [PMBOK 6th edition, Page 166] | أحمد مدير مشروع يعمل في شركة إنشاءات. كجزء من مشروعه الحالي ، يشرف على فحص المخرجات وقياسها مقابل المتطلبات الموثقة ومعايير القبول للحصول على قبول رسمي من أصحاب المصلحة لمخرجات المشروع. ما هي عملية إدارة المشروع التي يقوم بها؟ | التحكم بالجودة | إدارة الجودة | التحكم بالنطاق | التحقق من النطاق | أنشطة التفتيش مثل القياس والفحص والتحقق من الصحة لتحديد ما إذا كان العمل والتسليمات تفي بالمتطلبات ومعايير قبول المنتج هي أداة مستخدمة في عملية "التحقق من النطاق". تسمى عمليات التفتيش أحيانًا بالمراجعات ومراجعات المنتجات والجولات التفقدية. في بعض مجالات التطبيق، يكون لهذه المصطلحات المختلفة معاني فريدة ومحددة. [PMBOK الطبعة السادسة ، الصفحة 166] | 141 | 5 | False | "18" | Ahmad
104 | One of the project risks is likely to cause, a negative impact of SAR 15,000 with a probability of 50%. At the same time, there is a possibility of saving SAR 10,000 by choosing alternate resources, this has a likelihood of 25%. What is the Expected Monetary Value (EMV) of the project? | SAR -7,500 | SAR -25,000 | SAR 2,500 | SAR -5,000 | The Expected Monetary Value (EMV) of risks in the project is the sum of the probability multiplied by impact for each risk. Threats will have negative impact and opportunities will have positive impact. So, EMV = (Probability * Impact) for each Risk = - (0.5*15,000) + (0.25*10,000) = -5,000 SAR [PMBOK 6th edition, Page 435] | من المحتمل أن يتسبب أحد مخاطر المشروع في تأثير سلبي قدره 15,000 ريال سعودي مع احتمال بنسبة 50٪. في نفس الوقت ، هناك إمكانية لتوفير 10,000 ريال سعودي عن طريق اختيار موارد بديلة ، وهذا احتماله بنسبة 25٪. ما هي القيمة النقدية المتوقعة (EMV) للمشروع؟ | (-7,500) ريال سعودي | (25,000) ريال سعودي | (2,500) ريال سعودي | (- 5,000) ريال سعودي | القيمة النقدية المتوقعة (EMV) للمخاطر في المشروع هي مجموع الاحتمال مضروبًا في التأثير لكل خطر. سيكون للتهديدات تأثير سلبي والفرص سيكون لها تأثير إيجابي. لذا ، EMV = (الاحتمالية * التأثير) لكل خطر = - (0.5 * 15,000) + (0.25 * 10,000) = (5,000-) ريال سعودي. [الطبعة السادسة من PMBOK ، صفحة 435] | 147 | 3 | False | "17" | Ahmad
105 | Rework is an example of? | Cost of the contingency reserve | Cost of conformance | External failure costs | Cost of quality | The cost of quality (COQ) associated with a project consists of Prevention Costs, Appraisal Costs and Failure Costs (internal/external). Rework is an example of Internal Failure Costs. [PMBOK 6th edition, Page 282, 283] | إعادة العمل هو مثال؟ | تكلفة احتياطي الطوارئ | تكلفة المطابقة | تكاليف الفشل الخارجي | تكلفة الجودة | تتكون تكلفة الجودة (COQ) المرتبطة بالمشروع من تكاليف الوقاية وتكاليف التقييم وتكاليف الفشل (داخلي / خارجي). إعادة العمل مثال على تكاليف الفشل الداخلي. [PMBOK الطبعة السادسة ، الصفحة 282,283] | 144 | 3 | False | "18" | Ahmad
106 | You are a project manager, and your project is currently in the execution phase. One of your project team member leave the site early at 3:00 pm Thursday and mistreats his colleagues. You would like to establish clear expectations regarding the acceptable behavior of the team member. To avoid such situations, you should create: | Team-building activities | Interpersonal skills | Management skills | Team charter | The team charter establishes clear expectations regarding acceptable behavior by project team members. [PMBOK 6th edition, Page 319] | أنت مدير مشروع ، ومشروعك في مرحلة التنفيذ حاليًا. غادر أحد أفراد فريق مشروعك الموقع مبكرًا في الساعة 3:00 مساءً يوم الخميس وأساء معاملة زملائه. ترغب في وضع توقعات واضحة فيما يتعلق بالسلوك المقبول لعضو الفريق. لتجنب مثل هذه المواقف ، يجب عليك إنشاء: | أنشطة بناء الفريق | مهارات التعامل مع الآخرين | مهارات الإدارة | ميثاق الفريق | يحدد ميثاق الفريق توقعات واضحة فيما يتعلق بالسلوك المقبول من قبل أعضاء فريق المشروع. [الطبعة السادسة من PMBOK ، صفحة 319] | 145 | 4 | False | "20" | Ahmad
107 | During a presentation to CEO you want to display the project schedule with only the key deliverables displayed. What is the best tool help you with this? | Critical chain diagram | Control chart | Critical path method | Milestone chart | Milestone chart used by senior management. A milestone chart displays only the key deliverables and is simple and easy to understand. [PMBOK 6th edition, Page 218] | أثناء العرض التقديمي للمدير التنفيذي ، تريد عرض جدول المشروع مع عرض التسليمات الرئيسية فقط. ما هي أفضل أداة تساعدك في ذلك؟ | مخطط السلسلة الحرجة | مخطط التحكم | طريقة المسار الحرج | مخطط الأحداث الهامة | مخطط المعالم يستخدم من قبل الإدارة العليا. يعرض مخطط الأحداث الهامة فقط المخرجات الرئيسية وهو بسيط وسهل الفهم. [الطبعة السادسة من PMBOK ، صفحة 218] | 142 | 4 | False | "20" | Ahmad
108 | At the beginning of the project, you and your team would like to address all the strengths, weaknesses, opportunities, and threats the project is facing. What tool should be used? | Cause and effect diagram | Interviewing | Delphi Technique | SWOT Analysis | A SWOT Analysis would be the best choice. This technique examines the project from each of the strengths, weakness, opportunities, and threats perspectives. [PMBOK 6th edition, Page 415] | في بداية المشروع ، ترغب أنت وفريقك في تحديد جميع نقاط القوة والضعف والفرص والتهديدات التي يواجهها المشروع. ما الأداة التي يجب استخدامها؟ | تخطيط السبب والأثر | المقابلات | تقنية دلفي | تحليل SWOT | سيكون تحليل SWOT هو الخيار الأفضل. تفحص هذه التقنية المشروع من كل من جوانب القوة والضعف والفرص والتهديدات. [PMBOK الطبعة السادسة ، الصفحة 415] | 147 | 4 | False | "19" | Ahmad
109 | Which of the following items can be defined by creating the Cost Management Plan of a project? | Level of accuracy and Work Packages | Rules of Performance Measurement and Rewards | Units of Measure and Quality Metrics | Control Thresholds and Units of Measure | A Cost Management Plan defined the Control Thresholds and Units of Measure. Control Thresholds are typically expressed as a percentage of deviation from the baseline. Units of Measure is defined as units used to measure the project cost. [PMBOK 6th edition, Page 238] | أي من العناصر التالية يمكن تحديده عن طريق إنشاء خطة إدارة التكلفة لمشروع؟ | مستوى الدقة وحزم العمل | قواعد قياس الأداء والمكافآت | وحدات القياس ومقاييس الجودة | حدود التحكم ووحدات القياس | تحدد خطة إدارة التكلفة حدود التحكم ووحدات القياس. يتم التعبير عن حدود التحكم عادة كنسبة مئوية من الانحراف عن خط الأساس. يتم تعريف وحدات القياس على أنها وحدات تستخدم لقياس تكلفة المشروع. [PMBOK الطبعة السادسة ، الصفحة 238] | 143 | 3 | False | "18" | Ahmad
110 | You are managing a complex project with many stakeholders each with their own interest in the project. You have begun the process of monitoring overall project stakeholder relationships. Your goal is to increase the efficiency and effectiveness of stakeholder engagement activity. What process are you are engaged in? | Manage Communications | Monitor Communications | Manage Stakeholder Engagement | Monitor Stakeholder Engagement | Monitor Stakeholder Engagement is the process of monitoring project stakeholder relationships and tailoring strategies for engaging stakeholders through modification of engagement strategies and plans. The key benefit of this process is that it maintains or increases the efficiency and effectiveness of stakeholder engagement activities as the project evolves and its environment changes. [PMBOK 6th edition, Page 530] | أنت تدير مشروعًا معقدًا مع العديد من أصحاب المصلحة لكل منهم مصلحته الخاصة في المشروع. لقد بدأت في عملية مراقبة العلاقات العامة مع أصحاب المصلحة في المشروع. هدفك هو زيادة كفاءة وفعالية نشاط مشاركة أصحاب المصلحة. ما هي العملية التي تعمل فيها؟ | إدارة الاتصالات | مراقبة الاتصالات | إدارة إشراك أصحاب المصلحة | مراقبة مشاركة أصحاب المصلحة | مراقبة مشاركة أصحاب المصلحة هي عملية مراقبة علاقات أصحاب المصلحة في المشروع وتخصيص الاستراتيجيات لإشراك أصحاب المصلحة من خلال تعديل استراتيجيات وخطط المشاركة. وتتمثل الميزة الرئيسية لهذه العملية في أنها تحافظ على كفاءة وفعالية أنشطة إشراك أصحاب المصلحة أو تزيدها مع تطور المشروع وتغير بيئته. [PMBOK الطبعة السادسة ، الصفحة 530] | 149 | 5 | False | "18" | Ahmad
111 | Ali is a Project Manager of a project in which team members have a dual reporting structure. In addition to reporting to him, they also report to their functional manager. Also, the team members are expected to do the project work along with department work. Ali is working in which form of organization? | Functional | Tight Matrix | Projectized | Matrix | These are the characteristics of a matrix organization where team members have dual reporting structure, and the teams work in their respective functional areas while performing project work. Tight matrix has nothing to do with organization structure, it simply denotes keeping the project team in the vicinity. [PMBOK 6th edition, page 47] | علي هو مدير مشروع لمشروع أعضاء فريقه لهم هيكل مزدوج. بالإضافة إلى تقديم التقارير إليه، فإنهم أيضًا يقدمون تقاريرهم إلى مدراء أقسامهم. أيضًا من المتوقع أن يقوم أعضاء الفريق بأعمال المشروع جنبًا إلى جنب مع أعمالهم في أقسامهم. علي يعمل في أي شكل من أشكال الهياكل التنظيمية؟ | وظيفية | مصفوفة ضيقة | قائمة على المشروع | مصفوفية | هذه هي خصائص المنظمة المصفوفية حيث يكون لأعضاء الفريق هيكل مزدوج ، وتعمل الفرق في المجال الوظيفيي الخاص بهم أثناء أداء عمل المشروع. المصفوفة الضيقة لا علاقة لها بالهياكل التنظيمية، إنه يشير ببساطة إلى إبقاء فريق المشروع في المنطقة المجاورة. [PMBOK الطبعة السادسة ، الصفحة 47] | 140 | 4 | False | "17" | Ahmad
112 | A project manager is preparing a kick-off meeting for a new service assessment. A high-level description of the service has been provided. What should the project manager do next? | Develop the project charter. | Create the work breakdown structure (WBS). | Develop the responsible, accountable, consult, and inform (RACI) matrix. | Define the project scope statement. | Since a high-level description of the service has been provided, it's mean the "Collect Requirements" process completed and the Project Manager need to start "Define Scope" process to get the project scope statement. [PMBOK 6th edition, page 150] | يستعد مدير المشروع لاجتماع افتتاحي لتقييم خدمة جديدة. تم توفير وصف عالي المستوى للخدمة. ماذا يجب أن يفعل مدير المشروع بعد ذلك؟ | تطوير ميثاق المشروع. | القيام بإنشاء هيكل تنظيم العمل (WBS). | تطوير مصفوفة المسؤول والمحاسب والمشاور والمبلغ (RACI). | تحديد بيان نطاق المشروع. | نظرًا لأنه تم تقديم وصف عالي المستوى للخدمة ، فهذا يعني أن عملية "جمع المتطلبات" قد اكتملت وأن مدير المشروع بحاجة إلى بدء عملية "تحديد النطاق" للحصول على بيان نطاق المشروع. [PMBOK الطبعة السادسة ، الصفحة 150] | 141 | 3 | False | "17" | Ahmad
113 | You have been assigned as a project manager of a new project to be executed out of Orlando. The project is being implemented in an area with many hurricanes. What is the best risk response strategy appropriate for this project? | Accept | Enhance | Avoid | Transfer | The best risk response strategy appropriate for this project, is to hire a third party to complete this work and shifting ownership of a threat to him to manage the risk and to bear the impact if the threat occurs. [PMBOK 6th edition, page 443] | لقد تم تعيينك كمدير مشروع لمشروع جديد ليتم تنفيذه خارج أورلاندو. يتم تنفيذ المشروع في منطقة بها العديد من الأعاصير. ما هي أفضل استراتيجية مناسبة للاستجابة للمخاطر لهذا المشروع؟ | قبول | تحسين | تجنب | نقل | أفضل إستراتيجية استجابة للمخاطر مناسبة لهذا المشروع ، هي بتعيين طرف ثالث لإكمال هذا العمل وتحويل ملكية التهديد له لإدارة المخاطر وتحمل التأثير في حالة حدوث التهديد. [PMBOK الطبعة السادسة ، الصفحة 443] | 147 | 3 | False | "18" | Ahmad
114 | As a project manager, you are working on high rise building project. You are struggling to arrange your first meeting with project human resources. What should you do to ensure resource collaboration? | Obtain the general manager's authorization | Obtain Business case approval from the project sponsor | Meet with each stakeholder individually | Obtain project charter approval | The project charter is the document issued by the project initiator or sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. [PMBOK 6th edition Page, 81] | بصفتك مدير مشروع ، فأنت تعمل في مشروع بناء شاهق. أنت تكافح لترتيب أول اجتماع لك مع الموارد البشرية في المشروع. ما الذي يجب عليك فعله لضمان تعاون الموارد؟ | الحصول على إذن المدير العام | الحصول على موافقة مسوغ العمل من راعي المشروع | اجتمع مع كل صاحب مصلحة على حدة | الحصول على موافقة ميثاق المشروع | ميثاق المشروع هو المستند الصادر من الشخص البادئ للمشروع أو الراعي ويصرح رسميًا بوجود المشروع ويمنح مدير المشروع السلطة لإستخدام الموارد في المنظمة لتنفيذ أنشطة المشروع. [PMBOK الطبعة السادسة ، الصفحة 81] | 140 | 2 | False | "19" | Ahmad
115 | During half of the implementation phase, you notice that a competitor will release the same product into the marketplace. What should you do next? | Update the project charter | Advise the sponsor to cancel the project | Stakeholders analysis | Cost benefit analysis | If a competitor will release the same product in the marketplace you must make a cost-benefit analysis to see you will continue in the project or cancel the project. [PMBOK 6th edition Page, 105] | خلال منتصف مرحلة التنفيذ ، لاحظت أن أحد المنافسين سيطلق نفس المنتج في السوق. ماذا يجب ان تفعل بعد ذلك؟ | تحديث ميثاق المشروع | انصح الراعي بإلغاء المشروع | تحليل أصحاب المصلحة | تحليل التكلفة والمنفعة | إذا قام أحد المنافسين بإصدار نفس المنتج في السوق ، فيجب عليك إجراء تحليل التكلفة والمنفعة لمعرفة أذا كنت ستستمر في المشروع أو تلغي المشروع. [PMBOK الطبعة السادسة ، الصفحة 105] | 140 | 4 | False | "18" | Ahmad
116 | You are a project manager managing an IT project. During project closure, customer agreement cannot be achieved through negotiations. What should the project manager do next? | Unresolved claims may be subject to litigation | Start the closing phase | Inform project team members | Seek arbitration following the alternative dispute resolution ADR procedures | Whenever settlement cannot be achieved through direct negotiation, some form of alternative dispute resolution (ADR) including mediation or arbitration may be explored. When all else fails, litigation in the courts is the least desirable option. [PMBOK 6th edition, Page 498] | أنت مدير مشروع تدير مشروع تقنية معلومات. أثناء إغلاق المشروع ، لم تتمكن من تحقيق اتفاقية مع العميل من خلال المفاوضات. ماذا يجب أن يفعل مدير المشروع بعد ذلك؟ | المطالبات التي لم يتم حلها قد تكون عرضة للتقاضي | ابدأ مرحلة الإغلاق | إبلاغ أعضاء فريق المشروع | اطلب التحكيم باتباع الإجراءات البديلة لتسوية المنازعات ADR | عندما لا يمكن تحقيق التسوية من خلال التفاوض المباشر ، يمكن استكشاف شكل من أشكال الإجراءات البديلة لتسوية المنازعات ADR بما في ذلك الوساطة أو التحكيم. عندما يفشل كل شيء آخر ، فإن التقاضي في المحاكم هو الخيار الأقل استحسانًا. [الطبعة السادسة من PMBOK ، صفحة 498] | 148 | 5 | False | "16" | Ahmad
117 | You are over budget and it is impossible to complete the project with the given budget. Therefore, you submit a change request which your management approves. After approval, you update the cost baseline and update other project documents. The document used to register any changes occur during the project execution is known as: | Risk register | RACI matrix | Issue log | Change log | In the change log, you record all changes occurs during the project, along with its impact on any project objective. [PMBOK 6th edition, Page120 ] | لقد تجاوزت الميزانية ومن المستحيل إكمال المشروع بالميزانية المحددة. لذلك قمت بتقديم طلب تغيير ووافقت عليه إدارتك. بعد الموافقة، قمت بتحديث خط الأساس للتكلفة وحدثت مستندات المشروع الأخرى. يُعرف المستند المستخدم لتسجيل أي تغييرات تحدث أثناء تنفيذ المشروع باسم: | سجل المخاطر | مصفوفة RACI | سجل الأحداث | سجل التغيير | في سجل التغيير ، تقوم بتسجيل جميع التغييرات التي تحدث أثناء المشروع ، إلى جانب تأثيرها على أي هدف من أهداف المشروع. [PMBOK الطبعة السادسة ، الصفحة 120] | 140 | 4 | False | "19" | Ahmad
118 | During a risk audit, it was found that some risks were not analyzed correctly. It was suspected that risk-related information were not properly reviewed before concluding characteristics of risks like probability, etc. What could have been done to prevent this issue? | Risk probability and impact assessment | Effective interviews during the risk identification process | Analysis of other risk parameters | Risk data quality assessment | Risk data and quality assessment is about validating the accuracy and reliability of risk-related information. [PMBOK 6th edition, Page 423] | خلال مراجعة المخاطر ، تبين أن بعض المخاطر لم يتم تحليلها بشكل صحيح. كان هناك شك في أن المعلومات المتعلقة بالمخاطر لم تتم مراجعتها بشكل صحيح قبل استنتاج خصائص المخاطر مثل الاحتمالية ، وما إلى ذلك. ما الذي كان يمكن فعله لمنع هذه المشكلة؟ | تقييم احتمالية المخاطر وتأثيرها | المقابلات الشخصية الفعالة أثناء عملية تحديد المخاطر | تحليل معايير المخاطر الأخرى | تقييم جودة بيانات المخاطر | تتعلق بيانات المخاطر وتقييم الجودة بالتحقق من دقة وموثوقية المعلومات المتعلقة بالمخاطر. [PMBOK الطبعة السادسة ، الصفحة 423] | 147 | 5 | False | "17" | Ahmad
119 | Your project is in execution, and you identify a new important stakeholder with a high level of influence. As a project manager, what should you do? | Update the Project management plan | Update the Stakeholder engagement plan | Update the requirements traceability matrix | Update the Stakeholder register | Since you find "a new important stakeholder", the stakeholder should be identified and added to Stakeholder Register. [PMBOK 6th edition, Page 514] | مشروعك قيد التنفيذ ، وأنت حددت صاحب مصلحة جديد له مستوى عال من التأثير. كمدير مشروع ، ماذا يجب أن تفعل؟ | قم بتحديث خطة إدارة المشروع | تحديث خطة إشراك أصحاب المصلحة | قم بتحديث مصفوفة تتبع المتطلبات | قم بتحديث سجل أصحاب المصلحة | نظرًا لأنك وجدت صاحب مصلحة جديد ومهم، يجب تحديد صاحب المصلحة وإضافته إلى سجل أصحاب المصلحة. [PMBOK الطبعة السادسة ، الصفحة 514] | 147 | 4 | False | "20" | Ahmad
120 | You are a project manager who takes over a project during the execution phase. You would like to know more about project deliverables, the work required to complete those deliverables, project constraints, and assumptions. Which of the following documents would be MOST useful? | Work Breakdown Structure (WBS) | Activity List | Requirements Documentation | Project Scope Statement | The project manager should refer to the project scope statement as it captures all the details related to the project scope including the product acceptance criteria, scope description, project deliverables, constraints, and assumptions. [PMBOK 6th edition, Page 154] | أنت مدير المشروع الذي يتولى المشروع أثناء مرحلة التنفيذ. ترغب في معرفة المزيد عن مخرجات المشروع، والعمل المطلوب لإكمال تلك التسليمات، وقيود المشروع، والافتراضات. أي من الوثائق التالية سيكون أكثر فائدة؟ | هيكل تجزئة العمل (WBS) | قائمة الأنشطة | وثائق المتطلبات | بيان نطاق المشروع | يجب أن يرجع مدير المشروع إلى بيان نطاق المشروع لأنه يشمل جميع التفاصيل المتعلقة بنطاق المشروع بما في ذلك معايير قبول المنتج ووصف النطاق وتسليمات المشروع والقيود والافتراضات. [PMBOK الطبعة السادسة ، الصفحة 154] | 141 | 4 | False | "20" | Ahmad
121 | A project manager notices an unusually high rate of risks, but has limited resources to address them. To what should the project manager refer to determine risk priorities? | Risk breakdown structure (RBS) | Risk management plan | Risk mitigation strategy | Risk probability and impact matrix | A probability and impact matrix is a grid for mapping the probability of each risk occurrence and its impact on project objectives if that risk occurs. This matrix specifies combinations of probability and impact that allow individual project risks to be divided into priority groups. [PMBOK 6th edition, page 425] | لاحظ مدير المشروع ارتفاع معدل المخاطر بشكل غير عادي، ولكن لديه موارد محدودة لمعالجتها. إلى ماذا يجب أن يرجع مدير المشروع لتحديد أولويات المخاطر؟ | هيكل تجزئة المخاطر (RBS) | خطة إدارة المخاطر | استراتيجية التخفيف من المخاطر | مصفوفة إحتمالية وتأثير المخاطر | مصفوفة الاحتمالات والتأثير هي شبكة لرسم احتمالية حدوث كل خطر وتأثيره على أهداف المشروع في حالة حدوث ذلك الخطر. تحدد هذه المصفوفة مجموعات الاحتمالات والتأثير التي تسمح بتقسيم مخاطر المشروع الفردية إلى مجموعات ذات أولوية. [PMBOK الطبعة السادسة ، الصفحة 425] | 147 | 3 | False | "19" | Ahmad
122 | As a project manager, what is the estimating technique should be used to estimate a project cost using a firm-fixed-price contract? | Parametric Estimating | Analogous Estimating | Program Evaluation and Review Technique (PERT) | Bottom-up Estimating | Bottom-up estimating will give you the most accurate estimates as it's required if using firm-fixed-price contract type. [PMBOK 6th edition, page 244] | كمدير للمشروع ، ما هي تقنية التقدير التي يجب استخدامها لتقدير تكلفة المشروع باستخدام عقد ثابت السعر؟ | التقدير بالمحددات | التقدير التماثلي | تقنية تقييم ومراجعة البرامج (PERT) | التقدير التصاعدي | يمنحك التقدير التصاعدي أدق التقديرات كما هو مطلوب في حالة استخدام نوع عقد السعر الثابت. [PMBOK الطبعة السادسة ، الصفحة 244] | 143 | 3 | False | "19" | Ahmad
123 | A detailed milestone list is created as an output of which process? | Develop Schedule | Sequence Activities | Develop Project Charter | Define Activities | A detailed milestone list is created as an output of the Define Activities process and includes information on whether the milestone is mandatory or optional. Note that the project charter also contains milestone information but at a higher level. [PMBOK 6th edition, Page 186] | من أي عملية يتم إنشاء قائمة مفصلة بالأحداث الهامة ؟ | تطوير الجدول الزمني | تسلسل الأنشطة | تطوير ميثاق المشروع | تحديد الأنشطة | يتم يتم إنشاء قائمة مفصلة بالأحداث الهامة كمخرج من عملية تحديد الأنشطة وتتضمن معلومات حول ما إذا كان الحدث الهام إلزاميًا أم اختياريًا. لاحظ أن ميثاق المشروع يحتوي أيضًا على أحداث هامة ولكن على مستوى أعلى. [PMBOK الطبعة السادسة ، الصفحة 186] | 142 | 3 | False | "16" | Ahmad
124 | You are the project manager for a large construction project. You want to understand the process for preparing a project scope statement and how formal acceptance of the completed project deliverables will be obtained. Which of the following will you have to reference? | The requirements management plan | The stakeholder management plan | The quality management plan | The scope management plan | Scope management plan is a component of the project management plan that contains information and guidance on how the scope and the scope-related processes are to be managed. What is included varies, but should contain procedures and processes specifying how the formal acceptance of the completed project deliverables will be obtained. [PMBOK 6th edition, Page 137] | أنت مدير مشروع لمشروع بناء كبير. تريد أن تفهم عملية إعداد بيان نطاق المشروع وكيف سيتم الحصول على القبول الرسمي لتسليمات المشروع المكتملة. أي مما يلي يجب أن ترجع إليه؟ | خطة إدارة المتطلبات | خطة إدارة أصحاب المصلحة | خطة إدارة الجودة | خطة إدارة النطاق | خطة إدارة النطاق هي أحد مكونات خطة إدارة المشروع التي تحتوي على معلومات وإرشادات حول كيفية إدارة النطاق والعمليات ذات الصلة بالنطاق. يختلف ما يتم تضمينه ، ولكن يجب أن يحتوي على إجراءات وعمليات تحدد كيفية الحصول على القبول الرسمي لتسليمات المشروع المكتملة. [PMBOK الطبعة السادسة ، الصفحة 137] | 141 | 3 | False | "18" | Ahmad
125 | Which data representation techniques helps to categorize stakeholders and combine the grid elements into a three-dimensional model that can be useful to project managers and teams in identifying and engaging their stakeholder community and assists with the development of communication strategies? | Probability and impact matrix | Power/interest grid | Power/influence grid | Stakeholder cube | Stakeholder cube is a refinement of the grid models. This model combines the grid elements into a three-dimensional model that can be useful to project managers and teams in identifying and engaging their stakeholder community. It provides multiple dimensions that improve the depiction of the stakeholder community as a multidimensional entity and assists with the development of communication strategies. [PMBOK 6th edition, Page 513] | ما هي تقنيات تمثيل البيانات التي تساعد على تصنيف أصحاب المصلحة ودمج عناصر الشبكة في نموذج ثلاثي الأبعاد يمكن أن يكون مفيدًا لمدراء المشاريع وفرق العمل في تحديد مجموعات أصحاب المصلحة وإشراكهم ويساعدهم في تطوير استراتيجيات الاتصال؟ | مصفوفة الاحتمالات والأثر | شبكة القوة / الإهتمام | شبكة القوة / التأثير | مكعب أصحاب المصلحة | مكعب أصحاب المصلحة هو تحسين لنماذج الشبكة. يجمع هذا النموذج بين عناصر الشبكة في نموذج ثلاثي الأبعاد يمكن أن يكون مفيدًا لمدراء المشاريع وفرق العمل في تحديد مجموعات أصحاب المصلحة وإشراكهم. يوفر أبعادًا متعددة تعمل على تحسين تصوير مجموعات أصحاب المصلحة ككيان متعدد الأبعاد ويساعد في تطوير استراتيجيات الاتصال. [PMBOK الطبعة السادسة ، الصفحة 513] | 149 | 2 | False | "17" | Ahmad
126 | You have been appointed as a project manager for a project which involves more than 2,000 stakeholders. One of the key stakeholders does not have authority regarding project decisions, but you recently discovered that he has much interest in your project. What stakeholder management strategy should you use with this key stakeholder? | Keep him satisfied | Monitor his actions | Manage him closely | Keep him informed | A power/interest grid is a classification model used for stakeholder analysis and management that groups the stakeholders based on their level of authority (power) and their level of concern (interest) regarding project outcomes. The classification and recommended management strategies are as follows: Low-power/low-interest: monitor only Low-power/high-interest: keep informed High-power/low-interest: keep satisfied High-power/high-interest: manage closely Based on this scenario, the Key stakeholder can be classified as Low-power/high-interest. Therefore, the correct answer is to keep the key stakeholder informed. [PMBOK 6th edition, Page 512] | لقد تم تعيينك كمدير مشروع لمشروع يضم أكثر من 2000 من أصحاب المصلحة. لا يتمتع أحد أصحاب المصلحة الرئيسيين بالسلطة فيما يتعلق بقرارات المشروع ، لكنك اكتشفت مؤخرًا أنه يهتم كثيرًا بمشروعك. ما هي استراتيجية إدارة أصحاب المصلحة التي يجب أن تستخدمها مع صاحب المصلحة الرئيسي هذا؟ | اجعله راضيًا | راقب أفعاله | تدبيره عن كثب | ابقيه على اطلاع | شبكة السلطة / الاهتمامات هي نموذج تصنيف يستخدم لتحليل وإدارة أصحاب المصلحة الذي يجمع أصحاب المصلحة بناءً على مستوى سلطتهم (السلطة) ومستوى اهتمامهم (الاهتمام) فيما يتعلق بنتائج المشروع. التصنيف واستراتيجيات الإدارة الموصى بها هي كما يلي: طاقة منخفضة / فائدة منخفضة: مراقبة فقط طاقة منخفضة / اهتمام مرتفع: ابق على اطلاع عالي الطاقة / اهتمام منخفض: حافظ على رضاك ​​قوة عالية / اهتمام مرتفع: إدارة عن كثب بناءً على هذا السيناريو ، يمكن تصنيف صاحب المصلحة الرئيسي على أنه منخفض الطاقة / عالي الفائدة. لذلك ، فإن الإجابة الصحيحة هي إبقاء أصحاب المصلحة الرئيسيين على اطلاع. [الطبعة السادسة من PMBOK ، صفحة 512] | 149 | 2 | False | "18" | Ahmad
127 | You have been asked by your project manager to help create a chart that illustrates the project resources that will be working on each work package. What would be the best type of chart to use? | WBS | Milestone chart | Project organization chart | RACI chart | A RACI chart is used to illustrate the connections between work packages, or activities, and project team members. A RACI chart is a useful tool to use to ensure a clear assignment of roles and responsibilities when the team consists of internal and external resources. [PMBOK 6th edition, Page 317] | لقد طلب منك مدير المشروع المساعدة في إنشاء مخطط يوضح موارد المشروع التي ستعمل على كل حزمة عمل. ما هو أفضل نوع من المخططات لاستخدامه؟ | WBS | مخطط المعالم | المخطط التنظيمي للمشروع | مخطط RACI | يتم استخدام مخطط RACI لتوضيح الروابط بين حزم العمل أو الأنشطة وأعضاء فريق المشروع. يعد مخطط RACI أداة مفيدة لاستخدامها لضمان تعيين واضح للأدوار والمسؤوليات عندما يتكون الفريق من موارد داخلية وخارجية. [الطبعة السادسة من PMBOK ، صفحة 317] | 145 | 3 | False | "18" | Ahmad
128 | A project manager is running a complex transformation project. During a team briefing, the lead resource raises a concern that a critical milestone is being affected because tasks are taking longer than expected. What should the project manager do? | Increase the number of resources to ensure that milestones are achieved | Review the project management plan to identify how the estimates were built | Inform the project sponsor of the expected delay and potential impact | Identify corrective actions and raise the issue to the change control board CCB if needed | Since the critical milestone is being affected because tasks are taking longer than expected. The project manager should Identify corrective actions and raise a change request to the change control board CCB if needed. Option (Increase the number of resources to ensure that milestones are achieved) is the next step after CCB approval. [PMBOK 6th edition, Page 229] | مدير مشروع يدير مشروع تحويل معقد. أثناء إحاطة الفريق ، يثير المورد الرئيسي قلقًا من تأثر حدث هام لأن المهام تستغرق وقتًا أطول من المتوقع. ماذا يجب أن يفعل مدير المشروع؟ | زيادة عدد الموارد لضمان تحقيق المعالم | قم بمراجعة خطة إدارة المشروع لتحديد كيفية بناء التقديرات | إبلاغ راعي المشروع بالتأخير المتوقع والأثر المحتمل | تحديد الإجراءات التصحيحية ورفع المشكلة إلى لجنة التحكم في التغيير CCB إذا لزم الأمر | نظرًا لأن الحدث الرئيسي الهام يتأثر لأن المهام تستغرق وقتًا أطول من المتوقع. يجب على مدير المشروع تحديد الإجراءات التصحيحية ورفع طلب التغيير إلى لجنة التحكم في التغيير CCB إذا لزم الأمر. الخيار (زيادة عدد الموارد لضمان تحقيق المعالم) هو الخطوة التالية بعد موافقة لجنة التحكم في التغيير CCB. [PMBOK الطبعة السادسة ، الصفحة 229] | 142 | 5 | False | "19" | Ahmad
129 | A senior project manager is working on monitoring the progress of the schedule. To determine whether performance is getting better or worse, he analyzes project performance over time. What technique is the project manager using? | Performance reviews | Variance analysis | Inspection | Trend Analysis | Trend analysis examines project performance over time to determine whether performance is improving or deteriorating. Graphical analysis techniques are valuable for understanding performance to date and for comparing to future performance goals in the form of completion dates. [PMBOK 6th edition, Page 227] | يعمل مدير مشروع كبير على مراقبة تقدم الجدول الزمني. لتحديد ما إذا كان الأداء يتحسن أو يسوء ، يقوم بتحليل أداء المشروع بمرور الوقت. ما هي التقنية التي يستخدمها مدير المشروع؟ | استعراضات الأداء | تحليل التباين | تفتيش | تحليل الاتجاه | يفحص تحليل الاتجاهات أداء المشروع بمرور الوقت لتحديد ما إذا كان الأداء يتحسن أو يتدهور. تعتبر تقنيات التحليل الرسومية ذات قيمة لفهم الأداء حتى الآن وللمقارنة بأهداف الأداء المستقبلية في شكل تواريخ الإنجاز. [PMBOK الطبعة السادسة ، الصفحة 227] | 142 | 5 | False | "16" | Ahmad
130 | Which of the following Manage Quality techniques examines problems, constraints, and non-value-added activities that occur during project work? | Reserve Analysis | Earned Value Analysis | Expected monetary value analysis | Process Analysis | Process Analysis examines problems, constraints, and non-value added activities that occur during project work. [PMBOK 6th edition, Page 292] | أي من تقنيات إدارة الجودة التالية يفحص المشكلات والقيود والأنشطة غير ذات القيمة المضافة التي تحدث أثناء عمل المشروع؟ | تحليل الاحتياطي | تحليل القيمة المكتسبة | تحليل القيمة المالية المتوقعة | تحليل العملية | يفحص تحليل العملية المشكلات والقيود والأنشطة غير ذات القيمة المضافة التي تحدث أثناء عمل المشروع. [PMBOK الطبعة السادسة ، الصفحة 292] | 144 | 4 | False | "16" | Ahmad
131 | You are in the process of analyzing the stakeholders on your project. You have grouped them based on their authority and their degree of active involvement in the project. Which of the following would you use to document this information? | Model Power/Interest Grid | Influence/Impact Grid | Salience | Power/Influence Grid | A Power/Influence Grid groups the stakeholders based on their authority and their degree of active involvement in the project. [PMBOK 6th edition, Page, 512] | أنت بصدد تحليل أصحاب المصلحة في مشروعك. لقد جمعتهم بناءً على سلطتهم ودرجة مشاركتهم النشطة في المشروع. أي مما يلي قد تستخدمه لتوثيق هذه المعلومات؟ | نموذج شبكة التأثير / الاهتمام | شبكة التحفيز / التأثير | بروز | شبكة النفوذ / التحفيز | تجمع شبكة النفوذ / التحفيز أصحاب المصلحة بناءً على سلطتهم ودرجة مشاركتهم النشطة في المشروع. [PMBOK الطبعة السادسة ، الصفحة 512] | 149 | 2 | False | "19" | Ahmad
132 | Nada has been assigned to establish a PMO in her organization. Nada believes this project cannot succeed unless all the key project stakeholders support the project. She also believes she needs to pay special attention to stakeholder management to ensure the success of this project. First, she needs to develop her stakeholder register. To produce the project stakeholder register, which of the following processes must Nada start? | Plan Stakeholder Engagement | Manage Stakeholder Engagement | Monitor Stakeholder Engagement | Identify Stakeholders | The stakeholder register is developed during the Identify Stakeholders process. [PMBOK 6th edition, Page 514] | تم تكليف ندى بتأسيس مكتب إدارة المشاريع PMO في مؤسستها. تعتقد ندى أن هذا المشروع لا يمكن أن ينجح ما لم يدعمه جميع أصحاب المصلحة الرئيسيين في المشروع. كما تعتقد أنها بحاجة إلى إيلاء اهتمام خاص لإدارة أصحاب المصلحة لضمان نجاح هذا المشروع. أولاً ، تحتاج إلى تطوير سجل أصحاب المصلحة. لإنتاج سجل أصحاب المصلحة في المشروع ، أي من العمليات التالية يجب أن تبدأ ندى؟ | خطة إشراك أصحاب المصلحة | إدارة إشراك أصحاب المصلحة | مراقبة مشاركة أصحاب المصلحة | تحديد أصحاب المصلحة | تم تطوير سجل أصحاب المصلحة أثناء عملية تحديد أصحاب المصلحة. [PMBOK الطبعة السادسة ، الصفحة 514] | 149 | 2 | False | "20" | Ahmad
133 | During the implementation phase, one of your project team has told you that the Concrete delivery will be delayed one week. As a project manager, what document should you refer to FIRST? | Plan Risk management plan | Issue Log | Risk Response | Risk Register | You should refer First to Risk Register to check this risk was identified before or not. If yes so this identified risk and you should implement the response. if it's not identified before then it's considered unidentified risk occurred and you should do workaround. [PMBOK 6th edition, Page 449] | أثناء مرحلة التنفيذ ، أخبرك أحد أعضاء فريق المشروع الخاص بك أن تسليم الخرسانة سيتأخر لمدة أسبوع. بصفتك مدير مشروع ، ما هي الوثيقة التي يجب الرجوع اليها اولا؟ | خطة خطة إدارة المخاطر | سجل المشاكل | الاستجابة للمخاطر | سجل المخاطر | يجب عليك الرجوع أولاً إلى سجل المخاطر للتحقق من تحديد هذه المخاطر من قبل أم لا. إذا كانت الإجابة بنعم ، فقد حددت هذه المخاطر ويجب عليك تنفيذ الاستجابة. إذا لم يتم تحديدها من قبل ، فسيتم اعتبارها مخاطرة غير محددة ويجب عليك حلها. [الطبعة السادسة من PMBOK ، صفحة 449] | 147 | 4 | False | "20" | Ahmad
134 | Which of the following techniques should a project manager use to optimize and reduce the duration of a project? | Simulation | Critical path method | Resource leveling | Fast-tracking | Fast tracking. A schedule compression technique in which activities or phases are normally done in sequence are performed in parallel for at least a portion of their duration. [PMBOK 6th edition page, 215] | أي من الأساليب التالية يجب أن يستخدمها مدير المشروع لتحسين مدة المشروع وتقليلها؟ | محاكاة | طريقة المسار الحرج | تسوية الموارد | تتبع سريع | تتبع سريع. تقنية ضغط الجدول الزمني التي تتم فيها الأنشطة أو المراحل عادة في تسلسل يتم إجراؤها بالتوازي على الأقل لجزء من مدتها. [PMBOK الطبعة السادسة ، الصفحة 215] | 142 | 3 | False | "20" | Ahmad
135 | A project manager is executing a new office building. Which of the following activities might the project manager and the team conduct during the Monitor and Control Project Work process? | Implementing approved change requests to achieve the project's objectives | Transfer the ownership of deliverables to the assigned stakeholders | Prepare and share the final project report according to the communications management plan | Comparing actual project performance against the project management plan | Monitor and Control Project Work is the process of tracking, reviewing, and reporting overall progress to meet the performance objectives defined in the project management plan. From the answers, only comparing actual project performance against the project management plan is performed during monitor and control project work process. [PMBOK 6th edition, Page 105] | مدير مشروع يقوم بتنفيذ مبنى إداري جديد. أي من الأنشطة التالية قد يقوم بها مدير المشروع والفريق أثناء عملية المراقبة والتحكم في عمل المشروع؟ | تنفيذ طلبات التغيير المعتمدة لتحقيق أهداف المشروع | نقل ملكية المخرجات إلى أصحاب المصلحة المعينين | قم بإعداد التقرير النهائي للمشروع ومشاركته وفقًا لخطة إدارة الاتصالات | مقارنة أداء المشروع الفعلي مع خطة إدارة المشروع | مراقبة العمل في المشروع والتحكم فيه هي عملية تتبع التقدم الإجمالي ومراجعته والإبلاغ عنه لتلبية أهداف الأداء المحددة في خطة إدارة المشروع. من الإجابات ، يتم فقط مقارنة أداء المشروع الفعلي مقابل خطة إدارة المشروع أثناء مراقبة عملية عمل المشروع والتحكم فيها. [PMBOK الطبعة السادسة ، الصفحة 105] | 140 | 5 | False | "16" | Ahmad
136 | You are managing a software development project. You want to determine who are the individuals or groups might participate in identifying risks to the project, as well as those who are available to act as risk owners. Which of the following documents should you review? | Risk breakdown structure (RBS) | RACI chart | Stakeholder engagement plan | Stakeholder register | The project team is performing the Identify Risks process. One of the input to this process is the Stakeholder Register. The Stakeholder Register indicates which individuals or groups might participate in identifying the project risks. It also details those individuals who are available to act as risk owners. [PMBOK 6th edition, Page 413] | أنت تدير مشروع تطوير برمجيات. تريد تحديد الأفراد أو المجموعات التي قد تشارك في تحديد المخاطر التي يتعرض لها المشروع ، بالإضافة إلى أولئك المتاحين للعمل كمالكين للمخاطر. أي من المستندات التالية يجب عليك مراجعتها؟ | هيكل توزيع المخاطر (RBS) | مخطط RACI | خطة إشراك أصحاب المصلحة | سجل أصحاب المصلحة | يقوم فريق المشروع بتنفيذ عملية تحديد المخاطر. أحد المدخلات في هذه العملية هو سجل أصحاب المصلحة. يشير سجل أصحاب المصلحة إلى الأفراد أو المجموعات التي قد تشارك في تحديد مخاطر المشروع. كما يفصل هؤلاء الأفراد المتاحين للعمل كمالكين للمخاطر. [الطبعة السادسة من PMBOK ، صفحة 413] | 147 | 3 | False | "20" | Ahmad
137 | You are managing a one year duration project. During the middle of the project, it is found that the quality standards require a major change because of the project quality is not effective. As a project manager, what should you do next? | Follow the risk management plan | Follow the Communication management plan | Follow the scope management plan | Follow the change management plan | Change management plan. Describes how the change requests throughout the project will be formally authorized and incorporated. The change management plan defines the process for managing change on the project. [PMBOK 6th edition, Page 88] | أنت تدير مشروعًا مدته عام واحد. خلال منتصف المشروع ، وجد أن معايير الجودة تتطلب تغييرًا كبيرًا نظرًا لأن جودة المشروع ليست فعالة. كمدير مشروع ، ماذا يجب أن تفعل بعد ذلك؟ | اتبع خطة إدارة المخاطر | اتبع خطة إدارة الاتصالات | اتبع خطة إدارة النطاق | اتبع خطة إدارة التغيير | خطة ادارة التغيير. تصف كيف سيتم اعتماد طلبات التغيير رسميًا ودمجها في جميع مراحل المشروع. تحدد خطة إدارة التغيير عملية إدارة التغيير في المشروع. [الطبعة السادسة من PMBOK ، صفحة 88] | 144 | 4 | False | "17" | Ahmad
138 | Main Sponsor is really interested in reviewing the key performance indicators of the project. Where will you find this information for the project? | KPI is part of the change control tool | KPI can be part of organizational process assets | KPI is included in the project charter in the business case section | KPI is included in the project charter as success criteria | KPI is an Enterprise Environmental Factors EEF, so it as input in developing the project charter process. it will be part of measurable project objectives in the Project Charter. [PMBOK 6th edition, Page 75] | الراعي الرئيسي مهتم حقًا بمراجعة مؤشرات الأداء الرئيسية للمشروع. أين ستجد هذه المعلومات الخاصة بالمشروع؟ | KPI هي جزء من أداة التحكم في التغيير | يمكن أن يكون KPI جزءًا من أصول العملية التنظيمية | يتم تضمين مؤشر الأداء الرئيسي في ميثاق المشروع في قسم دراسة الجدوى | تم تضمين KPI في ميثاق المشروع كمعايير النجاح | مؤشرات الاداء KPI هي جزء من العوامل البيئية المؤسسية EEF لذلك فهي بمثابة مدخلات في عملية تطوير ميثاق المشروع. ستكون جزءًا من أهداف المشروع القابلة للقياس في ميثاق المشروع[ PMBOK الطبعة السادسة ، الصفحة 75] | 140 | 2 | False | "20" | Ahmad
139 | You are a project manager, your company would like to outsource the landscaping works to the subcontractor to complete within 2 months. The budget of the works is SAR 40,000 and the scope is well defined. What type of contract preferred to be used: | Cost plus incentive fee | Cost-reimbursable | Time and material | Fixed-price | Fixed-price contracts involves setting a fixed total price for a defined product, service, or result to be provided. These contracts type used when the requirements are well defined and no significant changes to the scope are expected. [PMBOK 6th edition, Page 471] | أنت مدير مشروع ، وتود شركتك الاستعانة بمصادر خارجية لأعمال تنسيق الحدائق إلى مقاول من الباطن لإكمالها في غضون شهرين. ميزانية الأعمال 40،000 ريال سعودي والنطاق محدد بشكل جيد. ما نوع العقد المفضل استخدامه: | التكلفة بالإضافة إلى رسوم الحوافز | للسداد التكاليف | الوقت والمواد | سعر ثابت | تتضمن عقود السعر الثابت تحديد سعر إجمالي ثابت لمنتج أو خدمة محددة أو نتيجة يتم تقديمها. يتم استخدام هذا النوع من العقود عندما تكون المتطلبات محددة جيدًا ولا يُتوقع حدوث تغييرات كبيرة في النطاق. [PMBOK الطبعة السادسة ، الصفحة 571] | 148 | 3 | False | "17" | Ahmad
140 | You are leading your team in the preparation of your project schedule and are currently sequencing the activities and determining which type of precedence relationship exists between them. Which of the following is the most commonly used type of precedence relationship that you will use? | Start-to-start | Finish-to-finish | Start-to-finish | Finish-to-start | In PDM, FS is the most commonly used type of precedence relationship. The SF relationship is very rarely. [PMBOK 6th edition, Page 190] | أنت تقود فريقك في إعداد الجدول الزمني لمشروعك وتقوم حاليًا بترتيب الأنشطة وتحديد نوع علاقة الأسبقية الموجودة بينهم. أي مما يلي هو النوع الأكثر استخدامًا لعلاقة الأسبقية التي ستستخدمها؟ | من البداية إلى البداية | من النهاية إلى النهاية | البداية وحتى النهاية | من الإنهاء للبدء | في PDM , FS هو النوع الأكثر استخدامًا لعلاقة الأسبقية. علاقة SF نادرا جدا. [PMBOK الطبعة السادسة ، الصفحة 190] | 142 | 3 | False | "17" | Ahmad
141 | As a project manager, if you want to determine the best corrective action in terms of cost in case of project deviations, which of the following data analysis techniques should you use? | Trend analysis | Variance analysis | Earned value analysis | Cost-benefit analysis | The cost-benefit analysis helps to determine the best corrective action in terms of cost in case of project deviations. [PMBOK 6th edition, Page 111] | بصفتك مدير مشروع ، إذا كنت ترغب في تحديد أفضل إجراء تصحيحي من حيث التكلفة في حالة انحرافات المشروع ، أي من تقنيات تحليل البيانات التالية يجب أن تستخدمها؟ | تحليل الاتجاه | تحليل التباين | تحليل القيمة المكتسبة | تحليل التكاليف والفوائد | يساعد تحليل التكلفة والفوائد على تحديد أفضل إجراء تصحيحي من حيث التكلفة في حالة انحرافات المشروع. [الطبعة السادسة من PMBOK ، صفحة 111] | 140 | 5 | False | "17" | Ahmad
142 | A project manager needs to communicate the start of the project, key milestones, and other relevant information to stakeholders, and then gain their commitment. What should the project manager do? | Review and assess detailed project requirements, constraints, and assumptions with stakeholders. | Develop the project charter | Develop the communication management plan. | Conduct a kick-off meeting. | The project kick-off meeting is usually associated with the end of planning and the start of executing. It's purpose is to communicate the objectives of the project, gain the commitment of the team for the project, and explain the roles and responsibilities of each stakeholder. [PMBOK 6th edition, Page 86] | يحتاج مدير المشروع إلى توصيل بداية المشروع والمعالم الرئيسية والمعلومات الأخرى ذات الصلة إلى أصحاب المصلحة ، ثم الحصول على التزامهم. ماذا يجب أن يفعل مدير المشروع؟ | مراجعة وتقييم متطلبات المشروع التفصيلية والقيود والافتراضات مع أصحاب المصلحة. | تطوير ميثاق المشروع | تطوير خطة إدارة الاتصال. | عقد اجتماع اطلاق المشروع | عادة ما يرتبط اجتماع إطلاق المشروع بنهاية التخطيط وبداية التنفيذ. والغرض منه هو إيصال أهداف المشروع ، وكسب التزام الفريق بالمشروع ، وشرح أدوار ومسؤوليات كل صاحب مصلحة. [PMBOK الطبعة السادسة ، الصفحة 86] | 140 | 3 | False | "18" | Ahmad
143 | You have recently been assigned to lead a project that is halfway into execution. The project has many stakeholders, and you are trying to determine how to engage them effectively. Which of the following will best help you in this effort? | Scope Management Plan | Project Charter | Change Management Plan | Project Management Plan | You are using Manage Stakeholder Engagement process which is concerned with communicating and working with stakeholders to meet their needs, address issues, and foster involvement. One of the inputs to this process is the project management plan which provides guidance regarding stakeholder communications, risk management, change management, and stakeholder engagement. Specifically, the stakeholder engagement plan contains information on how to manage stakeholder expectations this helping to determine how to engage the stakeholders effectively. [PMBOK 6th edition, Page 523] | لقد تم تكليفك مؤخرًا لقيادة مشروع في منتصف طريق التنفيذ. يحتوي المشروع على العديد من أصحاب المصلحة ، وأنت تحاول تحديد كيفية إشراكهم بفعالية. أي مما يلي سيساعدك على أفضل وجه في هذا الجهد؟ | خطة إدارة النطاق | ميثاق المشروع | خطة إدارة التغيير | خطة إدارة المشروع | انت تستخدم عملية إدارة إشراك أصحاب المصلحة والتي تهتم بالتواصل والعمل مع أصحاب المصلحة لتلبية احتياجاتهم ومعالجة المشكلات وتعزيز المشاركة. أحد مدخلات هذه العملية هو خطة إدارة المشروع التي توفر التوجيه فيما يتعلق بالاتصالات مع أصحاب المصلحة ، وإدارة المخاطر ، وإدارة التغيير ، وإشراك أصحاب المصلحة. على وجه التحديد ، تحتوي خطة إشراك أصحاب المصلحة على معلومات حول كيفية إدارة توقعات أصحاب المصلحة وهذا يساعد على تحديد كيفية إشراك أصحاب المصلحة بشكل فعال. [PMBOK الطبعة السادسة ، الصفحة 523] | 149 | 4 | False | "16" | Ahmad
144 | Which of the following project processes would you use to monitor the implementation of approved changes? | Control Scope | Perform Integrated Change Control | Validate Scope | Monitor and Control Project Work | During the Monitor and Control Project Work process, all project work is monitored and controlled, including approved changes and defect repairs. [PMBOK 6th edition, Page 107] | أي من عمليات المشروع التالية ستستخدمها لمراقبة تنفيذ التغييرات المعتمدة؟ | نطاق التحكم | أداء مراقبة التغيير المتكامل | تحقق من النطاق | المراقبة والتحكم في أعمال المشروع | أثناء عملية المراقبة والتحكم في اعمال المشروع ، تتم مراقبة جميع أعمال المشروع والتحكم فيها ، بما في ذلك التغييرات المعتمدة وإصلاحات العيوب. [PMBOK الطبعة السادسة ، الصفحة 107] | 140 | 2 | False | "18" | Ahmad
145 | A project manager begins working for a project that is already in progress. The project manager will be meeting with the project sponsor very shortly to review the project's overall scope and expected deliverables. How should the project manager prepare for the meeting? | Review the schedule forecast | Interview project team members | Examine the Gantt chart | Review the project charter | Since the meeting with sponsor to review (Overall scope and expected deliverables). A project manager need to prepare for the meeting by review the Project Charter which include the project's overall scope and expected deliverables. [PMBOK 6th edition, Page 523] | يبدأ مدير المشروع العمل في مشروع قيد التنفيذ بالفعل. سيجتمع مدير المشروع مع راعي المشروع في وقت قريب جدًا لمراجعة النطاق العام للمشروع والتسليمات المتوقعة. كيف يجب أن يستعد مدير المشروع للاجتماع؟ | راجع توقعات الجدول الزمني | مقابلة أعضاء فريق المشروع | افحص مخطط جانت | مراجعة ميثاق المشروع | طالما الاجتماع مع الراعي لمراجعة (النطاق العام والمخرجات المتوقعة). يحتاج مدير المشروع إلى التحضير للاجتماع من خلال مراجعة ميثاق المشروع الذي يتضمن النطاق العام للمشروع والتسليمات المتوقعة. [PMBOK الطبعة السادسة ، الصفحة 523] | 149 | 4 | False | "16" | Ahmad
146 | A stakeholder requests a change to the project. The project manager wants to avoid wasting the change control board (CCB) time and decides to approve the change himself. What should the project manager do to make sure he can approve this change? | Request that all stakeholders vote before making a decision. | Review the change with all stakeholders. | Obtain the customer's approval before implementation. | Verify that the change does not affect the project baseline. | Changes may or may not impact the project baselines. Sometimes only the performance against the baseline is affected. Decisions on those changes are usually made by the project manager. [PMBOK 6th edition, Page 117] | أحد أصحاب المصلحة يطلب تغيير في المشروع. يريد مدير المشروع تجنب إضاعة وقت لجنة التحكم في التغيير (CCB) ويقرر الموافقة على التغيير بنفسه. ما الذي يجب أن يفعله مدير المشروع للتأكد من أنه يمكنه الموافقة على هذا التغيير؟ | اطلب من جميع أصحاب المصلحة التصويت قبل اتخاذ القرار. | راجع التغيير مع جميع أصحاب المصلحة. | الحصول على موافقة العميل قبل التنفيذ. | تحقق من أن التغيير لا يؤثر على خط الأساس للمشروع. | قد تؤثر التغييرات أو لا تؤثر على خطوط الأساس للمشروع. في بعض الأحيان يتأثر الأداء مقابل خط الأساس فقط. عادة ما يتخذ مدير المشروع القرارات بشأن هذه التغييرات. [PMBOK الطبعة السادسة ، الصفحة 117] | 140 | 5 | False | "18" | Ahmad
147 | A project manager has two projects of equal strategic importance. However, due to budget constraints, only one can be keep ongoing. There are uncertainties and risks associated with both projects. What tool or technique should the project manager use to decide which project to keep running? | Influence diagram | Simulations | Sensitivity analysis | Decision tree analysis | Decision trees analysis are used to support selection of the best of several alternative courses of action. Alternative paths through the project are shown in the decision tree using branches representing different decisions or events, each of which can have associated costs and related individual project risks (including both threats and opportunities). The end-points of branches in the decision tree represent the outcome from following that particular path, which can be negative or positive. The decision tree is evaluated by calculating the expected monetary value of each branch, allowing the optimal path to be selected. [PMBOK 6th edition page, 435] | لدى مدير المشروع مشروعان لهما أهمية استراتيجية متساوية. ومع ذلك ، نظرًا لقيود الميزانية ، يمكن الاستمرار في تشغيل واحد فقط. هناك أوجه عدم يقين ومخاطر مرتبطة بكلا المشروعين. ما الأداة أو التقنية التي يجب أن يستخدمها مدير المشروع لتحديد المشروع الذي يجب الاستمرار في تشغيله؟ | مخطط التأثير | المحاكاة | تحليل الحساسية | تحليل شجرة القرار | يُستخدم تحليل أشجار القرار لدعم اختيار أفضل مسارات العمل البديلة العديدة. تظهر المسارات البديلة من خلال المشروع في شجرة القرار باستخدام الفروع التي تمثل قرارات أو أحداثًا مختلفة ، يمكن أن يكون لكل منها تكاليف مرتبطة ومخاطر المشروع الفردية ذات الصلة (بما في ذلك التهديدات والفرص). تمثل النقاط النهائية للفروع في شجرة القرار النتيجة من اتباع هذا المسار المحدد ، والذي يمكن أن يكون سالبًا أو إيجابيًا. يتم تقييم شجرة القرار من خلال حساب القيمة النقدية المتوقعة لكل فرع ، مما يسمح بتحديد المسار الأمثل. [PMBOK الطبعة السادسة ، الصفحة 435] | 147 | 3 | False | "18" | Ahmad
148 | A project sponsor ask the project manager to obtain a summary of the performance of a project that recently closed. What document can the project manager provide the sponsor and contain this information? | Work performance information | Project management plan | Work performance report | Final report | The final report provides a summary of the project performance. [PMBOK 6th edition, Page 127] | يطلب راعي المشروع من مدير المشروع الحصول على ملخص لأداء مشروع تم إغلاقه مؤخرًا. ما هي الوثيقة التي يمكن لمدير المشروع تقديمها للراعي وتحتوي على هذه المعلومات؟ | معلومات أداء العمل | خطة إدارة المشروع | تقرير أداء العمل | التقرير النهائي | يقدم التقرير النهائي ملخصًا لأداء المشروع. [PMBOK الطبعة السادسة ، الصفحة 127] | 140 | 6 | False | "18" | Ahmad
149 | Team members on a life cycle replacement project are consumed to frequently changing requirements even without formal approval. What should the project manager do? | Review the cost baseline with team members, and ask that any changes to requirements with cost are captured | Review the configuration management plan to identify what items will be changed and the frequency of the change | Ask the project sponsor to provide directions to the project team with regard to the frequency of any changes to requirements | Develop and implement a change management plan to define how changes will be addressed and controlled | The change management plan is very important plan for every project because Its provide the direction for managing the change control process and documents the roles and responsibilities of the change control board (CCB). The project manager should develop and implement a change management plan to define how changes will be addressed and controlled. [PMBOK 6th edition, Page 88] | يتم استهلاك أعضاء الفريق في مشروع استبدال دورة الحياة لتغيير المتطلبات بشكل متكرر حتى بدون موافقة رسمية. ماذا يجب أن يفعل مدير المشروع؟ | راجع خط أساس التكلفة مع أعضاء الفريق ، واطلب تسجيل أي تغييرات على المتطلبات مع التكلفة | راجع خطة إدارة التكوين لتحديد العناصر التي سيتم تغييرها وتكرار التغيير | اطلب من راعي المشروع تقديم توجيهات لفريق المشروع فيما يتعلق بتكرار أي تغييرات على المتطلبات | تطوير وتنفيذ خطة إدارة التغيير لتحديد كيفية معالجة التغييرات والتحكم فيها | تعد خطة إدارة التغيير خطة مهمة للغاية لكل مشروع لأنها توفر التوجيه لإدارة عملية التحكم في التغيير وتوثيق أدوار ومسؤوليات لجنة التحكم في التغيير (CCB). يجب على مدير المشروع تطوير وتنفيذ خطة إدارة التغيير لتحديد كيفية معالجة التغييرات والتحكم فيها. [الطبعة السادسة من PMBOK ، صفحة 88] | 140 | 5 | False | "19" | Ahmad
150 | A project manager is aware of a high risk item prior to starting a project. The project manager has completed a risk analysis and concluded that the risk is positive, high impact, and low probability. What should the project manager do? | Conduct cost-benefit analysis | Conduct a strengths, weaknesses, opportunities, and threats (SOWT) analysis | Facilitate a risk brainstorming session | Take action to capture the positive effect of uncertainty | The project manager has completed identify risks and risk analysis process. The next process is plan risk responses which is the process of developing options, selecting strategies, and agreeing on actions to address overall project risk exposure, as well as to treat individual project risks. so the correct answer is (Take action to capture the positive effect of uncertainty). [PMBOK 6th edition Page, 437] | يدرك مدير المشروع عنصرًا عالي الخطورة قبل بدء المشروع. أكمل مدير المشروع تحليل المخاطر وخلص إلى أن الخطر إيجابي وعالي التأثير ومنخفض الاحتمال. ماذا يجب أن يفعل مدير المشروع؟ | إجراء تحليل التكلفة والعائد | إجراء تحليل لنقاط القوة والضعف والفرص والتهديدات (SOWT) | تسهيل جلسة عصف ذهني للمخاطر | اتخذ إجراءً لالتقاط التأثير الإيجابي لعدم اليقين | أكمل مدير المشروع تحديد المخاطر وعملية تحليل المخاطر. تتمثل العملية التالية في تخطيط الاستجابات للمخاطر وهي عملية تطوير الخيارات واختيار الاستراتيجيات والاتفاق على الإجراءات لمعالجة التعرض العام لمخاطر المشروع ، فضلاً عن معالجة مخاطر المشروع الفردية. لذا فإن الإجابة الصحيحة هي (اتخذ إجراءً لالتقاط التأثير الإيجابي لعدم اليقين). [PMBOK الطبعة السادسة ، الصفحة 437] | 147 | 3 | False | "19" | Ahmad
151 | During execution, a project manager identifies a major obstacle that is delay progress. An escalation to the client's project manager has gone unanswered, and project progress is worsening each week. What should the project manager do? | Inform the supervisor of the client's project manager | Follow the escalation matrix in the project management plan, and escalate it to the next level | Escalate the issue directly to the steering committee | Revise the communication management plan | Since (Escalation has gone unanswered), so its a communication issue and the project manager should revise the communication management plan because its contains the escalation processes with person or groups who will receive the information, methods or technologies used to convey the information, such as memos, email, press releases, or social media and method for updating and refining the communications management plan. [PMBOK 6th edition Page, 377] | أثناء التنفيذ ، يحدد مدير المشروع عقبة رئيسية تتمثل في تأخير التقدم. لم يتم الرد على التصعيد إلى مدير مشروع العميل ، ويزداد تقدم المشروع سوءًا كل أسبوع. ماذا يجب أن يفعل مدير المشروع؟ | إبلاغ المشرف بمدير مشروع العميل | اتبع مصفوفة التصعيد في خطة إدارة المشروع ، وقم بتصعيدها إلى المستوى التالي | تصعيد المسألة مباشرة إلى اللجنة التوجيهية | مراجعة خطة إدارة الاتصالات | نظرًا لأن (التصعيد لم يتم الرد عليه) ، فهذه مشكلة اتصال ويجب على مدير المشروع مراجعة خطة إدارة الاتصالات لأنها تحتوي على عمليات التصعيد مع شخص أو مجموعات ستتلقى المعلومات أو الأساليب أو التقنيات المستخدمة لنقل المعلومات ، مثل المذكرات أو البريد الإلكتروني أو البيانات الصحفية أو وسائل التواصل الاجتماعي وطريقة تحديث وتحسين خطة إدارة الاتصالات. [PMBOK الطبعة السادسة ، الصفحة 377] | 146 | 4 | False | "19" | Ahmad
152 | During a weekly status meeting, a team member informs the project manager that the design submitted to the local government for approval has been rejected due to an error in the blueprint. Resubmission of the design will require an additional two weeks. What should the project manager do first? | Review the reject submission and begin working on the resubmission | Add another layer of review for future projects to avoid similar problems | Inform the project sponsor and look for support | Update the issue log and identify the possible cause of the error | Resubmission of the design will require an additional two weeks this Is an issue and the project manager should FIRST update the issue log and identify the possible cause of the error. [PMBOK 6th edition Page, 96] | خلال اجتماع الحالة الأسبوعي ، يقوم أحد أعضاء الفريق بإبلاغ مدير المشروع بأن التصميم المقدم إلى الحكومة المحلية للموافقة عليه قد تم رفضه بسبب خطأ في المخطط. سيتطلب إعادة تقديم التصميم أسبوعين إضافيين. ما الذي يجب أن يفعله مدير المشروع أولاً؟ | راجع تقديم الرفض وابدأ في العمل على إعادة التقديم | أضف طبقة أخرى من المراجعة للمشاريع المستقبلية لتجنب مشاكل مماثلة | أبلغ راعي المشروع وابحث عن الدعم | قم بتحديث سجل المشاكل وحدد السبب المحتمل للخطأ | ستتطلب إعادة تقديم التصميم أسبوعين إضافيين ، وهذه مشكلة ويجب على مدير المشروع أولاً تحديث سجل المشاكل وتحديد السبب المحتمل للخطأ. [PMBOK الطبعة السادسة ، الصفحة 96] | 140 | 4 | False | "20" | Ahmad
153 | A project to develop a new product contains many stakeholders who are trying to influence the project but have conflicting interests. The project manager has just completed the project charter and is working on the project management plan, which only gives a high-level view of both the product specifications and the project scope. What should the project manager do next to build a detailed scope description? | List all concerns in the stakeholder engagement plan | Create the work breakdown structure. WBS | Develop the scope statement with stakeholder input. | Implement the plan scope management process. | The project manager has only completed the project charter and now is working on planning. So the first process in the planning is plan scope management, that helps in know how to collect requirement , how to build a detailed scope description, how to create WBS, and how formal acceptance of the completed project deliverables will be obtained. [PMBOK 6th edition Page, 137] | يحتوي مشروع تطوير منتج جديد على العديد من أصحاب المصلحة الذين يحاولون التأثير على المشروع ولكن لديهم مصالح متضاربة. أكمل مدير المشروع للتو ميثاق المشروع ويعمل على خطة إدارة المشروع ، والتي لا تقدم سوى رؤية عالية المستوى لكل من مواصفات المنتج ونطاق المشروع. ما الذي يجب أن يفعله مدير المشروع بعد ذلك لبناء وصف مفصل للنطاق؟ | ضع قائمة بجميع المخاوف في خطة إشراك أصحاب المصلحة | إنشاء هيكل تنظيم العمل. WBS | تطوير بيان النطاق مع مدخلات أصحاب المصلحة. | تنفيذ عملية إدارة النطاق | أكمل مدير المشروع ميثاق المشروع فقط ويعمل الآن على التخطيط. لذا فإن العملية الأولى في التخطيط هي إدارة النطاق ، والتي تساعد في معرفة كيفية جمع المتطلبات ، وكيفية بناء وصف مفصل للنطاق ، وكيفية إنشاء WBS ، وكيف سيتم الحصول على القبول الرسمي لتسليمات المشروع المكتملة. [PMBOK الطبعة السادسة ، الصفحة 137] | 141 | 3 | False | "19" | Ahmad
154 | A global technology company invested in an infrastructure upgrade project as a part of its business strategy. During the planning phase, the project team works with stakeholders to identify project requirements. The project manager is having difficulty engaging stakeholders who work internationally in different time zones. The stakeholders are unable to participate in regularly scheduled planning meetings, and often don't provide timely responses to emails and other requests for information. What should the project manager do next to minimize the impact this issue may have on the project? | Arrange a meeting to discuss the issue. | Alert senior management. | Create a resource management plan. | Create a communication management plan. | The project manager is having difficulty engaging stakeholders who work internationally In different time zones and stakeholders are unable to participate in regularly scheduled planning meetings, so the project manager should create a communication management plan to minimize the impact this issue may have on the project. [PMBOK 6th edition Page, 137] | استثمرت شركة تقنية عالمية في مشروع ترقية البنية التحتية كجزء من إستراتيجية أعمالها. خلال مرحلة التخطيط ، يعمل فريق المشروع مع أصحاب المصلحة لتحديد متطلبات المشروع. يواجه مدير المشروع صعوبة في إشراك أصحاب المصلحة الذين يعملون دوليًا في مناطق زمنية مختلفة. لا يستطيع أصحاب المصلحة المشاركة في اجتماعات التخطيط المجدولة بانتظام ، ولا يقدمون في الغالب ردودًا في الوقت المناسب على رسائل البريد الإلكتروني وطلبات المعلومات الأخرى. ما الذي يجب أن يفعله مدير المشروع بعد ذلك لتقليل تأثير هذه المشكلة على المشروع؟ | رتب اجتماعًا لمناقشة المشكلة. | تنبيه الإدارة العليا. | قم بإنشاء خطة إدارة الموارد. | وضع خطة لإدارة الاتصالات. | يواجه مدير المشروع صعوبة في إشراك أصحاب المصلحة الذين يعملون دوليًا في مناطق زمنية مختلفة ولا يتمكن أصحاب المصلحة من المشاركة في اجتماعات التخطيط المجدولة بانتظام ، لذلك يجب على مدير المشروع إنشاء خطة إدارة اتصالات لتقليل التأثير الذي قد تحدثه هذه المشكلة على المشروع. [PMBOK 6th edition Page، 137] | 146 | 3 | False | "17" | Ahmad
155 | During the execution phase, a project manager discovers that team members have started to work on task that are coming directly from the customer. What should the project manager do? | Split the project into two projects to keep the scopes separate and bill the client separately. | Continue working on tasks that have already been started and revise the baseline | Hold a risk review board meeting and add the tasks that have already been started to the risk log. | Stop the work that is outside the project scope statement and submit a change request. | The project manager should stop the work that is outside the project scope statement and submit a change request to take the approval from CCB, and only do the works included in the project scope statement or the approved change request. [PMBOK 6th edition Page, 90] | أثناء مرحلة التنفيذ ، يكتشف مدير المشروع أن أعضاء الفريق قد بدأوا العمل في مهمة تأتي مباشرة من العميل. ماذا يجب أن يفعل مدير المشروع؟ | قسّم المشروع إلى مشروعين للإبقاء على النطاقات منفصلة وفاتورة العميل بشكل منفصل. | استمر في العمل على المهام التي بدأت بالفعل وقم بمراجعة الأساس | اعقد اجتماعًا لمجلس إدارة مراجعة المخاطر وأضف المهام التي بدأت بالفعل إلى سجل المخاطر. | أوقف العمل الذي يقع خارج بيان نطاق المشروع وأرسل طلب التغيير. | يجب على مدير المشروع إيقاف العمل الذي يقع خارج بيان نطاق المشروع وتقديم طلب تغيير للحصول على الموافقة من لجنة التحكم في التغيير CCB ، والقيام فقط بالأعمال المدرجة في بيان نطاق المشروع أو طلب التغيير المعتمد. [PMBOK الطبعة السادسة ، الصفحة 90] | 140 | 4 | False | "18" | Ahmad
156 | You are a project manager and have just assigned to the project in the execution phase. A project is in jeopardy. It is behind schedule and resources are limited. What is the first action you should take? | Hold a project team meeting. | Review the work performance report. | Ask management for additional resources. | Revise the project management plan | When a project manager assign in the execution phase, the first action should be taken is Revise (Review) the project management plan. [PMBOK 6th edition Page, 90] | أنت مدير مشروع وتم للتو تعيينك للمشروع في مرحلة التنفيذ. المشروع في خطر. إنه متأخر عن الجدول الزمني والموارد محدودة. ما هو الإجراء الأول الذي يجب أن تقوم به؟ | عقد اجتماع فريق المشروع. | مراجعة تقرير أداء العمل. | اطلب من الإدارة موارد إضافية. | مراجعة خطة إدارة المشروع | عندما يتم تعيين مدير المشروع في مرحلة التنفيذ ، الإجراء الأول الذي يجب اتخاذه هو مراجعة خطة إدارة المشروع. [PMBOK الطبعة السادسة ، الصفحة 90] | 140 | 4 | False | "19" | Ahmad
157 | You are managing the changes made to the scope baseline. The causes of variances and the corrective action chosen should be included in: | Recommended corrective action | Scope management plan | Risk Register | Lessons learned register | The lessons learned register could be updated with techniques that are efficient and effective in controlling scope, including causes of variances and corrective actions chosen. [PMBOK 6th edition, Page 171] | أنت تدير التغييرات التي تم إجراؤها على خط الأساس للنطاق. يجب تضمين أسباب الفروق والإجراء التصحيحي المختار في: | الإجراءات التصحيحية الموصى بها | خطة إدارة النطاق | سجل المخاطر | سجل الدروس المستفادة | يمكن تحديث سجل الدروس المستفادة بالتقنيات التي تتسم بالكفاءة والفعالية في التحكم في النطاق ، بما في ذلك أسباب الفروق والإجراءات التصحيحية المختارة. [PMBOK الطبعة السادسة ، الصفحة 171] | 141 | 5 | False | "19" | Ahmad
158 | A project is behind schedule and over budget. As a result of increased stakeholder pressure, the project team has been placed under serious pressure. This causes a conflict between the quality and production managers, with each blaming the other for the delay and cost overruns. What should the project manager do? | Meet with both managers, and ask them to immediately end the conflict to avoid negatively impacting the project. | Meet with the managers' supervisors to discuss possible actions. | Discuss the situation with the stakeholders, and follow their suggestions for dealing with the conflict. | Refer to the team charter for guidelines on how to deal with this conflict. | The team charter is a document that establishes the team values, agreements, and operating guidelines for the team. The team charter include Conflict( resolution process. SO the project manager should Refer to the team charter for guidelines on how to deal with this conflict. [PMBOK 6th edition Page, 319] | المشروع متأخر عن الجدول الزمني ومتجاوز ميزانيته. نتيجة لزيادة ضغط أصحاب المصلحة ، تعرض فريق المشروع لضغوط شديدة. يؤدي هذا إلى حدوث تضارب بين مديري الجودة والإنتاج ، حيث يلوم كل منهم الآخر على التأخير وتجاوز التكاليف. ماذا يجب أن يفعل مدير المشروع؟ | قابل كلا المديرين ، واطلب منهم إنهاء النزاع على الفور لتجنب التأثير سلبًا على المشروع. | قابل مشرفي المديرين لمناقشة الإجراءات الممكنة. | ناقش الموقف مع أصحاب المصلحة ، واتبع اقتراحاتهم للتعامل مع النزاع. | راجع ميثاق الفريق للحصول على إرشادات حول كيفية التعامل مع هذا التعارض. | ميثاق الفريق هو مستند يحدد قيم الفريق والاتفاقيات وإرشادات التشغيل للفريق. يتضمن ميثاق الفريق التعارض (عملية الحل. لذا يجب على مدير المشروع الرجوع إلى ميثاق الفريق للحصول على إرشادات حول كيفية التعامل مع هذا التعارض. [PMBOK الطبعة السادسة ، الصفحة 319] | 145 | 4 | False | "16" | Ahmad
159 | You are working with your team on estimating how much time each activity will take. One of the documents you are using contains information on categories of labor, material, and equipment required to complete your project. You are also interested to see skill levels of your labor, any certifications required, and grade levels your supplies. Which of the following documents would you primarily refer to for this purpose? | Risk breakdown structure | Organizational breakdown structure | Work breakdown structure | Resource breakdown structure | The project team is performing the Estimate Activity Durations process. An input to this process is the Resource Breakdown Structure (RBS) which is a hierarchical list of team and physical resources related by category and resource type that is used for planning, managing. and controlling project work. Each descending level represents an increasingly detailed description of the resource until the information is a small enough to be used in conjunction with the WBS to allow the work to be planned, monitored, and controlled. [PMBOK 6th edition, Page 198] | أنت تعمل مع فريقك لتقدير الوقت الذي سيستغرقه كل نشاط. تحتوي إحدى المستندات التي تستخدمها على معلومات حول فئات العمالة والمواد والمعدات المطلوبة لإكمال مشروعك. أنت مهتم أيضًا برؤية مستويات مهارة عمالك ، وأي شهادات مطلوبة ، ومستويات درجات الإمدادات الخاصة بك. أي من المستندات التالية قد تشير إليها بشكل أساسي لهذا الغرض؟ | هيكل تفكيك المخاطر | الهيكل التنظيمي | انهيار الهيكل العمل | هيكل توزيع الموارد | يقوم فريق المشروع بتنفيذ عملية تقدير مدد النشاط. أحد المدخلات في هذه العملية هو هيكل توزيع الموارد (RBS) وهو عبارة عن قائمة هرمية من الفريق والموارد المادية المرتبطة حسب الفئة ونوع المورد المستخدمة للتخطيط والإدارة. والتحكم في عمل المشروع. يمثل كل مستوى تنازلي وصفًا تفصيليًا متزايدًا للمورد حتى تصبح المعلومات صغيرة بما يكفي لاستخدامها مع WBS للسماح بتخطيط العمل ومراقبته والتحكم فيه. [PMBOK الطبعة السادسة ، الصفحة 198] | 142 | 3 | False | "18" | Ahmad
160 | Which of the following technique can be used to identify the key issues and suitable alternatives to be prioritized as a set of decisions for implementation? | Requirements traceability matrix | A responsibility assignment matrix (RAM) | Stakeholder engagement assessment matrix | Prioritization matrix | Prioritization matrix can be used to identify the key issues and suitable alternatives to be prioritized as a set of decisions for implementation. [PMBOK 6th edition, Page 283] | أي من الأساليب التالية يمكن استخدامه لتحديد القضايا الرئيسية والبدائل المناسبة التي يجب تحديد أولوياتها كمجموعة من القرارات للتنفيذ؟ | مصفوفة تتبع المتطلبات | مصفوفة تخصيص المسؤولية (RAM) | مصفوفة تقييم مشاركة أصحاب المصلحة | مصفوفة تحديد الأولويات | يمكن استخدام مصفوفة تحديد الأولويات لتحديد القضايا الرئيسية والبدائل المناسبة التي يجب ترتيبها حسب الأولوية كمجموعة من القرارات للتنفيذ. [PMBOK الطبعة السادسة ، الصفحة 283] | 144 | 3 | False | "19" | Ahmad
161 | A project manager is currently developing the project schedule for a mandatory regulatory project. The project manager is receiving input from different stakeholders and finds that many of them are estimating completion times that are longer than the established end date. What should the project manager do next? | Apply crashing to the project management plan in order to reduce the extension of the proposed schedule. | Remind the stakeholders about the project constraints and request a revision of their inputs. | Identify a new critical path that could guarantee the project's completion by the end date. | Notify the sponsor and request to modify the end date to accommodate the proposed schedule. | Since the stakeholders inputs will impact the established end date, the project manager should FIRST Notify the sponsor and request to modify the end date to accommodate the proposed schedule. The option (Remind the stakeholders about the project constraints and request a revision of their inputs) may be the next step if the project sponsor refuse to modify the end date. [PMBOK 6th edition, Page 205] | يقوم مدير المشروع حاليًا بتطوير جدول المشروع لمشروع تنظيمي إلزامي. يتلقى مدير المشروع مدخلات من مختلف أصحاب المصلحة ويجد أن العديد منهم يقدرون أوقات الإنجاز التي تكون أطول من تاريخ الانتهاء المحدد. ماذا يجب أن يفعل مدير المشروع بعد ذلك؟ | تطبيق حشد الموارد على خطة إدارة المشروع من أجل تقليل تمديد الجدول الزمني المقترح. | ذكر أصحاب المصلحة حول قيود المشروع واطلب مراجعة مدخلاتهم. | حدد مسارًا حرجًا جديدًا يمكن أن يضمن اكتمال المشروع بحلول تاريخ الانتهاء. | قم بإخطار الراعي واطلب تعديل تاريخ الانتهاء لملاءمة الجدول الزمني المقترح. | نظرًا لأن مدخلات أصحاب المصلحة ستؤثر على تاريخ الانتهاء المحدد ، يجب على مدير المشروع أولاً إخطار الراعي وطلب تعديل تاريخ الانتهاء لاستيعاب الجدول الزمني المقترح. قد يكون الخيار (تذكير أصحاب المصلحة بشأن قيود المشروع وطلب مراجعة مدخلاتهم) هو الخطوة التالية إذا رفض راعي المشروع تعديل تاريخ الانتهاء. [PMBOK الطبعة السادسة ، الصفحة 205] | 142 | 3 | False | "19" | Ahmad
162 | During the development of the scope management plan, a stakeholder requests the addition of pilot technology into the project scope to assist with the product marketing. What should the project manager do? | Use the project reserve for the pilot technology. | Review the scope baseline with the stakeholder. | Increase the project budget with the cost of the pilot technology. | Include the stakeholder in the scope planning meetings. | The project manager should Include the stakeholder in the scope planning meetings. Note that meeting is one of the tools and techniques in the Plan Scope Management process to develop the Scope Management Plan. [PMBOK 6th edition Page, 136] | أثناء تطوير خطة إدارة النطاق ، يطلب أحد أصحاب المصلحة إضافة تقنية تجريبية إلى نطاق المشروع للمساعدة في تسويق المنتج. ماذا يجب أن يفعل مدير المشروع؟ | استخدم احتياطي المشروع للتكنولوجيا التجريبية. | راجع خط الأساس للنطاق مع أصحاب المصلحة. | زيادة ميزانية المشروع بتكلفة التكنولوجيا التجريبية. | تضمين صاحب المصلحة في اجتماعات تخطيط النطاق. | يجب على مدير المشروع تضمين أصحاب المصلحة في اجتماعات تخطيط النطاق. لاحظ أن الاجتماع هو أحد الأدوات والتقنيات في عملية إدارة نطاق الخطة لتطوير خطة إدارة النطاق. [PMBOK الطبعة السادسة ، الصفحة 136] | 141 | 3 | False | "20" | Ahmad
163 | You are the project manager of a Construction project. The project sponsor has information about the project which is behind schedule and over budget, but he wants more details about the progress of the project. As a project manager, what should you provide to the project sponsor about the status of the project? | Work performance information | Work performance data | Earned value report | Work performance report | Sponsor know that the project are behind schedule and over budget, so he knows Earned Value report, in this case the project manager should provide the sponsor with (Work performance report) because it includes status reports and progress reports. [PMBOK 6th edition, Page 382] | أنت مدير مشروع بناء. لدى راعي المشروع معلومات حول المشروع المتأخر عن الجدول الزمني والمتخطي الميزانية ، لكنه يريد مزيدًا من التفاصيل حول تقدم المشروع. بصفتك مدير مشروع ، ما الذي يجب أن تقدمه لراعي المشروع حول حالة المشروع؟ | معلومات أداء العمل | بيانات أداء العمل | تقرير القيمة المكتسبة | تقرير أداء العمل | يعرف الراعي أن المشروع متأخر عن الجدول الزمني ومتخطي ميزانيته ، لذلك فهو يعرف تقرير القيمة المكتسبة ، وفي هذه الحالة يجب على مدير المشروع تزويد الراعي بـ (تقرير أداء العمل) لأنه يتضمن تقارير الحالة وتقارير التقدم. [PMBOK الطبعة السادسة ، الصفحة 382] | 146 | 4 | False | "20" | Ahmad
164 | A project's primary focus is on schedule. To monitor this, the project manager requests monthly progress reports from the contractor. What should the project manager ask the contractor to include in these reports? | Schedule attributes. | Work breakdown structure (WBS) | Network chart. | Gantt chart. | The project manager should ask the contractor to include Gantt charts or also known as Bar charts in these reports because its represent schedule information where activities are listed on the vertical axis, dates are shown on the horizontal axis, and activity durations are shown as horizontal bars placed according to start and finish dates. Gantt or Bar charts are relatively easy to read and are commonly used. [PMBOK 6th edition Page, 217] | ينصب التركيز الأساسي للمشروع على الجدول الزمني. لمراقبة ذلك ، يطلب مدير المشروع تقارير مرحلية شهرية من المقاول. ما الذي يجب أن يطلب مدير المشروع من المقاول تضمينه في هذه التقارير؟ | سمات الجدول. | هيكل تنظيم العمل (WBS) | مخطط الشبكة. | مخطط جانت. | يجب أن يطلب مدير المشروع من المقاول تضمين مخططات جانت أو المعروف أيضًا باسم المخططات الشريطية في هذه التقارير لأنها تمثل معلومات الجدول الزمني حيث يتم سرد الأنشطة على المحور الرأسي ، وتظهر التواريخ على المحور الأفقي ، ويتم عرض فترات النشاط كأشرطة أفقية يتم وضعها وفقًا لتواريخ البدء والانتهاء. من السهل نسبيًا قراءة المخططات الشريطية أو مخططات جانت وشائعة الاستخدام. [PMBOK الطبعة السادسة ، الصفحة 217] | 142 | 5 | False | "20" | Ahmad
165 | During the planning stage of a project, a company goes under an organizational structure change. The project manager believes most of the stakeholders have changed. Which tool or technique should the project manager uses to verify whether the stakeholders have changed? | Mind mapping. | Decision-making matrix. | Fishbone diagram. | Questionnaires and surveys. | Questionnaires and surveys are a Data-gathering techniques that written sets of questions designed to quickly accumulate information from a large number of respondents. Questionnaires and/or surveys are most appropriate with varied audiences, when a quick turnaround is needed, when respondents are geographically dispersed, and where statistical analysis could be appropriate.S0 the project manager should uses Questionnaires and surveys to verify whether the stakeholders have changed. [PMBOK 6th edition Page, 507] | خلال مرحلة التخطيط للمشروع ، تخضع الشركة لتغيير الهيكل التنظيمي. يعتقد مدير المشروع أن معظم أصحاب المصلحة قد تغيروا. ما الأداة أو التقنية التي يجب أن يستخدمها مدير المشروع للتحقق مما إذا كان أصحاب المصلحة قد تغيروا؟ | خريطة ذهنية. | مصفوفة اتخاذ القرار. | مخطط هيكل السمكة. | الاستبيانات والمسوحات. | الاستبيانات والمسوحات هي تقنيات لجمع البيانات تكتب مجموعات من الأسئلة المصممة لتجميع المعلومات بسرعة من عدد كبير من المستجيبين. الاستبيانات و / أو الاستطلاعات هي الأنسب مع الجماهير المتنوعة ، عندما تكون هناك حاجة إلى تحول سريع ، وعندما يكون المستجيبون مشتتين جغرافيًا ، وحيث يمكن أن يكون التحليل الإحصائي مناسبًا .0 يجب على مدير المشروع استخدام الاستبيانات والمسوحات للتحقق مما إذا كان أصحاب المصلحة قد تغيروا. [PMBOK الطبعة السادسة ، الصفحة 507] | 149 | 2 | False | "16" | Ahmad
166 | A project manager for a large, ongoing project is under a tight deadline to finish each of the project's three phases. The executives have decided to increase the budget and time to ensure their standards are met. The project manager has updated the schedule to reflect the increases. What should the project manager do next? | Update the success criteria in the scope management plan. | Review the requirements in the quality management plan. | Add the tasks mentioned to the schedule management plan. | Communicate the updated schedule to the stakeholder. | The project manager has updated the schedule to reflect the new changes. The next step is communicate the updated schedule to the stakeholders. This is one of the change request steps. [PMBOK 6th edition Page, 90] | مدير مشروع لمشروع كبير ومستمر يخضع لموعد نهائي ضيق لإنهاء كل مرحلة من مراحل المشروع الثلاث. قرر المسؤولون التنفيذيون زيادة الميزانية والوقت لضمان تلبية معاييرهم. قام مدير المشروع بتحديث الجدول الزمني ليعكس الزيادات. ماذا يجب أن يفعل مدير المشروع بعد ذلك؟ | تحديث معايير النجاح في خطة إدارة النطاق. | مراجعة المتطلبات في خطة إدارة الجودة. | أضف المهام المذكورة إلى خطة إدارة الجدول الزمني. | إبلاغ الجدول الزمني المحدث إلى أصحاب المصلحة. | قام مدير المشروع بتحديث الجدول الزمني ليعكس التغييرات الجديدة. الخطوة التالية هي توصيل الجدول المحدث لأصحاب المصلحة. هذه إحدى خطوات طلب التغيير. [PMBOK الطبعة السادسة ، الصفحة 90] | 140 | 4 | False | "20" | Ahmad
167 | A stakeholder informs the project manager that they don't receive the weekly project status reports, even though they participated in the project kick-off meeting. What should the project manager do? | Forward the latest report to this stakeholder. | Adjust the stakeholder register to include this stakeholder | Escalate this issue to the project sponsor. | Review the communication management plan. | Since the stakeholder didn't receive the reports, the project manager should review the communication management plan because its contain the person or groups will receive the information, stakeholder communication requirements, reason for the distribution of that information, time-frame, and frequency for the distribution of required information. [PMBOK 6th edition Page, 377] | يقوم أحد أصحاب المصلحة بإبلاغ مدير المشروع بأنهم لا يتلقون تقارير حالة المشروع الأسبوعية ، على الرغم من مشاركتهم في اجتماع بدء المشروع. ماذا يجب أن يفعل مدير المشروع؟ | أرسل أحدث تقرير إلى صاحب المصلحة هذا. | تعديل سجل أصحاب المصلحة ليشمل هذا أصحاب المصلحة | تصعيد هذه المشكلة إلى راعي المشروع. | مراجعة خطة إدارة الاتصالات. | نظرًا لأن أصحاب المصلحة لم يتلقوا التقارير ، يجب على مدير المشروع مراجعة خطة إدارة الاتصالات لأنها تحتوي على الشخص أو المجموعات التي ستتلقى المعلومات ومتطلبات التواصل مع أصحاب المصلحة وسبب توزيع تلك المعلومات والإطار الزمني وتكرارها. توزيع المعلومات المطلوبة. [PMBOK الطبعة السادسة ، الصفحة377] | 146 | 4 | False | "19" | Ahmad
168 | A project manager has completed his project on time and within budget. An unexpected complaint from a customer regarding the project's scope raised. It turns out that the customer wanted a much simpler solution. What should the project manager have done differently? | Defined project scope with the customer. | Controlled scope with the help of the project team. | Validated project scope with stakeholders. | Collect requirements with the customer. | Since the project manager has almost completed a project, and the customer wanted a much simpler solution. This means that the project manager did not engage the customer as required and compiled all of his requirements. [PMBOK 6th edition Page, 138] | أكمل مدير المشروع مشروعه في الوقت المحدد وفي حدود الميزانية. تم رفع شكوى غير متوقعة من أحد العملاء بخصوص نطاق المشروع. اتضح أن العميل أراد حلاً أبسط بكثير. ما الذي كان يجب أن يفعله مدير المشروع بشكل مختلف؟ | نطاق المشروع المحدد مع العميل. | النطاق المتحكم فيه بمساعدة فريق المشروع. | التحقق من نطاق المشروع مع أصحاب المصلحة. | جمع المتطلبات مع العميل. | نظرًا لأن مدير المشروع قد أكمل تقريبًا مشروعًا ، وأراد العميل حلاً أبسط بكثير. هذا يعني أن مدير المشروع لم يشرك العميل كما هو مطلوب وقام بتجميع جميع متطلباته. [PMBOK الطبعة السادسة ، الصفحة 138] | 141 | 3 | False | "16" | Ahmad
169 | A pilot project is ready to close and the project team wants to capture the challenges that were overcome and the opportunities for future work. Where will they document this information? | Organizational process Assets updates. | Project management plan | Work performance reports. | Lessons learned register. | The lessons learned in the phase or project should be finalized before being entered into the lessons learned repository. The challenges that were overcome and the opportunities for future work should be documented in the lessons learned register before being entered into the lessons learned repository as a part of Organizational Process Assets updates. [PMBOK 6th edition Page, 128] | مشروع تجريبي جاهز للإغلاق ويريد فريق المشروع التقاط التحديات التي تم التغلب عليها وفرص العمل في المستقبل. أين سيوثقون هذه المعلومات؟ | تحديثات أصول العملية التنظيمية. | خطة إدارة المشروع | تقارير أداء العمل. | سجل الدروس المستفادة. | يجب الانتهاء من الدروس المستفادة في المرحلة أو المشروع قبل إدخالها في مستودع الدروس المستفادة. يجب توثيق التحديات التي تم التغلب عليها وفرص العمل المستقبلي في سجل الدروس المستفادة قبل إدخالها في مستودع الدروس المستفادة كجزء من تحديثات أصول العمليات التنظيمية. [PMBOK الطبعة السادسة ، الصفحة 128] | 140 | 6 | False | "18" | Ahmad
170 | While browsing a local archive, a new project manager finds the previous project's lessons learned notes. They observe that the notes have not yet been stored in the project management information system PMIS. What should the project manager do with the notes? | As the notes are already available, no further action is required. | Store a local copy on their hard drive for future use. | Disregard the notes since they are not in the PMIS. | Ask the previous project manager to archive the notes in the PMIS. | Since the previous project's lessons learned notes not yet been stored in the project management information system (PMIS). The project manager should ask the previous project manager to archive the notes in the PMIS. The option (As the notes are already available, no further action is required) not correct because this notes related to the previous project and should be archived. [PMBOK 6th edition Page, 128] | أثناء تصفح أرشيف محلي ، يجد مدير مشروع جديد ملاحظات الدروس المستفادة للمشروع السابق. لاحظوا أن الملاحظات لم يتم تخزينها بعد في نظام معلومات إدارة المشروع PMIS. ماذا يجب أن يفعل مدير المشروع بالملاحظات؟ | نظرًا لأن الملاحظات متوفرة بالفعل ، فلا يلزم اتخاذ أي إجراء آخر. | قم بتخزين نسخة محلية على محرك الأقراص الثابتة لاستخدامها في المستقبل. | تجاهل الملاحظات لأنها ليست في PMIS. | اطلب من مدير المشروع السابق أرشفة الملاحظات في PMIS. | منذ الدروس المستفادة من المشروع السابق ، لم يتم تخزين الملاحظات في نظام معلومات إدارة المشروع (PMIS). يجب أن يطلب مدير المشروع من مدير المشروع السابق أرشفة الملاحظات في PMIS. الخيار (نظرًا لأن الملاحظات متوفرة بالفعل ، لا يلزم اتخاذ أي إجراء آخر) غير صحيح لأن هذه الملاحظات تتعلق بالمشروع السابق ويجب أرشفتها. [PMBOK الطبعة السادسة ، الصفحة 128] | 140 | 6 | False | "19" | Ahmad
171 | A project manager has been hired to develop a product for a multinational company. While writing the key deliverables for the project charter, the project manager has two technology options and is unsure of which to use. One is safer and the other is cheaper. What should the project manager do to determine the key deliverables for the project? | Establish requirements with the project sponsor. | Use the cheaper technology in order to maintain the budget. | Choose the best option based on the project manager's experience. | Meet with the client to understand their technological requirements. | Refer to PMP exam content outline in Initiating (Task 02). Project Manager have to Identify key deliverables based on the business requirements in order to manage customer expectations and direct the achievement of project goals. So, the correct answer Is to meet with the client to understand their technological requirements. [PMBOK 6th edition Page, 80] | تم تعيين مدير مشروع لتطوير منتج لشركة متعددة الجنسيات. أثناء كتابة التسليمات الرئيسية لميثاق المشروع ، يكون لدى مدير المشروع خياران تقنيان وهو غير متأكد من أيهما يستخدم. أحدهما أكثر أمانًا والآخر أرخص. ما الذي يجب على مدير المشروع فعله لتحديد النواتج الرئيسية للمشروع؟ | تحديد المتطلبات مع راعي المشروع. | استخدم التكنولوجيا الأرخص من أجل الحفاظ على الميزانية. | اختر الخيار الأفضل بناءً على خبرة مدير المشروع. | مقابلة العميل لفهم متطلباته التكنولوجية. | راجع مخطط محتوى اختبار PMP في البدء (المهمة 02). يتعين على مدير المشروع تحديد المخرجات الرئيسية بناءً على متطلبات العمل من أجل إدارة توقعات العملاء وتوجيه تحقيق أهداف المشروع. لذا ، فإن الإجابة الصحيحة هي مقابلة العميل لفهم متطلباته التكنولوجية. [PMBOK الطبعة السادسة ، الصفحة 80] | 140 | 2 | False | "18" | Ahmad
172 | A recently appointed project manager is in constant conflict with a senior manager. Since this is not ideal for the team, the project manager wants to resolve this. What should the project manager do? | Escalate the issue to the project sponsor. | Seek guidance from the other project managers. | Enlist the help of a neutral mediator. | Request a scheduled face-to-face meetings with the senior manager. | The project manager should request scheduled face-to-face meetings with the senior manager. This is an example of problem solving technique (The best Conflict Resolutions technique). [PMBOK 6th edition Page, 356] | مدير مشروع تم تعيينه مؤخرًا في نزاع دائم مع مدير أقدم. نظرًا لأن هذا ليس مثاليًا للفريق ، فإن مدير المشروع يريد حل هذا الأمر. ماذا يجب أن يفعل مدير المشروع؟ | تصعيد المشكلة إلى راعي المشروع. | اطلب التوجيه من مديري المشروع الآخرين. | استعن بمساعدة وسيط محايد. | طلب اجتماعات مجدولة وجهًا لوجه مع المدير الأقدم. | يجب أن يطلب مدير المشروع اجتماعات مجدولة وجهًا لوجه مع المدير الأقدم. هذا مثال على تقنية حل المشكلات (أفضل تقنية لحل النزاعات). [PMBOK الطبعة السادسة ، الصفحة 356] | 145 | 5 | False | "18" | Ahmad
173 | During project execution, it is noticed that the actual expenditure is too high compared to baseline cost estimates. What should the project manager do next? | Revisit project scope and cut high-cost items. | Review historical data to get new cost estimates. | Review assumption log to understand which cost assumptions were wrong. | Update cost forecasts and discuss the options with the project sponsor. | Because the actual expenditure is too high compared to baseline cost estimates, the project manager should update cost forecasts and discuss the options with the project sponsor. [PMBOK 6th edition Page, 269] | أثناء تنفيذ المشروع ، يُلاحظ أن النفقات الفعلية مرتفعة للغاية مقارنة بتقديرات التكلفة الأساسية. ماذا يجب أن يفعل مدير المشروع بعد ذلك؟ | قم بإعادة النظر في نطاق المشروع وخفض العناصر عالية التكلفة. | راجع البيانات التاريخية للحصول على تقديرات التكلفة الجديدة. | راجع سجل الافتراضات لفهم افتراضات التكلفة التي كانت خاطئة. | تحديث توقعات التكلفة و مناقشة الخيارات مع راعي المشروع. | نظرًا لأن النفقات الفعلية مرتفعة جدًا مقارنة بتقديرات التكلفة الأساسية ، يجب على مدير المشروع تحديث توقعات التكلفة ومناقشة الخيارات مع راعي المشروع. [PMBOK الطبعة السادسة ، الصفحة 269] | 143 | 5 | False | "17" | Ahmad
174 | A project earned value = SAR 40,000 , Actual Cost = SAR 50,000 , and BAC = SAR 200,000. What is the Estimate To Complete (ETC) for the project if the work is performed at the budgeted rate? | SAR 200,000 | SAR 210 | SAR 250,000 | SAR 160,000 | The Formula used for EAC is EAC = AC + BAC - EV = 50,000 + 200,000 - 40,000 = SAR 210,000 ETC = EAC - AC = 210,000 - 50,000 = SAR 160,000 [PMBOK 6th edition, Page 267] | القيمة المكتسبة للمشروع = 40.000 ريال سعودي ، التكلفة الفعلية = 50.000 ريال سعودي ، و BAC = 200.000 ريال سعودي. ما هو تقدير الاكتمال (ETC) للمشروع إذا تم تنفيذ العمل بالمعدل المدرج في الميزانية؟ | 200،000 ريال سعودي | 210 ريال سعودي | 250،000 ريال سعودي | 160،000 ريال سعودي | الصيغة المستخدمة في EAC هي EAC = AC + BAC - EV = 50،000 + 200،000 - 40،000 = SAR 210،000 ETC = EAC - AC = 210،000 - 50،000 = 160،000 ريال سعودي [PMBOK الإصدار السادس ، صفحة 267] | 143 | 5 | False | "19" | Ahmad
175 | A project manager wants to ensure sufficient stakeholder participation throughout a project's life cycle. What should the project manager include in the stakeholder engagement plan? | Feedback from stakeholders on project operations. | Change requests initiated by stakeholders. | Stakeholder power/interest grid. | Desired and current stakeholder engagement levels. | A stakeholder engagement assessment matrix supports comparison between the current engagement levels of stakeholders and the desired engagement levels required for successful project delivery. To ensure sufficient stakeholder participation throughout a project's life cycle, the project manager should include the desired and current stakeholder engagement levels in the stakeholder engagement plan. [PMBOK 6th edition Page,521] | يريد مدير المشروع ضمان مشاركة كافية من أصحاب المصلحة طوال دورة حياة المشروع. ما الذي يجب أن يدرجه مدير المشروع في خطة إشراك أصحاب المصلحة؟ | ردود الفعل من أصحاب المصلحة على عمليات المشروع. | طلبات التغيير التي بدأها أصحاب المصلحة. | سلطة أصحاب المصلحة / شبكة المصالح. | مستويات مشاركة أصحاب المصلحة المرغوبة والحالية. | تدعم مصفوفة تقييم مشاركة أصحاب المصلحة المقارنة بين مستويات المشاركة الحالية لأصحاب المصلحة ومستويات المشاركة المطلوبة لإنجاز المشروع بنجاح. لضمان مشاركة كافية لأصحاب المصلحة طوال دورة حياة المشروع ، يجب على مدير المشروع تضمين المستويات المرغوبة والحالية لإشراك أصحاب المصلحة في خطة إشراك أصحاب المصلحة. [PMBOK الطبعة السادسة ، الصفحة 521] | 149 | 3 | False | "19" | Ahmad
176 | A project manager joins a new project for an organization that does not have a lessons learned repository. How should the project manager establish the project baselines? | Identify and map the benefits and outcomes of the project. | Ask stakeholders to provide their recommendations for the project. | Develop a business case to document project objectives. | Perform a data gathering analysis and review the organizational process assets | Since he is a new project manager, he should perform a data gathering analysis and review the organizational process assets to establish the project baseline. [PMBOK 6th edition Page, 82] | ينضم مدير المشروع إلى مشروع جديد لمؤسسة ليس لديها مستودع للدروس المستفادة. كيف يجب على مدير المشروع إنشاء خطوط الأساس للمشروع؟ | تحديد ورسم خرائط فوائد ونتائج المشروع. | اطلب من أصحاب المصلحة تقديم توصياتهم للمشروع. | تطوير دراسة جدوى لتوثيق أهداف المشروع. | إجراء تحليل لجمع البيانات ومراجعة أصول العملية التنظيمية | نظرًا لأنه مدير مشروع جديد ، يجب عليه إجراء تحليل لجمع البيانات ومراجعة أصول العملية التنظيمية لإنشاء خط الأساس للمشروع. [PMBOK الطبعة السادسة ، الصفحة 82] | 140 | 3 | False | "19" | Ahmad
177 | During an audit, it was noted that only 20 percent of completed projects had documented lessons learned. What should the project manager have updated to document this? | Quality process Assets. | Stakeholder responsibility matrix. | Change control documentation. | Organizational process assets | The lessons learned is updated in the Organizational process Assets . [PMBOK 6th edition Page, 39] | أثناء المراجعة ، لوحظ أن 20 في المائة فقط من المشاريع المكتملة قد وثقت الدروس المستفادة. ما الذي يجب على مدير المشروع تحديثه لتوثيق ذلك؟ | أصول عملية الجودة. | مصفوفة مسؤولية أصحاب المصلحة. | تغيير وثائق التحكم. | أصول العملية التنظيمية | يتم تحديث الدروس المستفادة في أصول العملية التنظيمية. [PMBOK الطبعة السادسة ، الصفحة 39] | 144 | 4 | False | "20" | Ahmad
178 | During a group activity to identify an input to the plan procurement management process, some participants disagree with the ranking of compliance-related items. What tool or technique should the project manager use to resolve this? | Brainstorming. | Affinity diagram multi-criteria | Decision analysis. | Nominal group technique. | Since some participants disagree with the ranking. Requirements documentation is an input of the plan procurement management process. One of the tools in the collect requirement process is Nominal Group Technique. This technique enhances brainstorming with a voting process used to rank the most useful ideas for further brainstorming or for prioritization. [PMBOK 6th edition page, 144] | أثناء نشاط جماعي لتحديد مدخلات في عملية إدارة مشتريات الخطة ، يختلف بعض المشاركين مع ترتيب العناصر المتعلقة بالامتثال. ما الأداة أو التقنية التي يجب أن يستخدمها مدير المشروع لحل هذه المشكلة؟ | العصف الذهني. | مخطط تقارب متعدد المعايير | تحليل القرار. | تقنية المجموعة الاسمية. | لأن بعض المشاركين يختلفون مع الترتيب. توثيق المتطلبات هو أحد مدخلات عملية إدارة المشتريات في الخطة. إحدى الأدوات في عملية جمع المتطلبات هي تقنية المجموعة الاسمية. تعزز هذه التقنية عملية العصف الذهني من خلال عملية التصويت المستخدمة لتصنيف الأفكار الأكثر فائدة لمزيد من العصف الذهني أو لتحديد الأولويات. [صفحة الإصدار السادس من PMBOK ، 144] | 141 | 3 | False | "19" | Ahmad
179 | A project manager has just completed the project management plan for a construction project. This is a high-visibility project for many stakeholders across multiple functional departments and level of understanding. What can the project manager do to ensure approval of the project management plan? | Develop a stakeholder register and then select the most important stakeholder to obtain their approval. | Ask the project sponsor to approve the project management plan as a first step, then communicate this to other stakeholders to help approve the project . | Conduct interviews with each stakeholders separately in order to obtain approval of the project management plan individually. | Organize a meeting for stakeholders and provide the appropriate information to obtain their approval. | Refer to PMP exam content outline in the planning (Task no. 11). Present the project management plan to the relevant stakeholders according to applicable policies and procedures in order to obtain approval to proceed with project execution. So the correct answer is: Organize a meeting for stakeholders and provide the appropriate information to obtain their approval. [PMBOK 6th edition page, 86] | أكمل مدير المشروع للتو خطة إدارة المشروع لمشروع البناء. هذا مشروع عالي الوضوح للعديد من أصحاب المصلحة عبر إدارات وظيفية متعددة ومستوى من الفهم. ما الذي يمكن أن يفعله مدير المشروع لضمان الموافقة على خطة إدارة المشروع؟ | قم بتطوير سجل لأصحاب المصلحة ثم حدد أصحاب المصلحة الأكثر أهمية للحصول على موافقتهم. | اطلب من راعي المشروع الموافقة على خطة إدارة المشروع كخطوة أولى ، ثم إبلاغ أصحاب المصلحة الآخرين بذلك للمساعدة في الموافقة على المشروع. | قم بإجراء مقابلات مع كل أصحاب المصلحة بشكل منفصل من أجل الحصول على الموافقة على خطة إدارة المشروع بشكل فردي. | تنظيم اجتماع لأصحاب المصلحة وتقديم المعلومات المناسبة للحصول على موافقتهم. | راجع مخطط محتوى اختبار PMP في التخطيط (المهمة رقم 11). قدم خطة إدارة المشروع لأصحاب المصلحة المعنيين وفقًا للسياسات والإجراءات المعمول بها من أجل الحصول على الموافقة للمضي قدمًا في تنفيذ المشروع. لذا فإن الإجابة الصحيحة هي: تنظيم اجتماع لأصحاب المصلحة وتقديم المعلومات المناسبة للحصول على موافقتهم. [PMBOK الطبعة السادسة ، الصفحة 86] | 140 | 5 | False | "20" | Ahmad
180 | During project execution, a high-performing team member leaves. Following this loss, a planned quality audit is conducted that indicates the work product's quality standards are unmet. What should the project manager do next? | Perform a reserve analysis of the work performance. | Crash the schedule. | Consult the resource management plan. | Create a cause and effect diagram. | The issue is not only related to the leaving of the team member. Since the work product's quality standards are unmet, the project manager should first create a cause and effect diagram to identify the root cause of the problem. [PMBOK 6th edition page, 288] | أثناء تنفيذ المشروع ، يغادر أحد أعضاء الفريق عالي الأداء. بعد هذه الخسارة ، يتم إجراء تدقيق جودة مخطط يشير إلى عدم تلبية معايير جودة منتج العمل. ماذا يجب أن يفعل مدير المشروع بعد ذلك؟ | قم بإجراء تحليل احتياطي لأداء العمل. | حشد الموارد للجدول. | استشر خطة إدارة الموارد. | إنشاء مخطط السبب والنتيجة. | المشكلة لا تتعلق فقط بمغادرة عضو الفريق. نظرًا لعدم تلبية معايير جودة منتج العمل ، يجب على مدير المشروع أولاً إنشاء مخطط السبب والنتيجة لتحديد السبب الجذري للمشكلة. [PMBOK الطبعة السادسة ، الصفحة 288] | 144 | 4 | False | "18" | Ahmad
181 | A project manager joins a global project that will be supported by virtual teams in different time zones. How should the project manager share information in this situation? | Review the responsibility assignments matrix (RAM) to understand the virtual teams' roles | Use the resource breakdown structure (RBS) to set up the virtual teams. | Communicate the work breakdown structure(WBS) to the virtual team members. | Employ project communication and technical tools to adapt to the virtual teams. | The Project manager will share Information by employ project communication and technical tools to adapt to the virtual teams. The other options are not useful in this situation. [PMBOK 6th edition page, 379] | ينضم مدير المشروع إلى مشروع عالمي تدعمه فرق افتراضية في مناطق زمنية مختلفة. كيف يجب على مدير المشروع مشاركة المعلومات في هذه الحالة؟ | راجع مصفوفة تعيينات المسؤولية (RAM) لفهم أدوار الفرق الافتراضية | استخدم هيكل توزيع الموارد (RBS) لإعداد الفرق الافتراضية. | قم بتوصيل هيكل تقسيم العمل (WBS) لأعضاء الفريق الظاهري. | توظيف اتصالات المشروع والأدوات الفنية للتكيف مع الفرق الافتراضية. | سيتبادل مدير المشروع المعلومات عن طريق استخدام اتصالات المشروع والأدوات الفنية للتكيف مع الفرق الافتراضية. الخيارات الأخرى ليست مفيدة في هذه الحالة. [PMBOK الطبعة السادسة ، الصفحة 379] | 146 | 4 | False | "20" | Ahmad
182 | A functional manager for the organization is also the direct supervisor for one of the team members on a current project. The functional manager requests that the project manager provide a weekly summary of the team member's work performance. The functional manager and the project manager are not in the same geographical area. What should the project manager do? | Make a phone call at the end of the week to quickly debrief the functional manager on the tasks performed. | Hold a weekly meeting with the functional manager to review the tasks performed. | Deny the functional manager's request and escalate the situation to the steering committee. | Draft a weekly email to the functional manager with a short list of the tasks performed. | Since the functional manager and the project manager are not in the same geographical area, and the functional manager requests a weekly summary of the team member's work performance from PM. Therefore, FM not requested a phone call or a weekly meeting, and it's not good practice to deny the functional manager's request and escalate the situation to the steering committee. So the project manager should draft a weekly email to the functional manager with a short list of the tasks performed. [PMBOK 6th edition page, 379] | المدير الوظيفي للمؤسسة هو أيضًا المشرف المباشر على أحد أعضاء الفريق في المشروع الحالي. يطلب المدير الوظيفي من مدير المشروع تقديم ملخص أسبوعي لأداء عمل عضو الفريق. المدير الوظيفي ومدير المشروع ليسا في نفس المنطقة الجغرافية. ماذا يجب أن يفعل مدير المشروع؟ | قم بإجراء مكالمة هاتفية في نهاية الأسبوع لاستخلاص المعلومات بسرعة من المدير الوظيفي عن المهام التي تم أداؤها. | عقد اجتماع أسبوعي مع المدير الوظيفي لمراجعة المهام التي يتم تنفيذها. | رفض طلب المدير الوظيفي وتصعيد الموقف للجنة التوجيهية. | قم بصياغة بريد إلكتروني أسبوعي للمدير الوظيفي مع قائمة مختصرة بالمهام التي تم تنفيذها. | نظرًا لأن المدير الوظيفي ومدير المشروع ليسا في نفس المنطقة الجغرافية ، ويطلب المدير الوظيفي ملخصًا أسبوعيًا لأداء عمل عضو الفريق من مدير المشروع. لذلك ، لم يطلب المدير الوظيفي إجراء مكالمة هاتفية أو اجتماعًا أسبوعيًا ، وليس من الممارسات الجيدة رفض طلب المدير الوظيفي وتصعيد الموقف إلى اللجنة التوجيهية. لذلك يجب على مدير المشروع صياغة رسالة بريد إلكتروني أسبوعية للمدير الوظيفي مع قائمة مختصرة بالمهام التي تم تنفيذها. [PMBOK الطبعة السادسة ، الصفحة 379] | 146 | 4 | False | "19" | Ahmad
183 | You are a project manager in an construction project. You and your team planned, identified, analyzed risks and planned risk responses for your project. During the implementation phase, an unidentified risk occurs. How will you fund to face this risk? | Cost baseline | Contingency Reserve | Risk Mitigation | Management Reserve | Management Reserve used to fund unidentified risks when occurs, management reserves are intended to address the unknown-unknowns that can affect a project. While Contingency reserve used to fund identified risks when occurs. [PMBOK 6th edition, Page 449] | أنت مدير مشروع في مشروع بناء. قمت أنت وفريقك بتخطيط وتحديد وتحليل المخاطر والاستجابات المخططة للمخاطر لمشروعك. خلال مرحلة التنفيذ ، تحدث مخاطر غير محددة. كيف ستمول لمواجهة هذا الخطر؟ | خط الأساس للتكلفة | احتياطي الطوارئ | تخفيف المخاطر | احتياطي الإدارة | يستخدم احتياطي الإدارة لتمويل المخاطر غير المحددة عند حدوثها ، وتهدف احتياطيات الإدارة إلى معالجة المجهول غير المعروف الذي يمكن أن يؤثر على المشروع. بينما يستخدم احتياطي الطوارئ لتمويل المخاطر المحددة عند حدوثها. [الطبعة السادسة من PMBOK ، صفحة 449] | 147 | 4 | False | "17" | Ahmad
184 | A project manager is meeting with the steering committee to obtain approval to deploy a develop software solution. After ten minutes of explaining why the solution is ready for deployment, the project manager is told to better prepare and return with more facts. What should the project manager do to improve their approach? | Email the steering committee explaining why the solution is ready for deployment. | Ask the sponsor to directly obtain approval from the steering committee. | Ask the project administrator to explain that user acceptance testing was completed then present this to the steering committee. | Review the communication management plan and present that all deliverables have been developed and are ready for deployment. | Review the communication management plan and present that all deliverables have been developed and are ready for deployment. [PMBOK 6th edition page, 379] | يجتمع مدير المشروع مع اللجنة التوجيهية للحصول على موافقة لنشر حل برمجي للتطوير. بعد عشر دقائق من شرح سبب جاهزية الحل للنشر ، يُطلب من مدير المشروع الاستعداد والعودة بمزيد من الحقائق. ما الذي يجب على مدير المشروع فعله لتحسين نهجهم؟ | أرسل بريدًا إلكترونيًا إلى اللجنة التوجيهية لتوضيح سبب جاهزية الحل للنشر. | اطلب من الراعي الحصول على موافقة مباشرة من اللجنة التوجيهية. | اطلب من مدير المشروع أن يوضح أن اختبار قبول المستخدم قد اكتمل ثم قدم ذلك إلى اللجنة التوجيهية. | راجع خطة إدارة الاتصالات واعرض أن جميع المخرجات قد تم تطويرها وجاهزة للنشر. | راجع خطة إدارة الاتصالات واعرض أن جميع المخرجات قد تم تطويرها وجاهزة للنشر. [PMBOK الطبعة السادسة ، الصفحة 379] | 146 | 4 | False | "20" | Ahmad
185 | A project manager is managing a project to build a telecommunications tower. The project requires a crane, but the crane previously booked for this project receives a last-minute reassignment to a higher-priority government project. What should the project manager do first? | Review the service agreement with the vendor. | Prepare resolution for the situation. | Escalate the solution to stakeholders. | Add this to the issue log. | The first action to do by project manager is to add this issue to the issue log. Then prepare resolution for the situation. Hint: If the question ask "what is the best course of action", then the best answer is prepare resolution for the situation. [PMBOK 6th edition page, 358] | مدير مشروع يدير مشروعًا لبناء برج اتصالات. يتطلب المشروع رافعة ، لكن الرافعة التي تم حجزها مسبقًا لهذا المشروع تتلقى إعادة تعيين في اللحظة الأخيرة إلى مشروع حكومي ذي أولوية أعلى. ما الذي يجب أن يفعله مدير المشروع أولاً؟ | راجع اتفاقية الخدمة مع البائع. | استعد لحل الموقف. | تصعيد الحل لأصحاب المصلحة. | أضف هذا إلى سجل الأحداث. | أول إجراء يقوم به مدير المشروع هو إضافة هذه المشكلة إلى سجل الأحداث. ثم إعداد حل للموقف. تلميح: إذا طرح السؤال "ما هو أفضل مسار للعمل" ، فإن أفضل إجابة هي إعداد حل للموقف. [ الإصدار السادس من صفحة PMBOK ، 358] | 145 | 5 | False | "19" | Ahmad
186 | During a project status meeting, a team member informs the project manager of an unexpected increase in the price of an essential component required to complete the deliverable. What should the project manager do? | Include the increased price in the project budget. | Refer to the procurement management plan. | Update the risk management plan to adapt to the new scenario. | Analyze the impact of the price increase on the project. | Analyze the impact of the price Increase on the project. [PMBOK 6th edition page, 257] | أثناء اجتماع حالة المشروع ، يقوم أحد أعضاء الفريق بإبلاغ مدير المشروع بزيادة غير متوقعة في سعر أحد المكونات الأساسية المطلوبة لإكمال التسليم. ماذا يجب أن يفعل مدير المشروع؟ | قم بتضمين السعر المتزايد في ميزانية المشروع. | الرجوع إلى خطة إدارة المشتريات. | قم بتحديث خطة إدارة المخاطر للتكيف مع السيناريو الجديد. | تحليل تأثير ارتفاع الأسعار على المشروع. | تحليل تأثير زيادة الأسعار على المشروع. [ الإصدار السادس من صفحةPMBOK ، 257] | 143 | 5 | False | "20" | Ahmad
187 | While controlling project work, the team discovers that the schedule performance index (SPI) is 0.8 and the cost performance index (CPI) is 0.95 . If the schedule for this project is a priority and no additional resources are available, what should the project manager do? | Use resource smoothing. | Use crashing. | Use resource levelling. | Use fast tracking. | Since (The schedule is a priority & No additional resources are available & The schedule performance index (SPI) is .8 & the cost performance index (CPI) is .95). This mean that the project is behind schedule and over budget. So the project manager should use fast tracking as there is no additional resources are available to use crashing. [PMBOK 6th edition page, 215] | أثناء التحكم في عمل المشروع ، اكتشف الفريق أن مؤشر أداء الجدول (SPI) يبلغ 0.8 وأن مؤشر أداء التكلفة (CPI) هو 0.95. إذا كان الجدول الزمني لهذا المشروع يمثل أولوية ولم تتوفر موارد إضافية ، فماذا يجب أن يفعل مدير المشروع؟ | استخدام تجانس الموارد. | استخدم حشد الموارد | استخدم تسوية الموارد. | استخدم التتبع السريع. | بما أن (الجدول هو أولوية ولا توجد موارد إضافية متاحة & مؤشر أداء الجدول (SPI) هو 0.8 ومؤشر أداء التكلفة (CPI) هو 0.95). هذا يعني أن المشروع متأخر عن الجدول الزمني والميزانية. لذلك يجب على مدير المشروع استخدام التتبع السريع حيث لا توجد موارد إضافية متاحة لاستخدام التعطل. [ الإصدار السادس من صفحة PMBOK ، 215] | 142 | 5 | False | "19" | Ahmad
188 | A stakeholder refuses to accept delivery of a project that has passed the acceptance criteria, and provides a new set of acceptance criteria. What should the project manager do to enable project completion? | Escalate the issue to the stakeholder's manager. | Rework the project deliverables to meet the new acceptance criteria. | Execute the change control process to accommodate the new acceptance criteria. | Negotiate with the stakeholder to accept the project in its current state. | Since the deliverable of the project has passed the acceptance criteria, therefore the project manager should first negotiate with the stakeholder to accept the project in its current state within the existing acceptance criteria before any change or escalation. [PMBOK 6th edition page, 163] | صاحب المصلحة يرفض قبول تسليم المشروع الذي اجتاز معايير القبول ، ويقدم مجموعة جديدة من معايير القبول. ما الذي يجب على مدير المشروع فعله لتمكين إكمال المشروع؟ | تصعيد المشكلة إلى مدير أصحاب المصلحة. | أعد صياغة مخرجات المشروع للوفاء بمعايير القبول الجديدة. | تنفيذ عملية التحكم في التغيير لاستيعاب معايير القبول الجديدة. | تفاوض مع أصحاب المصلحة لقبول المشروع في حالته الحالية. | نظرًا لأن تسليمات المشروع قد اجتازت معايير القبول ، يجب على مدير المشروع أولاً التفاوض مع أصحاب المصلحة لقبول المشروع في حالته الحالية ضمن معايير القبول الحالية قبل أي تغيير أو تصعيد. [ الإصدار السادس من صفحة PMBOK ، 163] | 141 | 5 | False | "20" | Ahmad
189 | A project task involves the procurement of a specific raw materials at regular intervals. Price fluctuations was identified as a risk during planning. The risk response is to exploit a price drop if it occurs. The price of the raw material has now reduced drastically. What should the project manager do? | Purchase the raw material at the existing price. | Wait for the prices to further reduce. | Ask the management for advice. | Review the risk register for the recommended responses. | The risk response is to exploit a price drop if it occurs, now the raw material has reduced drastically. So the project manager should review the response strategy that included in the risk register to exploit the opportunity. [PMBOK 6th edition page, 449] | تتضمن مهمة المشروع شراء مواد خام محددة على فترات منتظمة. تم تحديد تقلبات الأسعار على أنها خطر أثناء التخطيط. تتمثل الاستجابة للمخاطر في استغلال انخفاض السعر في حالة حدوثه. انخفض سعر المواد الخام الآن بشكل كبير. ماذا يجب أن يفعل مدير المشروع؟ | شراء المواد الخام بالسعر الحالي. | انتظر حتى تنخفض الأسعار أكثر. | اطلب المشورة من الإدارة. | مراجعة سجل المخاطر للاستجابات الموصى بها. | تتمثل الاستجابة للمخاطر في استغلال انخفاض السعر في حالة حدوثه ، فقد انخفضت الآن المواد الخام بشكل كبير. لذلك يجب على مدير المشروع مراجعة استراتيجية الاستجابة المضمنة في سجل المخاطر لاستغلال الفرصة. [PMBOK الطبعة السادسة ، الصفحة 449] | 147 | 4 | False | "20" | Ahmad
190 | A project manager is managing a project with a major deliverable that failed its final acceptance test. The project is now behind schedule and over budget because a replacement must be created. What process should the project manager use to determine why the failure occurred? | Critical path method. | Alternative analysis. | Decomposition. | Root cause analysis. | Root cause analysis is an analytical technique used to determine the basic underlying reason that causes a variance, defect, or risk. A root cause may underlie more than one variance, defect, or risk. It may also be used as a technique for identifying root causes of a problem and solving them. When all root causes for a problem are removed, the problem does not recur. [PMBOK 6th edition page, 288] | مدير مشروع يدير مشروعًا مع نتيجة رئيسية فشلت في اختبار القبول النهائي. المشروع الآن متأخر عن الجدول الزمني وميزانيته لأنه يجب إنشاء بديل. ما هي العملية التي يجب أن يستخدمها مدير المشروع لتحديد سبب حدوث الفشل؟ | طريقة المسار الحرج. | التحليل البديل. | تقسيم. | تحليل السبب الجذري. | تحليل السبب الجذري هو أسلوب تحليلي يستخدم لتحديد السبب الرئيسي الأساسي الذي يسبب تباينًا أو عيبًا أو خطرًا. قد يكمن السبب الجذري وراء أكثر من اختلاف أو عيب أو خطر. يمكن استخدامه أيضًا كطريقة لتحديد الأسباب الجذرية للمشكلة وحلها. عند إزالة جميع الأسباب الجذرية لمشكلة ما ، لا تتكرر المشكلة. [PMBOK الطبعة السادسة ، الصفحة 288] | 144 | 4 | False | "19" | Ahmad
191 | A lead business analyst on a large project has consistently been working late to finalize requirements for the next sprint. In the weekly team lead meeting. The project manager learns there are several business analysts on the team who have free cycles. What should the project manager do to ensure an even workload? | Delay the start date of the next sprint to allow more time for gathering requirements. | Review the list of open requirements and reassign them to team members with free cycles. | Direct the business analysts with free cycles to take more ownership of the project. | Facilitate a discussion within the team to redistribute the work within the project team. | Since there are several business analysts on the team who have tree cycles, the project manager should facilitate a discussion within the team to redistribute the work within the project team. [PMBOK 6th edition page, 345] | يعمل محلل الأعمال الرائد في مشروع كبير باستمرار حتى وقت متأخر لإنهاء متطلبات السباق التالي. في الاجتماع الأسبوعي للفريق. يعلم مدير المشروع أن هناك العديد من محللي الأعمال في الفريق الذين لديهم دورات مجانية. ما الذي يجب على مدير المشروع فعله لضمان تساوي عبء العمل؟ | قم بتأجيل تاريخ بدء السباق التالي للسماح بمزيد من الوقت لجمع المتطلبات. | راجع قائمة المتطلبات المفتوحة وأعد تعيينها لأعضاء الفريق بدورات مجانية. | وجّه محللي الأعمال الذين لديهم دورات مجانية للحصول على ملكية أكبر للمشروع. | تيسير المناقشة داخل الفريق لإعادة توزيع العمل داخل فريق المشروع. | نظرًا لوجود العديد من محللي الأعمال في الفريق الذين لديهم دورات متفرعة ، يجب على مدير المشروع تسهيل المناقشة داخل الفريق لإعادة توزيع العمل داخل فريق المشروع. [ الطبعة السادسة من صفحة PMBOK ، 345] | 145 | 4 | False | "17" | Ahmad
192 | A project manager is gathering formal project requirements. After conducting stakeholder interviews, the project manager realizes that some objectives are inconsistent with those in the project charter. Based on information learned during the initiation phase, this project must be highly focused to stay within budget limits. To manage requirements and meet stakeholder expectations, what should the project manager do? | Disregard stakeholders' objectives that may be outside the scope detailed in the project charter. | Expand the project charter to include the newly identified objectives. | Remove objectives in the project charter that are not aligned with the stakeholders' objectives. | Realign the stakeholders' expectations with the objectives in the project charter. | Since some objectives are inconsistent with those in the project charter, the project manager should realign the stakeholders' expectations with the objectives in the project charter to manage requirements and meet stakeholder expectations. [PMBOK 6th edition page, 138] | يقوم مدير المشروع بجمع متطلبات المشروع الرسمية. بعد إجراء مقابلات مع أصحاب المصلحة ، يدرك مدير المشروع أن بعض الأهداف لا تتوافق مع تلك الواردة في ميثاق المشروع. بناءً على المعلومات التي تم تعلمها خلال مرحلة البدء ، يجب أن يكون هذا المشروع شديد التركيز للبقاء ضمن حدود الميزانية. لإدارة المتطلبات وتلبية توقعات أصحاب المصلحة ، ماذا يجب أن يفعل مدير المشروع؟ | تجاهل أهداف أصحاب المصلحة التي قد تكون خارج النطاق المفصل في ميثاق المشروع. | قم بتوسيع ميثاق المشروع ليشمل الأهداف المحددة حديثًا. | قم بإزالة الأهداف في ميثاق المشروع التي لا تتماشى مع أهداف أصحاب المصلحة. | أعد مواءمة توقعات أصحاب المصلحة مع الأهداف الواردة في ميثاق المشروع. | نظرًا لأن بعض الأهداف لا تتسق مع تلك الواردة في ميثاق المشروع ، يجب على مدير المشروع إعادة مواءمة توقعات أصحاب المصلحة مع الأهداف الواردة في ميثاق المشروع لإدارة المتطلبات وتلبية توقعات أصحاب المصلحة. [ الإصدار السادس من صفحة PMBOK ، 138] | 141 | 3 | False | "20" | Ahmad
193 | A project manager has just been assigned in the middle of the execution phase. The project is delayed and two important stakeholders are not cooperating with project objectives. Documentation states not to interact directly with either stakeholder, leaving this role to the company's chief information officer . What should the project manager do? | Perform a root cause analysis and escalate to the two important stakeholders. | Perform a data analysis and review the stakeholders' roles and responsibilities matrix. | Perform a stakeholder analysis and escalate the issue to upper management. | Perform an assumption and constraint analysis and review the stakeholder engagement plan. | Analysis of current assumptions and constraints may be conducted in order to tailor appropriate engagement strategies. Review The stakeholder engagement plan that identifies the strategies and actions required to promote productive involvement of stakeholders in decision making and execution. [PMBOK 6th edition Page, 521] | تم تعيين مدير المشروع للتو في منتصف مرحلة التنفيذ. تأخر المشروع ولا يتعاون اثنان من أصحاب المصلحة المهمين مع أهداف المشروع. تنص الوثائق على عدم التفاعل مباشرة مع أي من أصحاب المصلحة ، وترك هذا الدور لرئيس قسم المعلومات في الشركة. ماذا يجب أن يفعل مدير المشروع؟ | قم بإجراء تحليل السبب الجذري وتصعيده إلى أصحاب المصلحة المهمين. | قم بإجراء تحليل للبيانات واستعرض مصفوفة أدوار ومسؤوليات أصحاب المصلحة. | قم بإجراء تحليل لأصحاب المصلحة وتصعيد المشكلة إلى الإدارة العليا. | قم بإجراء تحليل للافتراضات والقيود ومراجعة خطة مشاركة أصحاب المصلحة. | يمكن إجراء تحليل الافتراضات والقيود الحالية من أجل تصميم استراتيجيات مهمة مناسبة. مراجعة خطة إشراك أصحاب المصلحة التي تحدد الاستراتيجيات والإجراءات المطلوبة لتعزيز المشاركة المثمرة لأصحاب المصلحة في صنع القرار والتنفيذ. [PMBOK الطبعة السادسة ، الصفحة 521] | 149 | 3 | False | "20" | Ahmad
194 | A client approaches a design team member requesting that a current task be stopped and a new concept be developed. This will significantly change the design, and impact the project budget and schedule. The team member asks the project manager for the next course of action. What should the project manager do? | Hold a team meeting to discuss the request. | Accept the request and make the changes. | Ask the client to refrain from directly contacting team members. | Refer to the perform integrated change control process. | Since the new concept be developed will significantly change the design, and impact the project budget and schedule, the project manager should refer to the perform integrated change control process to manage this change. [PMBOK 6th edition Page, 113] | يقترب العميل من عضو فريق التصميم ويطلب إيقاف مهمة حالية وتطوير مفهوم جديد. سيؤدي هذا إلى تغيير التصميم بشكل كبير ، وسيؤثر على ميزانية المشروع والجدول الزمني. يسأل عضو الفريق مدير المشروع عن مسار العمل التالي. ماذا يجب أن يفعل مدير المشروع؟ | عقد اجتماع الفريق لمناقشة الطلب. | اقبل الطلب وقم بإجراء التغييرات. | اطلب من العميل الامتناع عن الاتصال المباشر بأعضاء الفريق. | الرجوع إلى عملية إجراء التحكم في التغيير المتكامل. | نظرًا لأن تطوير المفهوم الجديد سيغير التصميم بشكل كبير ، وسيؤثر على ميزانية المشروع والجدول الزمني ، يجب على مدير المشروع الرجوع إلى عملية إجراء التحكم في التغيير المتكامل لإدارة هذا التغيير. [PMBOK الطبعة السادسة ، الصفحة 113] | 140 | 5 | False | "18" | Ahmad
195 | To documents a configuration management system, which of the following Project Scope Management processes is used? | Verify Scope | Define Scope | Control Scope | Plan Scope Management | Configuration management activities are documented as part of the requirements management plan which is an output of the Plan Scope Management process. [PMBOK 6th edition, Page.137] | لتوثيق نظام إدارة التكوين ، أي من عمليات إدارة نطاق المشروع التالية يتم استخدامها؟ | تحقق من النطاق | تحديد النطاق | نطاق التحكم | إدارة نطاق الخطة | يتم توثيق أنشطة إدارة التكوين كجزء من خطة إدارة المتطلبات التي تعد ناتجًا عن عملية إدارة نطاق الخطة. [PMBOK الطبعة السادسة ، الصفحة 137] | 141 | 3 | False | "18" | Ahmad
196 | Two team members who have conflicting opinions. One team member explains her side of the conflict. The other team member responds by saying, "I know you'll never really listen to my side, so let's just go with her opinion and get back to work." The team member used which of the following techniques for resolving conflict? | Forcing | Smoothing | Compromise | Withdrawal | It's clear that the team member avoids the situation and thought that PM not listen to him and go with another opinion. [PMBOK 6th edition, Page.349] | اثنان من أعضاء الفريق لديهما آراء متضاربة. تشرح إحدى أعضاء الفريق جانبها من الصراع. يرد عضو الفريق الآخر بالقول: "أعلم أنك لن تستمع أبدًا إلى جانبي ، لذا دعنا نذهب برأيها ونعود إلى العمل." استخدم عضو الفريق أيًا من الأساليب التالية لحل النزاع؟ | إجبار | التنعيم | مرونة | انسحاب | من الواضح أن عضو الفريق يتفادى الموقف ويعتقد أن مدير المشروع لا يستمع إليه ويذهب برأي آخر. [PMBOK الطبعة السادسة ، الصفحة 349] | 145 | 4 | False | "18" | Ahmad
197 | As a project manager in a communication project. The project is ahead of schedule and under budget. The sponsor then suggests a change to include a value-added feature that wouldn't impact project schedule and cost. What should you do next? | Advise the stakeholder that changes shouldn't be implemented when a project is behind schedule. | Update the project management plan to include the new feature. | Advise the stakeholder that, since the project is under budget, the feature will be added | Evaluate the change's impact with the team. | The change does not impact the schedule and cost but the project manager should Evaluate the change's impact with the team on other project constraints... [PMBOK 6th edition, Page.117] | كمدير مشروع في مشروع اتصالات. المشروع قبل الجدول الزمني وتحت الميزانية. ثم يقترح الراعي إجراء تغيير ليشمل ميزة ذات قيمة مضافة لن تؤثر على جدول المشروع وتكلفته. ماذا يجب ان تفعل بعد ذلك؟ | أخبر أصحاب المصلحة بأنه لا ينبغي تنفيذ التغييرات عندما يتأخر المشروع عن الجدول الزمني. | قم بتحديث خطة إدارة المشروع لتضمين الميزة الجديدة. | أخبر أصحاب المصلحة أنه نظرًا لأن المشروع تحت الميزانية ، ستتم إضافة الميزة | قم بتقييم تأثير التغيير مع الفريق. | لا يؤثر التغيير على الجدول الزمني والتكلفة ولكن يجب على مدير المشروع تقييم تأثير التغيير مع الفريق على قيود المشروع الأخرى . [PMBOK الطبعة السادسة ، الصفحة 117] | 140 | 5 | False | "19" | Ahmad
198 | To improve the quality of project deliverables, you decides to involve the project team in defining project standards, policies, and guidelines. The team thinks that this a waste of effort, and would like to continue to execute the project as planned. What should you do next? | Produce the quality management plan, and distribute it to stakeholders. | Meet with individual team members, and force them to comply. | Log an issue with the team and discuss it with the human resources department. | Organize a project team meeting to create a shared vision. | The project manager should Organize a project team meeting to create a shared vision and the importance of the quality of the project deliverable and this is not a waste of effort and should defining project standards, policies, and guidelines To improve the quality of the project deliverables. The next step Produce the quality management plan, and distribute it to stakeholders. [PMBOK 6th edition, Page.286] | لتحسين جودة مخرجات المشروع ، قررت إشراك فريق المشروع في تحديد معايير المشروع وسياساته وإرشاداته. يعتقد الفريق أن هذا مضيعة للجهد ، ويود الاستمرار في تنفيذ المشروع كما هو مخطط له. ماذا يجب ان تفعل بعد ذلك؟ | إعداد خطة إدارة الجودة وتوزيعها على أصحاب المصلحة. | قابل أعضاء الفريق الفردي واجبرهم على الامتثال. | سجل مشكلة مع الفريق وناقشها مع قسم الموارد البشرية. | تنظيم اجتماع فريق المشروع لخلق رؤية مشتركة. | يجب على مدير المشروع تنظيم اجتماع فريق المشروع لإنشاء رؤية مشتركة وأهمية جودة المشروع المنجز وهذا ليس مضيعة للجهد ويجب تحديد معايير المشروع وسياساته وإرشاداته لتحسين جودة مخرجات المشروع . الخطوة التالية قم بإعداد خطة إدارة الجودة وتوزيعها على أصحاب المصلحة. [PMBOK الطبعة السادسة ، الصفحة 286] | 144 | 4 | False | "20" | Ahmad
199 | You are managing a program and the sponsor asks you to submit CPI and TCPI numbers for your projects. You provided CPI = 1 for project A, CPI = 1.2 for project B, TCPI = 0.9 for project C and TCPI = 1.2 for project D. Which project do you think the sponsor might terminate based on this data? | Project A | Project C | Project B | Project D | Project D has a TCPI of 1.2, a higher TCPI indicates a higher task rate for the CPI in future which is not good and Harder to complete. All other projects are in good shape. [PMBOK 6th edition, Page 267] | أنت تدير برنامجًا ويطلب منك الراعي تقديم أرقام CPI و TCPI لمشاريعك. لقد قدمت CPI = 1 للمشروع A ، CPI = 1.2 للمشروع B ، TCPI = 0.9 للمشروع C و TCPI = 1.2 للمشروع D. ما المشروع الذي تعتقد أن الراعي قد ينتهي بناءً على هذه البيانات؟ | مشروع أ | مشروع ج | المشروع ب | مشروع D | يحتوي المشروع D على TCPI يبلغ 1.2 ، يشير TCPI الأعلى إلى معدل CPI اعلى في المستقبل وهو ليس جيدًا ويصعب إكماله. جميع المشاريع الأخرى في حالة جيدة. [PMBOK الطبعة السادسة ، الصفحة 267] | 143 | 5 | False | "19" | Ahmad
200 | (EEF) enterprise environmental factors play an important role during the development of the project charter. It includes some elements such as: | Organizational standard policies, processes, and procedures | Templates (e.g., project charter template) | Historical information and lessons learned . | Organizational culture and political climate | Organizational culture, and political climate is examples of (EEF). [PMBOK 6th edition, Page 78] | (EEF) تلعب العوامل البيئية للمؤسسة دورًا مهمًا أثناء تطوير ميثاق المشروع. يتضمن بعض العناصر مثل: | السياسات والعمليات والإجراءات القياسية التنظيمية | القوالب (على سبيل المثال ، قالب ميثاق المشروع) | المعلومات التاريخية والدروس المستفادة. | الثقافة التنظيمية والمناخ السياسي | الثقافة التنظيمية والمناخ السياسي أمثلة على العوامل البيئية للمؤسسة (EEF). [الطبعة السادسة من PMBOK ، صفحة 78] | 140 | 2 | False | "19" | Ahmad
201 | A vendor delayed in supplying some resources even the accounting system by an hourly rate. What should you refer for resolving this issue as a Project Manager? | Arbitration | Procurement documents | Procurement management plan | Agreement | Any problem appears after signing the contract you should follow the Agreement because the Agreement includes Incentives. penalties, Termination clause, and alternative dispute resolution mechanisms and General terms and conditions. [PMBOK 6th edition, Page 489] | تأخر البائع في توفير بعض الموارد بالرغم ان نظام المحاسبة بمعدل ساعة. ما الذي يجب أن تشير إليه لحل هذه المشكلة بصفتك مدير مشروع؟ | تحكيم | وثائق المشتريات | خطة إدارة المشتريات | الاتفاقية | أي مشكلة تظهر بعد توقيع العقد يجب عليك اتباع الاتفاقية لأن الاتفاقية تتضمن حوافز. العقوبات ، شرط الإنهاء ، والآليات البديلة لتسوية المنازعات والشروط والأحكام العامة. [الطبعة السادسة ، صفحة 489 PMBOK] | 148 | 5 | False | "17" | Abdulfattah
202 | Your customer wants to remove certain attributes from the product. You submits a change request which is approved by the change control board ( CCB ). What should you do next? | Update the project charter. | Update the Issue log. | Update the risk register. | Update the project management plan. | The project management plan should be updated after a change request takes approval by CCB. [PMBOK 6th edition, Page.96] | يريد عميلك إزالة سمات معينة من المنتج. ثم قمت بتقديم طلب تغيير وقد تمت الموافقة عليه من قبل لجنة التحكم في التغيير (CCB). ماذا يجب ان تفعل بعد ذلك؟ | تحديث ميثاق المشروع. | بتحديث سجل المشاكل. | تحديث سجل المخاطر. | تحديث خطة إدارة المشروع. | يجب تحديث خطة إدارة المشروع بعد أن يأخذ طلب التغيير موافقة بنك التعمير الصينى. [الطبعة السادسة ، صفحة 96 PMBOK] | 140 | 4 | False | "19" | Abdulfattah
203 | The Company CEO is asking you to make a presentation on your project, which has been in progress for 18 months to over 50 identified internal and external stakeholders. You have been conducting such presentations and holding meetings regularly on this critical project. You should begin by— | Deciding on the general form of the presentation | Determining the objective | Defining the audience | Circulating issues to be discussed | In the regular meeting, the Project manager should First begin to present the issues to be discussed. [PMBOK 6th edition, Page.383] | يطلب منك الرئيس التنفيذي للشركة تقديم عرض تقديمي عن مشروعك الذي استمر لمدة 18 شهرًا والتعامل ممع اكثر من 50 شخص من أصحاب المصلحة الداخليين والخارجيين المحددين. لقد أجريت مثل هذه العروض التقديمية وعقدت اجتماعات بانتظام حول هذا المشروع الهام. يجب أن تبدأ بـ - | تحديد الشكل العام للعرض | تحديد الهدف | تحديد الجمهور | تحديد المشاكل المتداولة التي ستناقش | في الاجتماع العادي ، يجب أن يبدأ مدير المشروع أولاً في تقديم القضايا التي سيتم مناقشتها.[الطبعة السادسة ، صفحة 383 PMBOK] | 146 | 4 | False | "19" | Abdulfattah
204 | A resources can't be retained for the full project life cycle and there is no additional budget available. What should the project manager do to ensure effective project delivery while utilizing resources within budgeted limits? | Move budgeted funds from other project areas to mitigate any risk of gaps in assignments. | Create a budget change request for stakeholders before presenting project progress. | Identify those resources who can likely perform all necessary project tasks, and remove resources that are specialized. | Schedule similar tasks around the same time to limit the duration of resources' engagement. | Because of the resources can't be retained for the full project life cycle and there is no additional budget available, the project manager should Schedule similar tasks around the same time to limit the duration of resources' engagement to ensure effective project delivery within budgeted limits. [PMBOK 6th edition, Page.211] | لا يمكن الاحتفاظ بالموارد طول فترة حياة المشروع ولا توجد ميزانية إضافية متاحة. ما الذي يجب أن يفعله مدير المشروع لضمان التسليم الفعال للمشروع أثناء استخدام الموارد ضمن حدود الميزانية؟ | الحصول على تمويل من مشاريع أخرى للتخفيف من أي مخاطر لحدوث فجوات في المهام. | إنشاء طلب تغيير الميزانية لأصحاب المصلحة قبل تقديم تقدم المشروع. | تحديد تلك الموارد التي من المرجح أن تؤدي جميع مهام الضرورية للمشروع ، و إزالة الموارد المتخصصة. | جدولة مهام مماثلة في نفس الوقت تقريبًا للحد من مدة مشاركة الموارد. | نظرًا لأنه لا يمكن الاحتفاظ بالموارد طول فترة حياة المشروع ولا توجد ميزانية إضافية متاحة ، يجب على مدير المشروع جدولة مهام مماثلة في نفس الوقت تقريبًا للحد من مدة مشاركة الموارد لضمان التسليم الفعال للمشروع ضمن حدود الميزانية . [الطبعة السادسة ، صفحة 211 PMBOK] | 142 | 3 | False | "20" | Abdulfattah
205 | You are working on a project for which some requirements have not been clearly defined. The customer insist that this should not be considered a problem and the project should continue without delay. What should you do as the project manager? | Accept the risk and start project work. | Meet with the team to discuss the concerns | Speak with the customer to avoid the risk. | Log the risk in the risk register. | Some requirements have not been clearly defined , its a risk and the project manager should Log the risk in the risk register then analyze the impact on project objectives. The three other options will be done after updating risk register. [PMBOK 6th edition, Page.417] | أنت تعمل في مشروع لم يتم تحديد بعض متطلباته بوضوح. يصر العميل على أن هذا لا ينبغي اعتباره مشكلة ويجب أن يستمر المشروع دون تأخير. ماذا يجب أن تفعل كمدير المشروع؟ | اقبل المخاطر وابدأ العمل في المشروع. | لقاء مع الفريق لمناقشة المخاوف المحتملة. | التحدث مع العميل لتجنب المخاطر. | تسجل المخاطر في سجل المخاطر. | لم يتم تحديد بعض المتطلبات بوضوح ، فهي تمثل مخاطرة ويجب على مدير المشروع تسجيل المخاطر في سجل المخاطر ثم تحليل التأثير على أهداف المشروع. سيتم تنفيذ الخيارات الثلاثة الأخرى بعد تحديث سجل المخاطر. [الطبعة السادسة ، صفحة 417 PMBOK] | 147 | 3 | False | "20" | Abdulfattah
206 | You are a project manager of a project that was originally estimated to be completed in 12 months. During the testing phase, a higher- than- expected failure rate is reported. What should you do? | Create a product flowchart. | Initiate perform integrated change control. | Create Scatter diagram. | Create a fishbone diagram. | The project manager should create a fishbone diagram to determine the root cause of the problem. If the corrective action will impact any baseline, the next step is to Initiate perform integrated change control. [PMBOK 6th edition, Page.293] | أنت تعمل كمدير مشروع و كان من المقدر في الأصل أن يكتمل المشروع خلال 12 شهرًا. خلال مرحلة الاختبار ، تم الإبلاغ عن معدل فشل أعلى من المتوقع. ماذا عليك ان تفعل؟ | قم بإنشاء مخطط انسيابي للمنتج. | بدء تنفيذ عملية التحكم المتكامل في التغيير. | إنشاءمخطط التشتت. | إنشاء مخطط هيكل السمكة. | يجب على مدير المشروع إنشاء مخطط هيكل السمكة لتحديد السبب الجذري للمشكلة. إذا كان الإجراء التصحيحي سيؤثر على أي خط أساس ، فإن الخطوة التالية هي بدء تنفيذ عملية التحكم المتكامل في التغيير. [الطبعة السادسة ، صفحة 293 PMBOK] | 144 | 4 | False | "19" | Abdulfattah
207 | You joined a project during it's initial planning phase. The project involves various local government institutions. While interviewing the project sponsor, you learn the importance of keeping the security officers of two of these institutions satisfied, since project development will be affected without their involvement. What should you use to record and monitor this information? | Communication management plan | Risk register. | Responsibility assignments matrix RAM. | Power /interest grid | Power /interest grid supports a grouping of stakeholders according to their level of authority (power), level of concern about the project's outcomes (interest), [PMBOK 6th edition, Page.512] | لقد انضممت إلى مشروع أثناء مرحلة التخطيط الأولية. يشمل المشروع مؤسسات حكومية محلية مختلفة. أثناء إجراء مقابلة مع راعي المشروع ، تتعلم أهمية الحفاظ على رضاء ضباط الأمن في اثنتين من هذه المؤسسات ، حيث سيتأثر تطوير المشروع بدون مشاركتهم بالمشروع. ما الذي يجب أن تستخدمه لتسجيل هذه المعلومات ومراقبتها؟ | خطة إدارة الاتصالات | سجل المخاطر. | مصفوفة تعيين المسؤوليات RAM. | شبكة السلطة / الاهتمام | تدعم شبكة الطاقة / الاهتمامات مجموعة من أصحاب المصلحة وفقًا لمستوى سلطتهم (القوة) ، ومستوى القلق بشأن نتائج المشروع (الفائدة). [الطبعة السادسة ، صفحة 512 PMBOK] | 149 | 2 | False | "17" | Abdulfattah
208 | You often has to deal with change requests to expand or reduce the project scope. Changes in project scope impact a variety of project documents. In this context, approved change requests can impact all of the following except: | Cost Estimates | Project Management Plan | Project Deliverables | Project Charter | Changes can impact the Project Management Plan, Cost Estimates, and Project Deliverables. Frequent change requests to the project scope would not impact the Project Charter. [PMBOK 6th edition, Page.170] | غالبًا ما يتعين عليك التعامل مع طلبات التغيير لتوسيع نطاق المشروع أو تقليله. تؤثر التغييرات في نطاق المشروع على مجموعة متنوعة من وثائق المشروع. في هذا السياق ، يمكن أن تؤثر طلبات التغيير المعتمدة على كل ما يلي باستثناء: | تقديرات التكلفة | خطة إدارة المشروع | مخرجات المشروع | ميثاق المشروع | يمكن أن تؤثر التغييرات على خطة إدارة المشروع وتقديرات التكلفة وتسليمات المشروع. لن تؤثر طلبات التغيير المتكررة في نطاق المشروع على ميثاق المشروع. [الطبعة السادسة ، صفحة 170 PMBOK] | 141 | 5 | False | "19" | Abdulfattah
209 | During the Kick- off meeting, the CEO did not accept a project management plan. What should you refer to persuade the CEO? | Cost benefit analysis | Project management plan | SOW Bottom of Form | Project charter | Project charter includes High-level requirements, Project purpose, High-level project description and boundaries, High-level risks, Summary budget, Key Stakeholder list, and the project charter is the key input in develop project management plan process. so you refer to charter to persuade the stakeholders. [PMBOK 6th edition, Page 81] | خلال الاجتماع الافتتاحي ، لم يقبل الرئيس التنفيذي خطة إدارة المشروع. ما الذي يجب أن تشير إليه لإقناع الرئيس التنفيذي؟ | تحليل التكاليف والمنفعة | خطة إدارة المشروع | نموذج بيانات العمل | ميثاق المشروع | يتضمن ميثاق المشروع المتطلبات عالية المستوى ، والغرض من المشروع ، ووصف المشروع عالي المستوى وحدوده ، والمخاطر عالية المستوى ، والميزانية الموجزة ، وقائمة أصحاب المصلحة الرئيسيين ، وميثاق المشروع هو المدخل الرئيسي في تطوير عملية خطة إدارة المشروع. لذا فأنت تشير إلى الميثاق لإقناع أصحاب المصلحة. [الطبعة السادسة ، صفحة 81 PMBOK] | 140 | 3 | False | "18" | Abdulfattah
210 | At the end of project execution, Michel the project manager has retained some team members. What should the team be primarily focused on doing at this point? | Providing support as part of the warranty period associated with the handover | Operating the newly completed facilities until the owners are fully competent | Assisting with clean up, site restoration, commissioning, and personnel training | Supporting administrative project closure procedures as per company policies | The project manager has retained some team members to Supporting administrative project closure procedures as per company policies..... Refer to PMP Exam Outline ( Task no 03 ) Obtain financial, legal, and administrative closure using generally accepted practices and policies in order to communicate formal project closure and ensure transfer of liability. [PMBOK 6th edition, Page.123] | في نهاية مرحلة التنفيذ بالمشروع ، احتفظ ميشيل مدير المشروع ببعض أعضاء الفريق. ما الذي يجب أن يركز عليه الفريق في المقام الأول في هذه المرحلة؟ | تقديم الدعم كجزء من فترة الضمان المرتبطة بعملية التسليم | تشغيل المرافق المكتملة حديثًا حتى يصبح أصحابها مؤهلين تمامًا | المساعدة في التنظيف وترميم الموقع والتكليف وتدريب الموظفين | دعم إجراءات إغلاق المشاريع الإدارية حسب سياسات الشركة | يحتفظ مدير المشروع ببعض أعضاء الفريق لدعم إجراءات إغلاق المشروع الإدارية وفقًا لسياسات الشركة ..... الرجوع إلى مخطط اختبار PMP (المهمة رقم 03) الحصول على الإغلاق المالي والقانوني والإداري باستخدام الممارسات والسياسات المقبولة عمومًا من أجل الإبلاغ عن الإغلاق الرسمي للمشروع والتأكد من نقل المسؤولية. [الطبعة السادسة ، صفحة 123 PMBOK] | 140 | 6 | False | "20" | Abdulfattah
211 | After analyzing risk with the project team, the project manager, decides to establish a contingency reserve to handle the threat if it occurs. What type of strategy is this? | Passive acceptance | Passive transference | Active mitigation | Active acceptance | The most common active acceptance strategy is to establish a contingency reserve, including amounts of time, money, or resources to handle the threat if it occurs. [PMBOK 6th edition, Page 443] | بعد تحليل المخاطر مع فريق المشروع ، يقرر مدير المشروع إنشاء احتياطي للطوارئ للتعامل مع التهديد في حالة حدوثه. ما نوع هذه الاستراتيجية؟ | القبول السلبي | التحويل السلبي | التخفيف النشط | قبول نشط | إستراتيجية القبول الأكثر شيوعًا هي إنشاء احتياطي للطوارئ ، بما في ذلك مقدار الوقت أو المال أو الموارد للتعامل مع التهديد في حالة حدوثه. [الطبعة السادسة ، صفحة 443 PMBOK] | 147 | 3 | False | "18" | Abdulfattah
212 | You was asked to create a business case for a company's new business in the Cyber Security sector. There is little expertise available within the company as these types of projects have not been done before. What should you as the project manager do? | Conduct a market analysis and finalize project requirements. | Identify key stakeholders and meet with them to discuss the new business endeavors. | Suggest that management doesn't pursue this business endeavors since there is a lack of experience. | Consult with subject matter experts. SMEs | As there is little expertise available within the company as these types of projects, the project manager should Consult with subject matter experts. SMEs. [PMBOK 6th edition, Page.141] | لقد طُلب منك إنشاء حالة عمل للأعمال التجارية الجديدة للشركة في قطاع الأمن السيبراني. هناك القليل من الخبرة المتاحة داخل الشركة لأن هذه الأنواع من المشاريع لم يتم تنفيذها من قبل. ماذا يجب أن تفعل كمدير المشروع؟ | إجراء تحليل السوق والانتهاء من متطلبات المشروع. | تحديد أصحاب المصلحة الرئيسيين والاجتماع معهم لمناقشة المساعي التجارية الجديدة. | اقتراح أن الإدارة لا تتابع مساعي العمل هذه نظرًا لنقص الخبرة. | استشر الخبراء المتخصصين. الشركات الصغيرة والمتوسطة | نظرًا لوجود القليل من الخبرة المتاحة داخل الشركة مثل هذه الأنواع من المشاريع ، يجب على مدير المشروع التشاور مع الخبراء المتخصصين. الشركات الصغيرة والمتوسطة. [الطبعة السادسة ، صفحة 141 PMBOK] | 141 | 3 | False | "19" | Abdulfattah
213 | The building of a Stadium has been stopped for four months due to region-specific prohibition. What should the project manager have done to avoid this issue? | Document all assumptions. | Made a prioritized list of the project constraints. | Crashed the project schedule. | Identified this as a risk in the risk register. | The project manager should have Identified this as a risk in the risk register and analyzed the impact to avoid this issue …[PMBOK 6th edition, Page.471] | تم إيقاف بناء الملعب لمدة أربعة أشهر بسبب الحظر الخاص بالمنطقة. ما الذي كان يجب على مدير المشروع فعله لتجنب هذه المشكلة؟ | توثيق جميع الافتراضات. | قدم قائمة أولويات قيود المشروع. | حشد الموارد للجدول الزمني للمشروع. | كان يجب عليه تحديد هذا الخطر وتوثيقه في سجل المخاطر. | يجب أن يكون مدير المشروع قد حدد هذا على أنه خطر في سجل المخاطر وتحليل التأثير لتجنب هذه المشكلة . [الطبعة السادسة ، صفحة 471 PMBOK] | 147 | 3 | False | "19" | Abdulfattah
214 | You work for Yory's, a food equipment manufacturer. Your organization is installing some new manufacturing equipment, and you are managing the project. Your project sponsor has asked for an EAC and has told you that he wants you to use ETC work considering CPI and SPI factors. If EV = 145, PV = 162, AC = 148, and BAC = 200, what is EAC? | 58 | 207 | 63 | 210 | The EAC formula for this question is Ac + [(BAC - EV) ÷ (CPI x SPI)]. First, calculate CPI, which is EV ÷ AC: therefore, $145 ÷ $148 = .$98. SP) is EV ÷ PV; therefore, $145 ÷ $162 = .$90. Plugging in the numbers from the question, you get $148 + [($200 - $14S) (.898 x .890)] $210. [PMBOK 6th edition, Page.265] | أنت تعمل في Yory's ، شركة تصنيع معدات غذائية. تقوم مؤسستك بتركيب بعض معدات التصنيع الجديدة ، وأنت تدير المشروع. طلب راعي مشروعك الحصول على EAC وأخبرك أنه يريد منك استخدام عمل ETC مع الأخذ في الاعتبار عوامل CPI و SPI. إذا كانت قيمة EV = 145 ، و PV = 162 ، و AC = 148 ، و BAC = 200 ، فما هو EAC؟ | 58 | 207 | 63 | 210 | صيغة EAC لهذا السؤال هي Ac + [(BAC - EV) ÷ (CPI x SPI)]. أولاً ، احسب CPI ، وهو AC ÷ EV: وبالتالي ، 145$ ÷ 148$ = 0.98. SP هو PV ÷ EV ؛ لذلك ، 145$ ÷ 162$ = 90 $. بالتعويض عن الأرقام من السؤال ، تحصل على 148$ + [(200$ - 145$) (0.898 × ​​0.890)]= 210$. [الطبعة السادسة ، صفحة 265 PMBOK] | 143 | 5 | False | "20" | Abdulfattah
215 | John the project manager, discovers a significant flaw in a major project deliverable. Which project management process is being performed? | Manage quality. | Plan quality management. | Statistical sampling. | Control quality. | Keyword ( project deliverable ) The control Quality process is performed to measure the completeness, compliance, and fitness for use of a product or service prior to user acceptance and final delivery. This is done by measuring all steps, attributes, and variables used to verify conformance or compliance to the specifications stated during the planning stage. Deliverables that are output from the Direct and Manage Project Work process are inspected in the Control Quality process. [PMBOK 6th edition, Page 301] | يكتشف جون مدير المشروع عيبًا كبيرًا في تسليم مشروع كبير. ما هي عملية إدارة المشروع التي يتم تنفيذها؟ | إدارة الجودة. | خطة ادارة الجودة . | العينات الإحصائية. | جودة التحكم. | الكلمة الرئيسية (تسليم المشروع) المراقبة يتم تنفيذ عملية الجودة لقياس الاكتمال والامتثال والملاءمة لاستخدام منتج أو خدمة قبل قبول المستخدم والتسليم النهائي. يتم ذلك عن طريق قياس جميع الخطوات والسمات والمتغيرات المستخدمة للتحقق من المطابقة أو الامتثال للمواصفات المنصوص عليها خلال مرحلة التخطيط. يتم فحص التسليمات التي يتم إخراجها من عملية مباشرة وإدارة عمل المشروع في عملية مراقبة الجودة. [الطبعة السادسة ، صفحة 201 PMBOK] | 144 | 5 | False | "18" | Abdulfattah
216 | Why is it necessary to manage changes to the project by following the change management plan, while monitoring and controlling the projects, ? | To satisfy the customer | To satisfy project requirements | To satisfy the sponsor | To align project goals with business needs | According to the examination content outline, following the change management plan ensures that project goals remain aligned with business needs. Refer to PMP Exam Outline in the Monitoring and Controlling Process Group ( Task no.2 )[PMBOK 6th edition, Page.116] | لماذا من الضروري إدارة التغييرات في المشروع باتباع خطة إدارة التغيير ، أثناء مراقبة المشاريع والتحكم فيها؟ | لإرضاء العميل | لتلبية متطلبات المشروع | لإرضاء الراعي | لمواءمة أهداف المشروع مع احتياجات العمل | وفقًا لمخطط محتوى الاختبار ، فإن اتباع خطة إدارة التغيير يضمن أن تظل أهداف المشروع متوافقة مع احتياجات العمل. [الطبعة السادسة ، صفحة 116 PMBOK] | 140 | 5 | False | "20" | Abdulfattah
217 | A long term project for a company that is increasing its infrastructure is running . In month 13 of the project, the client escalates an issue that an expected delivery from a contracted third-party vendor wasn't received. Upon investigation, the project manager discovers that the vendor was unaware of this. Where should the project manager verify the delivery schedule? | Requirements traceability matrix. | Assumptions log. | Requirements management plan | Milestone list | A milestone is a significant point or event in a project. A milestone list identifies all project milestones and indicates whether the milestone is mandatory, such as those required by contract, or optional, such as those based on historical information. Milestones have zero duration because they represent a significant point or event. [PMBOK 6th edition, Page 186] | مشروع طويل الأجل لشركة تعمل على زيادة بنيتها التحتية قيد التشغيل. في الشهر 13 من المشروع ، يقوم العميل بتصعيد مشكلة عدم استلام التسليم المتوقع من مورد طرف ثالث متعاقد معه. عند التحقيق ، اكتشف مدير المشروع أن البائع لم يكن على علم بذلك. أين يجب على مدير المشروع التحقق من جدول التسليم؟ | مصفوفة تتبع المتطلبات. | سجل الافتراضات. | خطة إدارة المتطلبات | قائمة المعالم | المعلم الرئيسي هو نقطة أو حدث مهم في المشروع. تحدد قائمة المعالم الرئيسية جميع معالم المشروع وتشير إلى ما إذا كان الحدث الرئيسي إلزاميًا ، مثل تلك التي يتطلبها العقد ، أو اختيارية ، مثل تلك التي تستند إلى المعلومات التاريخية. لا تحتوي المعالم الرئيسية على مدة لأنها تمثل نقطة أو حدثًا مهمًا. [الطبعة السادسة ، صفحة 186 PMBOK] | 142 | 3 | False | "16" | Abdulfattah
218 | In the middle of the design phase of a software development project, the project manager realizes that planned tasks will be delivered late. What should the project manager do first? | Revise the task delivery dates in the project management plan. | Assume the delay, and report it during the next stakeholder meeting. | Email stakeholders about the delay, and update the project management plan. | Update the issue log. | It's an issue and the project manager should Update the issue log. The issue log will help the project manager effectively track and manage issues, ensuring that they are investigated and resolved. [PMBOK 6th edition, Page 96] | في منتصف مرحلة تصميم مشروع تطوير البرمجيات ، يدرك مدير المشروع أن المهام المخطط لها سيتم تسليمها متأخرًا. ما الذي يجب أن يفعله مدير المشروع أولاً؟ | قم بمراجعة تواريخ تسليم المهام في خطة إدارة المشروع. | افترض التأخير ، وأبلغ عنه خلال الاجتماع التالي لأصحاب المصلحة. | ارسال بريدًا إلكترونيًا إلى أصحاب المصلحة حول التأخير ، وقم بتحديث خطة إدارة المشروع. | بتحديث سجل المشكلة. | إنها مشكلة ويجب على مدير المشروع تحديث سجل المشكلة. سيساعد سجل الأحداث مدير المشروع على تتبع وإدارة المشكلات بشكل فعال ، مما يضمن التحقيق فيها وحلها. [الطبعة السادسة ، صفحة 96 PMBOK] | 140 | 4 | False | "20" | Abdulfattah
219 | During developing a quality management plan for your project. During the planning process, one of your team members tells you that, in the past, the organization has completed a similar project. You start to review the old project and find that some of its quality metrics can be used in your project as well. This technique is known as: | Process analysis | Prototyping | Reviewing organization process assets | Benchmarking | Explanation In benchmarking, you compare the current project parameters with past comparable project parameters to identify the best practices and ideas for improvement. [PMBOK 6th edition, Page 281] | أثناء وضع خطة إدارة الجودة لمشروعك. أثناء عملية التخطيط ، يخبرك أحد أعضاء فريقك أن المنظمة قد أكملت مشروعًا مشابهًا في الماضي. تبدأ في مراجعة المشروع القديم وتجد أن بعض مقاييس الجودة الخاصة به يمكن استخدامها في مشروعك أيضًا. تُعرف هذه التقنية باسم: | عملية التحليل | النماذج الاولية | مراجعة أصول العمليات التنظيمية | المرجعية | الشرح في المقارنة المعيارية ، تقارن المتغيرات المشروع الحالية بالمتغيرات المشروع السابقة القابلة للمقارنة لتحديد أفضل الممارسات والأفكار للتحسين. [الطبعة السادسة ، صفحة 281 PMBOK] | 144 | 3 | False | "20" | Abdulfattah
220 | You are managing a project with project teams in different geographical locations. During project execution, the customer requests a major scope change. The project manager wants to communicate and get approval for this change. What is the BEST communication method for this purpose? | Pull communication | Push communication | Static Communication | Interactive communication | (Interactive Communication) because scope change is critical and need more discussion with the stakeholders and the best communication method is interactive communication. [PMBOK 6th edition, Page.374] | أنت تدير مشروعًا مع فريق المشروع في مواقع جغرافية مختلفة. أثناء تنفيذ المشروع ، يطلب العميل تغييرًا كبيرًا في النطاق. يريد مدير المشروع التواصل والحصول على الموافقة على هذا التغيير. ما هي أفضل طريقة اتصال لهذا الغرض؟ | سحب التواصل | دفع التواصل | اتصالات ثابتة | التواصل التفاعلي | (الاتصال التفاعلي) لأن تغيير النطاق أمر بالغ الأهمية ويحتاج إلى مزيد من المناقشة مع أصحاب المصلحة وأفضل طريقة للاتصال هي الاتصال التفاعلي. [الطبعة السادسة ، صفحة 211 PMBOK] | 146 | 3 | False | "17" | Abdulfattah
221 | Jessy, a project team member identifies a simple change that will improve product quality without impacting the project budget. What should you do as the project manager? | Have team members include it in their assignments as quickly as possible. | After reviewing the change, include it in the quality management plan. | Ask the sponsor for their advice regarding the suggested change. | Meet with the team member to assess the impact, and follow the change control process | The change does not impact the budget but maybe impact the other constraints.. SO the project manager should Meet with the team member to assess the impact, and follow the change control process .... [PMBOK 6th edition, Page.113] | يحدد جيسي ، أحد أعضاء فريق المشروع ، تغييرًا بسيطًا من شأنه تحسين جودة المنتج دون التأثير على ميزانية المشروع. ماذا يجب أن تفعل كمدير المشروع؟ | الطلب من أعضاء الفريق تضمينها في مهامهم في أسرع وقت ممكن. | بعد مراجعة التغيير ، يتم إدراجه في خطة إدارة الجودة. | الطلب من الراعي نصيحته بخصوص التغيير المقترح. | مقابلة عضو الفريق لتقييم الأثر ، واتباع عملية التحكم في التغيير | لا يؤثر التغيير على الميزانية ولكن ربما يؤثر على القيود الأخرى .. لذا يجب على مدير المشروع الاجتماع مع عضو الفريق لتقييم التأثير ، ومتابعة عملية التحكم في التغيير . [الطبعة السادسة ، صفحة 113 PMBOK] | 140 | 5 | False | "18" | Abdulfattah
222 | Levi is meeting with the seller's project manager to review their construction work. In this review Levi's focus is on the deliverables and a site walkthrough. What is this known as? | Performance review | Earned value analysis | Audit | Inspection | This is an inspection. In a performance review, resources, cost, schedule, and quality will be reviewed. Audits are related to the procurement process. [PMBOK 6th edition, Page.303] | يجتمع ليفي مع مدير مشروع البائع لمراجعة أعمال البناء. في هذا الاستعراض ، ينصب تركيز ليفي على المخرجات ومراجعة الموقع. ما هو هذا المعروف؟ | مراجعة الأداء | تحليل القيمة المكتسبة | تدقيق | تفتيش | هذا فحص. في مراجعة الأداء ، ستتم مراجعة الموارد والتكلفة والجدول الزمني والجودة. ترتبط عمليات التدقيق بعملية الشراء. [الطبعة السادسة ، صفحة 303 PMBOK] | 144 | 5 | False | "20" | Abdulfattah
223 | You are a project manager in the telecom project for your organization. Due to the lateness of workers' payments, the workers made a strike, causing delays in an important component delivery. What could have been done differently to prevent this type of situation? | Fast-Tracking | Crashing | Change management plan | What-If Scenario Analysis | Keyword ( strike ) What-if scenario analysis is the process of evaluating scenarios to predict their effect, positive or negative, on project objectives. A schedule network analysis is performed using the schedule to compute the different scenarios, such as delaying a major component delivery, extending specific engineering durations, or introducing external factors, such as a strike or a change in the permit process. The outcome of the what-if scenario analysis can be used to assess the feasibility of the project schedule under different conditions, and in preparing schedule reserves and response plans to address the impact of unexpected situations. [PMBOK 6th edition, Page 213] | أنت مدير مشروع في مشروع الاتصالات لمؤسستك. بسبب تأخر مدفوعات العمال ، قام العمال بإضراب ، مما تسبب في تأخير تسليم مكون مهم. ما الذي كان يمكن فعله بشكل مختلف لمنع هذا النوع من المواقف؟ | تسريع انشطة المشروع | حشد الموارد | خطة إدارة التغيير | تحليل السيناريو ماذا لو | الكلمات الرئيسية (اضراب) تحليل سيناريو ماذا لو هو عملية تقييم السيناريوهات للتنبؤ بتأثيرها ، الإيجابي أو السلبي ، على أهداف المشروع. يتم إجراء تحليل شبكة الجدول باستخدام الجدول الزمني لحساب السيناريوهات المختلفة ، مثل تأخير تسليم مكون رئيسي ، أو تمديد فترات هندسية معينة ، أو إدخال عوامل خارجية ، مثل الإضراب أو تغيير في عملية التصريح. يمكن استخدام نتيجة تحليل سيناريو ماذا لو لتقييم جدوى الجدول الزمني للمشروع في ظل ظروف مختلفة ، وفي إعداد احتياطيات الجدول الزمني وخطط الاستجابة لمعالجة تأثير المواقف غير المتوقعة. [الطبعة السادسة ، صفحة 213 PMBOK] | 142 | 3 | False | "17" | Abdulfattah
224 | You are a project manager for a company that provides catering services for events, each of which is managed as a project. The company is awarded a contract to cater a conference for 1,500 participants. The conference organizer conducts an inspection of the delivered food and beverages and discovers that 10 out of 10.000 soft drink bottles were out of date. Based on that, the conference organizer rejects the entire delivery. The project manager's company is now faced with replacement costs, the loss of credibility, and disrupted logistics. To what cost of quality (COQ) category do these costs belong? | Internal failure. | Appraisal. | Prevention | External failure. | Failure costs (internal/external). Costs related to nonconformance of the products, deliverables, or services to the needs or expectations of the stakeholders. [PMBOK 6th edition, Page.282] | أنت مدير مشروع لشركة تقدم خدمات تموين للمناسبات ، كل منها يُدار كمشروع. حصلت الشركة على عقد لخدمة مؤتمر لـ 1500 مشارك. يقوم منظم المؤتمر بإجراء فحص للأطعمة والمشروبات التي تم تسليمها ويكتشف أن 10 من أصل 10.000 زجاجة من المشروبات الغازية كانت قديمة. بناءً على ذلك ، يرفض منظم المؤتمر التسليم بالكامل. تواجه شركة مدير المشروع الآن تكاليف الاستبدال ، وفقدان المصداقية ، وتعطل الخدمات اللوجستية. إلى أي فئة تكلفة الجودة (COQ) تنتمي هذه التكاليف؟ | فشل داخلي. | الاختبارات | الوقاية | فشل خارجي. | تكاليف الفشل (داخلي / خارجي). التكاليف المتعلقة بعدم توافق المنتجات أو المخرجات أو الخدمات مع احتياجات أو توقعات أصحاب المصلحة. [الطبعة السادسة ، صفحة 282 PMBOK] | 144 | 3 | False | "19" | Abdulfattah
225 | Markus is working on an international project which involves 150 team members and the project budget is $1,400,000. The weekly status meeting is conducted worldwide and is scheduled for Wednesday at 5:00 PM and the duration of the meeting is two hours. All of the team members globally communicate using the video conferencing unit at their location. What kind of communication method is this? | Pull communication | Push communication | Push Pull communication | Interactive communication | Interactive communication is the most efficient way to ensure a common understanding by all participants on specified topics and is performed between two or more parties performing a multidirectional exchange of information. It includes meetings, phone calls, video conferencing to name a few. [PMBOK 6th edition, Page.372] | يعمل ماركوس في مشروع دولي يضم 150 عضوًا في الفريق وتبلغ ميزانية المشروع 1400000 دولار. يُعقد اجتماع الحالة الأسبوعي في جميع أنحاء العالم ومن المقرر عقده يوم الأربعاء الساعة 5:00 مساءً ومدة الاجتماع ساعتان. يتواصل جميع أعضاء الفريق على مستوى العالم باستخدام وحدة مؤتمرات الفيديو في مواقعهم. ما نوع طريقة الاتصال هذه؟ | سحب التواصل | دفع التواصل | دفع سحب الاتصال | التواصل التفاعلي | الاتصال التفاعلي هو الطريقة الأكثر فعالية لضمان فهم مشترك من قبل جميع المشاركين حول مواضيع محددة ويتم إجراؤه بين طرفين أو أكثر يقومون بتبادل متعدد الاتجاهات للمعلومات. وهي تشمل الاجتماعات والمكالمات الهاتفية ومؤتمرات الفيديو على سبيل المثال لا الحصر. [الطبعة السادسة ، صفحة 372 PMBOK] | 146 | 3 | False | "20" | Abdulfattah
226 | Ann is a member of a software team, she identified a potential nonconformance in some recently developed software The person who wrote the software disagrees. How should the project manager respond? | Wait until the next automated test which will identify if the defect exists. | Ask the member who discovered the problem to rectify it urgently so it is available in the next release. | Record the disagreement for discussion at the next retrospective. | Bring both resources together to discuss and resolve the issue immediately. | Bring both resources together to discuss and resolve the issue immediately. This is an example of the solve problem technique... [PMBOK 6th edition, Page.349] | آن هي عضو في فريق برمجيات ، وقد حددت عدم توافق محتمل في بعض البرامج التي تم تطويرها مؤخرًا. يختلف الشخص الذي كتب البرنامج. كيف يجب أن يستجيب مدير المشروع؟ | انتظار نتيجة الاختبار الآلي التالي الذي سيحدد ما إذا كان العيب موجودًا. | الطلب من العضو الذي اكتشف المشكلة أن يصححها على وجه السرعة حتى تكون متاحة في الإصدار التالي. | تسجيل الخلاف للمناقشة في المعرض التالي. | جمع كلا الموردين معًا لمناقشة المشكلة وحلها على الفور. | اجمع كلا الموردين معًا لمناقشة المشكلة وحلها على الفور. هذا مثال على تقنية حل المشكلة . [الطبعة السادسة ، صفحة 394 PMBOK] | 145 | 4 | False | "19" | Abdulfattah
227 | In a construction project, concrete is unable to be used because heavy rain affected its consistency. This possibility and its estimated costs were already identified in the risk register. How should the project manager fund the additional costs? | Apply the budget reserve | Request reserves from the client | Use the management reserve | Access the contingency reserve | Keyword ( already identified in the risk register ) ... Contingency reserves are the budget within the cost baseline that is allocated for identified risks. Contingency reserves are often viewed as part of the budget intended to address the known unknowns that can affect4 a project. [PMBOK 6th edition, Page 245] | في مشروع البناء ، لا يمكن استخدام الخرسانة لأن الأمطار الغزيرة أثرت على تناسقها. تم بالفعل تحديد هذه الاحتمالية وتكاليفها المقدرة في سجل المخاطر. كيف يجب على مدير المشروع تمويل التكاليف الإضافية؟ | تطبيق احتياطي الميزانية | طلب احتياطيات من العميل | استخدم احتياطي الإدارة | الوصول إلى احتياطي الطوارئ | الكلمة الرئيسية (التي تم تحديدها بالفعل في سجل المخاطر) ... احتياطيات الطوارئ هي الميزانية ضمن خط الأساس للتكلفة والمخصصة للمخاطر المحددة. غالبًا ما يُنظر إلى احتياطيات الطوارئ على أنها جزء من الميزانية التي تهدف إلى معالجة الأمور المجهولة المعروفة التي يمكن أن تؤثر على المشروع. [الطبعة السادسة ، صفحة 245 PMBOK] | 143 | 3 | False | "20" | Abdulfattah
228 | You are working in a matrix organization. A team members indicate that they are also assigned to work on other initiatives and can no longer devote any time to their assigned activities. As a project manager, what should you do first to resolve this issue? | Evaluate the impact and use optimizations techniques to compensate for the delay. | Escalate the problem to the sponsor who can assign more staff to work on the project. | Implement the change control process and reduce the project scope to include less deliverables. | Speak to the functional manager and determine alternatives to address these activities. | Since the team members assigned to work on other initiatives and can no longer devote any time to their assigned activities. The project manager should Speak to the functional manager and determine alternatives to address these activities. [PMBOK 6th edition, Page.332] | أنت تعمل في منظمة مصفوفة. يشير أعضاء الفريق إلى أنهم مكلفون أيضًا بالعمل في مبادرات أخرى ولم يعد بإمكانهم تخصيص أي وقت للأنشطة المخصصة لهم. بصفتك مدير مشروع ، ما الذي يجب عليك فعله أولاً لحل هذه المشكلة؟ | قالقيام بتقييم التأثير واستخدام تقنيات التحسينات لتعويض التأخير. | تصعيد المشكلة للراعي الذي يمكنه تعيين المزيد من الموظفين للعمل في المشروع. | تنفيذ عملية التحكم في التغيير وتقليل نطاق المشروع ليشمل مخرجات أقل. | تحدث إلى المدير الوظيفي وحدد البدائل لمعالجة هذه الأنشطة. | نظرًا لأن أعضاء الفريق المعينين للعمل في مبادرات أخرى ولم يعد بإمكانهم تخصيص أي وقت للأنشطة المخصصة لهم. يجب على مدير المشروع التحدث إلى المدير الوظيفي وتحديد البدائل لمعالجة هذه الأنشطة. [الطبعة السادسة ، صفحة 332 PMBOK] | 145 | 4 | False | "20" | Abdulfattah
229 | Sara is a project manager for a small project periodically engages resources for tasks in the project management plan. However, due to current budget, the resources can't be retained for the full project life cycle. According to project stakeholders, there is no additional budget available, so Sara must carefully plan how resources will be used to execute the project. What should Sara do to ensure effective project delivery while utilizing resources within budgeted limits? | Move budgeted funds from other project areas to mitigate any risk of gaps in assignments. | Create a budget change request for stakeholders before presenting project progress. | Identify those resources who can likely perform all necessary project tasks, and remove resources that are specialized. | Schedule similar tasks around the same time to limit the duration of resources' engagement. | Resource leveling can be used when shared or critically required resources are available only at certain times or in limited quantities, or are over allocated, such as when a resource has been assigned to two or more activities during the same time period (as shown in Figure 6-17), or there is a need to keep resource usage at a constant level. [PMBOK 6th edition, Page.211] | سارة هي مديرة مشروع لمشروع صغير تستخدم الموارد بشكل دوري لمهام في خطة إدارة المشروع. ومع ذلك ، بسبب الميزانية الحالية ، لا يمكن الاحتفاظ بالموارد لدورة حياة المشروع الكاملة. وفقًا لأصحاب المصلحة في المشروع ، لا توجد ميزانية إضافية متاحة ، لذلك يجب على سارة التخطيط بعناية لكيفية استخدام الموارد لتنفيذ المشروع. ما الذي يجب أن تفعله سارة لضمان التسليم الفعال للمشروع مع استخدام الموارد ضمن حدود الميزانية؟ | نقل تمويل الميزانية المعتمدة من مناطق المشروع الأخرى للتخفيف من أي مخاطر لحدوث فجوات في التخصيصات. | إنشاء طلب تغيير الميزانية لأصحاب المصلحة قبل تقديم تقدم المشروع. | تحديد تلك الموارد التي من المحتمل أن تؤدي جميع مهام المشروع الضرورية ، وقم بإزالة الموارد المتخصصة. | القيام بجدولة مهام مماثلة في نفس الوقت تقريبًا للحد من مدة مشاركة الموارد. | يمكن استخدام تسوية الموارد عندما تكون الموارد المشتركة أو المطلوبة بشكل حاسم متاحة فقط في أوقات معينة أو بكميات محدودة ، أو عندما يتم تخصيصها أكثر من اللازم ، كما هو الحال عندما يتم تخصيص مورد لنشاطين أو أكثر خلال نفس الفترة الزمنية (كما هو موضح في الشكل 6-17) ، أو هناك حاجة للحفاظ على استخدام الموارد عند مستوى ثابت. [الطبعة السادسة ، صفحة 211 PMBOK] | 142 | 3 | False | "18" | Abdulfattah
230 | A quality control member informs a you about a one-week schedule delay to complete the testing phase. What should you do next? | Crash the schedule. | Negotiate with the customer for a change in the schedule. | Take corrective action to minimize the impact of delay | Check whether this task is on the critical path. | Before you take corrective measures, determine the impact of the delay. For example, if the task has 3 weeks float, you do not need other options. [PMBOK 6th edition, Page.210] | يعلمك أحد أعضاء مراقبة الجودة بتأخير الجدول الزمني لمدة أسبوع واحد لإكمال مرحلة الاختبار. ماذا يجب ان تفعل بعد ذلك؟ | حشد الموارد للجدول. | تفاوض مع العميل لتغيير الجدول. | اتخاذ إجراءات تصحيحية لتقليل تأثير التأخير | التحقق مما إذا كانت هذه المهمة على المسار الحرج. | قبل اتخاذ الإجراءات التصحيحية ، حدد تأثير التأخير. على سبيل المثال ، إذا كانت المهمة تحتوي على 3 أسابيع ، فلن تحتاج إلى خيارات أخرى. [الطبعة السادسة ، صفحة 210 PMBOK] | 142 | 5 | False | "20" | Abdulfattah
231 | A project is terminated early, and you sends the final project report to relevant stakeholders. A senior manager is interested in understanding the impact and requests a copy of the report. What should you do? | Send the report to the finance manager. | Don't send the report since the project was prematurely terminated. | Review the stakeholder engagement plan and act accordingly. | Check the communication management plan and act accordingly. | The project manager should Check the communication management plan and act accordingly because it contains Stakeholder communication requirements and Persons or groups who will receive the information. [PMBOK 6th edition, Page 377] | يتم إنهاء المشروع مبكرًا ، وترسل تقرير المشروع النهائي إلى أصحاب المصلحة المعنيين. يهتم أحد كبار المديرين بفهم التأثير ويطلب نسخة من التقرير. ماذا عليك ان تفعل؟ | إرسال التقرير إلى المدير المالي. | لا ترسل التقرير حيث تم إنهاء المشروع قبل الأوان. | مراجعة خطة إشراك أصحاب المصلحة والتصرف وفقًا لذلك. | تحقق من خطة إدارة الاتصالات وتصرف وفقًا لذلك. | يجب على مدير المشروع التحقق من خطة إدارة الاتصالات والتصرف وفقًا لذلك لأنها تحتوي على متطلبات الاتصال مع أصحاب المصلحة والأشخاص أو المجموعات التي ستتلقى المعلومات. [الطبعة السادسة ، صفحة 377 PMBOK] | 146 | 3 | False | "18" | Abdulfattah
232 | Which of the following analysis techniques is recommended when you need to analyze project stakeholders based on their power, urgency, and legitimacy and usefulness for large complex communities of stakeholders or where there are complex networks of relationships within the community? | Power/interest grid | Power/influence grid | Influence/impact grid | Salience model | Salience model. Describes classes of stakeholders based on assessments of their power (level of authority or ability to influence the outcomes of the project), urgency (need for immediate attention, either time-constrained or relating to the stakeholders' high stake in the outcome), and legitimacy (their involvement is appropriate). There is an adaptation of the salience model that substitutes proximity for legitimacy (applying to the team and measuring their level of involvement with the work of the project). The salience model is useful for large complex communities of stakeholders or where there are complex networks of relationships within the community. [PMBOK 6th edition, Page 513] | أي من تقنيات التحليل التالية يوصى به عندما تحتاج إلى تحليل أصحاب المصلحة في المشروع بناءً على قوتهم وإلحاحهم وشرعيتهم وفائدتهم للمجتمعات الكبيرة المعقدة من أصحاب المصلحة أو عندما تكون هناك شبكات معقدة من العلاقات داخل المجتمع؟ | شبكة السلطة / الاهتمام | شبكة السلطة / النفوذ | شبكة التاثير / النفوذ | نموذج البارز | النموذج البارز. يصف فئات أصحاب المصلحة بناءً على تقييمات قوتهم (مستوى السلطة أو القدرة على التأثير على نتائج المشروع) ، والإلحاح (الحاجة إلى الاهتمام الفوري ، سواء كانت محدودة الوقت أو تتعلق بالمشاركة الكبيرة لأصحاب المصلحة في النتيجة) ، و الشرعية (مشاركتهم مناسبة). هناك تعديل للنموذج البارز الذي يستبدل القرب بالشرعية (التقديم على الفريق وقياس مستوى مشاركته في عمل المشروع). نموذج البروز مفيد للمجتمعات الكبيرة المعقدة من أصحاب المصلحة أو حيث توجد شبكات معقدة من العلاقات داخل المجتمع. [الطبعة السادسة ، صفحة 513 PMBOK] | 149 | 2 | False | "18" | Abdulfattah
233 | You have been hired for a new project, and the project charter has already been approved. What documentation is needed to prepare for the kick-off meeting? | Quality management plan | Scope management plan | Business case | Project management plan | The Project management plan approval is needed before the kick-off meeting.... [PMBOK 6th edition, Page.86] | لقد تم تعيينك لمشروع جديد ، وتمت الموافقة على ميثاق المشروع بالفعل. ما هي الوثائق المطلوبة للتحضير لاجتماع الافتتاحي لانطلاق المشروع؟ | خطة إدارة الجودة | خطة إدارة النطاق | مستند حالة الأعمال | خطة إدارة المشروع | الموافقة على خطة إدارة المشروع مطلوبة قبل الاجتماع الافتتاحي لانطلاق المشروع . [الطبعة السادسة ، صفحة 86 PMBOK] | 140 | 3 | False | "20" | Abdulfattah
234 | The project manager of a strategic project was approached by the CEO who expressed concern that the project will not be worth the investment. What document should the project manager ask the CEO to review? | Cost management plan | Signed project charter | Company's business plan | Approved business case | The project business case is a documented economic feasibility study used to establish the validity of the benefits of a selected component lacking sufficient definition and that is used as a basis for the authorization of further project management activities.... The business case describes the necessary information from a business standpoint to determine [PMBOK 6th edition, Page.77] | تم الاتصال بمدير مشروع استراتيجي من قبل الرئيس التنفيذي الذي أعرب عن قلقه من أن المشروع لن يستحق الاستثمار. ما هي الوثيقة التي يجب أن يطلب مدير المشروع من الرئيس التنفيذي مراجعتها؟ | خطة إدارة التكلفة | توقيع ميثاق المشروع | خطة عمل الشركة | مستند حالة الاعمال المعتمدة | دراسة جدوى المشروع عبارة عن دراسة جدوى اقتصادية موثقة تستخدم لإثبات صحة فوائد المكون المحدد الذي يفتقر إلى التعريف الكافي والذي يستخدم كأساس للترخيص لمزيد من أنشطة إدارة المشروع ... تصف دراسة الجدوى الضرورة معلومات من وجهة نظر الأعمال لتحديد. [الطبعة السادسة ، صفحة 77 PMBOK] | 140 | 2 | False | "20" | Abdulfattah
235 | The customer rejects some type of deliverables, although many of the requirements are met. After conducting a root cause analysis, the project manager learns that a specific quality control process was not performed due to a lack of resources. What should the project manager have done to avoid this? | Created quality checklists. | Held quality control process meetings. | Requested more resources for quality control activity | Ensured that quality was managed | The root cause of this problem is the lack of resources. SO this is related to manage quality .. so the project manager should have ensured that quality was managed correctly to prevent this issue. [PMBOK 6th edition, Page.288] | يرفض العميل نوعًا من التسليمات ، على الرغم من استيفاء العديد من المتطلبات. بعد إجراء تحليل السبب الجذري ، يعلم مدير المشروع أنه لم يتم تنفيذ عملية مراقبة جودة محددة بسبب نقص الموارد. ما الذي كان يجب على مدير المشروع فعله لتجنب ذلك؟ | إنشاء قوائم مراجعة الجودة. | عقد اجتماعات عملية مراقبة الجودة. | طلب المزيد من الموارد لنشاط مراقبة الجودة | تأكد من أن الجودة تمت إدارتها | السبب الجذري لهذه المشكلة هو نقص الموارد. لذا فإن هذا مرتبط بإدارة الجودة .. لذلك كان على مدير المشروع التأكد من أن الجودة قد تمت إدارتها بشكل صحيح لمنع حدوث هذه المشكلة. [الطبعة السادسة ، صفحة 288 PMBOK] | 144 | 4 | False | "20" | Abdulfattah
236 | After a project's first status meeting, the team realizes that the tasks are more complex than the project leader programmed . What should the project manager do to address this? | Make changes to the original plan. | Hire more people for the critical path. | Use the fast tracking technique | Prepare a change request. | To address this situation, the project manager should Make changes to the original plan but FIRST he should Prepare a change request then analyze the impact on project constraints and get approval by CCB [PMBOK 6th edition, Page.96] | بعد اجتماع الحالة الأول للمشروع ، يدرك الفريق أن المهام أكثر تعقيدًا من قائد المشروع المبرمج. ماذا يجب أن يفعل مدير المشروع لمعالجة هذا؟ | القيام بإجراء تغييرات على الخطة الأصلية. | توظيف المزيد من الأشخاص للعمل في انشطة المسار الحرج. | استخدم تقنية تسريع الانشطة | الاعداد لطلب التغيير. | لمعالجة هذا الموقف ، يجب على مدير المشروع إجراء تغييرات على الخطة الأصلية ولكن يجب أولاً إعداد طلب التغيير ثم تحليل التأثير على قيود المشروع والحصول على موافقة لجنة التحكم في التغيير. [الطبعة السادسة ، صفحة 96 PMBOK] | 140 | 4 | False | "19" | Abdulfattah
237 | You are managing a process improvement project for your company. You need to analyze over 20 of the company's processes to identify weaknesses and give your recommendations for improvement. Which of the following techniques can you use to analyze these processes? | Cost-Benefit Analysis | Reserve Analysis | EMV Analysis | Process Analysis | Process analysis. Process analysis identifies opportunities for process improvements. This analysis also examines problems, constraints, and non-value-added activities that occur during a process. [PMBOK 6th edition, Page.292] | أنت تدير مشروع لتحسين العمليات لشركتك. تحتاج إلى تحليل أكثر من 20 عملية من عمليات الشركة لتحديد نقاط الضعف وتقديم توصياتك للتحسين. أي من الأساليب التالية يمكنك استخدامه لتحليل هذه العمليات؟ | تحليل التكاليف مقابل المنفعة | تحليل الاحتياطي | تحليل ادارة القيمة المكتسبة | عملية التحليل | عملية التحليل. يحدد عملية التحليل فرص تحسين العملية. يفحص هذا التحليل أيضًا المشكلات والقيود والأنشطة غير ذات القيمة المضافة التي تحدث أثناء العملية. [الطبعة السادسة ، صفحة 292 PMBOK] | 144 | 4 | False | "19" | Abdulfattah
238 | As a project manager for your company, two team members come to you with a dispute regarding who will perform and report the status of a particular task. To resolve the conflict, which document will you refer to? | Stakeholder register | Project sponsor. | Functional manager | Responsible, accountable, consult, and inform (RACI) matrix. | Assignment Matrix (RAM) or (RACI) matrix , shows the connection between work packages or activities and team members. RAM Matrix can be used to define the responsibilities of groups or any individual team member. [PMBOK 6th edition, Page 317] | بصفتك مدير مشروع لشركتك ، يأتي إليك اثنان من أعضاء الفريق لمناقشة نزاع بشأن من سيقوم بأداء مهمة معينة والإبلاغ عنها. لحل النزاع ، ما المستند الذي ستشير إليه؟ | سجل أصحاب المصلحة | راعي المشروع. | مدير وظيفي | مصفوفة تعيين المسؤوليات. المسؤولية والمحاسبة والتشاور والإبلاغ (RACI). | تُظهر مصفوفة تعيين المسؤوليات العلاقة بين حزم العمل أو الأنشطة وأعضاء الفريق. يمكن استخدام مصفوفة تعيين المسؤوليات لتحديد مسؤوليات المجموعات أو أي فرد من أعضاء الفريق. [الطبعة السادسة ، صفحة 317 PMBOK] | 145 | 3 | False | "16" | Abdulfattah
239 | In a project to develop a new product, The project has fallen behind schedule because team members are lacking motivation. What should the project manager do to motivate the project team? | Use coaching and monitoring skills. | Delegates the responsibilities. | Apply creative problem solving. | Offer recognition and rewards. | The team members are lacking motivation. SO the best thing should the project manager do to motivate them is to Offer recognition and rewards. People are motivated when they feel they are valued in the organization and this value is demonstrated by the rewards given to them. Generally, money is viewed as a tangible aspect of any reward system, but intangible rewards could be equally or even more effective. Most project team members are motivated by an opportunity to grow, accomplish, be appreciated, and apply their professional skills to meet new challenges. A good strategy for project managers is to give the team recognition throughout the life cycle of the project rather than waiting until the project is completed. [PMBOK 6th edition Page, 342] | في مشروع تطوير منتج جديد ، تأخر المشروع عن الجدول الزمني لأن أعضاء الفريق يفتقرون إلى الحافز. ما الذي يجب على مدير المشروع فعله لتحفيز فريق المشروع؟ | استخدم مهارات التدريب والمراقبة. | تفويض المسؤوليات. | تطبيق حل المشكلات الإبداعي. | تقديم التقدير والمكافآت. | أعضاء الفريق يفتقرون إلى الحافز. لذا فإن أفضل شيء يجب أن يفعله مدير المشروع لتحفيزهم هو تقديم التقدير والمكافآت. يتم تحفيز الأشخاص عندما يشعرون بالتقدير في المنظمة ويتم إظهار هذه القيمة من خلال المكافآت الممنوحة لهم. بشكل عام ، يُنظر إلى المال على أنه جانب ملموس لأي نظام مكافأة ، ولكن المكافآت غير الملموسة يمكن أن تكون متساوية أو حتى أكثر فعالية. يتم تحفيز معظم أعضاء فريق المشروع من خلال فرصة للنمو والإنجاز والتقدير وتطبيق مهاراتهم المهنية لمواجهة التحديات الجديدة. تتمثل الإستراتيجية الجيدة لمديري المشروع في منح الفريق تقديرًا طوال دورة حياة المشروع بدلاً من الانتظار حتى اكتمال المشروع. [الطبعة السادسة ، صفحة 342 PMBOK] | 145 | 4 | False | "18" | Abdulfattah
240 | Mayra is a project manager who is deep into project execution. Currently, she is looking for information about the quality management issues that have been escalated by the team, as well as recommendations for process, project, and product improvements. What should she do? | Review the issue log | Review the quality management plan | Review the Risk register | Review the quality reports | According to the scenario, he is looking for information about the quality management issues that have been escalated by the team as well as recommendations for process, project, and product improvements. This is the description of a quality report. Quality reports are an output of the Manage Quality process and include information that can be used by other processes and departments to take corrective actions in order to achieve the project quality objectives. [PMBOK 6th edition, Page 296] | مايرا هي مديرة مشروع في اثناء مرحلة تنفيذ المشروع. في الوقت الحالي ، تبحث عن معلومات حول مشكلات إدارة الجودة التي تم تصعيدها من قبل الفريق ، بالإضافة إلى توصيات للعملية والمشروع وتحسينات المنتج. ماذا تفعل؟ | مراجعة سجل المشاكل | مراجعة خطة إدارة الجودة | مراجعة سجل المخاطر | مراجعة تقارير الجودة | وفقًا للسيناريو ، فهي تبحث عن معلومات حول مشكلات إدارة الجودة التي تم تصعيدها من قبل الفريق بالإضافة إلى توصيات للعملية والمشروع وتحسينات المنتج. هذا هو وصف تقرير الجودة. تقارير الجودة هي نتاج لعملية إدارة الجودة وتتضمن المعلومات التي يمكن استخدامها من قبل العمليات والإدارات الأخرى لاتخاذ إجراءات تصحيحية من أجل تحقيق أهداف جودة المشروع. [الطبعة السادسة ، صفحة 296 PMBOK] | 144 | 4 | False | "20" | Abdulfattah
241 | During regular team meetings, you notices that there are clear signs of conflict and issues related to unclear task assignments and ownership. What should you as a project manager do to address this? | Change the structure of the regular project meetings to improve communication. | Investigate possible ways to improve team collaboration and morale. | Meet individually with team members to understand the conflicts and issues. | Define and obtain agreement on a responsible accountable, consult, and inform RACI Matrix. | A RACI Matrix is a useful tool to use to ensure clear assignment of roles and responsibilities when the team consists of internal and external resources. SO the project manager should Define and obtain agreement on a responsible accountable, consult, and inform RACI Matrix to address this situation. [PMBOK 6th edition, Page.317] | أثناء اجتماعات الفريق المنتظمة ، تلاحظ وجود علامات واضحة على التضارب والمشكلات المتعلقة بتعيينات المهام غير الواضحة والملكية. ما الذي يجب عليك فعله كمدير مشروع لمعالجة هذا الأمر؟ | تغيير هيكل اجتماعات المشروع العادية لتحسين الاتصال. | استكشاف الطرق الممكنة لتحسين التعاون الجماعي والروح المعنوية. | اجتمع بشكل فردي مع أعضاء الفريق لفهم الخلافات والقضايا. | تحديد والحصول على اتفاق بشأن مصفوفة تعيين المسؤوليات. | تعتبر مصفوفة تعيين المسؤوليات أداة مفيدة لاستخدامها لضمان تعيين واضح للأدوار والمسؤوليات عندما يتكون الفريق من موارد داخلية وخارجية. يجب على مدير المشروع تحديد والحصول على اتفاق بشأن مسؤول مسؤول ، والتشاور ، وإبلاغ RACI Matrix لمعالجة هذا الموقف. [الطبعة السادسة ، صفحة 317 PMBOK] | 145 | 3 | False | "17" | Abdulfattah
242 | Jessi is the project manager for a mobile application development project. At the end of the project kick-off meeting, what is the next phase? | Monitoring and Controlling | Closing | Planning | Executing | Explanation The project kick-off meeting is usually associated with the end of planning, so the next phase is Executing. [PMBOK 6th edition, Page 86] | جيسي هو مدير مشروع تطوير تطبيقات الهاتف المحمول. في نهاية الاجتماع انطلاق للمشروع ، ما هي المرحلة التالية؟ | التحكم ومراقبة | الإغلاق | التخطيط | التنفيذ | الشرح عادة ما يرتبط اجتماع إطلاق المشروع بنهاية التخطيط ، وبالتالي فإن المرحلة التالية هي التنفيذ. [الطبعة السادسة ، صفحة 86 PMBOK] | 140 | 3 | False | "20" | Abdulfattah
243 | Now, you wish to track the performance of individual members and optimize the team's performance. After you have completed resource planning and acquired resources and improved the team competency and performance. Which process will you perform? | Control Resources | Develop Team | Team building | Manage Team | All this is performed in the Manage Team process. [PMBOK 6th edition, Page.345] | الآن ، ترغب في تتبع أداء الأعضاء الفرديين وتحسين أداء الفريق. بعد الانتهاء من تخطيط الموارد واكتساب الموارد وتحسين كفاءة الفريق وأدائه. ما هي العملية التي ستقوم بها؟ | التحكم بالموارد | تطوير الفريق | بناء الفريق | إدارة الفريق | يتم تنفيذ كل هذا في عملية إدارة الفريق. [الطبعة السادسة ، صفحة 345 PMBOK] | 145 | 4 | False | "19" | Abdulfattah
244 | Midway of your project and working on a deliverable which is 90% completed. It is time for the yearly audit. A team of auditors are about to come and verify if you are following the process as defined or not. However, as the deliverable is about to be completed, you check it and measure all dimensions to find any possible dimensional defects. What process is this? | Manage quality | Plan quality management | Control scope | Control quality | In the quality control process, you inspect the deliverable for any possible defects. As you are doing an inspection, you are in the quality control process. Please note that although the quality audit is performed in the manage quality process, it has not started yet and you are doing an inspection, which is a tool of the quality control process. [PMBOK 6th edition, Page 303] | في منتصف مشروعك والعمل على إنجاز 90٪. حان الوقت للتدقيق السنوي. فريق من المراجعين على وشك القدوم والتحقق مما إذا كنت تتبع العملية كما هو محدد أم لا. ومع ذلك ، نظرًا لأن التسليم على وشك الانتهاء ، يمكنك التحقق منه وقياس جميع الأبعاد للعثور على أي عيوب محتملة في الأبعاد. ما هذه العملية؟ | إدارة الجودة | خطة إدارة جودة | التحكم بالنطاق | التحكم بالجودة | في عملية مراقبة الجودة ، تقوم بفحص المنتج بحثًا عن أي عيوب محتملة. أثناء قيامك بالفحص ، فأنت في عملية مراقبة الجودة. يرجى ملاحظة أنه على الرغم من إجراء تدقيق الجودة في عملية إدارة الجودة ، إلا أنه لم يبدأ بعد وأنت تقوم بإجراء فحص ، وهو أداة لعملية مراقبة الجودة. [الطبعة السادسة ، صفحة 303 PMBOK] | 144 | 5 | False | "19" | Abdulfattah
245 | Mustafa is a project manager of the civil project for your organization. In this project, you are currently performing quantitative risk analysis. The tool and technique you are using is a simulation where the project model is computed many times with the input values chosen at random for each iteration and Outputs representing the range of possible outcomes for the project. The goal is to create a probability distribution from the iterations for the project schedule. What technique will you use with this simulation? | Pareto charts | Expected Monetary Value | Cause and effect diagram | Monte Carlo Technique | Quantitative risk analysis uses a model that simulates the combined effects of individual project risks and other sources of uncertainty to evaluate their potential impact on achieving project objectives. Simulations are typically performed using a Monte Carlo analysis. [PMBOK 6th edition, Page.433] | مصطفى هو مدير مشروع مشروع مدني لمنظمتك. في هذا المشروع ، تقوم حاليًا بإجراء تحليل كمي للمخاطر. الأداة والتقنية التي تستخدمها هي محاكاة حيث يتم حساب نموذج المشروع عدة مرات باستخدام قيم الإدخال المختارة عشوائيًا لكل تكرار ومخرجات تمثل نطاق النتائج المحتملة للمشروع. الهدف هو إنشاء توزيع احتمالي من التكرارات لجدول المشروع. ما هي التقنية التي ستستخدمها مع هذه المحاكاة؟ | مخططات باريتو | القيمة النقدية المتوقعة | مخطط السبب والتأثير | تقنية مونت كارلو | يستخدم التحليل الكمي للمخاطر نموذجًا يحاكي الآثار المجمعة لمخاطر المشروع الفردية وغيرها من مصادر عدم اليقين لتقييم تأثيرها المحتمل على تحقيق أهداف المشروع. يتم إجراء عمليات المحاكاة عادةً باستخدام تحليل مونت كارلو. [الطبعة السادسة ، صفحة 443 PMBOK] | 147 | 3 | False | "18" | Abdulfattah
246 | Lisa has only a short timeframe in which to complete a project's cost estimation. What estimating technique should Lisa use? | Bottom up | Three point | Critical Path Method | Analogous | Analogous cost estimating uses values, or attributes, of a previous project that are similar to the current project. [PMBOK 6th edition, Page.244] | ليس لدى ليزا سوى إطار زمني قصير لإكمال تقدير تكلفة المشروع. ما هي تقنية التقدير التي يجب أن تستخدمها ليزا؟ | تصاعدي | ثلاث نقاط | طريقة المسار الحرج | مماثل | يستخدم تقدير التكلفة المتماثل قيمًا أو سمات لمشروع سابق تشبه المشروع الحالي. [الطبعة السادسة ، صفحة 244 PMBOK] | 143 | 3 | False | "18" | Abdulfattah
247 | Calculate the expected activity duration based on the following three-point estimates: Optimistic =18 days, Most Likely = 22days, Pessimistic = 27days. Using a triangular distribution formula. | 21.33 | 22.11 | 23.2 | 22.33 | uses a triangular distribution is as follows: (Optimistic + Pessimistic + Most Likely) ÷ 3. Plug in the values provided to calculate the following: (18 + 22 + 27) ÷ 3 = 22.33 days [PMBOK 6th edition, Page.201] | احسب مدة النشاط المتوقعة بناءً على تقديرات النقاط الثلاث التالية: متفائل = 18 يومًا ، الأرجح = 22 يومًا ، متشائمًا = 27 يومًا. باستخدام صيغة التوزيع المثلثية. | 21.33 | 22.11 | 23.2 | 22.33 | يستخدم التوزيع الثلاثي على النحو التالي: (متفائل + متشائم + الأرجح) ÷ 3. أدخل القيم المقدمة لحساب التالي: (18 + 22 + 27) ÷ 3 = 22.33 يومًا. [الطبعة السادسة ، صفحة 201 PMBOK] | 142 | 3 | False | "19" | Abdulfattah
248 | You are estimating the number of work periods needed to complete individual activities with estimated resources. One of the documents you are using contains information on categories of labor, material, and equipment required to complete your project. What is this document known as: | Resource Calendars | Organization breakdown structure (OBS) | RACI Chart | Resource breakdown structure ( RBS ) | Based on the scenario described, the project team is performing the Estimate Activity Durations process. An input to this process is the resource breakdown structure (RBS) which is a hierarchical list of team and physical resources related by category and resource type that is used for planning, managing, and controlling project work. Each descending level represents an increasingly detailed description of the resource until the information is small enough to be used in conjunction with the WBS to allow the work to be planned, monitored, and controlled. [PMBOK 6th edition, Page 198] | أنت تقدر عدد فترات العمل المطلوبة لإكمال الأنشطة الفردية بالموارد المقدرة. تحتوي إحدى المستندات التي تستخدمها على معلومات حول فئات العمالة والمواد والمعدات المطلوبة لإكمال مشروعك. ما هي هذه الوثيقة المعروفة باسم: | تقويم الموارد | الهيكل التنظيمي (OBS) | مخطط مصفوفة تعيين المسؤوليات RACI | هيكل توزيع الموارد (RBS) | بناءً على السيناريو الموضح ، يقوم فريق المشروع بتنفيذ عملية تقدير مدد النشاط. أحد المدخلات في هذه العملية هو هيكل تقسيم الموارد (RBS) وهو عبارة عن قائمة هرمية من الفريق والموارد المادية المرتبطة حسب الفئة ونوع المورد المستخدمة للتخطيط والإدارة والتحكم في عمل المشروع. يمثل كل مستوى تنازلي وصفًا تفصيليًا متزايدًا للمورد حتى تصبح المعلومات صغيرة بما يكفي لاستخدامها مع هيكل تجزئة الموارد للسماح بتخطيط العمل ومراقبته والتحكم فيه. [الطبعة السادسة ، صفحة 198 PMBOK] | 142 | 3 | False | "20" | Abdulfattah
249 | The building of a commercial mall has been stopped for four months due to region-specific prohibitions. What should the project manager have done to avoid this issue? | Documented all assumptions | Crashed the project schedule | Made a prioritized list of the project constraints | Identified this as a risk in the risk register | It is clear that this country has prohibitions... The project manager should have Identified this as a risk in the risk register, analyze the risk and plan risk response To avoid or mitigate this risk... [PMBOK 6th edition, Page.417] | تم إيقاف بناء مركز تجاري لمدة أربعة أشهر بسبب المحظورات الخاصة بالمنطقة. ما الذي كان يجب على مدير المشروع فعله لتجنب هذه المشكلة؟ | توثيق جميع الافتراضات | حشد الموارد للجدول الزمني للمشروع | تقديم قائمة أولويات لقيود المشروع | تحديد هذا الخطر في سجل المخاطر | من الواضح أن هذا البلد لديه محظورات ... كان ينبغي على مدير المشروع تحديد هذا على أنه خطر في سجل المخاطر ، وتحليل المخاطر والتخطيط للاستجابة للمخاطر لتجنب أو تخفيف هذه المخاطر .[الطبعة السادسة ، صفحة 417 PMBOK] | 147 | 3 | False | "20" | Abdulfattah
250 | Tid is a project manager in an IT project. During the deployment of a new system, an unexpected power outage occurs. What should the Tid do? | Risk categorization | Risk probability and impact assessment | Perform a qualitative risk analysis | Refer to the risk register and inform key stakeholders | As an unexpected power outage occurs, the project manager should first Refer to the risk register and inform key stakeholders to handle this scenario. Risk categorization and Risk probability and Impact assessment are T&T in Perform a qualitative risk analysis process, therefore they can be excluded. [PMBOK 6th edition, Page.417] | تيد مدير مشروع في مشروع تكنولوجيا المعلومات. أثناء نشر نظام جديد ، يحدث انقطاع غير متوقع للتيار الكهربائي. ماذا يجب أن يفعل تيد؟ | تصنيف المخاطر | احتمالية المخاطر وتقييم الأثر | قم بإجراء تحليل نوعي للمخاطر | الرجوع إلى سجل المخاطر وإبلاغ أصحاب المصلحة الرئيسيين | عند حدوث انقطاع غير متوقع للتيار الكهربائي ، يجب على مدير المشروع الرجوع أولاً إلى سجل المخاطر وإبلاغ أصحاب المصلحة الرئيسيين للتعامل مع هذا السيناريو. تصنيف المخاطر واحتمالية المخاطر وتقييم الأثر هي احد الادوات والتقنيات المستخدمة في إجراء عملية تحليل مخاطر نوعية ، وبالتالي يمكن استبعادها. [الطبعة السادسة ، صفحة 417 PMBOK] | 147 | 3 | False | "16" | Abdulfattah
251 | The project manager forgot to archive the project document at the closing process. What is the benefit of the archive project document? | Collecting lessons learned | Update the organization's knowledge base. | Update the OPA | For potential use in future projects and audits. | Archive project documents and materials using generally accepted practices in order to comply with statutory requirements, for potential use in future projects, and audits. PMP Exam Content Outline in ( Closing ) task no. 6 [PMBOK 6th edition, Page.121] | نسي مدير المشروع أرشفة وثيقة المشروع في عملية الإغلاق. ما فائدة وثيقة مشروع الأرشيف؟ | جمع الدروس المستفادة | تحديث القاعدة المعرفية للمنظمة. | القيام بتحديث اصول العمليات التنظيمية | للاستخدام المحتمل في المشاريع وعمليات التدقيق المستقبلية. | أرشفة مستندات ومواد المشروع باستخدام الممارسات المقبولة عمومًا من أجل الامتثال للمتطلبات القانونية ، للاستخدام المحتمل في المشاريع المستقبلية ، وعمليات التدقيق. [الطبعة السادسة ، صفحة 121 PMBOK] | 140 | 6 | False | "19" | Abdulfattah
252 | The sponsor complains about the quality of some deliverables. The project manager believes that these deliverables meet the project's quality standards. What tool or technique should the project manager use to support this? | Scatter diagrams | Cause-and-effect diagrams | Histograms | Control charts | Control charts are used to determine whether or not a process is stable or has predictable performance. Upper and lower specification limits are based on the requirements and reflect the maximum and minimum values allowed. The control limits are determined using standard statistical calculations and principles to ultimately establish the natural capability for a stable process... Control chart shows upper and lower limits of the product quality which have been defined based on the quality management plan and those limits will show if the product within or without the quality predefined standards.. this will support PM believes the product match the quality standard... SO the Control charts is the correct answer. [PMBOK 6th edition Page, 304] | يشكو الراعي من جودة بعض الإنجازات. يعتقد مدير المشروع أن هذه النتائج تلبي معايير جودة المشروع. ما الأداة أو التقنية التي يجب أن يستخدمها مدير المشروع لدعم ذلك؟ | مخططات التشتت | مخططات السبب والتأثير | الرسوم البيانية التوزيعية | مخططات التحكم | تُستخدم مخططات التحكم لتحديد ما إذا كانت العملية مستقرة أو لها أداء يمكن التنبؤ به أم لا. تعتمد حدود المواصفات العليا والسفلى على المتطلبات وتعكس القيم القصوى والدنيا المسموح بها. يتم تحديد حدود التحكم باستخدام الحسابات والمبادئ الإحصائية القياسية لإنشاء القدرة الطبيعية في النهاية على عملية مستقرة ... يوضح مخطط التحكم الحدود العليا والسفلى لجودة المنتج التي تم تحديدها بناءً على خطة إدارة الجودة وستظهر هذه الحدود إذا كان المنتج داخل أو بدون معايير الجودة المحددة مسبقًا. فهذا سيدعم مدير المشروع يعتقد أن المنتج يتوافق مع معايير الجودة . لذا فإن مخططات التحكم هي الإجابة الصحيحة. [الطبعة السادسة ، صفحة 304 PMBOK] | 144 | 5 | False | "19" | Abdulfattah
253 | Suzi is a new project manager on a project with a very tight budget, she is struggling as they have no experience working on this type of project. What can the project manager do to mitigate the lack of experience? | Ask for support from more senior project managers. | Review the lessons learned repository of similar projects. | Request reassignment to a different type of project. | Seek external training | The organization did not have experience. So options ( Review the lessons learned repository of similar projects. and Ask for support from more senior project managers ) not correct ... SO the project manager should Seek external training to mitigate the lack of experience .... The organization may cover the cost of training if required and if added skills will be useful in future projects.... [PMBOK 6th edition, Page.342] | سوزي هي مديرة مشروع جديدة في مشروع بميزانية محدودة للغاية ، فهي تكافح لأنها لا تملك خبرة في العمل في هذا النوع من المشاريع. ما الذي يمكن أن يفعله مدير المشروع للتخفيف من نقص الخبرة؟ | اطلب الدعم من كبار مديري المشروع. | مراجعة الدروس المستفادة السابقة من المشاريع المماثلة. | طلب إعادة التعيين إلى نوع مختلف من المشروع. | ابحث عن تدريب خارجي | لم يكن لدى المنظمة خبرة. لذا فإن الخيارات (راجع مستودع الدروس المستفادة من المشاريع المماثلة. واطلب الدعم من المزيد من كبار مديري المشاريع) غير صحيحة ... لذا يجب على مدير المشروع طلب تدريب خارجي للتخفيف من نقص الخبرة ... قد تغطي المنظمة تكلفة التدريب إذا لزم الأمر وإذا كانت المهارات المضافة ستكون مفيدة في المشاريع المستقبلية. [الطبعة السادسة ، صفحة 342 PMBOK] | 145 | 4 | False | "20" | Abdulfattah
254 | As a project manager, you notice one of your team members doesn't finish his tasks on time. What should you do next? | Meeting with the project team members and evaluate the impact on the project. | Schedule training sessions for the team member to optimize his performance. | Release a team member | Conduct One-on-One Meeting with the team member | The first step is to Conduct One-on-One Meeting with the team member to understand why he leaves the site early and why he does not finish his tasks on time. [PMBOK 6th edition, Page.342] | بصفتك مدير مشروع ، لاحظت أن أحد أعضاء فريقك لا ينهي مهامه في الوقت المحدد. ماذا يجب ان تفعل بعد ذلك؟ | لقاء مع أعضاء فريق المشروع وتقييم الأثر على المشروع. | القيام بجدولة جلسات تدريبية لعضو الفريق لتحسين أدائه. | الاستغناء عن أحد أعضاء الفريق | القيام بإجراء اجتماع فردي مع عضو الفريق | تتمثل الخطوة الأولى في إجراء اجتماع فردي مع عضو الفريق لفهم سبب مغادرته للموقع مبكرًا ولماذا لا ينهي مهامه في الوقت المحدد. [الطبعة السادسة ، صفحة 342 PMBOK] | 145 | 4 | False | "18" | Abdulfattah
255 | Alan is a project manager, he joins a project that is involved with an industry in which he have little experience. An urgent issue is raised on the software development portion of the project. From whom should the project manager request direction? | Development team | Project management office | All Stakeholders | Internal subject matter experts | Since the project manager has little experience, the project manager should request direction from Internal subject matter experts that familiar with this portion of the project and industry. [PMBOK 6th edition, Page.104] | آلان هو مدير مشروع ، وينضم إلى مشروع له علاقة بصناعة ليس لديه سوى خبرة قليلة فيها. أثيرت قضية عاجلة بشأن جزء تطوير البرمجيات من المشروع. من الذي يجب أن يطلب مدير المشروع التوجيه؟ | فريق التطوير | مكتب ادارة المشروع | جميع أصحاب المصلحة | الاستعانة بالخبراء من الداخل | نظرًا لأن مدير المشروع لديه خبرة قليلة ، يجب على مدير المشروع أن يطلب التوجيه من خبراء الموضوع الداخليين المطلعين على هذا الجزء من المشروع والصناعة. [الطبعة السادسة ، صفحة 104 PMBOK] | 140 | 4 | False | "20" | Abdulfattah
256 | A methods in the Control Schedule process is used to compute different scenarios to get the project realigned with the Project Management Plan. What is this method called? | Corrective Action | Delphi Technique | Pareto Chart | What if Scenario analysis | What if scenario analysis is a type of modeling technique, which can be used along with risk monitoring to review various scenarios and bring the schedule into alignment with the Project Management Plan. [PMBOK 6th edition, Page.227] | يتم استخدام طرق في عملية جدول التحكم لحساب سيناريوهات مختلفة لإعادة تنسيق المشروع مع خطة إدارة المشروع. ماذا تسمى هذه الطريقة؟ | اجراء تصحيحي | تقنية دلفي | مخطط باريتو | تحليل السيناريو ماذا لو كان | ماذا لو كان تحليل السيناريو نوعًا من تقنيات النمذجة ، والتي يمكن استخدامها جنبًا إلى جنب مع مراقبة المخاطر لمراجعة السيناريوهات المختلفة ومواءمة الجدول الزمني مع خطة إدارة المشروع. [الطبعة السادسة ، صفحة 227 PMBOK] | 142 | 5 | False | "19" | Abdulfattah
257 | You and your team are currently developing the project charter and are looking for valuable inputs you can use to complete it using all of the following inputs in the "Develop Project Charter process" except? | Business case | Enterprise environmental factors | Agreements | Project management plan | Business case, Agreements, and Enterprise environmental factors are Inputs of developing the project charter process [PMBOK 6th edition, Page75] | تقوم أنت وفريقك حاليًا بتطوير ميثاق المشروع وتبحثون عن مدخلات قيّمة يمكنك استخدامها لإكماله باستخدام جميع المدخلات التالية في "تطوير عملية ميثاق المشروع" باستثناء؟ | مستند حالة الأعمال | العوامل البيئية للمؤسسة | الاتفاقيات | خطة إدارة المشروع | دراسة الجدوى والاتفاقيات والعوامل البيئية للمؤسسة هي مدخلات لتطوير عملية ميثاق المشروع . [الطبعة السادسة ، صفحة 75 PMBOK] | 140 | 2 | False | "17" | Abdulfattah
258 | You are managing very critical project, some groups of stakeholders appear to have low product expectations. As a result, they are not performing as expected. This may put project objectives at risk . What should the you as a project manager do? | Ask the project sponsor to intervene and motivate the underperforming stakeholders. | Speak with the problematic stakeholders to increase their performance. | Submit a change request. | Follow the stakeholder engagement plan. | The stakeholder engagement plan is a component of the project management plan that identifies the strategies and actions required to promote the productive involvement of stakeholders in decision making and execution. It can be formal or informal and highly detailed or broadly framed, based on the needs of the project and the expectations of stakeholders. The stakeholder engagement plan may include but is not limited to specific strategies or approaches for engaging with individuals or groups of stakeholders. [PMBOK 6th edition, Page 522] | أنت تدير مشروعًا بالغ الأهمية ، ويبدو أن لدى بعض مجموعات أصحاب المصلحة توقعات منخفضة للمنتج. ونتيجة لذلك ، فإنهم لا يؤدون كما هو متوقع. هذا قد يعرض أهداف المشروع للخطر. ما الذي يجب عليك فعله كمدير مشروع؟ | اطلب من راعي المشروع التدخل وتحفيز أصحاب المصلحة ذوي الأداء الضعيف. | تحدث مع أصحاب المصلحة لديهم مشاكل في المشروع لزيادة أدائهم. | إرسال طلب التغيير. | اتباع خطة ارتباط أصحاب المصلحة. | تعد خطة ارتباط أصحاب المصلحة أحد مكونات خطة إدارة المشروع التي تحدد الاستراتيجيات والإجراءات المطلوبة لتعزيز المشاركة المثمرة لأصحاب المصلحة في صنع القرار والتنفيذ. يمكن أن تكون رسمية أو غير رسمية ومفصلة للغاية أو مؤطرة على نطاق واسع ، بناءً على احتياجات المشروع وتوقعات أصحاب المصلحة. قد تشمل خطة إشراك أصحاب المصلحة ، على سبيل المثال لا الحصر ، استراتيجيات أو مناهج محددة للمشاركة مع الأفراد أو مجموعات أصحاب المصلحة. [الطبعة السادسة ، صفحة 522 PMBOK] | 149 | 3 | False | "18" | Abdulfattah
259 | After finalizing some activities for the project, the customer is not satisfied and complains that his requirements are not being met. in which of the following processes should the project manager have involved him to ensure approval? | Collect requirements | Develop Project charter | Close project or phase | Validate scope | Validate Scope is the process of formalizing acceptance of the completed project deliverables. The key benefit of this process is that it brings objectivity to the acceptance process and increases the probability of the final product. [PMBOK 6th edition, Page 163] | بعد الانتهاء من بعض الأنشطة الخاصة بالمشروع ، لا يشعر العميل بالرضا ويشتكي من عدم تلبية متطلباته. في أي من العمليات التالية يجب على مدير المشروع إشراكه لضمان الموافقة؟ | جمع المتطلبات | تطوير ميثاق المشروع | أغلاق المشروع أو المرحلة | تحقق من النطاق | التحقق من النطاق هو عملية إضفاء الطابع الرسمي على قبول نواتج المشروع المكتملة. الفائدة الرئيسية من هذه العملية هي أنها تضفي الموضوعية على عملية القبول وتزيد من احتمالية المنتج النهائي. [الطبعة السادسة ، صفحة 163 PMBOK] | 141 | 5 | False | "19" | Abdulfattah
260 | The customer insist on using an alternative execution methodology, which is expected to increase project costs. What should the project manager do? | Explain to the stakeholders why the execution methodology cannot be changed. | Ignore the request, and continue with the planned execution methodology. | Assess the stakeholder's methodology see if their expectations can be met. | Escalate the potential methodology change to the project sponsor for approval. | The Best answer is Escalate the potential methodology change to the project sponsor for approval. Option ( Ignore the request ) not good practice to Ignore the important Stakeholder requests. Option ( Explain to the stakeholders why the execution methodology cannot be changed ) Not correct because you should first ask the sponsor for approval he have the authority to decide the implementation of methodology. Option ( Assess the stakeholder's methodology see if their expectations can be met. ) Not Correct because this is a request from important stakeholder not from others. [PMBOK 6th edition, Page.442] | يصر العميل على استخدام منهجية تنفيذ بديلة ، والتي من المتوقع أن تزيد من تكاليف المشروع. ماذا يجب أن يفعل مدير المشروع؟ | اقناع لأصحاب المصلحة لماذا لا يمكن تغيير المنهجية في مرحلة التنفيذ. | تجاهل الطلب واستمر في منهجية التنفيذ المخطط لها. | القيام بتقييم منهجية أصحاب المصلحة لمعرفة ما إذا كان يمكن تلبية توقعاتهم. | تصعيد تغيير المنهجية المحتملة إلى راعي المشروع للموافقة عليها. | أفضل إجابة هي تصعيد تغيير المنهجية المحتملة إلى راعي المشروع للموافقة عليها. الخيار (تجاهل الطلب) ليس ممارسة جيدة لتجاهل طلبات أصحاب المصلحة المهمة. الخيار (اشرح لأصحاب المصلحة لماذا لا يمكن تغيير منهجية التنفيذ) غير صحيح لأنه يجب عليك أولاً أن تطلب من الراعي الموافقة ، فلديه السلطة لاتخاذ قرار بشأن تنفيذ المنهجية. الخيار (تقييم منهجية أصحاب المصلحة لمعرفة ما إذا كان من الممكن تلبية توقعاتهم). غير صحيح لأن هذا طلب من أصحاب المصلحة المهمين وليس من الآخرين. [الطبعة السادسة ، صفحة 442 PMBOK] | 147 | 3 | False | "17" | Abdulfattah
261 | A project manager needed to monitor the technical performance of the project and capture data related to how many errors or defects had been identified and how many remained uncorrected. Which of the following techniques should he use? | Control chart | Flowchart | Scatter diagram | Histogram | Histograms show a graphical representation of numerical data. Histograms can display the number of defects per deliverable, a ranking of the cause of defects, the number of times each process is noncompliant, or other representations of project or product defects. [PMBOK 6th edition, Page 293] | يحتاج مدير المشروع إلى مراقبة الأداء الفني للمشروع والتقاط البيانات المتعلقة بعدد الأخطاء أو العيوب التي تم تحديدها وعدد الأخطاء التي لم يتم تصحيحها. أي من الأساليب التالية يجب أن يستخدمها؟ | مخطط التحكم | مخطط الانسيابية | مخطط التشتت | الرسم البياني التوزيعي | تُظهر الرسوم البيانية التوزيعية تمثيلاً رسوميًا للبيانات الرقمية. يمكن أن تعرض الرسوم البيانية عدد العيوب لكل منتج ، أو ترتيب سبب العيوب ، أو عدد المرات التي تكون فيها كل عملية غير متوافقة ، أو تمثيلات أخرى لعيوب المشروع أو المنتج. [الطبعة السادسة ، صفحة 293 PMBOK] | 144 | 4 | False | "19" | Abdulfattah
262 | The procurement manager of a civil project has emailed the project manager stating that the cost of the cement may exceed the amount budgeted. The project must have a cement delivery in the next two weeks. What should the project manager do first? | Request a quote from another supplier. | Negotiate with the item supplier. | Contact the project sponsor to get more money. | Perform the risk response. | The risk already identified and analyzed. The next step is to Perform the risk response. Option ( Request a quote from another supplier and Negotiate with the item supplier Related to The procurement manager ) [PMBOK 6th edition, Page.449] | أرسل مدير المشتريات لمشروع مدني بريدًا إلكترونيًا إلى مدير المشروع يفيد بأن تكلفة الأسمنت قد تتجاوز المبلغ المحدد في الميزانية. يجب على مدير المشروع تسليم الأسمنت في الأسبوعين المقبلين. ما الذي يجب أن يفعله مدير المشروع أولاً؟ | طلب عرض أسعار من مورد آخر. | التفاوض مع مورد العنصر. | تواصل مع راعي المشروع للحصول على المزيد من المال. | تنفيذ الاستجابة للمخاطر. | تم تحديد المخاطر وتحليلها بالفعل. الخطوة التالية هي تنفيذ الاستجابة للمخاطر. الخيار (طلب عرض أسعار من مورد آخر والتفاوض مع مورد الصنف المتعلق بمدير المشتريات). [الطبعة السادسة ، صفحة 449 PMBOK] | 147 | 4 | False | "19" | Abdulfattah
263 | As part of a joint venture, a project manager working with another company needs to share some confidential information related to intellectual property rights. He wants to know the person responsible for authorizing the release of this confidential information. Which project document should he refer to? | Stakeholder Management Plan | Organizational Breakdown Structure | Project Charter | Project Communication Management Plan | A project communication management plan captures the details of the person responsible for authorizing the release of the confidential information on the project. [PMBOK 6th edition, Page.377] | كجزء من مشروع مشترك ، يحتاج مدير المشروع الذي يعمل مع شركة أخرى إلى مشاركة بعض المعلومات السرية المتعلقة بحقوق الملكية الفكرية. يريد أن يعرف الشخص المسؤول عن الإذن بالافصاح عن هذه المعلومات السرية. ما هي وثيقة المشروع التي يجب أن يشير إليها؟ | خطة إدارة أصحاب المصلحة | الهيكل التنظيمي | ميثاق المشروع | خطة إدارة اتصالات المشروع | تتضمن خطة إدارة اتصالات المشروع تفاصيل الشخص المسؤول عن التصريح بالافصاح عن المعلومات السرية الخاصة بالمشروع. [الطبعة السادسة ، صفحة 377 PMBOK] | 146 | 3 | False | "19" | Abdulfattah
264 | John is a project manager of a construction project. While doing the estimation, he realize that he will need 8 resources for 6 months. John can get only 3 resources after negotiating with the functional manager and as per the organizational policy, he can hire 3 more every 6 months. What will be his next step? | Work with virtual team | Negotiate with the functional manager to get more two resources | Request your project Customer to get more resources | Negotiate with External organizations and suppliers | The project manager should Negotiate with External organizations and suppliers because he already negotiated with the functional manager and can not get the required resources. [PMBOK 6th edition, Page 332] | جون هو مدير مشروع في مشروع بناء. أثناء إجراء التقدير ، أدرك أنه سيحتاج إلى 8 موارد لمدة 6 أشهر. يمكن لجون الحصول على 3 موارد فقط بعد التفاوض مع المدير الوظيفي ووفقًا للسياسة التنظيمية ، يمكنه توظيف 3 آخرين كل 6 أشهر. ماذا ستكون خطوته التالية؟ | العمل مع فريق افتراضي | تفاوض مع المدير الوظيفي للحصول على أكثر من مصدرين | الطلب من عميل المشروع الحصول على المزيد من الموارد | التفاوض مع المنظمات الخارجية والموردين | يجب أن يتفاوض مدير المشروع مع المنظمات والموردين الخارجيين لأنه تفاوض بالفعل مع المدير الوظيفي ولا يمكنه الحصول على الموارد المطلوبة. [الطبعة السادسة ، صفحة 332 PMBOK] | 145 | 4 | False | "19" | Abdulfattah
265 | The CFO has become supportive after he was resistant. As a project manager, what should you do next? | Update Issue log | Update Risk Register | Update Communications Management plan | Update Stakeholder engagement assessment matrix | A stakeholder engagement assessment matrix supports the comparison between the current engagement levels of stakeholders and the desired engagement levels required for successful project delivery. So when Stakeholder has become supportive after he was resistive, you should update the matrix [PMBOK 6th edition, Page 521] | أصبح المدير المالي داعمًا بعد أن كان مقاومًا. كمدير مشروع ، ماذا يجب أن تفعل بعد ذلك؟ | تحديث سجل المشاكل | تحديث سجل المخاطر | تحديث خطة إدارة الاتصالات | تحديث مصفوفة تقييم مشاركة أصحاب المصلحة | تدعم مصفوفة تقييم مشاركة أصحاب المصلحة المقارنة بين مستويات المشاركة الحالية لأصحاب المصلحة ومستويات المشاركة المطلوبة المطلوبة لإنجاز المشروع بنجاح. لذلك عندما يصبح أصحاب المصلحة داعمين بعد أن كان مقاومًا ، يجب عليك تحديث المصفوفة . [الطبعة السادسة ، صفحة 521 PMBOK] | 149 | 3 | False | "19" | Abdulfattah
266 | Tom is a project manager joins a project with cross-functional stakeholders and a fixed go-live date. He wants to quickly gather requirements and ensure all stakeholders are aligned so that any conflicts are flagged as early as possible. What should Tom do? | Send a questionnaire to all stakeholders. | Conduct individual interviews with each stakeholder. | Set up job-shadowing sessions for all stakeholders. | Use facilitation techniques with all stakeholders. | Facilitation is used with focused sessions that bring key stakeholders together to define product requirements. Workshops can be used to quickly define cross-functional requirements and reconcile stakeholder differences. Because of their interactive group nature, well-facilitated sessions can build trust, foster relationships, and improve communication among the participants, which can lead to increased stakeholder consensus. In addition, issues can be discovered earlier and resolved more quickly than in individual sessions. [PMBOK 6th edition Page, 145] | توم هو مدير مشروع ينضم إلى مشروع مع أصحاب المصلحة متعددي الوظائف وتاريخ بدء التشغيل الثابت. إنه يريد جمع المتطلبات بسرعة والتأكد من توافق جميع أصحاب المصلحة بحيث يتم الإبلاغ عن أي تعارضات في أقرب وقت ممكن. ماذا يجب أن يفعل توم؟ | إرسال استبيان إلى جميع أصحاب المصلحة. | القيام بإجراء مقابلات فردية مع كل صاحب مصلحة. | القيام بإعداد جلسات الظل الوظيفي لجميع أصحاب المصلحة. | استخدم تقنيات التيسير مع جميع أصحاب المصلحة. | يتم استخدام التيسير مع الجلسات المركزة التي تجمع أصحاب المصلحة الرئيسيين معًا لتحديد متطلبات المنتج. يمكن استخدام ورش العمل لتحديد المتطلبات متعددة الوظائف بسرعة وتسوية الاختلافات بين أصحاب المصلحة. نظرًا لطبيعة المجموعة التفاعلية ، يمكن للجلسات المنسقة جيدًا بناء الثقة وتعزيز العلاقات وتحسين التواصل بين المشاركين ، مما قد يؤدي إلى زيادة إجماع أصحاب المصلحة. بالإضافة إلى ذلك ، يمكن اكتشاف المشكلات في وقت مبكر وحلها بسرعة أكبر من الجلسات الفردية. [الطبعة السادسة ، صفحة 145 PMBOK] | 141 | 3 | False | "20" | Abdulfattah
267 | Liza is managing a civil project . During the implementation phase, a team member has told her that one of the risks previously identified has occurred. As a project manager, what should Liza do next? | Update the risk management plan | Implement a workaround plan | Update the change log | Update Risk Register | When a previously identified risk occurs, you should update the risk register. [PMBOK 6th edition, Page.417] | ليزا تدير مشروعًا مدنيًا. خلال مرحلة التنفيذ ، أخبرها أحد أعضاء الفريق بحدوث أحد المخاطر التي تم تحديدها مسبقًا. كمدير مشروع ، ما الذي يجب أن تفعله ليزا بعد ذلك؟ | تحديث خطة إدارة المخاطر | تنفيذ خطة حل بديل | قم بتحديث سجل التغيير | تحديث سجل المخاطر | عند حدوث خطر تم تحديده مسبقًا ، يجب عليك تحديث سجل المخاطر. [الطبعة السادسة ، صفحة 417 PMBOK] | 147 | 3 | False | "18" | Abdulfattah
268 | Robin is a project manager on a large civil project. Robin had originally planned to use both of the company's tower crane simultaneously for a project but has just learned that one of them will be unavailable. Robin adjusts the schedule so that the components are created sequentially using the one remaining tower crane. Unfortunately, this action affects the critical path and delays the planned finish date of the project. Which of the following techniques has been used by Robin in this situation? | Fast tracking | Reserve analysis | Critical path method | Resource leveling | Resource leveling is a resource optimization technique in which start and finish dates are adjusted based on resource constraints with the goal of balancing the demand for the resources with the available supply. Resource leveling can often cause the original critical path to change which is what happened in the scenario described. Adjusting the schedule to accommodate the loss of one of the tower crane is an example of resource leveling. [PMBOK 6th edition, Page 211] | روبن هو مدير مشروع في مشروع مدني كبير. كان روبن قد خطط في الأصل لاستخدام كل من الرافعة البرجية للشركة في وقت واحد لمشروع ما ، لكنه علم للتو أن أحدهما لن يكون متاحًا. يقوم روبن بضبط الجدول الزمني بحيث يتم إنشاء المكونات بالتتابع باستخدام الرافعة البرجية المتبقية. لسوء الحظ ، يؤثر هذا الإجراء على المسار الحرج وبالتالي يؤدي الى تأخر تاريخ الانتهاء المخطط للمشروع. أي من الأساليب التالية استخدمها روبن في هذه الحالة؟ | تسريع الانشطة | تحليل الاحتياطي | طريقة المسار الحرج | تسوية الموارد | تسوية الموارد هي تقنية لتحسين الموارد يتم فيها تعديل تواريخ البدء والانتهاء بناءً على قيود الموارد بهدف موازنة الطلب على الموارد مع العرض المتاح. غالبًا ما يتسبب تسوية الموارد في تغيير المسار الحرج الأصلي وهو ما حدث في السيناريو الموضح. يعد تعديل الجدول الزمني لاستيعاب فقدان إحدى الرافعات مثالاً على تسوية الموارد. [الطبعة السادسة ، صفحة 211 PMBOK] | 142 | 3 | False | "18" | Abdulfattah
269 | In a project with a tight time frame, the project manager needs continuous stakeholder buy-in and input to avoid errors. Inevitably, changes occur as the project progresses. What should the project manager do? | Speak with management about stakeholders involvement to initiate a change in schedule expectations. | Provide increased project updates to stakeholders and deliver accurate change management documentation. | Stop work before The changes cause a schedule delay and update the project schedule to reflect this. | Monitor and update stakeholder relationships and tailor strategies for engaging stakeholders through changes. | Monitor and update stakeholder relationships and tailor strategies for engaging stakeholders through changes to gain continuous stakeholder buy-in and input to avoid errors. [PMBOK 6th edition, Page.530] | في مشروع ذي إطار زمني ضيق ، يحتاج مدير المشروع إلى مشاركة مستمرة لأصحاب المصلحة ومدخلات لتجنب الأخطاء. حتما ، تحدث التغييرات مع تقدم المشروع. ماذا يجب أن يفعل مدير المشروع؟ | تحدث مع الإدارة حول مشاركة أصحاب المصلحة لبدء تغيير في توقعات الجدول الزمني. | توفير تحديثات المشروع المتزايدة لأصحاب المصلحة وتقديم وثائق دقيقة لإدارة التغيير. | ايقاف العمل قبل أن تتسبب التغييرات في تأخير الجدول الزمني وتحديث جدول المشروع ليعكس ذلك. | رصد وتحديث العلاقات مع أصحاب المصلحة والاستراتيجيات المخصصة لإشراك أصحاب المصلحة من خلال التغييرات. | مراقبة وتحديث علاقات أصحاب المصلحة والاستراتيجيات المخصصة لإشراك أصحاب المصلحة من خلال التغييرات للحصول على دعم مستمر لأصحاب المصلحة ومدخلات لتجنب الأخطاء. [الطبعة السادسة ، صفحة 530 PMBOK] | 149 | 4 | False | "17" | Abdulfattah
270 | You are estimating activity durations for a project. Which of the following is the best to help the project manager to estimate duration? | Project sponsor | All Stakeholders | HR manger | Subject matter expert (SME) | SME is a part of EXPERT JUDGMENT and Expert Judgment Tools and Techniques in the Estimate Activity Duration Process. [PMBOK 6th edition, Page 200] | أنت تقوم بتقدير مدد النشاط لمشروع. أي مما يلي هو الأفضل لمساعدة مدير المشروع على تقدير المدة؟ | راعي المشروع | جميع أصحاب المصلحة | مدير الموارد البشرية | الاستعانة بالخبراء في نفس المجال | الشركات الصغيرة والمتوسطة هي جزء من حكم الخبراء وأدوات وتقنيات الاستعانة بالخبراء في عملية تقدير مدد الانشطة. [الطبعة السادسة ، صفحة 200 PMBOK] | 142 | 3 | False | "19" | Abdulfattah
271 | In a conference call, the project manager failed the delivery date. Based on that, the conference organizer rejects the entire delivery. The project manager's company is now faced with replacement costs, the loss of credibility, and disrupted logistics. To what cost of quality (COQ) category do these costs belong? | Internal failure. | Appraisal. | Prevention | External failure. | loss of credibility and disrupted logistics are an example of external failure cost. [PMBOK 6th edition, Page.283] | في مكالمة جماعية ، فشل مدير المشروع في تاريخ التسليم. بناءً على ذلك ، يرفض منظم المؤتمر التسليم بالكامل. تواجه شركة مدير المشروع الآن تكاليف الاستبدال ، وفقدان المصداقية ، وتعطل الخدمات اللوجستية. إلى أي فئة تكلفة الجودة (COQ) تنتمي هذه التكاليف؟ | فشل داخلي. | اجراء الاختبارات | الوقاية | فشل خارجي. | يعد فقدان المصداقية واللوجستيات المعطلة مثالاً على تكلفة الفشل الخارجي. [الطبعة السادسة ، صفحة 283 PMBOK] | 144 | 3 | False | "20" | Abdulfattah
272 | One month after project deployment, a project manager unsuccessfully tries to resolve an issue on their own. The project manager failed to inform stakeholders, which resulted in their frustration. To avoid stakeholders frustration, what should the project manager have done? | Referenced the lessons learned repository. | Updated the issue log. | Referred to the stakeholder engagement plan. | Adhere to the communication management plan. | Because PM failed to inform stakeholders to avoid stakeholders frustration, the project manager should have done Adhere to the communication management plan. [PMBOK 6th edition, Page.377] | بعد شهر واحد من نشر المشروع ، يحاول مدير المشروع حل المشكلة بنفسه دون جدوى. فشل مدير المشروع في إبلاغ أصحاب المصلحة ، مما أدى إلى إحباطهم. لتجنب إحباط أصحاب المصلحة ، ما الذي كان يجب على مدير المشروع فعله؟ | يشار إلى مستودع الدروس المستفادة. | تحديث سجل القضية. | يشار إلى خطة إشراك أصحاب المصلحة. | التقيد بخطة إدارة الاتصالات. | نظرًا لأن مدير المشروع فشل في إبلاغ أصحاب المصلحة لتجنب إحباط أصحاب المصلحة ، كان ينبغي على مدير المشروع الالتزام بخطة إدارة الاتصالات. [الطبعة [الطبعة السادسة ، صفحة 377 PMBOK] | 146 | 3 | False | "20" | Abdulfattah
273 | You receive an email requesting modification to a project's baseline. From whom should the project manager request formal approval to implement this change? | Project sponsor | Project customer | Project management office (PMO) | Change control board (CCB) | The change control board (CCB), which is a formally chartered group responsible for reviewing, evaluating, approving, deferring, or rejecting changes to the project and for recording and communicating such decisions. [PMBOK 6th edition Page, 115] | تتلقى بريدًا إلكترونيًا يطلب تعديل خط الأساس للمشروع. من الذي يجب أن يطلب مدير المشروع الموافقة الرسمية لتنفيذ هذا التغيير؟ | راعي المشروع | عميل المشروع | مكتب إدارة المشاريع | لجنة التحكم في التغيير | لجنة التحكم في التغيير (CCB) ، وهو مجموعة معتمدة رسميًا مسؤولة عن مراجعة أو تقييم أو الموافقة على أو تأجيل أو رفض التغييرات في المشروع وتسجيل هذه القرارات والإبلاغ عنها. [الطبعة السادسة ، صفحة 115 PMBOK] | 140 | 5 | False | "19" | Abdulfattah
274 | The change control board (CCB) has rejected a change request made by a key stakeholder. What should the project manager do? | Ask the CCB to reconsider and review the change request again. | Ask the sponsor to review and approve the change request. | Implement the change that the key stakeholder has requested. | Notify the key stakeholder about the decision made by the CCB. | Refer to change request steps , If The change control board (CCB) has rejected a change request , the next step is update the change log then Notify the key stakeholder who request the change about the decision made by the CCB. [PMBOK 6th edition, Page.120] | رفض لجنة التحكم في التغيير طلب التغيير الذي قدمه أحد أصحاب المصلحة الرئيسيين. ماذا يجب أن يفعل مدير المشروع؟ | الطلب من لجنة التحكم في التغيير إعادة النظر ومراجعة طلب التغيير مرة أخرى. | الطلب من الراعي مراجعة طلب التغيير والموافقة عليه. | تنفيذ طلب التغيير الذي طلبه صاحب المصلحة الرئيسي. | إخطار أصحاب المصلحة الرئيسيين بالقرار الذي اتخذه مجلس التحكم في التغيي. | الرجوع إلى خطوات طلب التغيير ، إذا رفض لجنة التحكم في التغيير (CCB) طلب التغيير ، فإن الخطوة التالية هي تحديث سجل التغيير ثم إخطار صاحب المصلحة الرئيسي الذي يطلب التغيير بشأن القرار الذي لجنة التحكم في التغيير. [الطبعة السادسة ، صفحة 120 PMBOK] | 140 | 5 | False | "20" | Abdulfattah
275 | You are a project manager. One of your team members identifies a risk for which new requirements may be needed for a project. This risk has a high impact but a low chance of occurrence. As a project manager, what should you do? | Assess and monitor the risk, and develop a risk response strategy. | Update the Risk register and scope baseline | Issue a change request and get it approved through Integrated Change Control process | Accept the risk and plan to use the contingency reserve. | The team member identified the risk then complete the analysis ( a high impact but a low chance of occurrence) . Since the chance of occurrence is low, so the best answer is to Accept the risk and plan to use the contingency reserve. option ( Assess and monitor the risk, and develop a risk response strategy. ) incorrect because the risk already analyzed. [PMBOK 6th edition, Page.443] | انت مدير مشروع يحدد أحد أعضاء فريقك المخاطر التي قد تكون هناك حاجة إلى متطلبات جديدة لمشروع ما. هذا الخطر له تأثير كبير ولكن فرصة حدوثه منخفضة. كمدير مشروع ، ماذا يجب أن تفعل؟ | تقييم ومراقبة المخاطر وتطوير استراتيجية الاستجابة للمخاطر. | تحديث سجل المخاطر وخط الأساس المرجعي للنطاق | إصدار طلب تغيير واعتماده من خلال عملية التحكم المتكامل في التغيير | قبول المخاطر والتخطيط لاستخدام احتياطي الطوارئ. | حدد عضو الفريق الخطر ثم أكمل التحليل (تأثير كبير لكن فرصة حدوثه منخفضة). نظرًا لأن فرصة الحدوث منخفضة ، فإن أفضل إجابة هي قبول المخاطر والتخطيط لاستخدام احتياطي الطوارئ. الخيار (تقييم ومراقبة المخاطر ، وتطوير استراتيجية الاستجابة للمخاطر.) غير صحيح لأن المخاطر تم تحليلها بالفعل. [الطبعة السادسة ، صفحة 443 PMBOK] | 147 | 3 | False | "18" | Abdulfattah
276 | To create a probability distribution from the iterations for the project schedule. What technique will you use with this simulation? | Pareto charts | Expected Monetary Value | Cause and effect diagram | Monte Carlo Technique | Computer software is used to iterate the quantitative risk analysis model several thousand times. The input values (e.g.. cost estimates, duration estimates, or occurrence of probabilistic branches) are chosen at random for each iteration. Outputs represent the range of possible outcomes for the project. [PMBOK 6th edition, Page 433] | لإنشاء توزيع احتمالي من عملية التكرارات لجدول المشروع. ما هي التقنية التي ستستخدمها مع هذه المحاكاة؟ | مخططات باريتو | القيمة النقدية المتوقعة | مخطط السبب والتأثير | تقنية مونت كارلو | يتم استخدام برامج الكمبيوتر لتكرار نموذج التحليل الكمي للمخاطر عدة آلاف من المرات. يتم اختيار قيم الإدخال (مثل تقديرات التكلفة أو تقديرات المدة أو حدوث الفروع الاحتمالية) بشكل عشوائي لكل تكرار. تمثل المخرجات مجموعة النتائج المحتملة للمشروع. [الطبعة السادسة ، صفحة 433 PMBOK] | 147 | 3 | False | "20" | Abdulfattah
277 | A new government regulation requires financial resources to be added to a project, the CEO request to add another project activity. What should the project manager do? | Update the schedule to include the new activity because it was requested by the CEO. | Execute the new activity because it was requested by the CEO. | Use funding allocated to other activities to execute the CEO's request. | Document the request from the CEO and perform the change request procedure | The project manager should Document the request from the CEO and perform the change request procedure .. Other options not correct because the change request should be approved before Updating the pan or Executing the new activity... [PMBOK 6th edition, Page.113] | تتطلب لائحة حكومية جديدة إضافة موارد مالية إلى المشروع ، ويطلب الرئيس التنفيذي إضافة نشاط مشروع آخر. ماذا يجب أن يفعل مدير المشروع؟ | القيام بتحديث الجدول الزمني ليشمل النشاط الجديد لأنه تم طلبه من قبل الرئيس التنفيذي. | تنفيذ النشاط الجديد بناءً على طلب الرئيس التنفيذي. | استخدم التمويل المخصص للأنشطة الأخرى لتنفيذ طلب الرئيس التنفيذي. | توثيق الطلب من الرئيس التنفيذي وتنفيذ إجراء طلب التغيير | يجب على مدير المشروع توثيق الطلب من المدير التنفيذي وتنفيذ إجراء طلب التغيير .. خيارات أخرى غير صحيحة لأنه يجب الموافقة على طلب التغيير قبل تحديث عموم أو تنفيذ النشاط الجديد . [الطبعة السادسة ، صفحة 113 PMBOK] | 140 | 5 | False | "18" | Abdulfattah
278 | You identify that three leaders in the organization have three different expectations about what should be implemented in a project. What did you use to identify this? | Root cause analysis | Communication requirements analysis | Bidder conferences | Stakeholder analysis. | Stakeholder analysis results in a list of stakeholders and relevant information such as their positions in the organization, roles on the project, expectations, attitudes (their levels of support for the project), and their interest in information about the project. [PMBOK 6th edition, Page, 512] | أنت تحدد أن ثلاثة قادة في المنظمة لديهم ثلاثة توقعات مختلفة حول ما يجب تنفيذه في المشروع. ماذا كنت تستخدم لتحديد هذا؟ | تحليل السبب الجذري | تحليل متطلبات الاتصال | مؤتمرات مقدمي العروض | تحليل اصحاب المصلحة | ينتج عن تحليل أصحاب المصلحة قائمة بأصحاب المصلحة والمعلومات ذات الصلة مثل مواقفهم في المنظمة ، والأدوار في المشروع ، والتوقعات ، والمواقف (مستويات دعمهم للمشروع) ، واهتمامهم بالمعلومات حول المشروع. [الطبعة السادسة ، صفحة 512 PMBOK] | 149 | 2 | False | "19" | Abdulfattah
279 | Ali have been assigned as a project manager for a project. Ali and his team members start to identify individual project risks as well as sources of overall project risk and documenting their characteristics. Which of the following Data analysis techniques can be used for this process? | Interviews | Probability and impact matrix | Brainstorming | Root cause analysis | Root cause analysis is Data analysis techniques used in identify risk process .typically used to discover the underlying causes that lead to a problem and develop preventive action. It can be used to determine threats by starting with a problem statement and exploring which threats might result in that problem occurring. The same technique can be used to find opportunities by beginning with a benefit statement and exploring which opportunities might result in that benefit being realized. [PMBOK 6th edition, Page 415] | علي تم تعيينه كمدير مشروع لمشروع. يبدأ علي وأعضاء فريقه في تحديد مخاطر المشروع الفردية بالإضافة إلى مصادر مخاطر المشروع الإجمالية وتوثيق خصائصها. أي من تقنيات تحليل البيانات التالية يمكن استخدامها لهذه العملية؟ | المقابلات | مصفوفة الاحتمالات والأثر | العصف الذهني | تحليل السبب الجذري | تحليل السبب الجذري هو تقنيات تحليل البيانات المستخدمة في تحديد عملية المخاطر. تُستخدم عادةً لاكتشاف الأسباب الكامنة التي تؤدي إلى حدوث مشكلة وتطوير الإجراءات الوقائية. يمكن استخدامه لتحديد التهديدات من خلال البدء ببيان المشكلة واستكشاف التهديدات التي قد تؤدي إلى حدوث هذه المشكلة. يمكن استخدام نفس الأسلوب لإيجاد الفرص من خلال البدء ببيان المنافع واستكشاف الفرص التي قد تؤدي إلى تحقيق هذه الميزة. [الطبعة السادسة ، صفحة 415 PMBOK] | 147 | 3 | False | "19" | Abdulfattah
280 | You are managing a large project approaching its completion. You have to send the final project report to all stakeholders but receives an email from an executive manager in the company asking about the status of the project. How should you handle this request? | Review the risk register to find a response for the executive. | Ask the executive to join the next progress meeting | Send the project milestones to the executive. | Ensure the executive manager is in the communications management plan. | The project manager should Ensure the executive manager is in the communications management plan or not because it includes Stakeholder communication requirements and Persons or groups who will receive the information, including information about their needs, requirements, and expectations. [PMBOK 6th edition, Page 377] | أنت تدير مشروعًا كبيرًا يقترب من اكتماله. يجب عليك إرسال تقرير المشروع النهائي إلى جميع أصحاب المصلحة ولكن تتلقى رسالة بريد إلكتروني من مدير تنفيذي في الشركة يسأل عن حالة المشروع. كيف ينبغي التعامل مع هذا الطلب؟ | مراجعة سجل المخاطر للعثور على استجابة للمدير التنفيذي. | الطلب من المدير التنفيذي الانضمام إلى اجتماع التقدم التالي | أرسال معالم المشروع إلى السلطة التنفيذية. | التأكد من أن المدير التنفيذي في خطة إدارة الاتصالات. | يجب على مدير المشروع التأكد من أن المدير التنفيذي في خطة إدارة الاتصالات أم لا لأنه يشمل متطلبات الاتصال مع أصحاب المصلحة والأشخاص أو المجموعات التي ستتلقى المعلومات ، بما في ذلك المعلومات حول احتياجاتهم ومتطلباتهم وتوقعاتهم. [الطبعة السادسة ، صفحة 377 PMBOK] | 146 | 3 | False | "19" | Abdulfattah
281 | A key stakeholder of your project particularly wants to understand which work packages, or activities each team member is responsible to complete. As a project manager, you should direct the key stakeholder of the project to which of the following Charts? | Project Charter | Resource calendars | Stakeholder's engagement assessment matrix | RACI Chart | A RACI chart is a useful tool to use to ensure a clear assignment of roles and responsibilities when the team consists of internal and external resources. [PMBOK 6th edition, Page 317] | يرغب أحد أصحاب المصلحة الرئيسيين في مشروعك تحديدًا في فهم حزم العمل أو الأنشطة التي يتحمل كل عضو في الفريق مسؤولية إكمالها. بصفتك مدير مشروع ، يجب عليك توجيه صاحب المصلحة الرئيسي في المشروع إلى أي من المخططات التالية؟ | ميثاق المشروع | تقويم الموارد | مصفوفة تقييم مشاركة أصحاب المصلحة | مخطط مصفوفة تعيين المسؤوليات | يعد مخطط مصفوفة تعيين المسؤوليات أداة مفيدة لاستخدامها لضمان تعيين واضح للأدوار والمسؤوليات عندما يتكون الفريق من موارد داخلية وخارجية. [الطبعة السادسة ، صفحة 317 PMBOK] | 145 | 3 | False | "18" | Abdulfattah
282 | Martin is a project manager in an infrastructure project. After finalizing all activities for the project, which of the following documents will help him in this process? | Stakeholder Register | Verified deliverables | Probability and Impact Matrix | Project Charter | Project Charter Key inputs in Close project or phase process because of The project charter documents the project success criteria, the approval requirements, and who will sign off on the project. [PMBOK 6th edition, Page 124] | مارتن هو مدير مشروع في مشروع البنية التحتية. بعد الانتهاء من جميع أنشطة المشروع ، أي من المستندات التالية ستساعده في هذه العملية؟ | سجل أصحاب المصلحة | مخرجات تم التحقق منها | مصفوفة الاحتمالات والأثر | ميثاق المشروع | مدخلات ميثاق المشروع المستند الرئيسي في إغلاق المشروع أو عملية المرحلة بسبب توثيق ميثاق المشروع لمعايير نجاح المشروع ، ومتطلبات الموافقة ، والشخص الذي سيوقع على المشروع. [الطبعة السادسة ، صفحة 124 PMBOK] | 140 | 6 | False | "16" | Abdulfattah
283 | During testing, a team member escalates a quality defect to you "the project manager". While brainstorming with the team, you realizes there is more than one cause of the problem. What should you use to identify the primary cause? | Qualitative risk analysis | Statistical sampling | Scatter diagram | Ishikawa diagram | Because "primary cause" Cause-and-effect diagrams are also known as fishbone diagrams, why-why diagrams, or lshikawa diagrams. This type of diagram breaks down the causes of the problem statement identified into discrete branches, helping to identify the main or root cause of the problem. [PMBOK 6th Page, 293] | أثناء الاختبار ، يقوم أحد أعضاء الفريق بتصعيد عيب في الجودة إلى "مدير المشروع". أثناء تبادل الأفكار مع الفريق ، تدرك أن هناك أكثر من سبب واحد للمشكلة. ما الذي يجب أن تستخدمه لتحديد السبب الرئيسي؟ | التحليل النوعي للمخاطر | أخذ العينات الإحصائية | مخطط التشتت | مخطط إيشيكاوا | نظرًا لأن مخططات السبب والنتيجة "الأولية" تُعرف أيضًا باسم مخططات هيكل السمكة أو مخططات لماذا ولماذا أو مخططات ايشيكاوا. يقسم هذا النوع من المخططات أسباب بيان المشكلة المحددة إلى فروع منفصلة ، مما يساعد على تحديد السبب الرئيسي أو الجذري للمشكلة. [الطبعة السادسة ، صفحة 293 PMBOK] | 144 | 4 | False | "20" | Abdulfattah
284 | The collect requirements team has generated a large number of ideas during sessions to gather product and project requirements. Which of the following techniques is best suited to generate, organize information and allows large numbers of ideas to be classified into groups for review and analysis? | Idea/mind mapping | Nominal group technique | Brainstorming | Affinity diagram | Affinity diagrams allow large numbers of ideas to be classified into groups for review and analysis. [PMBOK 6th edition, Page 144] | أنتج فريق جمع المتطلبات عددًا كبيرًا من الأفكار أثناء الجلسات لجمع متطلبات المنتج والمشروع. أي من الأساليب التالية هو الأنسب لإنشاء المعلومات وتنظيمها والسماح بتصنيف أعداد كبيرة من الأفكار في مجموعات للمراجعة والتحليل؟ | الخريطة الذهنية | تقنية مجموعة الاسمية | العصف الذهني | مخطط التقارب | تسمح مخططات التقارب بتصنيف أعداد كبيرة من الأفكار إلى مجموعات للمراجعة والتحليل. [الطبعة السادسة ، صفحة 144 PMBOK] | 141 | 3 | False | "18" | Abdulfattah
285 | Your are managing a project which needs a few vendors to finish the work. One of the vendors before signing asked you to first get a part of payment before he makes the first shipment. As a Project manager, you will review: | Contract and agreement | Project Charter | Company process and conditions | Procurement Management Plan | The vendor asked you to get first a part of payment before he makes the first shipping before signing the contract , you should first review Procurement management Plan Because the Procurement Management Plan includes Timetable of key procurement activities and The legal jurisdiction and the currency in which payments will be made, but if this situation after signing the contract you should review Contract. [PMBOK 6th edition, Page 475] | أنت تدير مشروعًا يحتاج إلى عدد قليل من البائعين لإنهاء العمل. طلب منك أحد البائعين قبل التوقيع أن تحصل أولاً على جزء من الدفع قبل أن يقوم بالشحنة الأولى. بصفتك مدير المشروع ، سوف تراجع: | العقد والاتفاقية | ميثاق المشروع | شروط وعمليات الشركة | خطة إدارة المشتريات | طلب منك البائع الحصول أولاً على جزء من الدفع قبل أن يقوم بالشحن الأول قبل توقيع العقد ، يجب عليك أولاً مراجعة خطة إدارة المشتريات لأن خطة إدارة المشتريات تتضمن الجدول الزمني لأنشطة المشتريات الرئيسية والولاية القضائية القانونية والعملة التي يتم بها الدفع ، ولكن إذا كان هذا الموقف بعد توقيع العقد ، يجب عليك مراجعة العقد. [الطبعة السادسة ، صفحة 457 PMBOK] | 148 | 3 | False | "18" | Abdulfattah
286 | You are the project manager of a large communication project. During the implementation phase, you sign a contract to rent an additional server from a local company because of the possibility that the main server may fail due to constant, local-area electrical outages. As a project manager, what strategy are you using? | Transfer | Avoid | Escalate | Mitigate | In risk mitigation, the action is taken to reduce the probability of occurrence and/or impact of a threat. the project manager wants to reduce the probability and impact by renting the generator. [PMBOK 6th edition, Page 443] | أنت مدير مشروع مشروع اتصالات كبير. أثناء مرحلة التنفيذ ، تقوم بتوقيع عقد لاستئجار خادم إضافي من شركة محلية بسبب احتمال تعطل الخادم الرئيسي بسبب انقطاع التيار الكهربائي المستمر في المنطقة المحلية. كمدير مشروع ، ما هي الاستراتيجية التي تستخدمها؟ | النقل | التجنب | التصعيد | التخفيف | في التخفيف من المخاطر ، يتم اتخاذ الإجراء لتقليل احتمالية حدوث و / أو تأثير التهديد. يريد مدير المشروع تقليل الاحتمالية والتأثير من خلال استئجار المولد. [الطبعة السادسة ، صفحة 443 PMBOK] | 147 | 4 | False | "20" | Abdulfattah
287 | The customer and hardware engineering team disagree about the limits on the control chart being used to measure quality. You meet with both stakeholders and listens to their opinions. In order to proceed with the project, you decides to use an average of their opinions. What is this an example of? | Problem solving | Collaboration | Smoothing | Compromise | This is an example of Compromise ...... Compromise/reconcile. Searching for solutions that bring some degree of satisfaction to all parties in order to temporarily or partially resolve the conflict. This approach occasionally results in a lose-lose situation..... Option ( Collaboration ,Problem solving ) not correct as both is the same.... [PMBOK 6th edition, Page.349] | يختلف فريق هندسة الأجهزة والعميل حول القيود المفروضة على مخطط التحكم المستخدم لقياس الجودة. تلتقي مع كل من أصحاب المصلحة وتستمع إلى آرائهم. من أجل المضي قدمًا في المشروع ، قررت استخدام متوسط ​​آرائهم. ما هو هذا مثال؟ | حل المشاكل | التعاون | التجانس | التسوية | هذا مثال على حل وسط تسوية / المرونة. البحث عن حلول تحقق درجة معينة من الرضا لجميع الأطراف من أجل حل النزاع بشكل مؤقت أو جزئي. ينتج عن هذا النهج أحيانًا موقف خاسر. الخيار (التعاون ، حل المشكلات) غير صحيح لأن كليهما هو نفسه. [الطبعة السادسة ، صفحة 349 PMBOK] | 145 | 4 | False | "20" | Abdulfattah
288 | A large, publicly funded civil project regulatory requirements specify that the contractor's project work be visually monitored on a continuous basis. Which method is suitable for meeting this compliance obligation'? | Video feedback using a drone | Photographs by an onsite photographer | Photographs attached to documentation submitted on a weekly basis | Video feedback through onsite web cameras | Publicly funded projects are under increasing scrutiny. A trend in infrastructure and commercial construction projects is the use of technology including web cameras (webcams) to improve stakeholder communications and relations. During construction, one or more webcams are installed on the site, with periodic updates to a publicly available website. The progress on the project can be viewed on the Internet by all stakeholders. Video data can also be stored, allowing analysis if a claim arises. Some projects have discovered that the use of webcams minimizes disputes relating to the construction work on site, as the webcam has recorded the events, so there should be no disagreement about the facts of the matter. [PMBOK 6th edition Page, 464] | تحدد المتطلبات التنظيمية لمشروع مدني كبير ممول من القطاع العام أن عمل المشروع للمقاول يتم مراقبته بصريًا على أساس مستمر. ما هي الطريقة المناسبة للوفاء بالتزام الامتثال هذا؟ | ردود الفعل بالفيديو باستخدام طائرة بدون طيار | تصوير من قبل المصور | الصور المرفقة بالوثائق المقدمة على أساس أسبوعي | ملاحظات الفيديو من خلال كاميرات الويب في الموقع | تخضع المشاريع الممولة من القطاع العام لمزيد من التدقيق. الاتجاه السائد في مشاريع البنية التحتية والبناء التجاري هو استخدام التكنولوجيا بما في ذلك كاميرات الويب (كاميرات الويب) لتحسين اتصالات وعلاقات أصحاب المصلحة. أثناء البناء ، يتم تثبيت كاميرا ويب واحدة أو أكثر على الموقع ، مع تحديثات دورية لموقع ويب متاح للجمهور. يمكن لجميع أصحاب المصلحة الاطلاع على التقدم المحرز في المشروع على الإنترنت. يمكن أيضًا تخزين بيانات الفيديو ، مما يسمح بالتحليل إذا ظهرت مطالبة. اكتشفت بعض المشاريع أن استخدام كاميرات الويب يقلل من النزاعات المتعلقة بأعمال البناء في الموقع ، حيث سجلت كاميرا الويب الأحداث ، لذا يجب ألا يكون هناك خلاف حول حقائق الأمر. [الطبعة السادسة ، صفحة 464 PMBOK] | 148 | 3 | False | "19" | Abdulfattah
289 | Which of the following soft skills helps to reduce misunderstandings and improves communication and knowledge sharing? | Leadership | Political awareness | Lessons learned register | Active listening | Active listening helps reduce misunderstandings and improves communication and knowledge sharing. [PMBOK 6th edition, Page 104] | أي من المهارات الشخصية التالية يساعد على تقليل سوء الفهم وتحسين التواصل وتبادل المعرفة؟ | القيادة | الوعي السياسي | تسجيل الدروس المستفادة | الاستماع الفعال | الاستماع الفعال يساعد على تقليل سوء الفهم وتحسين التواصل وتبادل المعرفة. [الطبعة السادسة ، صفحة 104 PMBOK] | 140 | 4 | False | "19" | Abdulfattah
290 | You want to establish benchmark for comparing actual project performance with the project management plan. What process should you complete to generate this model? | Develop schedule | Sequence activities | Develop project Charter | Create WBS | Create WBS process is the correct answer because the scope baseline is an output from this process and The scope baseline is compared to actual results to determine if a change, corrective action, or preventive action is necessary.S0 will use as a benchmark for Comparison [PMBOK 6th edition, Page.156] | تريد إنشاء معيار لمقارنة أداء المشروع الفعلي مع خطة إدارة المشروع. ما العملية التي يجب عليك إكمالها لإنشاء هذا النموذج؟ | وضع الجدول الزمني | تسلسل الانشطة | تطوير ميثاق المشروع | القيام يإنشاء هيكل تجزئة العمل | إن عملية إنشاء هيكل تجزئة العمل هي الإجابة الصحيحة لأن خط الأساس للنطاق هو ناتج من هذه العملية ويتم مقارنة خط الأساس للنطاق بالنتائج الفعلية لتحديد ما إذا كان التغيير أو الإجراء التصحيحي أو الإجراء الوقائي ضروريًا. سيستخدم كمعيار للمقارنة. [الطبعة السادسة ، صفحة 156 PMBOK] | 141 | 3 | False | "19" | Abdulfattah
291 | Tom is in the executing phase of his project and stakeholders are escalating issues to management directly without involving him. Which of the following would have prevented this from happening if well documented and communicated? | Project Charter | Issues log | Risk register | Communications Management Plan | The Communications Management Plan contains information about the escalation process. This process describes how and when to escalate issues. This process has to be defined and also adequately explained and communicated to stakeholders, so you an have an effective escalation process. [PMBOK 6th edition, Page.377] | توم في مرحلة تنفيذ مشروعه ويقوم أصحاب المصلحة بتصعيد المشكلات إلى الإدارة مباشرة دون إشراكه. أي مما يلي كان سيمنع حدوث ذلك إذا تم توثيقه وإبلاغه جيدًا؟ | ميثاق المشروع | سجل المشاكل | سجل المخاطر | خطة إدارة الاتصالات | تحتوي خطة إدارة الاتصالات على معلومات حول عملية التصعيد. توضح هذه العملية كيف ومتى يتم تصعيد المشكلات. يجب تحديد هذه العملية وشرحها بشكل مناسب وإبلاغها لأصحاب المصلحة ، حتى يكون لديك عملية تصعيد فعالة. [الطبعة السادسة ، صفحة 377 PMBOK] | 146 | 3 | False | "20" | Abdulfattah
292 | While Estimating costs - the PM expecting some rework in deliverables. However, the amount of rework is not known. This is an example of: | Management reserves | Three-Point Estimation | Betters-Up Estimation | Contingency Reserves | Expecting rework is known. However, the 'amount' of rework is unknown - which is an 'unknown.' Contingency reserves are meant for 'known unknowns' such as - risks which are identified and accepted. [PMBOK 6th edition, Page.245] | أثناء تقدير التكاليف - يتوقع مدير المشروع بعض إعادة العمل في المخرجات. ومع ذلك ، فإن مقدار إعادة العمل غير معروف. هذا مثال على: | إدارة الاحتياطيات | تقدير ثلاث نقاط | أفضل تقدير | احتياطيات الطوارئ | من المعروف أن توقع إعادة العمل. ومع ذلك ، فإن "مقدار" إعادة العمل غير معروف - وهو "غير معروف". احتياطيات الطوارئ مخصصة لـ "المجهول المعروف" مثل - المخاطر التي تم تحديدها وقبولها. [الطبعة السادسة ، صفحة 245 PMBOK] | 143 | 3 | False | "19" | Abdulfattah
293 | During the planning phase of a project, you learn that the sponsor has eliminated some important deliverables in other projects over the past three years, producing a negative cost variance. What should the you as a project manager do next? | Document the lessons learned. | Define the scope baseline correctly. | Document the issue in the issue log. | Include the risk in the risk register. | In the past project, the project sponsor eliminated some important deliverables causing negative cost variance. This considers risk and should be included in the risk register. [PMBOK 6th edition, Page.417] | أثناء مرحلة التخطيط لمشروع ما ، تعلم أن الراعي قد ألغى بعض الإنجازات المهمة في مشاريع أخرى على مدار السنوات الثلاث الماضية ، مما أدى إلى تباين سلبي في التكلفة. ماذا يجب عليك كمدير مشروع أن تفعل بعد ذلك؟ | توثيق الدروس المستفادة. | تحديد النطاق الأساسي بشكل صحيح. | القيام بتوثيق المشكلة في سجل القضية. | القيام بتضمين المخاطر في سجل المخاطر. | في المشروع السابق ، ألغى راعي المشروع بعض الإنجازات المهمة مما تسبب في تباين سلبي في التكلفة. هذا يأخذ في الاعتبار المخاطر ويجب إدراجها في سجل المخاطر. [الطبعة السادسة ، صفحة 417 PMBOK] | 147 | 3 | False | "20" | Abdulfattah
294 | You have only completed the project charter and is working on the project management plan. What should you as the project manager do next to build a detailed scope description? | Develop the scope statement with stakeholder input. | List all concerns in the stakeholder engagement plan. | Create the work breakdown structure. WBS | Implement the plan scope management process. | After developing the project charter and initiation phase, the first process in planning is to plan scope management then collect requirements then define scope process to Develop the scope statement. [PMBOK 6th edition, Page.134] | لقد أكملت ميثاق المشروع فقط وتعمل على خطة إدارة المشروع. ما الذي يجب عليك فعله كمدير للمشروع بعد ذلك لإنشاء وصف تفصيلي للنطاق؟ | تطوير بيان النطاق للمشروع مع مدخلات أصحاب المصلحة. | وضع قائمة بجميع المخاوف في خطة إشراك أصحاب المصلحة. | إنشاء هيكل تجزئة العمل. | تنفيذ عملية خطة إدارة نالطاق . | بعد تطوير ميثاق المشروع ومرحلة البدء ، فإن العملية الأولى في التخطيط هي تخطيط إدارة النطاق ثم جمع المتطلبات ثم تحديد عملية النطاق لتطوير بيان النطاق. [الطبعة السادسة ، صفحة 134 PMBOK] | 141 | 3 | False | "20" | Abdulfattah
295 | Your CEO asked you what the Estimate at Completion (EAC) will be for a small project you are working on. You were given a budget of $30,000, and to date, you have spent $20,000 but only completed $10,000 worth of work. You are sure the future work will be accomplished at the planned rate. What is the EAC? | $30,000 as Planned Rate | $60,000 as CPI is expected to be the same | $10,000 as CPI is expected to be the same | $40,000 as Planned Rate | If the future work will be accomplished at the planned rate, that the Estimate at Completion (EAC) will be AC + BAC - EV. Budget at Completion (BAC) is $30,000, Earned Value (EV) is $10,000, and Actual Cost (AC) is $20,000. Hence, the EAC is $40,000. [PMBOK 6th edition, Page 267] | سألك رئيسك التنفيذي عن التقدير عند الانتهاء (EAC) لمشروع صغير تعمل عليه. لقد حصلت على ميزانية قدرها 30000 دولار ، وحتى الآن ، أنفقت 20000 دولار ولكنك أكملت فقط 10000 دولار من العمل. أنت متأكد من أن العمل المستقبلي سيتم إنجازه بالمعدل المخطط له. ما هو EAC؟ | 30،000 دولار كماهو مخطط | من المتوقع أن يكون مبلغ 60،000 دولار (CPI) هو نفسه | 10000دولار المتوقع أن يكون CPI هو نفسه | 40,000دولار كماهو مخطط | إذا كان سيتم إنجاز العمل المستقبلي بالسعر المخطط له ، فإن التقدير عند الانتهاء (EAC) سيكون AC + BAC - EV. تبلغ الميزانية عند الانتهاء (BAC) 30،000 دولار ، والقيمة المكتسبة (EV) هي 10،000 دولار ، والتكلفة الفعلية (AC) هي 20،000 دولار. وبالتالي ، فإن EAC هو 40000 دولار. [الطبعة السادسة ، صفحة 267 PMBOK] | 143 | 5 | False | "19" | Abdulfattah
296 | You have been hired as a project manager for a new project. After several weeks, you discover that the accounting department has declined all charges because the project was not approved. What should the project manager have done to prevent this? | Planned the resources necessary to start the project | Verified that the business case was authorized by the project initiator | Obtained the fund needed to start the project | Obtained the project charter approval from the project sponsor | The sponsor or initiator of the project Is responsible to establish (approve and issue) the charter and can take the help of the prospect project manager to develop it. The project manager should obtain the project charter approval from the project sponsor because the project charter is a document that formally authorizes the existence of a project al d provides the project manager with the authority to apply organizational resources to project activities. [PMBOK 6th edition page, 75] | لقد تم تعيينك كمدير مشروع لمشروع جديد. بعد عدة أسابيع ، تكتشف أن قسم المحاسبة قد رفض جميع الرسوم بسبب عدم الموافقة على المشروع. ما الذي كان يجب على مدير المشروع فعله لمنع ذلك؟ | تخطيط الموارد اللازمة لبدء المشروع | التحقق من اعتماد دراسة الجدوى من قبل بادئ المشروع | الحصول على الأموال اللازمة لبدء المشروع | الحصول على موافقة ميثاق المشروع من راعي المشروع | يكون الراعي أو البادئ بالمشروع مسؤولاً عن إنشاء (الموافقة وإصدار) الميثاق ويمكنه الاستعانة بمدير المشروع المحتمل لتطويره. يجب أن يحصل مدير المشروع على موافقة ميثاق المشروع من الجهة الراعية للمشروع لأن ميثاق المشروع هو مستند يصرح رسميًا بوجود مشروع ، وهو ما يمنح مدير المشروع السلطة لتطبيق الموارد التنظيمية على أنشطة المشروع. [الطبعة السادسة ، صفحة 75 PMBOK] | 140 | 2 | False | "19" | Abdulfattah
297 | You are a project manager in a communication project. During the deployment of a new system, an unexpected power outage occurs. What should the project manager do? | Risk categorization | Risk probability and impact assessment | Perform a qualitative risk analysis | Refer to the risk register and inform key stakeholders | As an unexpected power outage occurs, the project manager should first Refer to the risk register and inform key stakeholders to handle this scenario. Risk categorization and Risk probability and Impact assessment are Tools & Techniques in Perform a qualitative risk analysis process, therefore they can be excluded. [PMBOK 6th edition, Page.417] | أنت مدير مشروع في مشروع اتصالات. أثناء نشر نظام جديد ، يحدث انقطاع غير متوقع للتيار الكهربائي. ماذا يجب أن يفعل مدير المشروع؟ | تصنيف المخاطر | اتقييم حتمالية المخاطر الأثر | القيام بإجراء تحليل نوعي للمخاطر | الرجوع إلى سجل المخاطر وإبلاغ أصحاب المصلحة الرئيسيين | عند حدوث انقطاع غير متوقع للتيار الكهربائي ، يجب على مدير المشروع الرجوع أولاً إلى سجل المخاطر وإبلاغ أصحاب المصلحة الرئيسيين للتعامل مع هذا السيناريو. تصنيف المخاطر واحتمالية المخاطر وتقييم الأثر هي أدوات وتقنيات في إجراء عملية تحليل مخاطر نوعية ، وبالتالي يمكن استبعادها. [الطبعة السادسة ، صفحة 417 PMBOK] | 147 | 4 | False | "18" | Abdulfattah
298 | During a review meeting, you observe that one team member performed tasks beyond the scope of work. What should you as the project manager do? | Crash the project to accommodate the additional scope that was performed. | Advice the team member to keep all work within project scope. | Inform the client of additional cost implications due to the extra work completed. | Review the impact on the baseline and initiate changes control procedures. | The project manager should Review the impact on the baseline and initiate changes control procedures. Option ( Advice the team member to keep all work within project scope. ) not enough because the out of scope tasks have already performed. Option ( Crash the project to accommodate the additional scope that was performed. ) Not correct because This means that the project manager agrees to carry out the tasks without requesting a change and this not good practice. Option ( Inform the client of additional cost implications due to the extra work completed. ) will be done by the CCB. [PMBOK 6th edition, Page.113] | أثناء اجتماع المراجعة ، لاحظت أن أحد أعضاء الفريق قد قام بمهام خارج نطاق العمل. ماذا يجب أن تفعل كمدير المشروع؟ | حشد الموارد المشروع لاستيعاب النطاق الإضافي الذي تم تنفيذه. | تقديم المشورة لعضو الفريق للحفاظ على كل العمل ضمن نطاق المشروع. | إبلاغ العميل بالآثار المترتبة على التكلفة الإضافية بسبب العمل الإضافي المنجز. | مراجعة التأثير على خط الأساس وابدأ في إجراءات التحكم في التغييرات. | يجب على مدير المشروع مراجعة التأثير على خط الأساس وبدء إجراءات التحكم في التغييرات. الخيار (نصيحة عضو الفريق لإبقاء كل العمل ضمن نطاق المشروع.) غير كافٍ لأن المهام خارج النطاق قد تم تنفيذها بالفعل. الخيار (حشد موارد المشروع لاستيعاب النطاق الإضافي الذي تم تنفيذه.) غير صحيح لأن هذا يعني أن مدير المشروع يوافق على تنفيذ المهام دون طلب تغيير وهذا ليس ممارسة جيدة. الخيار (إبلاغ العميل بالآثار المترتبة على التكاليف الإضافية بسبب العمل الإضافي المنجز.) سيتم تنفيذه بواسطة لجنة التحكم في التغيير. [الطبعة السادسة ، صفحة 113 PMBOK] | 141 | 5 | False | "17" | Abdulfattah
299 | You are a project manager of the civil Project. Your project is behind Schedule and the sponsor suggests reducing the time for quality assurance testing. What should you do first? | Perform quality audit. | Perform quality control measurements. | Change the quality requirements. | Follow the Quality Management Plan | The Project manager should Follow The quality management plan because it describes how applicable policies, procedures, and guidelines will be implemented to achieve the quality objectives. It describes the activities and resources necessary for the project management team to achieve the quality objectives set for the project. include Quality control and quality management activities planned for the project. [PMBOK 6th edition, Page 286] | أنت مدير مشروع في المشروع المدني. مشروعك متأخر عن الجدول الزمني ويقترح الراعي تقليل وقت اختبار ضمان الجودة. ما الذى ينبغى عليك فعله اولا؟ | القيام بإجراء تدقيق الجودة. | القيام بإجراء قياسات مراقبة الجودة. | تغيير متطلبات الجودة. | متابعة خطة إدارة الجودة | يجب على مدير المشروع اتباع خطة إدارة الجودة لأنها تصف كيفية تنفيذ السياسات والإجراءات والإرشادات المعمول بها لتحقيق أهداف الجودة. يصف الأنشطة والموارد اللازمة لفريق إدارة المشروع لتحقيق أهداف الجودة المحددة للمشروع. تشمل مراقبة الجودة وأنشطة إدارة الجودة المخطط لها للمشروع. [الطبعة السادسة ، صفحة 286 PMBOK] | 144 | 3 | False | "18" | Abdulfattah
300 | During initial project scheduling, an internal key stakeholder announces that they already agreed on some delivery dates with a vendor. What technique should you as the project manager use to ensure that all prerequisites are fulfilled for those deliverables to meet the agreed dates? | Discretionary dependencies. | Internal dependencies. | Finish-to-finish dependencies. | Mandatory dependencies. | Mandatory dependencies are those that are legally or contractually required or inherent in the nature of the work. In this scenario, a key stakeholder announces that they already agreed on some delivery dates with a vendor. The project manager should use the Mandatory dependencies to ensure that all prerequisites are fulfilled for those deliverables to meet the agreed dates. Option ( Discretionary dependencies and Internal dependencies ) not correct because the relation with the vendor..... [PMBOK 6th edition, Page.191] | أثناء الجدولة الأولية للمشروع ، يعلن أحد أصحاب المصلحة الرئيسيين الداخليين أنهم وافقوا بالفعل على بعض تواريخ التسليم مع البائع. ما هي التقنية التي يجب أن تستخدمها كمدير للمشروع لضمان استيفاء جميع المتطلبات الأساسية لتلك التسليمات لتلبية المواعيد المتفق عليها؟ | التبعيات التقديرية. | التبعيات الداخلية. | التبعيات من النهاية إلى النهاية. | التبعيات الإلزامية. | التبعيات الإلزامية هي تلك التي تكون مطلوبة قانونًا أو تعاقديًا أو متأصلة في طبيعة العمل. في هذا السيناريو ، يعلن أحد أصحاب المصلحة الرئيسيين عن موافقته بالفعل على بعض تواريخ التسليم مع البائع. يجب على مدير المشروع استخدام التبعيات الإلزامية لضمان استيفاء جميع المتطلبات الأساسية لتلك التسليمات للوفاء بالتواريخ المتفق عليها. الخيار (التبعيات التقديرية والتبعيات الداخلية) غير صحيح لأن العلاقة مع البائع . [الطبعة السادسة ، صفحة 191 PMBOK] | 142 | 3 | False | "20" | Abdulfattah
301 | Tom is the project manager of a project that is halfway through its execution. Jack realizes that the scope of the project should be changed due to a new government regulation affects the current project. What tool or technique should the project manager have considered before this issue occurred? | Stakeholder register. | Multicriteria decision analysis | Presentations | Stakeholder analysis. | Stakeholder analysis is the tool and technique in identify stakeholder process to know their requirements, expectations, the potential for influencing project outcomes, and the phase of the project life cycle where the stakeholder has the most influence or impact. [PMBOK 6th edition Page, 512] | توم هو مدير المشروع في منتصف الطريق من تنفيذه. يدرك جاك أنه يجب تغيير نطاق المشروع بسبب لائحة حكومية جديدة تؤثر على المشروع الحالي. ما الأداة أو التقنية التي يجب على مدير المشروع مراعاتها قبل حدوث هذه المشكلة؟ | سجل أصحاب المصلحة. | تحليل القرار متعدد المعايير | العروض التقديمية | تحليل اصحاب المصلحة. | تحليل أصحاب المصلحة هو الأداة والتقنية في تحديد عملية أصحاب المصلحة لمعرفة متطلباتهم وتوقعاتهم وإمكانية التأثير على نتائج المشروع ومرحلة دورة حياة المشروع حيث يكون لأصحاب المصلحة أكبر تأثير أو تأثير. [الطبعة السادسة ، صفحة 512 PMBOK] | 149 | 2 | False | "20" | Abdulfattah
302 | Which of the following data representation technique helps the project manager to classify the identified stakeholders? | Focus groups | Stakeholders assessment grid | Stakeholders register | Power/ interest grid | Power/interest grid. grouping the stakeholders based on their level of authority (power) and level of concern about the project's outcomes (interest). [PMBOK 6th edition, Page 512] | أي من تقنيات تمثيل البيانات التالية تساعد مدير المشروع على تصنيف أصحاب المصلحة المحددين؟ | المجموعات التخصصية | شبكة تقييم أصحاب المصلحة | سجل أصحاب المصلحة | شبكة السلطة / الاهتمام | شبكة القوة / الاهتمام. تجميع أصحاب المصلحة بناءً على مستوى سلطتهم (القوة) ومستوى القلق بشأن نتائج المشروع (الاهتمام). [الطبعة السادسة ، صفحة 512 PMBOK] | 149 | 2 | False | "18" | Abdulfattah
303 | The project charter has been signed, and a project management plan is in place. What should you as the project manager do next? | Develop the project schedule | Team-building activities | Meet with the project sponsor | Assign the project team. | The project charter has been signed and the project management plan is in place, this mean that the initiating and planning phase is finished and the next process is the execution phase. So, Assign the project team is the Correct answer. [PMBOK 6th edition, Page.328] | تم التوقيع على ميثاق المشروع ، وتم وضع خطة لإدارة المشروع. ماذا يجب أن تفعل بعد ذلك بصفتك مدير المشروع؟ | تطوير الجدول الزمني للمشروع | أنشطة بناء الفريق | لقاء مع راعي المشروع | تعيين فريق المشروع. | تم التوقيع على ميثاق المشروع وتم وضع خطة إدارة المشروع ، وهذا يعني أن مرحلة البدء والتخطيط قد انتهت وأن العملية التالية هي مرحلة التنفيذ. لذا ، فإن تعيين فريق المشروع هو الإجابة الصحيحة. [الطبعة السادسة ، صفحة 328 PMBOK] | 145 | 4 | False | "19" | Abdulfattah
304 | A project has a duration of three years. In the middle of the project, the project manager resigned. A new project manager was assigned, and at the first meeting, the project team told him that a flood may happen within the next few months and will affect the project equipment. What should the project manager do next? | Using a management reserves | Using a workaround | Update the risk register | Review a risk management plan | (Review a risk management plan), the Keyword in this question the ( new) project manager so the first thing the new project manager will do it review risk plan after this he will decide what will he do. [PMBOK 6th edition, Page.405] | مدة المشروع ثلاث سنوات. في منتصف المشروع ، استقال مدير المشروع. تم تعيين مدير مشروع جديد ، وفي الاجتماع الأول ، أخبره فريق المشروع أن فيضانًا قد يحدث خلال الأشهر القليلة المقبلة وسيؤثر على معدات المشروع. ماذا يجب أن يفعل مدير المشروع بعد ذلك؟ | استخدام إدارة الاحتياطيات | باستخدام الحل | تحديث سجل المخاطر | مراجعة خطة إدارة المخاطر | (راجع خطة إدارة المخاطر) ، الكلمة الرئيسية في هذا السؤال مدير المشروع (الجديد) ، لذا فإن أول شيء سيفعله مدير المشروع الجديد هو مراجعة خطة المخاطر بعد ذلك سيقرر ما سيفعله.[الطبعة السادسة ، صفحة 405 PMBOK] | 147 | 3 | False | "18" | Abdulfattah
305 | You are at the end of your civil project when the PMO head called you asking to ensure the transfer of liability of the buildings to the operation department. What should you do to achieve a PMO request? | Obtain Formal Acceptance from customer | Collect lessons learned and update knowledge base | Prepare and share the final project report | Obtain financial, legal, and administrative closure | Refer to PMP Exam Outline in the Closing Process Group ( Task no. 3 ) [PMBOK 6th edition, Page.121] | لقد وصلت إلى نهاية مشروعك المدني عندما اتصل بك رئيس مكتب إدارة المشروع ليطلب منك ضمان نقل مسؤولية المباني إلى قسم التشغيل. ماذا يجب أن تفعل لتحقيق طلب PMO؟ | الحصول على قبول رسمي من العميل | جمع الدروس المستفادة وتحديث قاعدة المعرفة | تحضير ومشاركة تقرير المشروع النهائي | الحصول على الإغلاق المالي والقانوني والإداري | راجع مخطط اختبار PMP في مجموعة عمليات الإغلاق (المهمة رقم 3) [الطبعة السادسة ، صفحة 121 PMBOK] | 140 | 6 | False | "18" | Abdulfattah
306 | You have recently been assigned to manage a project that is midway into execution. The project is behind schedule and under budget, but the customer is not happy with the performance of the project. What is the FIRST thing you should do? | Renegotiate the contract. | Reschedule baselines. | Discuss it with the project team. | Meet with the customer. | First, you need to find out why the customer is not happy. Then meet with the team and determine options. [PMBOK 6th edition, Page.95] | تم تكليفك مؤخرًا بإدارة مشروع في منتصف الطريق قيد التنفيذ. المشروع متأخر عن الجدول الزمني والميزانية ، لكن العميل غير راضٍ عن أداء المشروع. ما هو أول شيء يجب عليك فعله؟ | إعادة التفاوض على العقد. | إعادة جدولة خطوط الأساس. | المناقشة مع فريق المشروع. | مقابلة العميل. | أولاً ، عليك أن تعرف سبب عدم رضا العميل. ثم اجتمع مع الفريق وحدد الخيارات. [الطبعة السادسة ، صفحة 95 PMBOK] | 140 | 4 | False | "20" | Abdulfattah
307 | Fixed Price Contract is a form of which risk? | Avoiding | Mitigating | Working around | Transferring | The Buyer using Fixed Price Contract to Transfer the Risk to the Seller. [PMBOK 6th edition, Page 443] | عقد السعر الثابت هو شكل من أشكال أي مخاطر؟ | تجنب | التخفيف | يعمل حول | التحويل | يستخدم المشتري عقد السعر الثابت لنقل المخاطر إلى البائع. [الطبعة السادسة ، صفحة 443 PMBOK] | 147 | 3 | False | "19" | Abdulfattah
308 | Michel is managing a project. The project is about three-fourths done when the site engineer reports that due to inherent complexities in a specific task, the deliverables would be delayed. This would involve additional analysis and then implementation. He requests that this new work be added to the scope and also the time required to be added to the schedule. You and the site engineer have analyzed the impact of this change to cost, and have written up a change request and requested approval from the change control board. Just today, you have received approval from the change control board - what should be the immediate course of action? | Perform Quality Assurance | Ascertain the impact of this change to scope, schedule and cost before making any change | Start work immediately | Make sure that the scope baseline and schedule baseline are updated to reflect the approved change before implementing the change. | Direct and Manage Project Work is the process of leading and performing the work defined in the project management plan and implementing approved changes to achieve the project’s objectives. The key benefit of this process is that it provides overall management of the project work and deliverables, thus improving the probability of project success. [PMBOK 6th edition, Page.90] | ميشيل يدير مشروعًا. يتم تنفيذ المشروع حوالي ثلاثة أرباع عندما يبلغ مهندس الموقع أنه بسبب التعقيدات المتأصلة في مهمة معينة ، ستتأخر التسليمات. وسيشمل ذلك تحليلاً إضافياً ثم التنفيذ. ويطلب إضافة هذا العمل الجديد إلى النطاق وكذلك الوقت المطلوب لإضافته إلى الجدول. لقد قمت أنت ومهندس الموقع بتحليل تأثير هذا التغيير على التكلفة ، وقمت بكتابة طلب تغيير وطلب الموافقة من لوحة التحكم في التغيير. اليوم فقط ، تلقيت الموافقة من لجنة التحكم في التغيير - ما هو الإجراء الفوري للعمل؟ | أداء ضمان الجودة | التأكد من تأثير هذا التغيير على النطاق والجدول الزمني والتكلفة قبل إجراء أي تغيير | البدء العمل فورًا | التأكد من تحديث خط الأساس المرجعي للنطاق وخط الأساس المرجعي للجدول الزمني لتعكس التغيير المعتمد قبل تنفيذ التغيير. | توجيه وإدارة أعمال المشروع هي عملية قيادة وتنفيذ العمل المحدد في خطة إدارة المشروع وتنفيذ التغييرات المعتمدة لتحقيق أهداف المشروع. تتمثل الفائدة الرئيسية لهذه العملية في أنها توفر الإدارة الشاملة لعمل المشروع والتسليمات ، وبالتالي تحسين احتمالية نجاح المشروع. [الطبعة السادسة ، صفحة 90 PMBOK] | 140 | 4 | False | "19" | Abdulfattah
309 | Your project planner has just started working with your project and has produced defective reports for the past three accounting cycles. You are now checking your company policies before moving to the next step with the corrective actions. In which process are you now: | Control Scope | Validate Scope | Perform Quality Audit | Manage Quality | its - Audit technique- is a structured, independent process used to determine if project activities comply with organizational and project policies, processes, and procedures. [PMBOK 6th edition, Page 294] | بدأ مخطط المشروع الخاص بك للتو في العمل مع مشروعك وأصدر تقارير معيبة للدورات المحاسبية الثلاث الماضية. أنت الآن تتحقق من سياسات شركتك قبل الانتقال إلى الخطوة التالية بالإجراءات التصحيحية. في أي عملية أنت الآن: | نطاق التحكم | تحقق من النطاق | إجراء تدقيق الجودة | إدارة الجودة | تقنية التدقيق الخاصة بها هي عملية منظمة ومستقلة تستخدم لتحديد ما إذا كانت أنشطة المشروع تتوافق مع السياسات والعمليات والإجراءات التنظيمية والمتعلقة بالمشروع. [الطبعة السادسة ، صفحة 294 PMBOK] | 144 | 4 | False | "18" | Abdulfattah
310 | You are a project manager for a IT project. During the implementation phase, you found the budget of one of the supplied software packages became much more than you expected. What should you have been done to prevent this situation? | Procurement audit | Inspection and audit | Performance Review | Make or buy decision | If you make or buy decision in planning procurement, you could prevent this situation. [PMBOK 6th edition, Page 473] | أنت مدير مشروع لمشروع تكنولوجيا المعلومات. أثناء مرحلة التنفيذ ، وجدت أن ميزانية إحدى حزم البرامج المقدمة أصبحت أكثر بكثير مما كنت تتوقع. ما الذي كان يجب عليك فعله لمنع هذا الوضع؟ | تدقيق المشتريات | التفتيش والمراجعة | مراجعة الأداء | اتخاذ قرار الشراء أو الشراء | إذا قمت باتخاذ أو شراء قرار في التخطيط للمشتريات ، يمكنك منع هذا الموقف. [الطبعة السادسة ، صفحة 473 PMBOK] | 148 | 3 | False | "20" | Abdulfattah
311 | A recently promoted project manager must mange the weekly status update meeting. What should the project manager do to ensure a productive meeting? | Limit attendance to the project team and stakeholders | Avoid or smooth over any disagreements | Carefully read the latest meeting minutes | Circulate a defined agenda in advance | Meeting management is taking steps to ensure meetings meet their intended objectives effectively and efficiently. The following steps should be used for meeting planning: " Prepare and distribute the agenda stating the objectives of the meeting. "• Ensure that the meetings start and finish at the published time. Ensure the appropriate participants are invited and attend. " Stay on topic. " Manage expectations, issues, and conflicts during the meeting. " Record all actions and those who have been allocated the responsibility for completing the action. [PMBOK 6th edition page, 386] | يجب على مدير المشروع الذي تمت ترقيته مؤخرًا إدارة الاجتماع الأسبوعي لتحديث الحالة. ماذا يجب أن يفعل مدير المشروع لضمان اجتماع مثمر؟ | تحديد عدد الحضور لفريق المشروع وأصحاب المصلحة | تجنب أي خلافات أو حللها | القراءة بعناية آخر محضر الاجتماع | القيام بتوزيع جدول أعمال محدد مسبقًا | تتخذ إدارة الاجتماعات خطوات لضمان تلبية الاجتماعات لأهدافها المقصودة بفعالية وكفاءة. يجب استخدام الخطوات التالية للتخطيط للاجتماع: "إعداد وتوزيع جدول الأعمال الذي يوضح أهداف الاجتماع." • التأكد من أن الاجتماعات تبدأ وتنتهي في الوقت المنشور. تأكد من دعوة المشاركين المناسبين والحضور. "البقاء على الموضوع." إدارة التوقعات والقضايا والصراعات أثناء الاجتماع. "سجل جميع الإجراءات وأولئك الذين تم تكليفهم بمسؤولية إكمال الإجراء. [الطبعة السادسة ، صفحة 386 PMBOK] | 146 | 4 | False | "20" | Abdulfattah
312 | A security team notifies you of a change in security procedures. you use the change control process to update the project management plan. After seeing the change, a stakeholder complains that it was unnecessary because the project is almost complete. What should you as the project manager do? | Create a change request to reverse the change until a consensus is reached. | Add a risk to the risk register to track the impact of stakeholder disagreement. | Ignore the stakeholder's concern and follow the new procedures. | Convince the stakeholder of the benefits resulting from the change. | The project manager with the team member have evaluated the impact of this change on project constraints and then approved by the CCB. SO he should Convince the stakeholder of the benefits resulting from the change. Option ( Create a change request to reverse the change until a consensus is reached. ) not good because the change already approved after the consensus of CCB. Option ( Ignore the stakeholder's concern and follow the new procedures. ) not good practice to ignore the stakeholder's requests. Option ( Add a risk to the risk register to track the impact of stakeholder disagreement.) Not correct because this not a risk and the change has been approved. [PMBOK 6th edition, Page.530] | يخطرك فريق أمني بتغيير في الإجراءات الأمنية. تستخدم عملية التحكم في التغيير لتحديث خطة إدارة المشروع. بعد رؤية التغيير ، يشتكي أحد أصحاب المصلحة من أنه لم يكن ضروريًا لأن المشروع قد اكتمل تقريبًا. ماذا يجب أن تفعل كمدير المشروع؟ | القيام بإنشاء طلب تغيير لعكس التغيير حتى يتم التوصل إلى توافق في الآراء. | اضافة خطرًا إلى سجل المخاطر لتتبع تأثير خلاف أصحاب المصلحة. | تجاهل مخاوف أصحاب المصلحة واتبع الإجراءات الجديدة. | إقناع أصحاب المصلحة بالفوائد الناتجة عن التغيير. | قام مدير المشروع مع عضو الفريق بتقييم تأثير هذا التغيير على قيود المشروع ثم وافق عليه لجنة التحكم في التغيير. لذلك يجب عليه إقناع أصحاب المصلحة بالفوائد الناتجة عن التغيير. الخيار (إنشاء طلب تغيير لعكس التغيير حتى يتم التوصل إلى توافق في الآراء) ليس جيدًا لأن التغيير تمت الموافقة عليه بالفعل بعد إجماع لجنة التحكم في التغيير. الخيار (تجاهل مخاوف أصحاب المصلحة واتبع الإجراءات الجديدة.) ليس ممارسة جيدة لتجاهل طلبات أصحاب المصلحة. الخيار (إضافة مخاطرة إلى سجل المخاطر لتتبع تأثير خلاف أصحاب المصلحة.) غير صحيح لأن هذا لا يمثل مخاطرة وقد تمت الموافقة على التغيير. [الطبعة السادسة ، صفحة 530 PMBOK] | 149 | 5 | False | "19" | Abdulfattah
313 | The project team learns from a key stakeholders that some deliverables have been forwarded for approval without their knowledge. What should you have done to prevent this situation? | Notified the project team. | Scheduled a meeting with the customer and the project team | Consulted the most recent meeting minutes related to deliverable | Verified the communication management plan. | The communication management plan should be Verified to determine what communications should be shared and with whom. [PMBOK 6th edition, page 377] | علم فريق المشروع من أصحاب المصلحة الرئيسيين أنه تم إرسال بعض الإنجازات للموافقة عليها دون علمهم. ما الذي كان يجب عليك فعله لمنع هذا الوضع؟ | أخطر فريق المشروع. | حدد موعدًا لعقد اجتماع مع العميل وفريق المشروع | استشر محاضر الاجتماعات الأخيرة المتعلقة بالتسليم | التحقق من خطة إدارة الاتصالات. | يجب التحقق من خطة إدارة الاتصالات لتحديد الاتصالات التي يجب مشاركتها ومع من. [الطبعة السادسة ، صفحة 377 PMBOK] | 146 | 3 | False | "18" | Abdulfattah
314 | You are working as a research studying the growth of bacteria under different environmental conditions. Based on your experiments, you conclude that the immortality of bacteria increases as the temperature increases. What type of diagram can you use to illustrate your observation? | Control chart | Run Chart | Histogram | Scatter diagram | Scatter Diagram: Perfect Choice: As it is all about the correlation between two things. - Control Chart: Irrelevant choice: no where in the question, it has been asked about process in control/out of control/upper limit/lower limit. So ignore this choice - Pun Chart: It is all about trends. Did you see the keyword trends in the question? No, so you can ignore this choice - histogram: Are they talking about any bar graph? No, so eliminate this choice [PMBOK 6th edition, Page.293] | أنت تعمل كبحث يدرس نمو البكتيريا في ظل ظروف بيئية مختلفة. بناءً على تجاربك ، تستنتج أن خلود البكتيريا يزداد مع ارتفاع درجة الحرارة. ما نوع الرسم البياني الذي يمكنك استخدامه لتوضيح ملاحظتك؟ | مخطط التحكم | مخطط التشغيل | الرسم البياني التوزيعي | مخطط التشتت | مخطط التشتت: الخيار الأمثل: حيث يتعلق الأمر كله بالعلاقة بين شيئين. - مخطط التحكم: اختيار غير ذي صلة: لا في أي مكان في السؤال ، تم سؤاله عن العملية تحت السيطرة / خارج نطاق السيطرة / الحد الأعلى / الحد الأدنى. لذا تجاهل هذا الاختيار - مخطط التشغيل: يتعلق الأمر كله بالاتجاهات. هل رأيت اتجاهات الكلمات الرئيسية في السؤال؟ لا ، لذا يمكنك تجاهل هذا الاختيار - المدرج التكراري: هل يتحدثون عن أي رسم بياني التوزيعي؟ لا ، لذا تخلص من هذا الاختيار . [الطبعة السادسة ، صفحة 293 PMBOK] | 144 | 4 | False | "18" | Abdulfattah
315 | John finds that a specific work package was not delivered on time and will be delayed by an additional three weeks. He worries that this might impact project completion. What should John do first? | Determine if the work package is on the critical path. | Adjust the Gantt chart for the work package. | Use schedule compression to get the project back on track. | Calculate the amount of total float for the work package. | The work package will he delayed by an additional three weeks and may be have a float 4 weeks of more. So the project manager should FIRST Calculate the amount of total float for the work package. After this he will decide whether take corrective action or not. [PMBOK 6th edition, Page.210] | يرى جون أن حزمة عمل معينة لم يتم تسليمها في الوقت المحدد وستتأخر لمدة ثلاثة أسابيع إضافية. إنه قلق من أن هذا قد يؤثر على اكتمال المشروع. ما الذي يجب أن يفعله جون أولاً؟ | تحديد ما إذا كانت حزمة العمل على المسار الحرج. | ضبط مخطط جانت لحزمة العمل. | استخدام ضغط الجدول الزمني لإعادة المشروع إلى المسار الصحيح. | حساب مقدار السماحية الإجمالي لحزمة العمل. | سوف تتأخر حزمة العمل لمدة ثلاثة أسابيع إضافية وقد يكون لها فترة 4 أسابيع أخرى. لذلك يجب على مدير المشروع أولاً أن يحسب مقدار السماحية الإجمالي لحزمة العمل. بعد ذلك سيقرر اتخاذ إجراء تصحيحي أم لا. [الطبعة السادسة ، صفحة 210 PMBOK] | 142 | 5 | False | "20" | Abdulfattah
316 | During the testing phase, your testing team implemented a solution to correct a defect they discovered. The solution didn't have an impact on cost or time. You know the case now; as a Project manager your action should be: | Update management plans | Escalate the team member who did the action without letting you know | Issue a change request to CCB | Add the corrective action to a Lessons learned register | The lessons learned register is updated with information on the source of quality defects and how they could have been avoided as well as approaches that worked well. [PMBOK 6th edition, Page 306] | أثناء مرحلة الاختبار ، نفذ فريق الاختبار لديك حلاً لتصحيح العيب الذي اكتشفوه. لم يكن للحل تأثير على التكلفة أو الوقت. أنت تعرف الحالة الآن. كمدير للمشروع ، يجب أن يكون عملك: | تحديث خطط الإدارة | تصعيد عضو الفريق الذي نفذ الإجراء دون إخبارك | إصدار طلب تغيير للجنة التحكم في التغيير | أضافة الإجراء التصحيحي إلى سجل الدروس المستفادة | يتم تحديث سجل الدروس المستفادة بمعلومات عن مصدر عيوب الجودة وكيف كان من الممكن تجنبها بالإضافة إلى الأساليب التي نجحت. [الطبعة السادسة ، صفحة 306 PMBOK] | 144 | 5 | False | "20" | Abdulfattah
317 | All the following are true regarding resource calendars, except ? | Resource calendars are an output of the Acquire Resources process. | Resource calendars consider quantity, capability, and availability of equipment and material resources. | Resource calendars show the resources' vacation time | Resource calendars are an output of the Develop Schedule process. | Resource calendars are an input, not an output, of the Develop Schedule process as one of the project documents utilized. [PMBOK 6th edition, Page 205, 328] | كل ما يلي صحيح فيما يتعلق بتقاويم الموارد ، باستثناء؟ | تقاويم الموارد هي مخرج من عملية الحصول على الموارد. | تراعي تقاويم الموارد و الكمية والقدرة وتوافر المعدات والموارد المادية. | تعرض تقاويم الموارد وقت إجازة الموارد | تقاويم الموارد مخرج من عملية تطوير الجدول الجدول الزمني بالمشروع. | تقاويم الموارد هي مدخلات ، وليست مخرجات ، لعملية تطوير الجدول كأحد مستندات المشروع المستخدمة. [الطبعة السادسة ، صفحة 205, 328 PMBOK] | 142 | 3 | False | "18" | Abdulfattah
318 | You are a Project manager developing the project charter. Which of the Following are you using in this Process? | Project Management Plan | Deliverables | Stakeholder register | letters of intent | Agreements are used to define initial intentions for a project. Agreements may take the form of contracts, memorandums of understanding (MOUs), service level agreements (SLA), letters of agreement, letters of intent, verbal agreements, email, or other written agreements. Typically, a contract is used when a project is being performed for an external customer. [PMBOK 6th edition, Page78 ] | أنت مدير مشروع تقوم بتطوير ميثاق المشروع. أي مما يلي تستخدمه في هذه العملية؟ | خطة إدارة المشروع | مخرجات المشروع | سجل أصحاب المصلحة | خطابات النوايا | تستخدم الاتفاقيات لتحديد النوايا الأولية للمشروع. قد تتخذ الاتفاقيات شكل عقود أو مذكرات تفاهم (MOUs) أو اتفاقيات مستوى الخدمة (SLA) أو خطابات اتفاق أو خطابات نوايا أو اتفاقيات شفهية أو بريد إلكتروني أو اتفاقيات مكتوبة أخرى. عادة ، يتم استخدام العقد عندما يتم تنفيذ مشروع لعميل خارجي. [الطبعة السادسة ، صفحة 78 PMBOK] | 140 | 2 | False | "20" | Abdulfattah
319 | You are a project manager constructing a new railway. The rainy season in the area prevents on-site work for three months of each year. In which of the following should this information be documented initially? | Risk register. | Communication management plan. | Project schedule. | Project charter. | Since the project manager is aware of the rainy season will happen on a yearly basis, therefore it should be recorded in the project charter. [PMBOK 6th edition, Page.81] | أنت مدير مشروع إنشاء خط سكة حديد جديد. يمنع موسم الأمطار في المنطقة العمل في الموقع لمدة ثلاثة أشهر من كل عام. في أي مما يلي يجب توثيق هذه المعلومات مبدئيًا؟ | سجل المخاطر. | خطة إدارة الاتصالات. | الجدول الزمنى للمشروع. | ميثاق المشروع. | نظرًا لأن مدير المشروع على علم بأن موسم الأمطار سيحدث سنويًا ، لذلك يجب تسجيله في ميثاق المشروع. [الطبعة السادسة ، صفحة 81 PMBOK] | 140 | 2 | False | "19" | Abdulfattah
320 | A new resource has been assigned to a project team. He used to a different delivery method that is less productive and does not enforce deadline. The new delivery method is integrated so low productivity personnel have larger impact on the overall productivity of team performance. What strategy can the project manager apply to resolve the conflict with the new resource? | Force/direct. | Compromise/reconcile . | Smooth/accommodate. | Collaborate/problem solve. | Collaborate/problem solve is the best conflict resolution technique to resolve the conflict with the new resource. [PMBOK 6th edition Page, 349] | تم تعيين مورد جديد لفريق المشروع. لقد اعتاد على طريقة توصيل مختلفة أقل إنتاجية ولا يتم الوفاء ب الموعد النهائي. تم دمج طريقة التسليم الجديدة بحيث يكون للأفراد ذوي الإنتاجية المنخفضة تأثير أكبر على الإنتاجية الإجمالية لأداء الفريق. ما هي الإستراتيجية التي يمكن لمدير المشروع تطبيقها لحل التعارض مع المورد الجديد؟ | القوة / الاجبار. | حل وسط / تسوية. | التجانس / استيعاب. | التعاون / حل المشكلة. | حل التعاون / المشكلة هو أفضل تقنية لحل النزاعات لحل التعارض مع المورد الجديد. [الطبعة السادسة ، صفحة 349 PMBOK] | 145 | 4 | False | "20" | Abdulfattah
321 | You are managing a project which will provide web- base solutions to your customer. The requirements of this project are not clearly defined in the beginning and there will be modifications based on customer feedback as the project evolves. You plan as much as you can and work based on that. You continue the planning as you learn more about the project. Which techniques will be most helpful to define activities on the project? | Templates | WBS | Scope management | Rolling wave planning | Rolling wave planning is a form of progressive elaboration where work to be accomplished in the near term is planned in detail and future work is planned at a higher level of the WBS. Therefore, work can exist at various levels of detail, depending on where it is in the project life cycle. As more information is known about upcoming events, the near-term higher-level work packages can be decomposed further [PMBOK 6th edition, Page.185] | أنت تدير مشروعًا سيوفر حلول قاعدة الويب لعملائك. لم يتم تحديد متطلبات هذا المشروع بوضوح في البداية وستكون هناك تعديلات بناءً على ملاحظات العملاء مع تطور المشروع. أنت تخطط بقدر ما تستطيع وتعمل بناءً على ذلك. تستمر في التخطيط بينما تتعلم المزيد عن المشروع. ما هي التقنيات التي ستكون مفيدة للغاية في تحديد الأنشطة في المشروع؟ | النماذج | هيكل تنظيم العمل | إدارة نطاق | تخطيط الموجة المتدحرجة | يعد تخطيط الموجة المتدحرجة شكلاً من أشكال التفصيل التدريجي حيث يتم تخطيط العمل الذي يتعين إنجازه في المدى القريب بالتفصيل ويتم التخطيط للعمل المستقبلي على المدى البعيد بدون الدخول ف. لذلك ، يمكن أن يوجد العمل على مستويات مختلفة من التفاصيل ، اعتمادًا على مكانه في دورة حياة المشروع. مع معرفة المزيد من المعلومات حول الأحداث القادمة ، يمكن تحليل حزم العمل عالية المستوى على المدى القريب بشكل أكبر . [الطبعة السادسة ، صفحة 185 PMBOK] | 142 | 3 | False | "19" | Abdulfattah
322 | During the execution of the project, the project manager had to manage a change request. He evaluated the impact of the change on the other constraints of the project then he got the change request approved by CCB. The next step a project manager should do is: | Implement the Approved change. | Update Project Management plan. | Update the Issue Log. | Ask the Sponsor for authorization. | Customer or sponsor approval may be required for certain change requests after CCB approval unless they are part of the CCB. [PMBOK 6th edition, Page 115] | أثناء تنفيذ المشروع ، كان على مدير المشروع إدارة طلب التغيير. قام بتقييم تأثير التغيير على القيود الأخرى للمشروع ثم حصل على طلب التغيير الذي وافق عليه لجنة التحكم في التغيير. الخطوة التالية التي يجب على مدير المشروع القيام بها هي: | تنفيذ التغيير المعتمد. | تحديث خطة إدارة المشروع. | القيام بتحديث سجل المشاكل. | طلب الإذن من الراعي. | قد تكون موافقة العميل أو الراعي مطلوبة لطلبات تغيير معينة بعد التحكم في التغيير ما لم بكن الراعي جزء من هذا المجلس. [الطبعة السادسة ، صفحة 115 PMBOK] | 140 | 5 | False | "19" | Abdulfattah
323 | You are estimating the duration of your project activities using a triangular distribution formula. For a particular project activity, your Optimistic estimate is 14 days, Pessimistic estimate is 49 days, and Most Likely estimate is 27 days. What is the expected duration of this activity? | 50 | 25 | 32 | 30 | Triangular distribution allows the estimator to include three estimates: optimistic, pessimistic, and most likely. The expected duration is calculated using the equation: Expected Duration = [P + ML + O/3], where P is the pessimistic estimate, ML is the most likely estimate, and ) is the optimistic estimate. Using this method, the correct answer 14+49+27/3=30 days. [PMBOK 6th edition, Page.201] | أنت تقدر مدة أنشطة مشروعك باستخدام صيغة توزيع مثلثة. بالنسبة لنشاط مشروع معين ، فإن التقدير المتفائل الخاص بك هو 14 يومًا ، والتقدير المتشائم هو 49 يومًا ، والتقدير الأكثر احتمالًا هو 27 يومًا. ما هي المدة المتوقعة لهذا النشاط؟ | 50 | 25 | 32 | 30 | يسمح التوزيع الثلاثي للمقدر بتضمين ثلاثة تقديرات: متفائلة ، ومتشائمة ، والأرجح. يتم حساب المدة المتوقعة باستخدام المعادلة: المدة المتوقعة = (P+ML+O)/3 ، حيث P هو التقدير المتشائم ، و ML هو التقدير الأكثر احتمالية ، و) هو التقدير المتفائل. باستخدام هذه الطريقة ، فإن الإجابة الصحيحة (14 + 49 + 27)/3 = 30 يومًا. [الطبعة السادسة ، صفحة 201 PMBOK] | 142 | 3 | False | "20" | Abdulfattah
324 | During a unique product development project, you notice that the requirements are conceptual and that it is difficult to obtain a shared understanding by all stakeholders. What can you do to obtain a shared understanding of the project's requirements? | Benchmark with the other organizations. | Conduct a requirements walkthrough. | Hold brainstorming sessions with the stakeholders. | Build a prototype. | Prototyping is a method of obtaining early feedback on requirements by providing a model of the expected product before actually building it. Examples of prototypes are small-scale products, computer generated 2D and 3D models, mock-ups, or simulations. Prototypes allow stakeholders to experiment with a model of the final product rather than being limited to discussing abstract representations of their requirements. SO the project manager could obtain a shared understanding of the project's requirements by Build a prototype. [PMBOK 6th edition Page, 147] | أثناء مشروع تطوير منتج فريد ، لاحظت أن المتطلبات مفاهيمية وأنه من الصعب الحصول على فهم مشترك من قبل جميع أصحاب المصلحة. ما الذي يمكنك فعله للحصول على فهم مشترك لمتطلبات المشروع؟ | المقارنة مع المنظمات الأخرى. | القيام بجمع المتطلبات التفصيلية. | عقد جلسات عصف ذهني مع أصحاب المصلحة. | بناء نموذج أولي. | النماذج الأولية هي طريقة للحصول على ردود فعل مبكرة على المتطلبات من خلال تقديم نموذج للمنتج المتوقع قبل بنائه بالفعل. ومن الأمثلة على النماذج الأولية المنتجات الصغيرة أو النماذج ثنائية وثلاثية الأبعاد التي يتم إنشاؤها بواسطة الكمبيوتر أو النماذج أو المحاكاة. تسمح النماذج الأولية لأصحاب المصلحة بتجربة نموذج للمنتج النهائي بدلاً من الاقتصار على مناقشة التمثيلات المجردة لمتطلباتهم. لذلك يمكن لمدير المشروع الحصول على فهم مشترك لمتطلبات المشروع من خلال بناء نموذج أولي. [الطبعة السادسة ، صفحة 147 PMBOK] | 141 | 3 | False | "19" | Abdulfattah
325 | A supplier delivers equipment that fails to meet customer requirements in your project. After investigation, you determined that the supplier misunderstood the requirements and make incorrect assumptions without clarifying them with the customer. What type of communication methods should the project manager have used to avoid this? | Push communication | Pull communication | Manual communication | Interactive communication | ( Interactive communication ) is The best communication methods can be using to avoid the supplier misunderstood the requirements with the customer. [PMBOK 6th edition, Page.374] | يقوم المورد بتسليم المعدات التي لا تلبي متطلبات العملاء في مشروعك. بعد التحقيق ، اكتشفت أن المورد أساء فهم المتطلبات ووضع افتراضات غير صحيحة دون توضيحها مع العميل. ما نوع طرق الاتصال التي يجب على مدير المشروع استخدامها لتجنب ذلك؟ | دفع التواصل | سحب التواصل | الاتصال اليدوي | التواصل التفاعلي | (الاتصال التفاعلي) هو أفضل طرق الاتصال التي يمكن استخدامها لتجنب سوء فهم المورد للمتطلبات مع العميل.[الطبعة السادسة ، صفحة 374 PMBOK] | 146 | 3 | False | "19" | Abdulfattah
326 | The CTO identified a problem with one of the features of a software application your team was working on and submitted a change request. Even though it was out of the project's scope, the change control board approved the change. The BEST action to take next is: | Inform stakeholders with the new status of the project | Update Project management plan | Implement the Approved change request | Update the change log | The first step after the approved Change request is Update the change log . all change requests are recorded in the change log as a project document update. [PMBOK 6th edition, Page 120] | حدد كبير مهندسين التكنولوجيا مشكلة في إحدى ميزات تطبيق البرنامج الذي كان فريقك يعمل عليه وقدم طلب التغيير. على الرغم من أنه كان خارج نطاق المشروع ، وافق مجلس مراقبة التغيير على التغيير. أفضل إجراء بعد ذلك هو: | إبلاغ أصحاب المصلحة بالوضع الجديد للمشروع | تحديث خطة إدارة المشروع | تنفيذ طلب التغيير المعتمد | القيام بتحديث سجل التغيير | الخطوة الأولى بعد طلب التغيير المعتمد هي تحديث سجل التغيير. يتم تسجيل جميع طلبات التغيير في سجل التغيير كتحديث لوثيقة المشروع. [الطبعة السادسة ، صفحة 120 PMBOK] | 140 | 5 | False | "20" | Abdulfattah
327 | The Project team members and the subject matter expert (SME) are working on a design development project. You discover an enhancement that will improve the design. What should you as the project manager do? | Ask the subject matter expert (SME) to implement the enhancement. | Document this discovery, and present it to all stakeholders. | Ignore the enhancement, as no changes are allowed. | Ask the change control board (CCB) to review the enhancement. | Since the enhancement may impact the project baseline, so the next step, ask the change control board (CCB) to review the enhancement and make a decision. [PMBOK 6th edition, Page.113] | يعمل أعضاء فريق المشروع والخبير على مشروع تطوير التصميم. تكتشف انت مديسر المشروع تحسينًا من شأنه تحسين التصميم. ماذا يجب أن تفعل كمدير المشروع؟ | طلب رأي الخبير المتخصص لتنفيذ التحسين. | القيالن بتوثيق هذا الاكتشاف ، وتقديمه لجميع أصحاب المصلحة. | تجاهل التحسين ، حيث لا يسمح بإجراء أي تغييرات. | الطلب من لجنة التحكم في التغيير (CCB) مراجعة التحسين. | نظرًا لأن التحسين قد يؤثر على خط الأساس للمشروع ، فإن الخطوة التالية ، اطلب من لجنة التحكم في التغيير (CCB) مراجعة التحسين واتخاذ قرار. [الطبعة السادسة ، صفحة 113 PMBOK] | 140 | 5 | False | "19" | Abdulfattah
328 | Using quantitative risk analysis and modeling technique that helps to determine which risks have the most impact on a project. Your goal is to find whether the occurrence of a particular threat would be merely an inconvenience or would ruin the project. Which of the following tools will be most appropriate for your analysis? | Control chart | Expected monetary value | SWOT analysis | Tornado Diagram | A tornado diagram is a diagramming method to display sensitivity analysis data by examining all the uncertain elements at their baseline values. It gives a quick overview of how much the project will be impacted by various elements. The element with the greatest impact on the project appears at the top. This diagram can be used to determine sensitivity in cost, time, and objectives and is helpful in determining detailed response plans for elements with greater impacts. [PMBOK 6th edition, Page.434] | استخدام التحليل الكمي للمخاطر وتقنية النمذجة التي تساعد على تحديد المخاطر التي لها أكبر تأثير على المشروع. هدفك هو معرفة ما إذا كان حدوث تهديد معين سيكون مجرد إزعاج أو أنه سيدمر المشروع. أي من الأدوات التالية سيكون الأنسب لتحليلك؟ | مخطط التحكم | القيمة النقدية المتوقعة | تحليل نقاط القوة والضعف والتهديد والفرص | مخطط الاعصار | مخطط الإعصار هو طريقة رسم تخطيطي لعرض بيانات تحليل الحساسية عن طريق فحص جميع العناصر غير المؤكدة في قيمها الأساسية. يقدم نظرة عامة سريعة على مدى تأثر المشروع بالعناصر المختلفة. يظهر العنصر ذو التأثير الأكبر على المشروع في الأعلى. يمكن استخدام هذا الرسم البياني لتحديد الحساسية من حيث التكلفة والوقت والأهداف ، كما أنه مفيد في تحديد خطط الاستجابة التفصيلية للعناصر ذات التأثيرات الأكبر. [الطبعة السادسة ، صفحة 434 PMBOK] | 147 | 3 | False | "20" | Abdulfattah
329 | You notice that a process has 3 points between mean and lower control limit and 4 points between upper control limit and specification limit during the review of a control chart. How will you evaluate this process? | Cannot be determined | In control | Customer only can take decision for this process | Need solution | Although the Points is within the customer's specification limits, it is outside the control limit. Therefore, you will take corrective action so as to avoid any possible defect. [PMBOK 6th edition, Page 304] | لاحظت أن العملية بها 3 نقاط بين حد التحكم المتوسط ​​والسفلي و 4 نقاط بين حد التحكم الأعلى وحد المواصفات أثناء مراجعة مخطط التحكم. كيف ستقيم هذه العملية؟ | لا يمكن تحديدها | تحت السيطرة | يمكن للعميل فقط اتخاذ قرار لهذه العملية | بحاجة الى حل | على الرغم من أن النقاط تقع ضمن حدود مواصفات العميل ، إلا أنها خارج حدود التحكم. لذلك ، سوف تتخذ إجراءات تصحيحية لتجنب أي عيب محتمل. [الطبعة السادسة ، صفحة 304 PMBOK] | 144 | 5 | False | "18" | Abdulfattah
330 | The change control board (CCB) recently approved two change requests. 1st was a delay in activity on the critical path due to insufficient resources. 2nd was due to sending late communications to stakeholders. What should you do FIRST as a project manager? | Implement change request #2 | Hire additional resources to do both at the same time | Implement change request #1 | Ask CCB for further clarifications/explanations | The project manager should ask the CCB for further clarifications/explanations to Ensure that changes are made in a timely manner and Ensure changes are implemented in sequence. The CCB may also review configuration management activities. The roles and responsibilities of these boards are clearly defined and agreed upon by the appropriate stakeholders and are documented in the change management plan. CCB decisions are documented and communicated to the stakeholders for information and follow-up actions. [PMBOK 6th edition Page, 121] | وافق لجنة التحكم في التغيير (CCB) مؤخرًا على طلبين للتغيير. الأول كان تأخيرًا في النشاط على المسار الحرج بسبب عدم كفاية الموارد. الثاني كان بسبب إرسال الاتصالات المتأخرة إلى أصحاب المصلحة. ما الذي يجب عليك فعله أولاً كمدير مشروع؟ | تنفيذ طلب التغيير رقم 2 | الاستعانة بموارد إضافية للقيام بالأمرين معًا في نفس الوقت | تنفيذ طلب التغيير رقم 1 | الطلب من لجنة التحكم في التغيير المزيد من التوضيحات / التفسيرات | يجب على مدير المشروع أن يطلب من لجنة التحكم في التغيير المزيد من التوضيحات / التفسيرات لضمان إجراء التغييرات في الوقت المناسب وضمان تنفيذ التغييرات بالتسلسل. قد يقوم لجنة التحكم في التغيير أيضا بمراجعة أنشطة إدارة التهيئة. يتم تحديد أدوار ومسؤوليات هذه المجالس بوضوح والاتفاق عليها من قبل أصحاب المصلحة المناسبين ويتم توثيقها في خطة إدارة التغيير. يتم توثيق قرارات لجنة التحكم في التغيير وإبلاغ أصحاب المصلحة للحصول على المعلومات وإجراءات المتابعة. [الطبعة السادسة ، صفحة 121 PMBOK] | 140 | 6 | False | "20" | Abdulfattah
331 | The GM keeps asking for changes to the project scope that are not consistent with the original project requirements. One of the changes was requested one month before the project launch date. This change is projected to cause significant project delays. What should the project manager do? | Continue with the launch date as per the approved project management plan. | Update the change management document. | Inform the project steering committee about the project delay risk. | Submit a change request to the change control board (CCB). | Because changes to the project scope - cause significant project delays .. The project manager should Submit a change request to the change control board (CCB) for reviewing and approval. [PMBOK 6th edition, Page.113] | يستمر المدير العام في طلب إجراء تغييرات على نطاق المشروع لا تتوافق مع متطلبات المشروع الأصلية. تم طلب أحد التغييرات قبل شهر واحد من تاريخ إطلاق المشروع. من المتوقع أن يتسبب هذا التغيير في تأخيرات كبيرة في المشروع. ماذا يجب أن يفعل مدير المشروع؟ | الاستمرار في تاريخ الإطلاق وفقًا لخطة إدارة المشروع المعتمدة. | القيام بتحديث مستند إدارة التغيير. | إبلاغ اللجنة التوجيهية للمشروع عن مخاطر تأخير المشروع. | إرسال طلب تغيير إلى لجنة التحكم في التغيير (CCB). | لأن التغييرات في نطاق المشروع - تسبب تأخيرات كبيرة في المشروع .. يجب على مدير المشروع إرسال طلب تغيير إلى لجنة التحكم في التغيير (CCB) للمراجعة والموافقة. [الطبعة السادسة ، صفحة 113 PMBOK] | 141 | 5 | False | "16" | Abdulfattah
332 | You have a project that is three months behind but is surprisingly markedly under budget. You have decided to try to make up time, but needs to minimize the project risk. What is the best thing to do? | Fast track the project | Redefine the scope | Perform resource levelling | Crash the project | Crashing (adding resources) may be done as the project is within budget and crashing usually incurs an extra cost. Fast-tracking will increase the risk therefore not an option. [PMBOK 6th edition, Page.215] | لديك مشروع متأخر ثلاثة أشهر ولكن من المدهش أن الميزانية أقل بشكل ملحوظ. لقد قررت أن تحاول تعويض الوقت ، لكنك تحتاج إلى تقليل مخاطر المشروع. ما هو أفضل شيء نفعله؟ | تسريع انشطة المشروع | أعادة تحديد النطاق | القيام بتسوية الموارد | حشد الموارد بالمشروع | يمكن إجراء حشد الموارد (إضافة الموارد) لأن المشروع في حدود الميزانية وعادة ما يؤدي حشد الموارد إلى تكلفة إضافية. سيؤدي تسريع الانشطة إلى زيادة المخاطر وبالتالي ليس خيارًا. [الطبعة السادسة ، صفحة 215 PMBOK] | 142 | 3 | False | "18" | Abdulfattah
333 | You are working on a critical deliverable encounter a major change that affects the schedule baseline and the next milestone deliverable. You have assessed the impact of the change on the project constraints with your team, and the change control board just approved a change request. In which process will this change be implemented? | Perform integrated change control | Monitor and control project work | Develop project management plan | Direct and manage project work | Direct and Manage Project Work is the process of leading and performing the work defined in the project management plan and implementing approved changes to achieve the project's objectives. [PMBOK 6th edition, Page 90] | انت تعمل على تسليم مخرجات حرجة بالمشروع وتواجه تغييرًا رئيسيًا يؤثر على خط الأساس للجدول والتسليم الرئيسي التالي. لقد قمت بتقييم تأثير التغيير على قيود المشروع مع فريقك ، ووافق لجنة التحكم في التغيير للتو على طلب التغيير. في أي عملية سيتم تنفيذ هذا التغيير؟ | أداء مراقبة التغيير المتكامل | مراقبة عمل المشروع والتحكم فيه | تطوير خطة إدارة المشروع | توجيه وإدارة أعمال المشروع | توجيه وإدارة أعمال المشروع هي عملية قيادة وتنفيذ العمل المحدد في خطة إدارة المشروع وتنفيذ التغييرات المعتمدة لتحقيق أهداف المشروع. [الطبعة السادسة ، صفحة 90 PMBOK] | 140 | 4 | False | "19" | Abdulfattah
334 | The project manager is in the initiation phase of his project. What area should he consider when developing the business case? | Business benefits and portfolio analysis . | Expected resource performance to the strategic portfolio objectives. | Expected resource performance and cost-benefit analysis | Business benefits and the organizational strategy. | When developing the business case, the project manager should consider the business benefits and organizational strategy. Conduct benefit analysis with relevant stakeholders to validate project alignment with organizational strategy and expected business value. [PMBOK 6th edition, Page.29] | مدير المشروع في مرحلة البدء في مشروعه. ما المجال الذي يجب عليه مراعاته عند تطوير دراسة الجدوى؟ | فوائد الأعمال وتحليل المحفظة. | أداء الموارد المتوقع لأهداف المحفظة الاستراتيجية. | أداء الموارد المتوقع وتحليل التكلفة والعائد | فوائد الأعمال والاستراتيجية التنظيمية. | عند تطوير دراسة الجدوى ، يجب على مدير المشروع مراعاة فوائد العمل والاستراتيجية التنظيمية. قم بإجراء تحليل للمزايا مع أصحاب المصلحة المعنيين للتحقق من توافق المشروع مع الإستراتيجية التنظيمية وقيمة العمل المتوقعة. [الطبعة السادسة ، صفحة 29 PMBOK] | 140 | 2 | False | "20" | Abdulfattah
335 | Ben is the new project manager who has never managed a project before. He has been asked to plan a new project. Which of the following will help him to improve his chance of choices? | Configuration management. | Stakeholder analysis. | Your intuition and training. | Historical information. | Because Ben has no experience, he will have to look at the experience of others. This information is captured in the historical records from previous projects. [PMBOK 6th edition, Page.79] | بن هو مدير المشروع الجديد الذي لم يدير مشروعًا من قبل. لقد طُلب منه التخطيط لمشروع جديد. أي مما يلي سيساعده على تحسين فرصته في الاختيار؟ | إدارة التهيئة. | تحليل اصحاب المصلحة. | الحدس الخاص بك والتدريب. | السجلات التاريخية من مشاريع سابقة. | نظرًا لأن بن ليس لديه خبرة ، فسيتعين عليه النظر إلى تجربة الآخرين. يتم التقاط هذه المعلومات في السجلات التاريخية من المشاريع السابقة. [الطبعة السادسة ، صفحة 79 PMBOK] | 140 | 3 | False | "18" | Abdulfattah
336 | In order to determine the target fuel efficiency for a hybrid car being designed, you are looking at published statistics for similar models in the industry. The technique being used is called: | Brainstorming | Statistical sampling | Scatter diagrams | Benchmarking | What the Project Manager is trying to do is essentially look at the industry benchmark and make sure that the product is in line with it. This is the benchmarking technique. [PMBOK 6th edition, Page.281] | من أجل تحديد كفاءة الوقود المستهدفة لسيارة هجينة يتم تصميمها ، فأنت تبحث في الإحصائيات المنشورة عن الطراز المتماثلة في الصناعة. التقنية المستخدمة تسمى: | العصف الذهني | أخذ العينات الإحصائية | مخطط التشتت | المرجعية | ما يحاول مدير المشروع القيام به هو بشكل أساسي إلقاء نظرة على معيار الصناعة والتأكد من أن المنتج يتماشى معه. هذه هي تقنية القياس. [الطبعة السادسة ، صفحة 281 PMBOK] | 144 | 3 | False | "19" | Abdulfattah
337 | You are the project manager of the Mega IT Project. Before the implementation of a system upgrade, one of the team members discovers a critical defect in the current system that must be fixed. What should the project manager do? | Implement the fix | No action taken because the project scope has been finalized | Update the Risk register | Inform the project sponsor and follow the perform integrated change control process. | The correct answer is to Inform the project sponsor and follow the perform integrated change control process to fix the defect. [PMBOK 6th edition, Page.113] | أنت مدير مشروع ضخم في مجال تقنية المعلومات. قبل تنفيذ ترقية النظام ، يكتشف أحد أعضاء الفريق عيبًا خطيرًا في النظام الحالي يجب إصلاحه. ماذا يجب أن يفعل مدير المشروع؟ | تنفيذ الإصلاح | لم يتم اتخاذ أي إجراء لأنه تم الانتهاء من نطاق المشروع | تحديث سجل المخاطر | إبلاغ راعي المشروع واتباع عملية التحكم في التغيير المتكاملة. | الإجابة الصحيحة هي إبلاغ راعي المشروع واتباع عملية التحكم في التغيير المتكامل لإصلاح العيب. [الطبعة السادسة ، صفحة 113 PMBOK] | 140 | 5 | False | "20" | Abdulfattah
338 | After conducting a data analysis, John determines the cause and degree of variance relatives to the approved scope. What should the project manager do next? | Change the performance measurement baseline. | Revise the scope baseline. | Updates the scope management plan. | Decide if a corrective or preventative action is required | Important aspects of project scope control include determining the cause and degree of variance relative to the scope baseline and deciding whether corrective or preventive action is required. [PMBOK 6th edition Page, 170] | بعد إجراء تحليل البيانات ، يحدد جون سبب ودرجة التباين الأقارب للنطاق المعتمد. ماذا يجب أن يفعل مدير المشروع بعد ذلك؟ | تغيير الأساس لقياس الأداء. | القيام بمراجعة خط الأساس للنطاق. | تحديث خطة إدارة النطاق. | اتخاذ القرار ما إذا كان الإجراء التصحيحي أو الوقائي مطلوبًا | تشمل الجوانب المهمة للتحكم في نطاق المشروع تحديد سبب ودرجة التباين فيما يتعلق بخط الأساس للنطاق وتحديد ما إذا كان الإجراء التصحيحي أو الوقائي مطلوبًا. [الطبعة السادسة ، صفحة 170 PMBOK] | 141 | 5 | False | "20" | Abdulfattah
339 | Liza is a project manager in the execution stage of the project. Her team members are conducting a meeting to examine and document the effectiveness of risk responses in dealing with overall project risk and with identified individual project risk. What is the project team doing? | Reserve analysis | Risk reassessment | Status meeting | Risk review meeting | Risk reviews are scheduled regularly and should examine and document the effectiveness of risk responses in dealing with overall project risk and with identified individual project risks. [PMBOK 6th edition, Page 457] | ليزا هي مديرة المشروع في مرحلة تنفيذ المشروع. يعقد أعضاء فريقها اجتماعاً لفحص وتوثيق فعالية الاستجابات للمخاطر في التعامل مع مخاطر المشروع الإجمالية ومع مخاطر المشروع الفردية المحددة. ماذا يفعل فريق المشروع؟ | تحليل الاحتياطي | إعادة تقييم المخاطر | اجتماع الوضع | اجتماع مراجعة المخاطر | تتم جدولة مراجعات المخاطر بانتظام ويجب أن تدرس وتوثق فعالية الاستجابات للمخاطر في التعامل مع مخاطر المشروع الإجمالية ومع مخاطر المشروع الفردية المحددة. [الطبعة السادسة ، صفحة 457 PMBOK] | 147 | 5 | False | "19" | Abdulfattah
340 | You are the project manager of the Telecom Project and are working with the project stakeholders to determine the project requirements. You and the stakeholders are brainstorming privately to come up with as many solutions to the project as possible. After the brainstorming session, a recorder documents all the solutions on a white board so everyone can see the ideas and how they may be related. After the solutions have been documented, you lead the group through a voting process to discuss and rank each idea and requirement that has been proposed. What is this technique called? | Affinity diagram | Brainstorming | Mind mapping | Nominal group technique | The nominal group technique enhances brainstorming with a voting process used to rank the most useful ideas for further brainstorming or for prioritization. The nominal group technique is a structured form of brainstorming. [PMBOK 6th edition, Page.144] | أنت مدير مشروع الاتصالات وتعمل مع أصحاب المصلحة في المشروع لتحديد متطلبات المشروع. تقوم أنت وأصحاب المصلحة بتبادل الأفكار بشكل خاص للتوصل إلى أكبر عدد ممكن من الحلول للمشروع. بعد جلسة العصف الذهني ، يقوم المُسجل بتوثيق جميع الحلول على السبورة البيضاء حتى يتمكن الجميع من رؤية الأفكار وكيفية ارتباطها. بعد أن يتم توثيق الحلول ، تقوم بقيادة المجموعة خلال عملية التصويت لمناقشة وترتيب كل فكرة ومتطلبات تم اقتراحها. ماذا تسمى هذه التقنية؟ | مخطط التقارب | العصف الذهني | خريطة ذهنية | تقنية مجموعة الاسمية | تعزز تقنية المجموعة الاسمية العصف الذهني من خلال عملية التصويت المستخدمة لتصنيف الأفكار الأكثر فائدة لمزيد من العصف الذهني أو لتحديد الأولويات. تقنية المجموعة الاسمية هي شكل منظم من العصف الذهني. [الطبعة السادسة ، صفحة 144 PMBOK] | 141 | 3 | False | "20" | Abdulfattah
341 | The project manager got information that a very powerful stakeholder who was not identified in his stakeholder list isn't happy with his project performance. He asked for some updates to be done in the project. What is the first action project manager should do? | Implement the change. | Issue a change request to CCB. | Analyze the impact of the request on the project. | Update Stakeholder register. | Because ( the Stakeholder not identified ) so the first step you should update him in the Stakeholder register. [PMBOK 6th edition, Page.514] | حصل مدير المشروع على معلومات تفيد بأن أحد أصحاب المصلحة الأقوياء الذين لم يتم تحديدهم في قائمة أصحاب المصلحة ليس سعيدًا بأداء مشروعه. طلب بعض التحديثات التي يتعين القيام بها في المشروع. ما هو الإجراء الأول الذي يجب أن يفعله مدير المشروع؟ | تنفيذ التغيير. | إصدار طلب تغيير لبنك التعمير الصينى. | تحليل أثر الطلب على المشروع. | تحديث سجل اصحاب المصالح. | لأن (صاحب المصلحة لم يتم تحديده) لذا فإن الخطوة الأولى يجب عليك تحديثها في سجل أصحاب المصلحة. [الطبعة السادسة ، صفحة 514 PMBOK] | 149 | 2 | False | "19" | Abdulfattah
342 | While working on the project in the Manage Quality process, The project manager is determining the factors that may influence specific characteristics of a product under development and can improve the product's final characteristics. What technique is the PM using? | Analogous estimating | Benchmarking | Cost of quality | Design for X (Daft) | Design for X is a set of technical guidelines that may be applied during the design of a product for the optimization of a specific aspect of the design. Daft can control or even improve the product's final characteristics. [PMBOK 6th edition, Page 295] | أثناء العمل في المشروع في عملية إدارة الجودة ، يحدد مدير المشروع العوامل التي قد تؤثر على خصائص معينة لمنتج قيد التطوير ويمكن أن يحسن الخصائص النهائية للمنتج. ما هي التقنية التي يستخدمها PM؟ | تقدير مماثل | المرجعية | تكلفة الجودة | التصميم من اجل التميز | التصميم من اجل التميز عبارة عن مجموعة من الإرشادات الفنية التي يمكن تطبيقها أثناء تصميم منتج ما لتحسين جانب معين من التصميم. يمكن لـ Daft التحكم في الخصائص النهائية للمنتج أو حتى تحسينها. [الطبعة السادسة ، صفحة 295 PMBOK] | 144 | 4 | False | "19" | Abdulfattah
343 | Suzi is the project manager on a civil project. When she hears that her project has run into a snag due to weeks of bad weather on the job site, she says "No problem, we have insurance that covers cost overruns due to weather." What risk response strategy did she use? | Sharing | Avoidance | Mitigation | Transference | ( Transference), because of insurance. The transfer involves shifting ownership of a threat to a third party to manage the risk and to bear the impact if the threat occurs. A transfer can be achieved by a range of actions, which include but are not limited to the use of insurance, performance bonds, warranties, guarantees. [PMBOK 6th edition, Page 443] | سوزي هي مديرة المشروع في مشروع مدني. عندما علمت أن مشروعها واجه عقبة بسبب أسابيع من سوء الأحوال الجوية على موقع العمل ، قالت "لا مشكلة ، لدينا تأمين يغطي تجاوز التكاليف بسبب الطقس". ما هي استراتيجية الاستجابة للمخاطر التي استخدمتها؟ | مشاركة | تجنب | تخفيف | نقل | (نقل الخطر) بسبب التأمين. يتضمن النقل نقل ملكية التهديد إلى طرف ثالث لإدارة المخاطر وتحمل التأثير في حالة حدوث التهديد. يمكن تحقيق التحويل من خلال مجموعة من الإجراءات ، والتي تشمل على سبيل المثال لا الحصر استخدام التأمين وسندات حسن الأداء والضمانات والضمانات. [الطبعة السادسة ، صفحة 443 PMBOK] | 147 | 3 | False | "17" | Abdulfattah
344 | You are managing very complex project and due to a scope change, you need a few additional experts, which you did not think of earlier. You request that your company provide you with some experts for consultancy work. Although your company has provided you with those experts, they are located in a different geographical location. In this situation, how will you get their input? | None of the above | Recruit new members with same skills | Ask management to bring them to you | Create a virtual team | If your experts are located in different geographical locations and you need their input, you will create a virtual team including all these experts [PMBOK 6th edition, Page333] | أنت تدير مشروعًا معقدًا للغاية وبسبب تغيير النطاق ، فأنت بحاجة إلى عدد قليل من الخبراء الإضافيين ، وهو ما لم تفكر فيه من قبل. تطلب من شركتك تزويدك ببعض الخبراء للعمل الاستشاري. على الرغم من أن شركتك وفرت لك هؤلاء الخبراء ، إلا أنهم موجودون في موقع جغرافي مختلف. في هذه الحالة ، كيف ستحصل على مدخلاتهم؟ | لا شيء مما سبق | تجنيد أعضاء جدد بنفس المهارات | الطلب من الإدارة إحضارها إليك | إنشاء فريقًا افتراضيًا | إذا كان خبراؤك موجودين في مواقع جغرافية مختلفة وتحتاج إلى مدخلاتهم ، فستقوم بإنشاء فريق افتراضي يضم كل هؤلاء الخبراء [الطبعة السادسة ، صفحة 333 PMBOK] | 145 | 4 | False | "19" | Abdulfattah
345 | The project you are managing is large, when you starting to get approval for management reserve to use for unforeseen work happen in the execution phase, you were dealing with an interested stakeholder who has no authority. How can you handle that? | Monitor | Keep satisfied | Manage closely | Inform the stakeholder | The stakeholder Interested and no authority so the project manager should inform the Stakeholder. [PMBOK 6th edition, Page.512] | المشروع الذي تديره كبير ، عندما بدأت في الحصول على موافقة لاحتياطي الإدارة لاستخدامه في عمل غير متوقع يحدث في مرحلة التنفيذ ، كنت تتعامل مع صاحب مصلحة مهتم بالمشروع لكن ليس لديه سلطة. كيف يمكنك التعامل مع ذلك؟ | المراقبة | ابق راض | إدارة عن كثب | إبلاغ أصحاب المصلحة | صاحب المصلحة مهتم وليس لديه سلطة لذلك يجب على مدير المشروع إبلاغ أصحاب المصلحة. [الطبعة السادسة ، صفحة 512 PMBOK] | 149 | 2 | False | "20" | Abdulfattah
346 | During sequencing activities, your team defines that: • Activity A has a duration of three weeks. • Activity C with a duration of four weeks, will start first. • Activity B with a duration of two weeks, will start after completion of activity A • Activity D, with a duration of four weeks, will start with a lead time of one week upon completion of activity B • Activity E with a duration of five weeks, will start after the completion of activity C • Activity F, with a duration of three weeks, will have a start to start dependency with activity E, with a lag time of three weeks What is the project's critical path? | 8 weeks. | 12 weeks. | 9 weeks. | 10 weeks. | To calculate the project's Critical Path "shortest possible duration" , you should start drawing the network and sum the duration of the longest path to calculate the shortest possible duration First Path ( A-B-D = 8 Weeks ) Second Path ( C-E-F = 10 Weeks ) [PMBOK 6th edition, Page.210] | أثناء أنشطة التسلسل ، يحدد فريقك ما يلي: • مدة النشاط أ ثلاثة أسابيع. • النشاط ج لمدة أربعة أسابيع ، سيبدأ أولاً. • النشاط ب لمدة أسبوعين ، سيبدأ بعد الانتهاء من النشاط أ. • النشاط د ، لمدة أربعة أسابيع ، سيبدأ بمهلة أسبوع واحد عند الانتهاء من النشاط ب • النشاط هـ لمدة خمسة أسابيع ، ستبدأ بعد الانتهاء من النشاط C • النشاط F ، الذي يستمر لمدة ثلاثة أسابيع ، سيبدأ في بدء الاعتماد على النشاط E ، مع فترة تأخير تبلغ ثلاثة أسابيع. ما هو المسار الحرج للمشروع؟ | 8 أسابيع. | 12 أسبوعًا. | 9 أسابيع. | 10 أسابيع. | لحساب "أقصر مدة ممكنة" للمسار الحرج للمشروع ، يجب أن تبدأ في رسم الشبكة وتلخيص مدة أطول مسار لحساب أقصر مدة ممكنة المسار الأول (ABD = 8 أسابيع) المسار الثاني (CEF = 10 أسابيع). [الطبعة السادسة ، صفحة 210 PMBOK] | 142 | 3 | False | "19" | Abdulfattah
347 | The project manager is busy with an important milestone, and after that, he have to deliver a deliverable to the client. Since the client is known for his difficult behavior, management is worried whether the client will accept the deliverable. Therefore, they tell him to check the product acceptance criteria again before calling the client. What document will the PM look at to get this information.? | Control Chart | WBS dictionary | WBS | Project scope statement | In the project scope statement, you can see the product acceptance criteria. [PMBOK 6th edition, Page154] | مدير المشروع مشغول بإنجاز مهم ، وبعد ذلك ، عليه أن يسلم مخرجات المشروع الى العميل. نظرًا لأن العميل معروف بسلوكه الصعب ، فإن الإدارة تشعر بالقلق بشأن ما إذا كان العميل سيقبل التسليم. لذلك ، يطلبون منه التحقق من معايير قبول المنتج مرة أخرى قبل الاتصال بالعميل. ما هي الوثيقة التي سيبحثها مدير المشروع للحصول على هذه المعلومات.؟ | مخطط التحكم | قاموس هيكل تجزئة العمل | هيكل تجزئة العمل | بيان نطاق المشروع | في بيان نطاق المشروع ، يمكنك رؤية معايير قبول المنتج. [الطبعة السادسة ، صفحة 154 PMBOK] | 141 | 3 | False | "19" | Abdulfattah
348 | You are the project manager of a project near completion. After sending a follow-up report to the stakeholders, some stakeholders comment that some unresolved issues have been excluded from the report. What should you have done to prevent this? | Conducted the monitor Stakeholder Engagement process. | Followed the change control process. | Better controlled project documents. | Conducted the monitor communication process. | The monitor communication process requires reviewing data from the issue log, the issue log provides the project's history, a record of stakeholder engagement issues, and how they were resolved. The issue log may be updated with new information on issues raised, their progress, and resolution. [PMBOK 6th edition Page, 389, 390, 393] | أنت مدير مشروع على وشك الانتهاء. بعد إرسال تقرير متابعة إلى أصحاب المصلحة ، يعلق بعض أصحاب المصلحة بأن بعض المشاكل التي لم يتم حلها قد تم استبعادها من التقرير. ما الذي كان يجب عليك فعله لمنع ذلك؟ | إجراء رصد عملية إشراك أصحاب المصلحة. | متابعة عملية التحكم في التغيير. | التحكم بمستندات اعمال المشروع بشكل أفضل. | إجراء عملية مراقبة الاتصال. | تتطلب عملية مراقبة الاتصال مراجعة البيانات من سجل الأحداث ، ويوفر سجل الأحداث تاريخ المشروع ، وسجلًا لقضايا مشاركة أصحاب المصلحة ، وكيف تم حلها. قد يتم تحديث سجل الأحداث بمعلومات جديدة حول المشكلات المثارة ، وتقدمها ، وحلها. [الطبعة السادسة ، صفحة 389, 390, 393 PMBOK] | 146 | 5 | False | "19" | Abdulfattah
349 | During the design for a new laptop project, one of your team members discovers an approach for increasing the storage area for the laptop without increasing the expenses of the project. What is the best risk response to plan? | Mitigate | Accept | Transfer | Exploit | (Exploit) because of the approach for increasing the storage area for the laptop not increasing the expenses of the project so its opportunity, the best risk response is Exploit. [PMBOK 6th edition, Page.444] | أثناء تصميم مشروع كمبيوتر محمول جديد ، يكتشف أحد أعضاء فريقك طريقة لزيادة مساحة التخزين للكمبيوتر المحمول دون زيادة نفقات المشروع. ما هي أفضل استجابة للمخاطر للخطة؟ | تخفيف | قبول | نقل | استغلال | (استغلال الخطر) نظرًا لنهج زيادة مساحة التخزين للكمبيوتر المحمول وعدم زيادة نفقات المشروع ، وبالتالي فإن أفضل استجابة للمخاطر هي استغلال الخط. [الطبعة السادسة ، صفحة 444 PMBOK] | 147 | 3 | False | "19" | Abdulfattah
350 | You are a project manager during the initiation phase. Which of the following documents will help you while developing the project charter? | Brainstorming | Final report | Project Management Plan | Business case | The approved business case is the business document most commonly used to create the project charter. [PMBOK 6th edition, Page 77] | أنت مدير مشروع خلال مرحلة البدء. أي من المستندات التالية ستساعدك أثناء تطوير ميثاق المشروع؟ | العصف الذهني | التقرير الأخير | خطة إدارة المشروع | مستند حالة أعمال المشروع | مستند حالة أعمال المشروع المعتمدة هي وثيقة العمل الأكثر استخدامًا لإنشاء ميثاق المشروع. [الطبعة السادسة ، صفحة 77 PMBOK] | 140 | 2 | False | "19" | Abdulfattah
351 | A project manager has just learned that his project's sole equipment supplier has gone out of business. It is an unanticipated risk and will cause a delay in the project until a new vendor can be selected and contracts put in place. What do the PM do? | Continue working on non-critical path tasks. | Put out into RFP for new vendors. | Consult with legal counsel. | Notify the project stakeholders. | It’s an unanticipated risk, and will cause a delay, so the best thing to do as a project manager is Notify the project stakeholders (its workaround action to deal with unanticipated risk) [PMBOK 6th edition, Page.443] | علم مدير المشروع للتو أن مورد المعدات الوحيد لمشروعه قد توقف عن العمل. إنها مخاطرة غير متوقعة وستتسبب في تأخير المشروع حتى يتم اختيار بائع جديد وإبرام العقود. ماذا يجب ان يفعل مدير المشروع؟ | الاستمرار في العمل على مهام المسار غير الحرجة. | طرح طلب مقترح للبائعين الجدد. | استشارة مستشارًا قانونيًا. | إخطار أصحاب المصلحة في المشروع. | إنها مخاطرة غير متوقعة ، وستتسبب في تأخير ، لذا فإن أفضل ما يمكنك فعله كمدير للمشروع هو إخطار أصحاب المصلحة في المشروع (الإجراء البديل للتعامل مع المخاطر غير المتوقعة). [الطبعة السادسة ، صفحة 444 PMBOK] | 147 | 4 | False | "19" | Abdulfattah
352 | A key stakeholder has removed a key team resource from a project. The activities on the critical path will be negatively affected by this action. What should the project manager do? | Analyze the impact to the project management plan and submit a change request. | Engage the sponsor to discuss the importance of the resource with the functional leader. | Negotiate with and influence the functional leader to reverse their decision. | Acquire a replacement resource by following the resource management plan. | There is no benefit from the Negotiation with the functional leader to reverse their decision. Not good practice to Engage the sponsor as a first step. The project manager should Acquire a replacement resource by following the resource management plan because the critical path will be negatively affected by this action. [PMBOK 6th edition, Page.330] | قام أحد أصحاب المصلحة الرئيسيين بإزالة مورد الفريق الرئيسي من المشروع. ستتأثر الأنشطة على المسار الحرج سلبًا بهذا الإجراء. ماذا يجب أن يفعل مدير المشروع؟ | القيام بتحليل التأثير على خطة إدارة المشروع وإرسال طلب التغيير. | القيام بإشراك راعي المشروع لمناقشة أهمية المورد مع المدير الوظيفي. | التفاوض مع المدير الوظيفي والتأثير عليه لعكس قرارهم. | الحصول على مورد بديل باتباع خطة إدارة الموارد. | لا فائدة من التفاوض مع المدير الوظيفي لعكس قرارهم. ليست ممارسة جيدة لإشراك الراعي كخطوة أولى. يجب أن يحصل مدير المشروع على مورد بديل باتباع خطة إدارة الموارد لأن المسار الحرج سيتأثر سلبًا بهذا الإجراء. [الطبعة السادسة ، صفحة 330 PMBOK] | 145 | 4 | False | "20" | Abdulfattah
353 | A project manager in a multinational company has assigned to implement new software that will impact several departments. To guarantee alignment of stakeholder expectations with the final product, what should the PM develop? | Business case | Stakeholder engagement assessment matrix. | Risk Breakdown structure (RBS) | Stakeholder engagement plan. | The stakeholder engagement plan identifies the management strategies and actions required to effectively engage stakeholders. The stakeholder engagement plan provides guidance and information on managing stakeholder expectations. The stakeholder engagement plan include specific strategies or approaches for engaging with individuals or groups of stakeholders. [PMBOK 6 edition page, 509, 522] | كلف مدير مشروع في شركة متعددة الجنسيات بتنفيذ برنامج جديد من شأنه التأثير على العديد من الإدارات. لضمان مواءمة توقعات أصحاب المصلحة مع المنتج النهائي ، ما الذي يجب على مدير المشروع تطويره؟ | مستند حالة أعمال المشروع | مصفوفة تقييم مشاركة أصحاب المصلحة. | هيكل توزيع المخاطر (RBS) | خطة إشراك أصحاب المصلحة. | تحدد خطة إشراك أصحاب المصلحة استراتيجيات الإدارة والإجراءات المطلوبة لإشراك أصحاب المصلحة بشكل فعال. توفر خطة إشراك أصحاب المصلحة إرشادات ومعلومات حول إدارة توقعات أصحاب المصلحة. تتضمن خطة إشراك أصحاب المصلحة استراتيجيات أو مناهج محددة للمشاركة مع الأفراد أو مجموعات أصحاب المصلحة. [الطبعة السادسة ، صفحة 6, 509, 522 PMBOK] | 149 | 3 | False | "20" | Abdulfattah
354 | A project manager has signed a multi-year contract with a customer to complete a project for a fixed price. Since the duration of the contract is long, the PM has added a provision to adjust the price of the contract according to the market inflation. What kind of contract is this? | Cost plus fixed fee | Firm fixed price | Time and materials | Fixed price with economic price adjustment | The fixed price with economic price adjustment: This type is used whenever the seller's performance period spans a considerable period of years, or if the payments are made in a different currency. It is a fixed-price contract, but with a special provision allowing for predefined final adjustments to the contract price due to changed conditions, such as inflation changes or cost increases (or decreases) for specific commodities. [PMBOK 6th edition, Page 471] | وقع مدير المشروع عقدًا متعدد السنوات مع أحد العملاء لإكمال مشروع بسعر ثابت. نظرًا لأن مدة العقد طويلة ، فقد أضاف مدير المشروع بندًا لتعديل سعر العقد وفقًا لتضخم السوق. أي نوع من العقد هذا؟ | التكلفة بالإضافة إلى الرسوم الثابتة | سعر ثابت ثابت | الوقت والمواد | سعر ثابت مع تعديل السعر الاقتصادي | السعر الثابت مع تعديل السعر الاقتصادي: يستخدم هذا النوع كلما امتدت فترة أداء البائع لفترة طويلة من السنوات ، أو إذا تم سداد المدفوعات بعملة مختلفة. إنه عقد ثابت السعر ، ولكن مع بند خاص يسمح بإجراء تعديلات نهائية محددة مسبقًا على سعر العقد بسبب الظروف المتغيرة ، مثل تغيرات التضخم أو زيادة التكلفة (أو النقصان) لسلع معينة. [الطبعة السادسة ، صفحة 471 PMBOK] | 148 | 3 | False | "16" | Abdulfattah
355 | You are in the first meetings for your new project that you have been assigned to, two team members were discussing new ideas that each one thinks is correct and their opinion is the best for the project. You didn't interact or cut the discussion, as you know this is a normal discussion in this phase, which is? | Norming | Performing | Supporting | Storming | Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. if team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. [PMBOK 6th edition, Page 338] | أنت في الاجتماعات الأولى لمشروعك الجديد الذي تم تكليفك به ، وكان اثنان من أعضاء الفريق يناقشون أفكارًا جديدة يعتقد كل منهم أنها صحيحة ورأيهم هو الأفضل للمشروع. لم تتفاعل أو تقطع المناقشة كما تعلم أن هذا نقاش عادي في هذه المرحلة ، وهو؟ | مرحلة العصف | مرحلة الانجاز | مرحلة الدعم | مرحلة التشكل | مرحلة التشكل. خلال هذه المرحلة ، يبدأ الفريق في معالجة عمل المشروع والقرارات الفنية ونهج إدارة المشروع. إذا لم يكن أعضاء الفريق متعاونين أو منفتحين على أفكار ووجهات نظر مختلفة ، فقد تؤدي البيئة إلى نتائج عكسية. [الطبعة السادسة ، صفحة 338 PMBOK] | 145 | 4 | False | "19" | Abdulfattah
356 | During execution phase, a project manager learns that a team member's line manager believes they shouldn't execute a certain task. What document should the project manager review to resolve this? | Organizational chart | Work breakdown structure (WBS) | Resource management plan | RACI (responsible, accountable, consult, and inform) chart | The RACI chart is useful for ensuring team members' roles and responsibilities are clear, especially when the team consists of internal and external resources. [PMBOK 6th edition Page, 317] | أثناء مرحلة التنفيذ ، يتعلم مدير المشروع أن المدير المباشر لأحد أعضاء الفريق يعتقد أنه لا ينبغي له تنفيذ مهمة معينة. ما هي الوثيقة التي يجب على مدير المشروع مراجعتها لحل هذه المشكلة؟ | الهيكل التنظيمي | هيكل تنظيم العمل (WBS) | خطة إدارة الموارد | مخطط مصفوفة تعيين المسؤوليات (المسؤول والمحاسب والمستشار والإبلاغ) | يعد مخطط مصفوفة تعيين المسؤوليات مفيدًا لضمان وضوح أدوار ومسؤوليات أعضاء الفريق ، خاصةً عندما يتكون الفريق من موارد داخلية وخارجية. [الطبعة السادسة ، صفحة 317 PMBOK] | 145 | 3 | False | "19" | Abdulfattah
357 | One day before the launch of the new product, the project was terminated due to important distribution needs that were not identified. What should the PM developed to prevent this? | Stakeholder engagement plan | Risk management plan | Resource management plan | Communication management plan | The scenario implies there is a problem with project communications. To avoid this situation, the project manager should have been better developed the communication management plan. [PMBOK 6th edition, Page.377] | قبل يوم واحد من إطلاق المنتج الجديد ، تم إنهاء المشروع بسبب احتياجات التوزيع الهامة التي لم يتم تحديدها. ما الذي يجب على مدير المشروع تطويره لمنع ذلك؟ | خطة إشراك أصحاب المصلحة | خطة إدارة الخطر | خطة إدارة الموارد | خطة إدارة الاتصالات | يشير السيناريو إلى وجود مشكلة في اتصالات المشروع. لتجنب هذا الموقف ، كان ينبغي على مدير المشروع تطوير خطة إدارة الاتصالات بشكل أفضل. [الطبعة السادسة ، صفحة 377 PMBOK] | 146 | 3 | False | "20" | Abdulfattah
358 | Kim is a project manager for a big project. He want to outsource some of the works. The project schedule is very tight and the scope not well defined. What type of contract should Kim sign? | Firm fixed price contract (FFP) | Cost Plus Fixed Fee Contracts (CPFF) | Fixed Price Incentive Fee Contracts (FPIF) | Cost Plus Incentive Fee Contracts (CPIF) | The project scope not well defined so you can easily remove option Fixed Price Incentive Fee Contracts (FPIF) and Firm fixed price contract (FFP). Option Cost Plus Incentive Fee Contracts (CPIF) is the Best because this type Provide low risk for the buyer from CPFF. [PMBOK 6th edition, Page 472] | كيم هو مدير مشروع لمشروع كبير. يريد الاستعانة بمصادر خارجية لبعض الأعمال. جدول المشروع ضيق للغاية والنطاق غير محدد جيدًا. ما نوع العقد الذي يجب على كيم توقيعه؟ | عقد ثابت السعر (FFP) | عقود التكلفة بالإضافة إلى الرسوم الثابتة (CPFF) | عقود الرسوم الحافزة للأسعار الثابتة (FPIF) | عقود التكلفة بالإضافة إلى الرسوم الحافزة (CPIF) | نطاق المشروع غير محدد جيدًا حتى تتمكن بسهولة من إزالة عقود الرسوم الحافزة للأسعار الثابتة (FPIF) وعقد السعر الثابت للشركة (FFP). عقود الخيار التكلفة بالإضافة إلى الرسوم الحافزة (CPIF) هي الأفضل لأن هذا النوع يوفر مخاطر منخفضة للمشتري من CPFF. [الطبعة السادسة ، صفحة 472 PMBOK]. | 148 | 3 | False | "18" | Abdulfattah
359 | After defining project goals and objectives. The PMO conducts a meeting with stakeholders to align expectations. What result indicates that the project is moving forward correctly? | Statement of work (SOW) | Kick-off meeting | Business case | Key deliverables | Identify key deliverables based on the business requirements in order to manage customer expectations and direct the achievement of project goals. [PMBOK 6th edition, Page.95] | بعد تحديد أهداف وغايات المشروع. يعقد مكتب إدارة المشاريع اجتماعًا مع أصحاب المصلحة لمواءمة التوقعات. ما النتيجة التي تشير إلى أن المشروع يتقدم بشكل صحيح؟ | بيان العمل (SOW) | الإجتماع الإفتتاحي لانطلاق المشروع | مستند حالة أعمال المشروع | المخرجات الرئيسية | تحديد المخرجات الرئيسية بناءً على متطلبات العمل من أجل إدارة توقعات العملاء وتوجيه تحقيق أهداف المشروع. [الطبعة السادسة ، صفحة 95 PMBOK] | 140 | 4 | False | "20" | Abdulfattah
360 | Based on the following table, which of the following activities will be within the budget and behind schedule? | Activity C | Activity B | Activity D | Activity A | Budget is allocated by phase over the life of the project, but at a given point in time, planned value defines the physical work that should have been accomplished. The total of the PV is sometimes referred to as the performance measurement baseline (PMB). The total planned value for the project is also known as budget at completion (BAC). [PMBOK 6th edition, Page.267] | بناءً على الجدول التالي ، أي من الأنشطة التالية سيكون ضمن الميزانية ومتأخر عن الجدول الزمني؟ | النشاط ج | النشاط ب | النشاط د | النشاط أ | يتم تخصيص الميزانية حسب المرحلة على مدى عمر المشروع ، ولكن في وقت معين ، تحدد القيمة المخططة العمل المادي الذي كان ينبغي إنجازه. يُشار أحيانًا إلى إجمالي PV على أنه خط أساس قياس الأداء (PMB). يُعرف إجمالي القيمة المخططة للمشروع أيضًا باسم الميزانية عند الانتهاء (BAC). [PMBOK الطبعة السادسة ، الصفحة 267] | 143 | 5 | False | "19" | Abdulfattah
361 | You are a project manager and have received an acceptance of project deliverables and held the lessons learned session. What should you do next to close the project? | Validate the scope. | Release the resources. | Conduct performance evaluation. | Update the organizational process Assets. | The project manager has received an acceptance of project deliverables and held the lessons learned session so the validate scope process and Conduct performance evaluation have finished. Release the resources is the next step after update OPA. [PMBOK 6th edition, Page.121] | أنت مدير مشروع وتلقيت قبولًا لتسليمات المشروع وعقدت جلسة الدروس المستفادة. ماذا يجب أن تفعل بعد ذلك لإغلاق المشروع؟ | التحقق من صحة النطاق. | الاستغناء الموارد. | إجراء تقييم الأداء. | تحديث أصول العمليات التنظيمية. | تلقى مدير المشروع قبولًا لنواتج المشروع وعقد جلسة الدروس المستفادة حتى انتهت عملية التحقق من النطاق وتقييم أداء السلوك. تحرير الموارد هو الخطوة التالية بعد تحديث أصول العمليات التنظيمية. [الطبعة السادسة ، صفحة 121 PMBOK] | 140 | 6 | False | "19" | Abdulfattah
362 | You want to compare the baseline to the actual results and determine if the variance is within the threshold amount or if corrective or preventive action is appropriate during the implementation phase. Which of the following techniques can help you? | Trend analysis | Decomposition | Control chart | Variance Analysis | Variance analysis is used to compare the baseline to the actual results and determine if the variance is within the threshold amount or if corrective or preventive action is appropriate. [PMBOK 6th edition, Page 170] | تريد مقارنة خط الأساس بالنتائج الفعلية وتحديد ما إذا كان التباين ضمن مبلغ الحد أو ما إذا كان الإجراء التصحيحي أو الوقائي مناسبًا أثناء مرحلة التنفيذ. أي من الأساليب التالية يمكن أن تساعدك؟ | تحليل الاتجاه | التقسيم | مخطط التحكم | تحليل التباين | يستخدم تحليل التباين لمقارنة خط الأساس بالنتائج الفعلية وتحديد ما إذا كان التباين ضمن مبلغ الحد أو إذا كان الإجراء التصحيحي أو الوقائي مناسبًا. [الطبعة السادسة ، صفحة 170 PMBOK] | 141 | 5 | False | "19" | Abdulfattah
363 | A Project Manager is working on a project to create high-efficiency electric motors for a company introducing a new electric golf cart. The company's president is keenly interested in the project and requests a chart that shows the number of defects per deliverable and ranking of the causes of defects. Which type of chart would BEST meet this request? | Control chart | Statistical sampling | Scatter diagram | Histograms | Histograms show a graphical representation of numerical data Histograms can show the number of defects per deliverable, a ranking of the cause of defects, the number of times each process is noncompliant, or other representations of project or product defects. [PMBOK 6th edition, Page 293] | يعمل مدير المشروع على مشروع لإنشاء محركات كهربائية عالية الكفاءة لشركة تقدم عربة غولف كهربائية جديدة. يهتم رئيس الشركة بشدة بالمشروع ويطلب مخططًا يوضح عدد العيوب لكل منتج وترتيب أسباب العيوب. ما هو نوع الرسم البياني الأفضل لتلبية هذا الطلب؟ | مخطط التحكم | أخذ العينات الإحصائية | مخطط التشتت | الرسوم البيانية التوزيعية | تُظهر الرسوم البيانية التوزيعية تمثيلًا رسوميًا للبيانات الرقمية يمكن أن تُظهر الرسوم البيانية عدد العيوب لكل منتج ، أو ترتيب سبب العيوب ، أو عدد المرات التي تكون فيها كل عملية غير متوافقة ، أو تمثيلات أخرى لعيوب المشروع أو المنتج. [الطبعة السادسة ، صفحة 293 PMBOK] | 144 | 4 | False | "20" | Abdulfattah
364 | You receives an email from a vendor that a key deliverables will be delayed by a month. What should you as the project manager do first? | Call the vendor to obtain a justification for the delay. | Update the management and obtain their advice. | Meet with the team identify ways to absorb this delay. | Assess the impact of the delay on the project plan. | The project manager should FIRST Assess the impact of the delay on the project plan then take the corrective action such as Meet with the team identify ways to absorb this delay to find solutions. Option ( Update the management and obtain their advice. ) not good practice as the project manager should be proactive and find ways to solve the problems with the team members. Option Call the vendor to obtain a justification for the delay. ) not good also because he already received an email from a vendor that a key deliverables will be delayed by a month and the calling not will be useful. [PMBOK 6th edition, Page.419] | تتلقى بريدًا إلكترونيًا من أحد البائعين يفيد بأن التسليمات الرئيسية ستتأخر لمدة شهر. ما الذي يجب أن تفعله كمدير المشروع أولاً؟ | الاتصال بالبائع للحصول على مبرر للتأخير. | تحديث الإدارة والحصول على نصائحهم. | مقابلة الفريق وتحديد طرقًا لامتصاص هذا التأخير. | تقييم أثر التأخير على خطة المشروع. | يجب على مدير المشروع أولاً تقييم تأثير التأخير على خطة المشروع ثم اتخاذ الإجراء التصحيحي مثل مقابلة الفريق لتحديد طرق امتصاص هذا التأخير لإيجاد حلول. الخيار (تحديث الإدارة والحصول على نصائحهم.) ليس ممارسة جيدة حيث يجب أن يكون مدير المشروع استباقيًا ويجد طرقًا لحل المشكلات مع أعضاء الفريق. خيار اتصل بالبائع للحصول على سبب للتأخير. ) ليس جيدًا أيضًا لأنه تلقى بالفعل بريدًا إلكترونيًا من أحد البائعين يفيد بتأخير التسليمات الرئيسية لمدة شهر ولن يكون الاتصال مفيدًا. [الطبعة السادسة ، صفحة 419 PMBOK] | 147 | 3 | False | "20" | Abdulfattah
365 | Creating a network diagram for your project, Activity A (5 days ) can start immediately. Activity B ( 3 days ) can start after Activity A is complete. Activity C ( 2 days ) can start after Activity B is complete. Activity D (4 days ) can start after Activity A and B are complete. Activity E ( 3 days ) can start after Activity C and D are complete. While having all Activities as FS relation, what is the Float of Activity D? | 2 Day | 3 Day | 1 Day | 0 Day | After drawing the network, you will determine that Activity D on the Critical Path. So the float = zero. [PMBOK 6th edition, Page.210] | إنشاء مخطط شبكة لمشروعك ، يمكن أن يبدأ النشاط أ (5 أيام) على الفور. يمكن أن يبدأ النشاط ب (3 أيام) بعد اكتمال النشاط أ. يمكن أن يبدأ النشاط ج (يومان) بعد اكتمال النشاط ب. يمكن أن يبدأ النشاط د (4 أيام) بعد اكتمال النشاط أ وب. يمكن أن يبدأ النشاط هـ (3 أيام) بعد اكتمال النشاطين ج ود. أثناء وجود كل الأنشطة كعلاقة FS ، ما هو تعويم النشاط D؟ | 2 يوم | 3 يوم | يوم 1 | 0 يوم | بعد رسم الشبكة ، ستحدد النشاط D على المسار الحرج. لذا فإن السماحية في التاخر للنشاط = صفر. [الطبعة السادسة ، صفحة 210 PMBOK] | 142 | 3 | False | "20" | Abdulfattah
366 | You want to confirm that the project team implemented best practices for the requirements-gathering process. What should you as the project manager do? | Examine the lessons learned repository | Review quality control reports | Evaluate the work performance reports | Perform a quality audit | Quality audit objectives include: Identifying all good and best practices being implemented, sharing good practices introduced or implemented in similar projects in the organization and/or industry; and proactively offering assistance in a positive manner to improve the implementation of processes to help raise team productivity. So the project manager should perform a quality audit to confirm that the project team implemented best practices for the requirements-gathering process. [PMBOK 6th edition page, 294] | تريد التأكيد على أن فريق المشروع قد طبق أفضل الممارسات لعملية جمع المتطلبات. ماذا يجب أن تفعل كمدير المشروع؟ | فحص قاعد بيانات الدروس المستفادة | مراجعة تقارير مراقبة الجودة | تقييم تقارير أداء العمل | القيام بإجراء تدقيق الجودة | تشمل أهداف تدقيق الجودة ما يلي: تحديد جميع الممارسات الجيدة وأفضل الممارسات التي يتم تنفيذها ، ومشاركة الممارسات الجيدة التي تم إدخالها أو تنفيذها في مشاريع مماثلة في المنظمة و / أو الصناعة ؛ وتقديم المساعدة بشكل استباقي بطريقة إيجابية لتحسين تنفيذ العمليات للمساعدة في زيادة إنتاجية الفريق. لذلك يجب على مدير المشروع إجراء تدقيق الجودة للتأكد من أن فريق المشروع طبق أفضل الممارسات لعملية جمع المتطلبات. [الطبعة السادسة ، صفحة 294 PMBOK] | 144 | 4 | False | "19" | Abdulfattah
367 | During benefit analysis, the project sponsor requires that you submit a proposal for an implementation strategy. What should you do next? | Review the SOW | Invite the stakeholder for discussions | Identify the key deliverable | Identify high level risk, constrains and assumptions | Identify high-level risks, assumptions, and constraints based on the current environment, organizational factors, historical data, and expert judgment, in order to propose an implementation strategy. [PMBOK 6th edition, Page.81] | أثناء تحليل الفوائد ، يطلب راعي المشروع منك تقديم اقتراح لاستراتيجية التنفيذ. ماذا يجب ان تفعل بعد ذلك؟ | مراجعة بيان العمل SOW | القيام بدعوة أصحاب المصلحة للمناقشات | تحديد مفتاح التسليم | تحديد المخاطر والقيود والافتراضات عالية المستوى | حدد المخاطر والافتراضات والقيود عالية المستوى بناءً على البيئة الحالية والعوامل التنظيمية والبيانات التاريخية وأحكام الخبراء ، من أجل اقتراح استراتيجية التنفيذ. [الطبعة السادسة ، صفحة 81 PMBOK] | 140 | 2 | False | "19" | Abdulfattah
368 | You are in the execution phase of a project to build a stadium. The project team develops a new response for an existing risk that will reduce the schedule by 20 days. What document should the project manager update? | Risk breakdown structure (PBS). | Risk management plan | Schedule management plan | Risk register | The risk register is updated when appropriate risk responses are chosen and agreed upon. [PMBOK 6th edition, Page 448] | أنت في مرحلة تنفيذ مشروع لبناء ملعب. يطور فريق المشروع استجابة جديدة لمخاطر قائمة من شأنها تقليل الجدول الزمني بمقدار 20 يومًا. ما هي الوثيقة التي يجب على مدير المشروع تحديثها؟ | هيكل توزيع المخاطر (PBS). | خطة إدارة الخطر | خطة إدارة الجدول | سجل المخاطر | يتم تحديث سجل المخاطر عند اختيار الاستجابات المناسبة للمخاطر والاتفاق عليها. [الطبعة السادسة ، صفحة 448 PMBOK] | 147 | 3 | False | "16" | Abdulfattah
369 | The customer always asks for a lot of changes in scope and product features during the project execution. You accept all changes to meet customer satisfaction. After a period of implementation, you noticed inflation in the budget. What should you have done to prevent this situation? | Control scope | Cost management plan | Scope management plan | Change management plan | Change management plan, which provides the direction for managing the change control process and documents the formal change control board (CCB). if the PM implemented the change requests without analyzing the impact of the changes on time and cost and quality will increase the risks in the project and lead to increased costs (cost overruns). [PMBOK 6th edition, Page.88] | يطلب العميل دائمًا الكثير من التغييرات في النطاق وميزات المنتج أثناء تنفيذ المشروع. أنت تقبل جميع التغييرات لتلبية رضا العملاء. بعد فترة من التنفيذ لاحظت تضخم في الميزانية. ما الذي كان يجب عليك فعله لمنع هذا الوضع؟ | التحكم بالنطاق | خطة إدارة التكلفة | خطة إدارة النطاق | خطة ادارة التغيير | خطة إدارة التغيير ، والتي توفر التوجيه لإدارة عملية التحكم في التغيير وتوثيق لجنة التحكم في التغيير الرسمي (CCB). إذا نفذ مدير المشروع طلبات التغيير دون تحليل تأثير التغييرات على الوقت والتكلفة والجودة سيزيد من المخاطر في المشروع ويؤدي إلى زيادة التكاليف (تجاوز التكلفة المحددة). [الطبعة السادسة ، صفحة 88 PMBOK] | 140 | 3 | False | "19" | Abdulfattah
370 | You are the project manager for a mobile application development project. An issue has occurred and one of the team members identifies a workaround, but fails to inform you. After a few weeks, a similar issue appeared again that impact the project. What should have done to prevent this situation? | Escalate the problem to the sponsor | Updating the risk register | Revising the responsibility assignments matrix (RAM). | Performing a root cause analysis | To prevent this issue from appearing again, he should Performing the root cause of the problem and documented it in the lessons learned. [PMBOK 6th edition, Page.292] | أنت مدير المشروع لمشروع تطوير تطبيقات الهاتف المحمول. حدثت مشكلة وقام أحد أعضاء الفريق بتحديد حل بديل ، لكنه فشل في إبلاغك. بعد بضعة أسابيع ، ظهرت مشكلة مماثلة مرة أخرى تؤثر على المشروع. ما الذي كان يجب فعله لمنع هذا الوضع؟ | تصعيد المشكلة إلى الراعي | تحديث سجل المخاطر | مراجعة مصفوفة تعيين المسؤوليات. | إجراء تحليل السبب الجذري | لمنع ظهور هذه المشكلة مرة أخرى ، يجب عليه تنفيذ السبب الجذري للمشكلة وتوثيقه في الدروس المستفادة. [الطبعة السادسة ، صفحة 292 PMBOK] | 144 | 4 | False | "20" | Abdulfattah
371 | A project manager decides to procure the full amount of a required project material to exploit a price-volume discount. There months later, the price for that material drops by 50 percent due to over- production and change in technology. What should the project manager have done differently? | Purchased the material from two or more vendors. | Purchased the minimum amount of the material. | Negotiated with the vendor to adjust the price. | Properly identified the risks. | Procure the full amount of a required project material is a big risk and the project manager should have done Properly identified the risks. [PMBOK 6th edition, Page.409] | يقرر مدير المشروع شراء المبلغ الكامل لمادة المشروع المطلوبة لاستغلال خصم السعر على الكمية. بعد ذلك بأشهر ، انخفض سعر هذه المادة بنسبة 50 في المائة بسبب الإنتاج الزائد والتغير في التكنولوجيا. ما الذي كان يجب أن يفعله مدير المشروع بشكل مختلف؟ | شراء المادة من بائعين أو أكثر. | شراء الحد الأدنى من المواد. | تفاوض مع البائع لتعديل السعر. | تحديد المخاطر بشكل صحيح. | يعد شراء المبلغ الكامل لمواد المشروع المطلوبة مخاطرة كبيرة ويجب أن يقوم مدير المشروع بتحديد المخاطر بشكل صحيح.[الطبعة السادسة ، صفحة 409 PMBOK] | 147 | 3 | False | "19" | Abdulfattah
372 | A project is initiated, and planned. As a project manager, you are about to conduct the kick-off meeting with all stakeholders, and you feel that the strategic directions for the project need to be presented first. Who should present this topic? | customer | Project manager | Functional manager | Project sponsor | The project sponsor is the person presenting the organization's strategy ( strategic directions ) during the kick-off meeting, While the project manager presents the project (implementation strategy). [PMBOK 6th edition, Page.377] | تم البدء في المشروع والتخطيط له. بصفتك مديرًا للمشروع ، أنت على وشك إجراء الاجتماع الافتتاحي لانطلاق المشروع مع جميع أصحاب المصلحة ، وتشعر أن التوجيهات الإستراتيجية للمشروع تحتاج إلى تقديمها أولاً. من يجب أن يقدم هذا الموضوع؟ | العميل | مدير المشروع | مدير وظيفي | راعي المشروع | راعي المشروع هو الشخص الذي يقدم إستراتيجية المنظمة (الاتجاهات الإستراتيجية) خلال الاجتماع الافتتاحي ، بينما يقدم مدير المشروع المشروع (إستراتيجية التنفيذ). [الطبعة السادسة ، صفحة 377 PMBOK] | 146 | 3 | False | "18" | Abdulfattah
373 | Risk event should be removed from your project. The removal of the requirements does affect your project scope, but it can release the project from high-risk exposure. What risk response has been enacted in this project? | Mitigation | Transference | Acceptance | Avoidance | Risk avoidance is when the project team acts to eliminate the threat or protect the project from its impact. Avoidance may involve changing some aspect of the project management plan or changing the objective that is in jeopardy in order to eliminate the threat entirely, reducing its probability of occurrence to zero. Examples of avoidance actions may include removing the cause of a threat, extending the schedule, changing the project strategy, or reducing scope. [PMBOK 6th edition, Page 443 ] | يجب إزالة حدث الخطر من مشروعك. تؤثر إزالة المتطلبات على نطاق مشروعك ، ولكن يمكن أن تحرر المشروع من التعرض لمخاطر عالية. ما هي الاستجابة للمخاطر التي تم تفعيلها في هذا المشروع؟ | تخفيف | نقل | قبول | تجنب | يتم تجنب المخاطر عندما يعمل فريق المشروع للقضاء على التهديد أو حماية المشروع من تأثيره. قد يشمل التجنب تغيير بعض جوانب خطة إدارة المشروع أو تغيير الهدف المعرض للخطر من أجل القضاء على التهديد تمامًا ، مما يقلل من احتمال حدوثه إلى الصفر. قد تتضمن أمثلة إجراءات التجنب إزالة سبب التهديد ، أو تمديد الجدول ، أو تغيير استراتيجية المشروع ، أو تقليل النطاق. [الطبعة السادسة ، صفحة 443 PMBOK] | 147 | 3 | False | "19" | Abdulfattah
374 | You are informed that one of the suppliers who is working on your project has taken another project during the implementation phase. As a project manager, what should you do next? | Change management plan | Procurement review | Remove the supplier from your project. | Performance review | Performance reviews for contracts measure, compare and analyze quality, resource, schedule, and cost performance against the agreement. This includes identifying work packages that are ahead or behind schedule, over or under budget or have resource or quality issues. [PMBOK 6th edition, Page 498] | تم إخطارك بأن أحد الموردين الذين يعملون في مشروعك قد تولى مشروعًا آخر خلال مرحلة التنفيذ. كمدير مشروع ، ماذا يجب أن تفعل بعد ذلك؟ | تغيير خطة الإدارة | مراجعة المشتريات | القيام بإزالة المورد من مشروعك. | مراجعة الأداء | قياس مراجعات الأداء للعقود ، وتقارن وتحلل أداء الجودة والموارد والجدول الزمني والتكلفة مقابل الاتفاقية. يتضمن ذلك تحديد حزم العمل التي تتقدم أو تتأخر عن الجدول الزمني ، أو تزيد أو تقل عن الميزانية أو بها مشكلات تتعلق بالموارد أو الجودة. [الطبعة السادسة ، صفحة 498 PMBOK] | 148 | 5 | False | "18" | Abdulfattah
375 | On a virtual project status meeting, there is a team member who consistently has issues with the technology being used to join the meeting. These issues are preventing this team member from being actively engaged in the meetings. What should the project manager do? | Ask another team member to follow up and provide updates to the team member. | Call this team member separately to communicate the project status. | Replace the team member with someone who has more technology experience. | Have a separate meeting with the team member to find a solution together. | The project manager should have a separate meeting with the team member to find a solution together because these issues are preventing this team member from being actively engaged in the meetings. This is an example of solve problem technique. [PMBOK 6th edition, Page.356] | في اجتماع حالة المشروع الافتراضي ، هناك عضو في الفريق لديه مشكلات باستمرار مع التكنولوجيا المستخدمة للانضمام إلى الاجتماع. تمنع هذه المشكلات عضو الفريق هذا من المشاركة بنشاط في الاجتماعات. ماذا يجب أن يفعل مدير المشروع؟ | الطلب من عضو آخر في الفريق المتابعة وتقديم التحديثات لعضو الفريق. | الاتصال بعضو الفريق هذا بشكل منفصل للإبلاغ عن حالة المشروع. | استبدال عضو الفريق بشخص لديه خبرة تقنية أكبر. | عقد اجتماعًا منفصلاً مع عضو الفريق لإيجاد حل معًا. | يجب أن يعقد مدير المشروع اجتماعًا منفصلاً مع عضو الفريق لإيجاد حل معًا لأن هذه المشكلات تمنع عضو الفريق هذا من المشاركة بنشاط في الاجتماعات. هذا مثال على تقنية حل المشكلة. [الطبعة السادسة ، صفحة 356 PMBOK] | 145 | 4 | False | "20" | Abdulfattah
376 | William is the project manager of the civil Project. He and the project team have identified a risk event in the project with a high probability of occurrence and the risk event has a high-cost impact on the project. William discusses the risk event with Virginia, the primary project customer, and she decides that the requirements surrounding the risk event should be removed from the project. The removal of the requirements does affect the project scope, but it can release the project from high-risk exposure. What risk response has been enacted in this project? | Mitigation | Transference | Acceptance | Avoidance | Avoid. Where the level of overall project risk is significantly negative and outside the agreed-upon risk thresholds for the project, an avoid strategy may be adopted. This involves taking focused action to reduce the negative effect of uncertainty on the project as a whole and bring the project back within the thresholds. [PMBOK 6th edition, Page.445] | ويليام هو مدير مشروع المشروع المدني. لقد حدد هو وفريق المشروع حدثًا خطرًا في المشروع مع احتمال كبير لحدوثه ويكون لحدث الخطر تأثير عالي التكلفة على المشروع. تناقش ويليام حدث المخاطر مع فيرجينيا ، العميل الأساسي للمشروع ، وتقرر إزالة المتطلبات المحيطة بحدث الخطر من المشروع. تؤثر إزالة المتطلبات على نطاق المشروع ، ولكن يمكن أن تحرر المشروع من التعرض لمخاطر عالية. ما هي الاستجابة للمخاطر التي تم تفعيلها في هذا المشروع؟ | تخفيف | نقل | قبول | تجنب | تجنب. عندما يكون مستوى المخاطر الكلية للمشروع سلبيًا بشكل كبير وخارج حدود المخاطر المتفق عليها للمشروع ، يمكن اعتماد استراتيجية تجنب. يتضمن ذلك اتخاذ إجراءات مركزة لتقليل التأثير السلبي لعدم اليقين على المشروع ككل وإعادة المشروع إلى حدود العتبات. [الطبعة السادسة ، صفحة 445 PMBOK] | 147 | 4 | False | "16" | Abdulfattah
377 | During the execution phase. A risk management plan has been implemented and risk analysis is ongoing. How should the impacts of identified risks be communicated to the stakeholder? | Show the reasons for upcoming risks using either an affinity diagram or a matrix diagram. | Engage in opportunity management on the identified risks for added value. | Calculate the necessary contingency funding and time buffers needed for the risk response. | Draw a probability and impact matrix to prioritize risks. | Draw a probability and impact matrix or a hierarchical chart to prioritize risks to communicate the impacts of identified risks to the stakeholder. A probability and impact matrix is a grid for mapping the probability of each risk occurrence and its impact on project objectives if that risk occurs. Hierarchical charts. Where risks have been categorized using more than two parameters, the probability and impact matrix cannot be used and other graphical representations are required [PMBOK 6th edition, Page 425] | خلال مرحلة التنفيذ. تم تنفيذ خطة إدارة المخاطر وتحليل المخاطر بشكل مستمر. كيف ينبغي إبلاغ آثار المخاطر المحددة لأصحاب المصلحة؟ | القيام بعرض أسباب المخاطر القادمة باستخدام مخطط تقارب أو مخطط مصفوفة. | الانخراط في إدارة الفرص بشأن المخاطر المحددة لتحقيق قيمة مضافة. | حساب التمويل اللازم للطوارئ والمخازن الزمنية اللازمة للاستجابة للمخاطر. | رسم مصفوفة الاحتمالات والأثر لتحديد أولويات المخاطر. | رسم مصفوفة الاحتمالات والأثر أو مخططًا هرميًا لتحديد أولويات المخاطر لإبلاغ آثار المخاطر المحددة إلى أصحاب المصلحة. مصفوفة الاحتمالات والتأثير هي شبكة لرسم خرائط احتمالية حدوث كل خطر وتأثيره على أهداف المشروع في حالة حدوث ذلك الخطر. المخططات الهرمية. عندما يتم تصنيف المخاطر باستخدام أكثر من معلمتين ، لا يمكن استخدام مصفوفة الاحتمالات والتأثير ، ويلزم تقديم تمثيلات بيانية أخرى. [الطبعة السادسة ، صفحة 425 PMBOK] | 147 | 3 | False | "20" | Abdulfattah
378 | During managing stakeholder expectations, at the end of the design phase, you found one of the key stakeholders complain of one of work package still not complete. You do not agree and review with him the WBS dictionary but the stakeholder is still unsatisfied. What is the next document you should review? | Requirement management plan | Scope management plan | WBS | Scope Baseline | Scope baseline contains the approved project scope statement which includes Project scope description, Acceptance criteria, and Project deliverables. [PMBOK 6th edition, Page.161] | أثناء إدارة توقعات أصحاب المصلحة ، في نهاية مرحلة التصميم ، وجدت أحد أصحاب المصلحة الرئيسيين يشكو من إحدى حزم العمل التي لم تكتمل بعد. أنت لا توافق وتراجع معه قاموس WBS لكن صاحب المصلحة لا يزال غير راضٍ. ما هي الوثيقة التالية التي يجب عليك مراجعتها؟ | خطة إدارة المتطلبات | خطة إدارة النطاق | هيكل تجزئة العمل | الخط الاساس المرجعي للنطاق المعتمد | يحتوي خط الأساس للنطاق على بيان نطاق المشروع المعتمد والذي يتضمن وصف نطاق المشروع ومعايير القبول وتسليمات المشروع. [الطبعة السادسة ، صفحة 161 PMBOK] | 141 | 3 | False | "20" | Abdulfattah
379 | On your project, two team members often disagree. You need a long-term conflict resolution method. You decide to use which one of the following approaches? | Withdrawal | Smoothing | Compromise | Problem solving | ( Problem-solving ) which provides a long-term resolution. Collaborate/problem solve. Incorporating multiple viewpoints and insights from differing perspectives; requires a cooperative attitude and open dialogue that typically leads to consensus and commitment. This approach can result in a win-win situation. [PMBOK 6th edition, Page 349] | غالبًا ما يختلف اثنان من أعضاء الفريق في مشروعك. أنت بحاجة إلى طريقة طويلة الأمد لحل النزاعات. قررت استخدام أي من الأساليب التالية؟ | انسحاب | التجانس | مرونة | حل المشاكل | (حل المشكلات) الذي يوفر حلًا طويل المدى. التعاون / حل المشكلة. دمج وجهات نظر ورؤى متعددة من وجهات نظر مختلفة ؛ يتطلب موقفًا تعاونيًا وحوارًا مفتوحًا يؤدي عادةً إلى توافق والتزام. يمكن أن يؤدي هذا النهج إلى وضع مربح للجانبين. [الطبعة السادسة ، صفحة 161 PMBOK] | 145 | 4 | False | "19" | Abdulfattah
380 | You want to recruit another team member to replace an architect who resigned from your project. What document should capture this change? | Organizational process Assets. | Project management plan. | Ground rules | Responsibility assignments matrix (RAM) | RAMs are used within the group to designate roles, responsibilities, and levels of authority for specific activities. The matrix format shows all activities associated with one person and all people associated with one activity. This also ensures that there is only one person accountable for any one task to avoid confusion about who is ultimately in charge or has authority for the work. [PMBOK 6th edition Page, 317] | تريد تعيين عضو آخر في الفريق ليحل محل المهندس المعماري الذي استقال من مشروعك. ما هي الوثيقة التي يجب أن تلتقط هذا التغيير؟ | أصول العمليات التنظيمية. | خطة إدارة المشروع. | القواعد الأساسية | مصفوفة تعيين المسؤوليات | تُستخدم مصفوفة تعيين المسؤوليات داخل المجموعة لتحديد الأدوار والمسؤوليات ومستويات السلطة لأنشطة محددة. يُظهر تنسيق المصفوفة جميع الأنشطة المرتبطة بشخص واحد وجميع الأشخاص المرتبطين بنشاط واحد. وهذا يضمن أيضًا أن يكون هناك شخص واحد فقط مسؤول عن أي مهمة واحدة لتجنب الالتباس حول من هو المسؤول في النهاية أو الذي لديه السلطة على العمل. [الطبعة السادسة ، صفحة 317 PMBOK] | 145 | 3 | False | "20" | Abdulfattah
381 | You are managing a project in which your team members all work in the same location and have worked together on many projects. You have seniors and junior team members. Senior team members feel that they are always overloaded and junior team members are not learning that fast. As a Project manager, what should you do? | Focus on decreasing sources of conflicts Team | Team-building activities | A kick-off meeting | Recognition and Rewards throughout the project | People are motivated when they feel they are valued in the organization and the rewards are given to they demonstrate this value. Most project team members are motivated by an opportunity to grow, accomplish, and apply their professional skills to meet new challenges. A good strategy for project managers is to give team recognition throughout the life cycle of the project rather than waiting until the project is completed. [PMBOK 6th edition, Page 342] | أنت تدير مشروعًا يعمل فيه أعضاء فريقك جميعًا في نفس الموقع وعملوا معًا في العديد من المشاريع. لديك أعضاء فريق كبار وصغار. يشعر أعضاء الفريق الكبار أنهم مثقلون دائمًا وأن أعضاء الفريق المبتدئين لا يتعلمون بهذه السرعة. كمدير مشروع ، ماذا يجب أن تفعل؟ | التركيز على تقليل مصادر الصراع الفريق | أنشطة بناء الفريق | اجتماع افتتاحي لانطلاق المشروع | التقدير والمكافآت طوال المشروع | يتم تحفيز الأشخاص عندما يشعرون بالتقدير في المنظمة ويتم منح المكافآت لهم لإثبات هذه القيمة. يحفز معظم أعضاء فريق المشروع فرصة للنمو والإنجاز وتطبيق مهاراتهم المهنية لمواجهة التحديات الجديدة. تتمثل الإستراتيجية الجيدة لمديري المشروع في منح تقدير الفريق طوال دورة حياة المشروع بدلاً من الانتظار حتى اكتمال المشروع. [الطبعة السادسة ، صفحة 342 PMBOK] | 145 | 4 | False | "20" | Abdulfattah
382 | The customer has requested a change in the scope which you have processed through a change request and it is approved from CCB. Now, you are in the process of implementing this change into the project. In which of the following processes do you implement the approved change? | Perform integrated change control | Monitor and control project work | Control scope | Direct and manage project work | Approved change requests will be implemented through the Direct and Manage Project Work process. [PMBOK 6th edition, Page120] | طلب العميل تغيير النطاق الذي قمت بمعالجته من خلال طلب التغيير وتمت الموافقة عليه من بنك التعمير الصينى. الآن ، أنت بصدد تنفيذ هذا التغيير في المشروع. في أي من العمليات التالية يتم تنفيذ التغيير المعتمد؟ | أداء مراقبة التغيير المتكامل | مراقبة عمل المشروع والتحكم فيه | التحكم بالنطاق | توجيه وإدارة أعمال المشروع | سيتم تنفيذ طلبات التغيير المعتمدة من خلال عملية مباشرة وإدارة عمل المشروع. [الطبعة السادسة ، صفحة 120 PMBOK] | 140 | 5 | False | "16" | Abdulfattah
383 | Your project is currently in the execution phase. The team members have been implemented a change request without going through the CCB. As a project manager, what should you do? | Do nothing | Update the project management plan | Update the change log | Send the change request to CCB for approval | Since the team members implemented a change request without through the CCB, as a project manager you should send the change to CCB for approval.. [PMBOK 6th edition, Page.96] | مشروعك حاليا في مرحلة التنفيذ. تم تنفيذ طلب تغيير على أعضاء الفريق دون المرور عبر لجنة التحكم في التغيير. كمدير مشروع ، ماذا يجب أن تفعل؟ | لا تفعل شيئا | تحديث خطة إدارة المشروع | قم بتحديث سجل التغيير | إرسال طلب التغيير إلى لجنة التحكم في التغيير. للموافقة عليه | نظرًا لأن أعضاء الفريق قاموا بتنفيذ طلب التغيير بدون من خلال لجنة التحكم في التغيير.، بصفتك مدير مشروع ، يجب عليك إرسال التغيير إلى لجنة التحكم في التغيير. للموافقة عليه . [الطبعة السادسة ، صفحة 96 PMBOK] | 140 | 4 | False | "19" | Abdulfattah
384 | You have just been assigned as the project manager of a project to construct a hospital. During a planning meeting, the team decides to conduct a site survey to determine the ground conditions before engineering the design. Which of the following risk management processes is the team implementing? | Plan Risk Management process | Perform Qualitative Risk Analysis process | Plan risk response process | Identify Risks process | The project team is implementing the Identify Risks process to identify the risks that may impact the project before engineering the design. [PMBOK 6th edition, Page.409] | لقد تم تعيينك للتو كمدير مشروع لبناء مستشفى. خلال اجتماع التخطيط ، يقرر الفريق إجراء مسح للموقع لتحديد ظروف الأرض قبل هندسة التصميم. أي من عمليات إدارة المخاطر التالية ينفذها الفريق؟ | خطة عملية إدارة المخاطر | إجراء عملية التحليل النوعي للمخاطر | التخطيط لعملية الاستجابة للمخاطر | عملية تحديد المخاطر | يقوم فريق المشروع بتنفيذ عملية تحديد المخاطر لتحديد المخاطر التي قد تؤثر على المشروع قبل هندسة التصميم. [الطبعة السادسة ، صفحة 409 PMBOK] | 147 | 3 | False | "19" | Abdulfattah
385 | In the planning process of your project, you realize that your schedule requires more resources in certain months of the project than what are available to you. Your senior management has clearly instructed that you will not be able to obtain additional resources for the project. So, you instruct your planner to adjust the schedule to accommodate these constraints. What are you instructing the planner to do? | Crashing | Fast tracking | Evaluation and Review Technique | Resource leveling | Resource leveling. A technique in which start and finish dates are adjusted based on resource constraints with the goal of balancing the demand for resources with the available supply. [PMBOK 6th edition, Page 211] | في عملية التخطيط لمشروعك ، تدرك أن جدولك يتطلب موارد في أشهر معينة من المشروع أكثر مما هو متاح لك. لقد أوعزت إدارتك العليا بوضوح أنك لن تتمكن من الحصول على موارد إضافية للمشروع. لذلك ، فإنك تطلب من مخططك تعديل الجدول الزمني لملاءمة هذه القيود. ماذا تطلب من المخطط أن يفعل؟ | حشد الموارد | تسريع الانشطة | تقنية التقييم والمراجعة | تسوية الموارد | تسوية الموارد. تقنية يتم فيها تعديل تواريخ البدء والانتهاء بناءً على قيود الموارد بهدف موازنة الطلب على الموارد مع العرض المتاح. [الطبعة السادسة ، صفحة 211 PMBOK] | 142 | 3 | False | "19" | Abdulfattah
386 | During having a coffee with the CEO that you have a good relationship with, he was surprised that you do not have the information that your project will be canceled due to future changes in company plans, and your team members will be released. As a Project manager, what should you do? | Hold a meeting with your team and inform them about what will happen. | Hold a meeting with stakeholders and discuss this information openly with them | Hold a meeting with the sponsor and discuss this info with him. | Review the communication management plan and validate why you did not get this information through it. | The PM should Review the communication management plan because this plan contains the Information to be communicated and the Person or groups who will receive the information. [PMBOK 6th edition, Page 377] | أثناء تناول القهوة مع الرئيس التنفيذي الذي تربطك به علاقة جيدة ، تفاجأ بأنه ليس لديك المعلومات التي تفيد بأن مشروعك سيتم إلغاؤه بسبب التغييرات المستقبلية في خطط الشركة ، وسيتم الاستغناء أعضاء فريقك. كمدير مشروع ، ماذا يجب أن تفعل؟ | عقد اجتماعًا مع فريقك وأبلغهم بما سيحدث. | عقد اجتماعًا مع أصحاب المصلحة ومناقشة هذه المعلومات معهم بصراحة | عقد لقاء مع الراعي ومناقشة هذه المعلومات معه. | مراجعة خطة إدارة الاتصالات وتحقق من سبب عدم حصولك على هذه المعلومات من خلالها. | يجب على مدير المشروع مراجعة خطة إدارة الاتصالات لأن هذه الخطة تحتوي على المعلومات التي سيتم توصيلها والشخص أو المجموعات التي ستتلقى المعلومات. [الطبعة السادسة ، صفحة 377 PMBOK] | 146 | 3 | False | "19" | Abdulfattah
387 | A techniques help to identify and analyze risks. Which of below? | Probability and impact matrix. | SWOT Analysis | Monte Carol | Expert judgment | Expert Judgment is T&T in all Risk processes expect Monitor Risk. [PMBOK 6th edition. Page 396] | تقنيات تساعد على تحديد وتحليل المخاطر. أي مما يلي؟ | مصفوفة الاحتمالات والأثر. | تحليل نقاط القوة والضعف والفرص والتهديدات | مونتي كارول | الاستعانة بحكم الخبراء | حكم الخبراء هو احد الادوات والتقنيات المستخدمة في جميع عمليات المخاطر التي تتوقعها من مراقبة المخاطر. [[الطبعة السادسة ، صفحة 396 PMBOK] | 147 | 5 | False | "20" | Abdulfattah
388 | The project and product requirements have been identified by the project team members during the planning phase of your project. Which of the following were used to accomplish this? | Mind mapping, affinity diagram and Brainstorming | Observations conversations, trend analysis and work breakdown structure (WBS) | Network diagram, Benchmarking, and project scope statement. | Observations conversations, benchmarking and affinity diagram | You can easily remove two options that include Network diagram and WBS. Also, Mind mapping and Brainstorming both used to generate new ideas so not a good choice. So the best answer to identify the project and product requirements are Observations conversations, benchmarking, and affinity diagram. [PMBOK 6th edition page, 142] | تم تحديد متطلبات المشروع والمنتج من قبل أعضاء فريق المشروع أثناء مرحلة التخطيط لمشروعك. أي مما يلي تم استخدامه لتحقيق ذلك؟ | رسم خرائط العقل ومخطط التقارب والعصف الذهني | محادثات الملاحظات وتحليل الاتجاهات وهيكل تجزئة العمل (WBS) | مخطط الشبكة والقياس المعياري وبيان نطاق المشروع. | محادثات الملاحظات والقياس المعياري ومخطط التقارب | يمكنك بسهولة إزالة خيارين يتضمنان مخطط الشبكة و هيكل تجزئة العمل. أيضًا ، يتم استخدام كل من تخطيط العقل والعصف الذهني لتوليد أفكار جديدة لذلك ليس اختيارًا جيدًا. لذا فإن أفضل إجابة لتحديد متطلبات المشروع والمنتج هي محادثات الملاحظات ، وقياس الأداء ، ومخطط التقارب. [الطبعة السادسة ، صفحة 142 PMBOK] | 141 | 3 | False | "19" | Abdulfattah
389 | The customer comes to you during the project execution and tells you about a minor requirement that he forgot during the collect requirement process. He assures you that there will be no effect on the cost if you implement his request. What will your next step be? | You will deny his request | Update Scope Baseline | Implement the change | Evaluate the impact with team members | You should first evaluate the impact of the change with the team member then inform the customer of the impact on project constraints. [PMBOK 6th edition, Page.622] | يأتي العميل إليك أثناء تنفيذ المشروع ويخبرك بمتطلبات ثانوية نسيها أثناء عملية جمع المتطلبات. ويؤكد لك أنه لن يكون هناك أي تأثير على التكلفة إذا نفذت طلبه. ماذا ستكون خطوتك التالية؟ | سوف ترفض طلبه | تحديث خط الأساس للنطاق | تنفيذ التغيير | تقييم التأثير مع أعضاء الفريق | يجب عليك أولاً تقييم تأثير التغيير مع عضو الفريق ثم إبلاغ العميل بالتأثير على قيود المشروع. [الطبعة السادسة ، صفحة 622 PMBOK] | 141 | 5 | False | "18" | Abdulfattah
390 | The mitigation plan is failed to deal with the issue that occurred three weeks ago because of unavailable resources, and has negatively impacted the schedule. What should the project manager have done to prevent this? | Sent out status reports to stakeholders. | Updated the risk mitigation plan. | Updated the risk management plan. | Conducted stand-up meetings to communicate project status. | To avoid this situation, the project manager should have done conducted review meetings to communicate project status to stakeholders periodically. [PMBOK 6th edition, Page.95] | فشلت خطة التخفيف في التعامل مع المشكلة التي حدثت قبل ثلاثة أسابيع بسبب عدم توفر الموارد ، وأثرت سلبًا على الجدول. ما الذي كان يجب على مدير المشروع فعله لمنع ذلك؟ | إرسال تقارير الحالة إلى أصحاب المصلحة. | تحديث خطة التخفيف من المخاطر. | تحديث خطة إدارة المخاطر. | عقد اجتماعات وقائية للإبلاغ عن حالة المشروع. | لتجنب هذا الموقف ، كان ينبغي على مدير المشروع إجراء اجتماعات مراجعة لإبلاغ أصحاب المصلحة بشكل دوري بحالة المشروع. [الطبعة السادسة ، صفحة 95 PMBOK] | 140 | 4 | False | "20" | Abdulfattah
391 | As a project manager, what should you use to compare different suppliers and rate their proposals? | Bid documents | Bidder conferences | A contract. | Evaluation criteria | Evaluation criteria used to compare different subcontractors and rate their proposals. The buyer seeks to ensure that the proposal selected will offer the best quality for the services required. [PMBOK 6th edition Page, 478, 479] | بصفتك مدير مشروع ، ما الذي يجب عليك استخدامه لمقارنة الموردين المختلفين وتقييم عروضهم؟ | وثائق العطاء | اجتماعات الموردين | عقد. | معيار التقييم | معايير التقييم المستخدمة لمقارنة مختلف المتعاقدين من الباطن وتقييم عروضهم. يسعى المشتري إلى التأكد من أن العرض الذي تم اختياره سيقدم أفضل جودة للخدمات المطلوبة. [الطبعة السادسة ، صفحة 478, 479 PMBOK] | 148 | 3 | False | "17" | Abdulfattah
392 | In Critical Project for your organization, Your project is behind schedule and over budget. Therefore, the Project Sponsor asks you if the team members may work on weekends. As a Project manager, what should you do to persuade the team members to work during their weekends? | Ask the Management what should you do | Ignore the Sponsor | Update Issue Log | Recognition and rewards | To persuade the team members to work in their weekends; You should Apply Recognition and Rewards System. [PMBOK 6th edition, Page.341] | في المشروع الحرج لمؤسستك ، يتخلف مشروعك عن الجدول الزمني ويتجاوز الميزانية. لذلك ، يسألك راعي المشروع عما إذا كان بإمكان أعضاء الفريق العمل في عطلات نهاية الأسبوع. بصفتك مدير مشروع ، ما الذي يجب عليك فعله لإقناع أعضاء الفريق بالعمل خلال عطلات نهاية الأسبوع؟ | سوال الإدارة عما يجب عليك فعله | تجاهل الراعي | تحديث سجل المشاكل | التقدير والمكافآت | لإقناع أعضاء الفريق بالعمل في عطلات نهاية الأسبوع ؛ يجب عليك تطبيق نظام الاعتراف والمكافآت. [الطبعة السادسة ، صفحة 341 PMBOK] | 145 | 4 | False | "19" | Abdulfattah
393 | As a project manager, you discover that the concrete's composition is incorrect. What document should the project manager reviews to verify the concrete's performance and quality requirements? | Request for proposal REF. | Procurement management plan. | Quality management plan. | Procurement statement of work SOW. | The Procurement statement of work (SOW) Include, specifications, quantity desired, quality levels, performance data, period of performance, work location, and other requirements. The SOW describes the procurement item in sufficient detail to allow prospective sellers to determine if they are capable of providing the products, services, or results. Sufficient detail can vary based on the nature of the item, the needs of the buyer, or the expected contract form. [PMBOK 6th edition Page, 477] | كمدير للمشروع ، تكتشف أن تركيبة الخرسانة غير صحيحة. ما هي الوثيقة التي يجب على مدير المشروع مراجعتها للتحقق من أداء الخرسانة ومتطلبات الجودة؟ | مستند طلب اقتراح. | خطة إدارة المشتريات. | خطة إدارة الجودة. | مستند بيان اعمال المشتريات يالمشروع SOW. | يتضمن بيان المشتريات (SOW) المواصفات والكمية المطلوبة ومستويات الجودة وبيانات الأداء وفترة الأداء وموقع العمل والمتطلبات الأخرى. يصف بيان العمل (SOW) بند الشراء بتفاصيل كافية للسماح للبائعين المحتملين بتحديد ما إذا كانوا قادرين على توفير المنتجات أو الخدمات أو النتائج. يمكن أن تختلف التفاصيل الكافية بناءً على طبيعة العنصر أو احتياجات المشتري أو نموذج العقد المتوقع. [الطبعة السادسة ، صفحة 477 PMBOK] | 148 | 3 | False | "19" | Abdulfattah
394 | The customer sent an urgent change request. You review the request and find that it might cost a lot if you implement this change request. What will be your next step? | Implement the change | You will not allow any change request | Since it increases the cost, reject it | Discuss the cost impact with the client | You should discuss the impact of the change request on the project cost with the client. You cannot process the change request unless the client agrees with its impact on any project objective. [PMBOK 6th edition, Page.257] | أرسل العميل طلب تغيير عاجل. تقوم بمراجعة الطلب وتجد أنه قد يكلفك الكثير إذا قمت بتنفيذ طلب التغيير هذا. ماذا ستكون خطوتك التالية؟ | تنفيذ التغيير | عدم تسمح بأي طلب تغيير | لأنه يزيد التكلفة ، ارفضها | مناقشة تأثير التكلفة مع العميل | يجب عليك مناقشة تأثير طلب التغيير على تكلفة المشروع مع العميل. لا يمكنك معالجة طلب التغيير ما لم يوافق العميل على تأثيره على أي هدف من أهداف المشروع. [الطبعة السادسة ، صفحة 257 PMBOK] | 143 | 5 | False | "20" | Abdulfattah
395 | The project manager didn't accepted the deliverables because don't meet the agreed-upon acceptance criteria. What should the project manager reference to verify this with the contractor? | Request for proposal (RFP). | Procurement management plan | Quality log | Statement of work (SOW). | The SOW include: "Description of the procurement item, specifications, quality requirements, and performance metrics" Description of collateral services required acceptance methods and criteria. [PMBOK 6th edition Page, 481] | لم يقبل مدير المشروع التسليمات بسبب عدم استيفاء معايير القبول المتفق عليها. ما الذي يجب أن يشير إليه مدير المشروع للتحقق من ذلك مع المقاول؟ | مستند طلب اقتراح. | خطة إدارة المشتريات | سجل الجودة | مستند بيان العمل يالمشروع SOW. | يتضمن بيان العمل (SOW): "وصف بند الشراء والمواصفات ومتطلبات الجودة ومقاييس الأداء" وصف الخدمات الإضافية وأساليب ومعايير القبول المطلوبة. [الطبعة السادسة ، صفحة 481 PMBOK] | 148 | 3 | False | "20" | Abdulfattah
396 | The construction company is signing contract with consultant agent to finalize the project requirement. Which of the following estimating technique would be best in order to estimate the activity cost? | Three Point Estimating | Parametric Estimating | Analogous Estimating | Bottom-up-Estimating | Because Bottom-up will give you the most accurate estimates, and it requires a well-defined scope & accurate WBS. [PMBOK 6th edition Page, 244] | تقوم شركة البناء بتوقيع عقد مع الوكيل الاستشاري لإنهاء متطلبات المشروع. أي من تقنيات التقدير التالية هي الأفضل لتقدير تكلفة النشاط؟ | ثلاث نقاط تقدير | التقدير بااستخدام المعادلات الرياضية والاحصاء | تقدير مماثل | التقدير التصاعدي من اسفل الى اعلى | لأن التصاعدية ستمنحك أدق التقديرات ، وتتطلب نطاقًا محددًا جيدًا و هيكل تجزئة العمل دقيقة. [الطبعة السادسة ، صفحة 244 PMBOK] | 143 | 3 | False | "20" | Abdulfattah
397 | You are project manager responsible for executing houses construction project. The key stakeholders and the Project sponsor approved the project management plan. What is the next step? | Identify Stakeholders | Direct and Manage Project Work | Update Business Case | Conduct the project kick-off meeting | After approval the project management plan, the next step is Conduct kick-off meeting, communicating the start of the project, key milestones, and other relevant information in order to inform and engage stakeholders and gain commitment before the project execution. | أنت مدير المشروع المسؤول عن تنفيذ مشروع بناء المنازل. وافق أصحاب المصلحة الرئيسيون وراعي المشروع على خطة إدارة المشروع. ما هي الخطوة التالية؟ | تحديد أصحاب المصلحة | توجيه وإدارة أعمال المشروع | تحديث مستند حالة اعمال المشروع | عقد الاجتماع الافتتاحي لبدء انطلاق المشروع | بعد الموافقة على خطة إدارة المشروع ، فإن الخطوة التالية هي إجراء الاجتماع الافتتاحي لانطلاق المشروع ، والإبلاغ عن بداية المشروع ، والمعالم الرئيسية ، وغيرها من المعلومات ذات الصلة من أجل إبلاغ أصحاب المصلحة وإشراكهم وكسب الالتزام قبل تنفيذ المشروع. | 140 | 3 | False | "20" | Abdulfattah
398 | The relevant stakeholders inspected the deliverables and found that that there has been a change in the company strategy. Therefore, important changes must be made to the requirements. The project manager believes that these changes make the deliverables unstable. What should the project manager do? | Request the details about the new requirements, evaluate them with the project team, and recommend whether to continue or close the project. | Evaluate the impact on the project, coordinate with the sponsor and close the project. | Evaluate and incorporate the changes to the project management plan to start executing them. | Request that the stakeholders specify the new requirements and present them to the change control board (CCB). | Keyword ( important changes MUST be made to the requirements ) Any changes in project requirement can impact the baseline will require formal change request to take the approval from CCB. SO the project manager should Request that the stakeholders specify the new requirements and present them to the change control board (CCB). other options not correct because the change request can not be implemented without the approval by CCB. the other option ( close the project after evaluate the impact on project not correct ), [PMBOK 6th edition Page, 117, 120] | قام أصحاب المصلحة ذو الصلة بفحص المخرجات ووجدوا أنه كان هناك تغيير في استراتيجية الشركة. لذلك ، يجب إجراء تغييرات مهمة على المتطلبات. يعتقد مدير المشروع أن هذه التغييرات تجعل النواتج غير مستقرة. ماذا يجب أن يفعل مدير المشروع؟ | طلب التفاصيل حول المتطلبات الجديدة ، وقم بتقييمها مع فريق المشروع ، والتوصية بما إذا كنت تريد الاستمرار أو إغلاق المشروع. | تقييم الأثر على المشروع والتنسيق مع الراعي وإغلاق المشروع. | تقييم ودمج التغييرات في خطة إدارة المشروع للبدء في تنفيذها. | طلب من أصحاب المصلحة تحديد المتطلبات الجديدة وتقديمها إلى لجنة التحكم في التغيير (CCB). | الكلمة الرئيسية (يجب إجراء تغييرات مهمة على المتطلبات) أي تغييرات في متطلبات المشروع يمكن أن تؤثر على خط الأساس سيتطلب طلب تغيير رسمي للحصول على الموافقة من لجنة التحكم في التغيير. لذا يجب على مدير المشروع أن يطلب من أصحاب المصلحة تحديد المتطلبات الجديدة وتقديمها إلى لجنة التحكم في التغيير (CCB). خيارات أخرى غير صحيحة لأن طلب التغيير لا يمكن تنفيذه دون موافقة لجنة التحكم في التغيير. الخيار الآخر (إغلاق المشروع بعد تقييم التأثير على المشروع غير صحيح). [الطبعة السادسة ، صفحة 117, 120 PMBOK] | 140 | 5 | False | "20" | Abdulfattah
399 | Your project is complete and the product is ready to be delivered. The client inspects the deliverable and accepts it. What process is this? | Close project or phase | Close procurement | Control Quality | Validate scope | In the Validate Scope process, the customer accepts the deliverables or the product. [PMBOK 6th edition, Page166 ]. | اكتمل مشروعك والمنتج جاهز للتسليم. يتفقد العميل التسليم ويقبله. ما هذه العملية؟ | اغلاق المشروع أو المرحلة | توثيق عملية الشراء | التحكم بالجودة | التحقق من النطاق | في عملية التحقق من النطاق ، يقبل العميل التسليمات أو المنتج. [الطبعة السادسة ، صفحة 166 PMBOK] | 141 | 5 | False | "20" | Abdulfattah
400 | A project manager analyzed the project's communication requirements and decided that 15 out of the 30 stakeholders in the project would only need voicemail updates of certain information. This type of communication method is called: | Pull communication | Interactive communication | On-demand communication | Push communication | Voicemail is an example of Push communication. [PMBOK 6th edition, Page 374] | قام مدير المشروع بتحليل متطلبات الاتصال الخاصة بالمشروع وقرر أن 15 من أصل 30 من أصحاب المصلحة في المشروع سيحتاجون فقط إلى تحديثات البريد الصوتي لمعلومات معينة. يسمى هذا النوع من طرق الاتصال: | سحب التواصل | التواصل التفاعلي | الاتصال عند الطلب | دفع التواصل | البريد الصوتي هو مثال على اتصالات الدفع. [الطبعة السادسة ، صفحة 374 PMBOK] | 146 | 3 | False | "20" | Abdulfattah
401 | After the project charter is approved, what should you do NEXT? | Prepare Project Scope Statement | Scope baseline | Prepare a business case | Prepare Scope Management Plan | After the project charter is approved the next step should identify stakeholder but this option not included in the Choices so the correct answer is Scope management plan because it includes: Process for preparing a project scope statement and Process that establishes how the scope baseline will be approved and maintained. option (business case) prepared before the project. [PMBOK 6th edition, Page 134] | بعد الموافقة على ميثاق المشروع ، ماذا يجب أن تفعل بعد ذلك؟ | إعداد بيان نطاق المشروع | خطة الأساس المرجعي للنطاق | تحضير دراسة جدوى | إعداد خطة إدارة النطاق | بعد الموافقة على ميثاق المشروع ، يجب أن تكون الخطوة التالية هي تحديد أصحاب المصلحة ولكن هذا الخيار غير مدرج من ضمن الخيارات، لذا فإن الإجابة الصحيحة هي إعداد خطة إدارة النطاق لأنها تتضمن: عملية إعداد بيان نطاق المشروع والعملية التي تحدد كيفية الموافقة على خطة الأساس للنطاق والتعامل معها. الخيار رقم (دراسة الجدوى) يتم اعداده قبل المشروع. [PMBOK الطبعة السادسة ، الصفحة 134] | 141 | 3 | False | "17" | Haitham
402 | A construction manager is leading a project to study the feasibility of constructing a tower. The project needs to be analyzed from a technical, economic, and social point of view. The construction manager has created the project charter on behalf of the project sponsor, and it is now approved. Which of the following processes should be performed next? | Develop Project Charter | Scope Baseline | Identify Risks | Plan Scope Management | After the project charter is approved the next step should identify stakeholder but this option not included in the Choices so the correct answer is Scope management plan because it includes: Process for preparing a project scope statement and Process that establishes how the scope baseline will be approved and maintained. [PMBOK 6th edition, Page 134] | مدير إنشاءات يقود مشروعًا لدراسة جدوى بناء برج. يحتاج المشروع إلى التحليل من وجهة نظر فنية واقتصادية واجتماعية. قام مدير الإنشاءات بإعداد ميثاق المشروع نيابة عن راعي المشروع، وتمت الموافقة عليه الآن. أي من العمليات التالية يجب إجراؤها بعد ذلك؟ | تطوير ميثاق المشروع | خطة الأساس المرجعي للنطاق | تحديد المخاطر | خطة إدارة النطاق | بعد الموافقة على ميثاق المشروع ، يجب أن تحدد الخطوة التالية أصحاب المصلحة ولكن هذا الخيار غير مدرج في الخيارات ، لذا فإن الإجابة الصحيحة هي خطة إدارة النطاق لأنها تتضمن: عملية إعداد بيان نطاق المشروع والعملية التي تحدد كيفية الموافقة على خطة الأساس المرجعي للنطاق والتعامل معها. [PMBOK الطبعة السادسة ، الصفحة 134] | 141 | 3 | False | "19" | Haitham
403 | You have recently been assigned as a project manager to manage a project that was terminated five months ago because of funding related issues, but which has since been re-initiated. You want to find out the exact reasons for the termination of the project. You also want to know which deliverables were produced from the terminated project. Which of the following documentation should you review to obtain this information? | Operational and support documents | Historical Database | Final Product, Service, or Result | Project or phase closure documents | Project or phase closure documents, consisting of formal documentation that indicates completion of the project or phase and the transfer of the completed project or phase deliverables to others, such as an operations group or to the next phase. During project closure, the project manager reviews prior phase documentation, customer acceptance documentation from the Validate Scope. [PMBOK 6th edition, Page 128]. | لقد تم تعيينك مؤخرًا كمدير مشروع لإدارة مشروع تم إنهاؤه منذ خمسة أشهر بسبب مشكلات متعلقة بالتمويل ، ولكن تمت إعادة بدئه من جديد. تريد معرفة الأسباب الحقيقية لإنهاء المشروع. وتريد أيضًا معرفة المخرجات التي تم تسليمها من المشروع المنتهي. أي من الوثائق التالية يجب عليك مراجعتها للحصول على هذه المعلومات؟ | المستندات التشغيلية والداعمة | قاعدة البيانات التاريخية | المنتج النهائي أو الخدمة أو النتيجة | مستندات إغلاق المشروع أو المرحلة | مستندات إقفال المشروع أو المرحلة ، تتكون من وثائق رسمية تشير إلى اكتمال المشروع أو المرحلة ونقل المشروع المكتمل أو تسليمات المرحلة إلى الآخرين، مثل فرق التشغيل أو إلى المرحلة التالية. أثناء إغلاق المشروع ، يقوم مدير المشروع بمراجعة وثائق المرحلة السابقة ، ووثائق قبول العميل من عملية التحقق من النطاق. [PMBOK الطبعة السادسة، الصفحة 128]. | 140 | 6 | False | "17" | Haitham
404 | Four team members have just joined the project you are leading. The project is medium and involves many stakeholders. You want to get the new team members up to speed with the overall dynamics of the project and engage effectively with the project stakeholders. What should you do? | Schedule a meeting with the new team members and all project stakeholders | Submit a change request to update the stakeholder engagement plan | Ask the team members to record any issues they encounter into the issue log | Review the stakeholder register with the new team members | The stakeholder register is a project document that contains all current information about the stakeholders. The stakeholder register includes stakeholder identification information, assessment information, and stakeholder classification. It is used by the project team to maintain information about the stakeholder's expectations and interests with the project. By reviewing the stakeholder register with the new team members, the project manager can provide them with the information about each project stakeholder, politics surrounding the project, and other relevant details about the project and the stakeholders that may help the new team member. [PMBOK 6th edition, Page 514] | انضم أربعة أعضاء من الفريق للتو إلى المشروع الذي تديره. المشروع متوسط ​​ويشارك فيه العديد من أصحاب المصلحة. أنت ترغب في جعل أعضاء الفريق الجدد على دراية بالديناميكيات العامة للمشروع والمشاركة بفعالية مع أصحاب المصلحة في المشروع. ماذا عليك ان تفعل؟ | حدد موعدًا لاجتماع مع أعضاء الفريق الجدد وجميع أصحاب المصلحة في المشروع | إرسال طلب تغيير لتحديث خطة إشراك أصحاب المصلحة | اطلب من أعضاء الفريق تسجيل أي مشكلات يواجهونها في سجل الأحداث | مراجعة سجل أصحاب المصلحة مع أعضاء الفريق الجدد | سجل أصحاب المصلحة هو مستند المشروع الذي يحتوي على جميع المعلومات الحالية حول أصحاب المصلحة. يتضمن سجل أصحاب المصلحة معلومات تحديد أصحاب المصلحة ومعلومات التقييم وتصنيف أصحاب المصلحة. يتم استخدامه من قبل فريق المشروع للاحتفاظ بمعلومات حول توقعات أصحاب المصلحة واهتماماتهم بالمشروع. من خلال مراجعة سجل أصحاب المصلحة مع أعضاء الفريق الجدد ، يمكن لمدير المشروع تزويدهم بالمعلومات حول كل صاحب مصلحة في المشروع ، والسياسات المحيطة بالمشروع ، والتفاصيل الأخرى ذات الصلة حول المشروع وأصحاب المصلحة الذين قد يساعدون أعضاء الفريق الجديد. [PMBOK الطبعة السادسة ، الصفحة 514] | 149 | 4 | False | "18" | Haitham
405 | You are a Project Manager in a Engineering company. the sponsor of project has just developed the project charter, and has also provided you with a list of the project's key stakeholders that he has identified. He then asks you to immediately gather the requirements. What should be your next step as the project manager? | Develop a stakeholder engagement plan | Prepare a power/interest matrix for key stakeholders | Start working on define activities | Conduct the stakeholder identification process to identify all stakeholder's | Stakeholder identification is an important process in the initiating phase of a project and should be performed immediately after the project charter has been developed. Although the project sponsor has provided you with a list of what he considers "key" stakeholders, you must perform the Identify Stakeholders process until "all" stakeholders have been identified. Only then can you move on to the Planning processes of Plan Stakeholder Management and Collect Requirements. [PMBOK 6th edition, Page 514] | أنت مدير مشروع في شركة هندسية. لقد طور راعي المشروع للتو ميثاق المشروع ، وقدم لك أيضًا قائمة بأصحاب المصلحة الرئيسيين في المشروع الذين حددهم. ثم طلب منك جمع المتطلبات على الفور. ما الذي يجب أن تكون خطوتك التالية كمدير للمشروع؟ | وضع خطة إشراك أصحاب المصلحة | إعداد مصفوفة السلطة / الإهتمام لأصحاب المصلحة الرئيسيين | البدء بالعمل على تحديد الأنشطة | إجراء عملية تحديد أصحاب المصلحة لتحديد جميع أصحاب المصلحة | يعد تحديد أصحاب المصلحة عملية مهمة في مرحلة بدء المشروع ويجب إجراؤها فورًا بعد تطوير ميثاق المشروع. على الرغم من أن راعي المشروع قد قدم لك قائمة بما يعتبره أصحاب المصلحة "الرئيسيين" ، إلا أنه يجب عليك إجراء عملية تحديد أصحاب المصلحة حتى يتم تحديد "جميع" أصحاب المصلحة. عندها فقط يمكنك الانتقال إلى عمليات التخطيط الخاصة بإدارة أصحاب المصلحة وتجميع المتطلبات. [PMBOK الطبعة السادسة ، الصفحة 514] | 149 | 2 | False | "18" | Haitham
406 | During the team review, the project manager learns that the schedule performance index (SPI) is 0.6 and the cost performance index (CPI) is 0.8. The project manager asks team members to work overtime. How will this effect the ( CPI ) ? | It will increase. | It will return to 1.0 | It will remain the same. | It will decrease. | (SPI) is 0.6 and ( CPI ) is 0.8 it's mean that the project is behind schedule and over budget. So the added overtime will increase the actual cost (AC) so the CPI will decreases. [PMBOK 6th edition, Page 267] | أثناء مراجعة الفريق ، علم مدير المشروع أن مؤشر أداء الجدول (SPI) هو 0.6 وأن مؤشر أداء التكلفة (CPI) هو 0.8. طلب مدير المشروع من أعضاء الفريق العمل لوقت إضافي. كيف سيؤثر هذا على (CPI)؟ | سوف يزداد. | سيعود إلى 1.0 | ستبقى كما هي. | سوف تنخفض. | (SPI) هو 0.6 و (CPI) هو 0.8 وهذا يعني أن المشروع متأخر عن الجدول الزمني والميزانية. لذا فإن العمل الإضافي المضاف سيزيد من التكلفة الفعلية (AC) وبالتالي سينخفض مؤشر أداء التكلفة (CPI). [PMBOK الطبعة السادسة ، الصفحة 267] | 143 | 5 | False | "19" | Haitham
407 | A project team is staffed with experienced subject matter experts. The project is going well and there are no known quality issues. Team members believe that the quality control process is unnecessary for this project. What should the project manager do? | Review the risk management plan to update risks. | Create a cause and effect diagram to quantify impact. | Remove the process from the quality management plan. | Create a team culture that is committed to quality | Although the project is going well and there are no known quality issues, but the quality management processes are necessary , It applies to all projects to meet customer requirements and decrease the employee attrition, errors, or rework. So the project manager should create a team culture that is committed to quality. [PMBOK 6th edition, Page 338]. | يتكون فريق المشروع من خبراء متخصصين ذوي خبرة. يسير المشروع على ما يرام ولا توجد مشاكل جودة معروفة. يعتقد أعضاء الفريق أن عملية مراقبة الجودة غير ضرورية لهذا المشروع. ماذا يجب أن يفعل مدير المشروع؟ | مراجعة خطة إدارة المخاطر لتحديث المخاطر. | قم بإنشاء مخطط السبب والنتيجة لتقدير التأثير. | إزالة العملية من خطة إدارة الجودة. | خلق ثقافة فريق تلتزم بالجودة | على الرغم من أن المشروع يسير على ما يرام ولا توجد مشكلات معروفة في الجودة ، إلا أن عمليات إدارة الجودة ضرورية ، وتطبق على جميع المشاريع لتلبية متطلبات العملاء وتقليل انهاك الموظفين أو الأخطاء أو إعادة العمل. لذلك يجب على مدير المشروع إنشاء ثقافة جماعية تلتزم بالجودة. [PMBOK الطبعة السادسة، الصفحة 338]. | 145 | 4 | False | "20" | Haitham
408 | What is the key purpose of the Monitoring and Controlling process group? | Perform preventive actions so that no variances ever occur in the project lifecycle | Conduct daily status meetings | None of the above | Measure project performance in order to identify and quantify any variances and perform approved corrective actions | Measure project performance in order to identify and quantify any variances and perform approved corrective actions. Preventive actions should be identified and implemented during this process group but they will not ensure that variances won't take place throughout the project lifecycle. Only conducting daily status meetings will not assist in monitoring and controlling the project. Refer to PMP Exam Outline in the Monitoring and Controlling Process Group ( Task no 1 ) [PMBOK 6th edition, Page 613]. | ما هو الغرض الرئيسي من مجموعة عمليات المراقبة والتحكم؟ | تنفيذ الإجراءات الوقائية بحيث لا تحدث أي تباينات في دورة حياة المشروع | عقد اجتماعات الحالة اليومية | لا شيء مما سبق | قياس أداء المشروع من أجل تحديد وقياس أي تباينات وتنفيذ الإجراءات التصحيحية المعتمدة | قياس أداء المشروع من أجل تحديد وقياس أي تباينات وتنفيذ الإجراءات التصحيحية المعتمدة. يجب تحديد الإجراءات الوقائية وتنفيذها خلال مجموعة العملية هذه ولكنها لن تضمن عدم حدوث الفروق طوال دورة حياة المشروع. إن إجراء اجتماعات الحالة اليومية فقط لن يساعد في مراقبة المشروع والتحكم فيه. راجع مخطط اختبار PMP في مجموعة عمليات المراقبة والتحكم (المهمة رقم 1) [PMBOK الطبعة السادسة، الصفحة 613]. | 140 | 5 | False | "19" | Haitham
409 | You are working on a project to construct four buildings complex. The project management plan calls for completion of one building per year at a cost of US$ 100 Million each. At the end of year three, 1st Building was completed at a cost of US$100 million & 2nd Building completed at a cost of US$120 million & 3rd Building only 50% completed at a cost of US$ 60 million. To meet the original project management plan, what monthly performance is needed until the end of year four? | 120 percent | 110 percent | 115 percent | 125 percent | Here he ask to calculate the To Complete Performance Index TCPI , to meet the original project management plan you should use the equation TCPI= (BAC-EV) / (BAC-AC) BAC= 4*100 M = 400 M AC= 100 M+ 120M + 60M = 280 M EV= 2.5/4 X 400 M =250 M So, the TCPI= (BAC-EV) / (BAC-AC) ( 400 M -250 M ) / ( 400 M - 280 M ) = 1.25 = 125 %. [PMBOK 6th edition, Page 267] | أنت تعمل في مشروع إنشاء مجمع مكون من أربعة مباني. تدعو خطة إدارة المشروع إلى استكمال مبنى واحد سنويًا بتكلفة 100 مليون دولار أمريكي لكل مبنى. في نهاية العام الثالث ، تم الانتهاء من المبنى الأول بتكلفة 100 مليون دولار أمريكي وتم الانتهاء من المبنى الثاني بتكلفة 120 مليون دولار أمريكي والمبنى الثالث اكتمل بنسبة 50٪ فقط وبتكلفة 60 مليون دولار أمريكي. لتلبية خطة إدارة المشروع الأصلية ، ما هو الأداء الشهري المطلوب حتى نهاية السنة الرابعة؟ | 120 بالمائة | 110 بالمائة | 115 بالمائة | 125 بالمائة | هنا يطلب حساب مؤشر أداء إكمال المشروع TCPI، لتلبية خطة إدارة المشروع الأصلية ، يجب عليك استخدام المعادلة TCPI = (BAC-EV) / (BAC-AC) BAC = 4*100 M = 400 M AC = 100 M + 120M + 60M = 280 M EV = 2.5 / 4 X 400 M = 250 M لذا فإن TCPI = (BAC-EV) / (BAC-AC) (400 M -250 M) / (400 M - 280 M) = 1.25 = 125٪. [PMBOK الطبعة السادسة ، الصفحة 267] | 143 | 5 | False | "20" | Haitham
410 | You are a project manager in a infrastructure project. During a review, the project team member identifies a quality issue that may cause the product to be rejected by the customer. However, the project sponsor wants to deliver the product. As a project manager, what should you do? | Ensure that the product meets customer requirements. | Deliver the product. | Update the issue log. | Review the quality checklist. | The Quality issue may or may not cause the product to be rejected by the customer. SO, the project manager should first Review the quality checklist. Quality checklist used to verify that a set of required steps has been performed or to check if a list of requirements has been satisfied. Quality checklists should incorporate the acceptance criteria included in the scope baseline. After reviewing the Quality checklist by the project manager and verifying the existence of an issue, the issue must then be presented to the customer and if he not accept the product then it must be recorded in the issue log to start track and find the solution. [PMBOK 6th edition, Page 292, 302] | أنت مدير مشروع في مشروع بنية تحتية. أثناء المراجعة ، حدد عضو من فريق المشروع مشكلة جودة قد تتسبب في رفض العميل للمنتج. ومع ذلك ، فإن راعي المشروع يريد تسليم المنتج. كمدير مشروع ، ماذا يجب أن تفعل؟ | تأكد من أن المنتج يلبي متطلبات العملاء. | تسليم المنتج. | قم بتحديث سجل الأحداث. | راجع قائمة التحقق للجودة. | قد تتسبب مشكلة الجودة في رفض العميل للمنتج وقد لا تتسبب فيه. لذا ، يجب على مدير المشروع أولاً مراجعة قائمة التحقق للجودة. يتم استخدام قائمة التحقق للجودة للتحقق من تنفيذ مجموعة من الخطوات المطلوبة أو للتحقق مما إذا تم استيفاء قائمة المتطلبات. يجب أن تتضمن قوائم تحقق الجودة معايير القبول المدرجة في خطة الأساس للنطاق. بعد مراجعة قائمة التحقق للجودة من قبل مدير المشروع والتحقق من وجود مشكلة ، يجب بعد ذلك عرض المشكلة على العميل وإذا لم يقبل المنتج ، فيجب تسجيله في سجل الأحداث لبدء التتبع والعثور على الحل. [PMBOK الطبعة السادسة، الصفحة 292، 302] | 144 | 5 | False | "19" | Haitham
411 | You are a project manager of a company and you are in the implementation phase. The commercial authorities sent a notice to the project manager to stop work. What should the project manager have done to avoid this? | Identified project risks | Defined a detailed scope of work. | Developed a detailed project management plan. | Identified stakeholders. | To prevent this situation, the project manager should identify all the stakeholders that can impact the project. [PMBOK 6th edition, Page 524] | أنت مدير مشروع في شركة وأنت في مرحلة التنفيذ. وأرسلت السلطات التجارية إخطاراً إلى مدير المشروع بوقف العمل. ما الذي كان يجب على مدير المشروع فعله لتجنب ذلك؟ | تحديد مخاطر المشروع | تحديد نطاق مفصل للعمل | وضع خطة مفصلة لإدارة المشروع | تحديد أصحاب المصلحة | لمنع هذا الموقف ، يجب على مدير المشروع تحديد جميع أصحاب المصلحة الذين يمكنهم التأثير على المشروع. [PMBOK الطبعة السادسة ، الصفحة 524] | 149 | 4 | False | "19" | Haitham
412 | A project manager is in the process of identifying the likely stakeholders on a project and their interests in the project. The project manager has just compiled a list of potential stakeholders' names. What should the project manager do next? | Conduct kick-off meeting to inform and engage stakeholders and gain commitment | Develop the scope management plan | Develop the stakeholder engagement plan | Conduct stakeholder analysis | The question suggests that the project is still in the initiation stage, with the initial iteration of the Identify Stakeholders process, and has yet to progress to project planning. At this point, the project manager has only compiled a list of potential stakeholders' names. With only a list of individual and group names, the next logical step is to perform stakeholder analysis. Stakeholder analysis, an example of the data analysis technique which can be used during the Identify Stakeholder process, results in a list of stakeholders and relevant information such as their positions in the organization, roles on the project, expectations, attitudes, and their interest about the project. Therefore, of the available choices, conducting stakeholder analysis is what the project manager should do next. [PMBOK 6th edition, Page 512] | مدير المشروع بصدد تحديد أصحاب المصلحة المحتملين في المشروع واهتماماتهم في المشروع. قام مدير المشروع للتو بتجميع قائمة بأسماء أصحاب المصلحة المحتملين. ماذا يجب أن يفعل مدير المشروع بعد ذلك؟ | عقد اجتماع افتتاحي لإعلام أصحاب المصلحة وإشراكهم وكسب الالتزام | تطوير خطة إدارة النطاق | تطوير خطة إشراك أصحاب المصلحة | إجراء تحليل أصحاب المصلحة | يشير السؤال إلى أن المشروع لا يزال في مرحلة البدء، وفي التكرار الأولي لعملية تحديد أصحاب المصلحة ، ولم يتقدم بعد إلى تخطيط المشروع. في هذه المرحلة ، قام مدير المشروع فقط بتجميع قائمة بأسماء أصحاب المصلحة المحتملين. مع وجود قائمة بأسماء الأفراد والمجموعات فقط ، فإن الخطوة المنطقية التالية هي إجراء تحليل أصحاب المصلحة. ينتج عن تحليل أصحاب المصلحة ، وهو مثال على تقنية تحليل البيانات التي يمكن استخدامها أثناء عملية تحديد أصحاب المصلحة ، قائمة بأصحاب المصلحة والمعلومات ذات الصلة مثل مناصبهم في المنظمة ، والأدوار في المشروع ، والتوقعات ، وسلوكهم ، واهتماماتهم في المشروع. لذلك من بين الخيارات المتاحة ، إجراء تحليل أصحاب المصلحة هو ما يجب أن يفعله مدير المشروع بعد ذلك. [PMBOK الطبعة السادسة ، الصفحة 512] | 149 | 2 | False | "19" | Haitham
413 | Your project has been progressing well so far. Due to an unexpected increase in the cost of raw materials which was not factored as project risk, you are in need of some management reserve. The management reserve is available but the sponsor asks you to do something to obtain it. What is the sponsor asking you to do? | There is no need for a management reserve as the risk was not factored, and therefore it may be funded from the contingency reserve | To put in a request to the sponsor for the management reserve | To first move the required funds from the contingency reserve to the management reserve | To follow the change approval process to move the required management reserve funds to the cost baseline | A standard procedure in such a situation is to obtain change approval to move the required funds from the management reserve to the cost baseline and then use that amount from the cost baseline. All other options are incorrect. Putting in a request to the sponsor has already been done. [PMBOK 6th edition, Page 269] | يسير مشروعك بشكل جيد حتى الآن. نظرًا للزيادة غير المتوقعة في تكلفة المواد الخام التي لم يتم أخذها في الاعتبار كمخاطر للمشروع ، فأنت بحاجة إلى بعض احتياطي الإدارة. الاحتياطي الإداري متاح ولكن راعي المشروع يطلب منك القيام بشيء للحصول عليه. ماذا يطلب منك راعي المشروع أن تفعل؟ | ليست هناك حاجة لاحتياطي إداري حيث لم يتم احتساب المخاطر ، وبالتالي يمكن تمويلها من احتياطي الطوارئ | تقديم طلب لراعي المشروع للاحتياطي الإداري | نقل الأموال المطلوبة أولاً من احتياطي الطوارئ إلى احتياطي الإدارة | متابعة عملية الموافقة على التغيير لنقل الأموال الاحتياطية للإدارة المطلوبة إلى خط الأساس للتكلفة | يتمثل الإجراء القياسي في مثل هذه الحالة في الحصول على الموافقة على التغيير لنقل الأموال المطلوبة من احتياطي الإدارة إلى خطة الأساس للتكلفة ثم استخدام هذا المبلغ من خطة أساس التكلفة. جميع الخيارات الأخرى غير صحيحة، حيث تم تقديم طلب للراعي بالفعل. [PMBOK الطبعة السادسة ، الصفحة 269] | 143 | 5 | False | "20" | Haitham
414 | You are managing a project with a budget of $ 9,000, and $ 1,500 has been spent. However, you only completed $1000 worth of work. Your schedule says that you should have completed 50% of the work. What is the estimate at completion (EAC)? | US$ 9000 ( Based on original project Budget ) | US$ 9000 ( Based on performance data ) | US$13500 ( Based on original project Budget ) | US$13500 ( Based on performance data ) | The most common formula for EAC is BAC/CPI. CPI=EV/AC =1000/1500= 0.66 So, EAC=9000/0.66 =13500. [PMBOK 6th edition, Page 267] | أنت تدير مشروعًا بميزانية 9,000 دولار، وقد تم إنفاق 1,500 دولار. ومع ذلك ، فقد أكملت أعمال بقيمة 1,000 دولار. يشير جدولك إلى أنه كان يجب عليك إكمال 50٪ من العمل. ما هو التقدير عند الانتهاء (EAC)؟ | 9,000 دولار (بناءً على ميزانية المشروع الأصلية) | 9,000 دولار (بناءً على بيانات الأداء) | 13,500 دولار (بناءً على ميزانية المشروع الأصلية) | 13,500 دولار (بناءً على بيانات الأداء) | المعادلة الأكثر شيوعًا لـ EAC هي BAC / CPI CPI = EV / AC = 1000/1500 = 0.66 لذا ، EAC = 9000 / 0.66 = 13500. [PMBOK الطبعة السادسة ، الصفحة 267] | 143 | 5 | False | "16" | Haitham
415 | During the execution of the project, you had to manage a change request. You evaluated the impact of the change on the other constraints of the project, then you got the change request approved by Change Control Board CCB. The next step you should do is: | Implement the Approved change. | Inform stakeholders with new status of the project. | Update the Issue Log. | Update Project Management plan. | The next step after approved the change request by CCB is to update change log and Update the Plans and affected baselines before implementing the approved change request [PMBOK 6th edition, Page115] | أثناء تنفيذ المشروع ، كان عليك إدارة طلب تغيير. لقد قمت بتقييم تأثير التغيير على القيود الأخرى للمشروع ، ثم حصلت على الموافقة على طلب التغيير من قبل لجنة مراقبة التغييرات CCB. الخطوة التالية التي يجب عليك القيام بها هي: | تنفيذ التغيير المعتمد. | إبلاغ أصحاب المصلحة بالوضع الجديد للمشروع. | قم بتحديث سجل الأحداث. | تحديث خطة إدارة المشروع. | الخطوة التالية بعد الموافقة على طلب التغيير من لجنة مراقبة التغييرات CCB هي تحديث سجل التغيير وتحديث الخطط وخطوط الأساس المتأثرة قبل تنفيذ طلب التغيير المعتمد [PMBOK الطبعة السادسة، الصفحة 115] | 140 | 5 | False | "20" | Haitham
416 | During the initiation phase, the project manager classifying a list of project stakeholders and discovers an interested stakeholder with little authority. How should project manager manage this stakeholder? | Keep satisfied | Manage Closely | Monitor | Keep informed | The stakeholder is interested in the project with little authority so you will keep him informed. [PMBOK 6th edition, Page 514] | أثناء مرحلة البدء ، يصنف مدير المشروع قائمة أصحاب المصلحة في المشروع ويكتشف صاحب مصلحة مهتم بالمشروع ويملك القليل من السلطة. كيف ينبغي على مدير المشروع التعال مع صاحب المصلحة؟ | ابقائه راضياً | إدارته عن كثب | مراقبته | ابقه على إطلاع | صاحب المصلحة مهتم بالمشروع ويملك سلطة ضعيفة لذلك ستبقيه على اطلاع. [PMBOK الطبعة السادسة ، الصفحة 514] | 149 | 2 | False | "20" | Haitham
417 | You are a project manager to construct a new industries in a typhoon prone area and may impact the schedule and quality. As a project manager, what should you do? | Establish a contingency reserve | Perform Quantitative Risk Analysis, and plan risk response | Develop the risk management plan and establish a management reserve | Outsource the project and transfer the risk | The best risk response strategy appropriate for this project, Outsource the project and transfer the risk to complete this work and shifting ownership of a threat to a third party to manage the risk and to bear the impact if the threat occurs. [PMBOK 6th edition, Page 443]. | أنت مدير مشروع لإنشاء صناعات جديدة في منطقة معرضة للأعاصير وقد تؤثر على الجدول الزمني والجودة. كمدير مشروع ، ماذا يجب أن تفعل؟ | إنشاء احتياطي للطوارئ | إجراء التحليل الكمي للمخاطر ، وتخطيط الاستجابة للمخاطر | وضع خطة إدارة المخاطر وإنشاء احتياطي إداري | الاستعانة بمصادر خارجية للمشروع ونقل المخاطر | أفضل إستراتيجية استجابة للمخاطر مناسبة لهذا المشروع ، الاستعانة بمصادر خارجية للمشروع ونقل المخاطر لإكمال هذا العمل وتحويل ملكية التهديد إلى طرف ثالث لإدارة المخاطر وتحمل التأثير في حالة حدوث التهديدات. [PMBOK الطبعة السادسة، الصفحة 443]. | 147 | 3 | False | "20" | Haitham
418 | A project manager leading constructing dams and must provide cost estimates to stakeholders. What should the project manager present to avoid unreasonable cuts in the budget that will undermine the project? | High-level costs summarized by resource. | Cost estimates as per historical data and other variables. | Cost estimates using expert judgment. | Bottom-up cost as the basis for the estimate. | Bottom-up estimating is a method of estimating a component of work. The cost of individual work packages or activities is estimated to the greatest level of specified detail.[PMBOK 6th edition, Page 244] | مدير مشروع يقود بناء سدود ويجب أن يقدم تقديرات التكلفة لأصحاب المصلحة. ما الذي يجب على مدير المشروع تقديمه لتجنب التخفيضات غير المعقولة في الميزانية التي من شأنها إفشال المشروع؟ | التكاليف عالية المستوى ملخصة بالموارد. | تقديرات التكلفة حسب البيانات التاريخية والمتغيرات الأخرى. | تقديرات التكلفة باستخدام رأي الخبراء. | التكلفة التصاعدية (من أسفل لأعلى) كأساس للتقدير. | التقدير من أسفل إلى أعلى هو طريقة لتقدير أحد مكونات العمل. تقدر تكلفة حزم العمل الفردية أو الأنشطة حتى أعلى مستوى من التفاصيل المحددة. [PMBOK الطبعة السادسة، الصفحة 244] | 143 | 3 | False | "18" | Haitham
419 | Project stakeholders are concerned that the project changes may have an unplanned impact on the business documents. They want to understand these changes before they occur. What should the project manager do? | Update the change management plan to track and communicate change. | Escalate all changes to key stakeholders to obtain agreement before implementation. | Ensure that all potential changes are part of the risk mitigation plan. | Review the project plan to handle upcoming change requests. | The project stakeholders want to understand changes before they occur because of the change management plan is a part of the project management plan, so the project manager should review the project plan to handle upcoming change requests. [PMBOK 6th edition, Page115] | يشعر أصحاب المصلحة في المشروع بالقلق من أن تغييرات المشروع قد يكون لها تأثير غير مخطط له على وثائق العمل. يريدون فهم هذه التغييرات قبل حدوثها. ماذا يجب أن يفعل مدير المشروع؟ | القيام بتحديث خطة إدارة التغيير لتتبع التغيير والإبلاغ عنه. | تصعيد جميع التغييرات لأصحاب المصلحة الرئيسيين للحصول على اتفاق قبل التنفيذ. | التأكد من أن جميع التغييرات المحتملة هي جزء من خطة التخفيف من المخاطر. | مراجعة خطة المشروع للتعامل مع طلبات التغيير القادمة. | يرغب أصحاب المصلحة في المشروع في فهم التغييرات قبل حدوثها لأن خطة إدارة التغيير هي جزء من خطة إدارة المشروع ، لذلك يجب على مدير المشروع مراجعة خطة إدارة المشروع للتعامل مع طلبات التغيير القادمة. [PMBOK الطبعة السادسة، الصفحة 115] | 140 | 5 | False | "19" | Haitham
420 | You are managing a houses project, your cost performance is not as planned and your Project is over budget. Therefore, you again estimate the cost of the project and find that you will require more funding to complete the project. This will require an update of the cost baseline. What will you do? | Update the cost baseline. | Update Change Log. | Terminate the Project. | Issue a change request. | If there is a change which requires an update to the cost baseline, you will raise It, get it approved, and then update the cost baseline. [The PMBOK Guide, 6th Edition, Page: 113, 115]. | أنت تدير مشروع بناء منازل، وأداء التكلفة ليس كما هو مخطط له ومشروعك تجاوز الميزانية. لذلك تقوم مرة أخرى بتقدير تكلفة المشروع وتجد أنك ستحتاج إلى مزيد من التمويل لإكمال المشروع. سيتطلب هذا تحديثًا لخط الأساس المرجعي للتكلفة. ماذا ستفعل؟ | تحديث خط الأساس المرجعي التكلفة. | تحديث سجل التغيير. | إنهاء المشروع. | إصدار طلب تغيير. | إذا كان هناك تغيير يتطلب تحديثًا لخط الأساس للتكلفة ، فستقوم برفعه والحصول على الموافقة عليه ثم تحديث خط الأساس للتكلفة. [PMBOK الطبعة السادسة، الصفحة 113 ، 115]. | 143 | 5 | False | "18" | Haitham
421 | The project manager reviews the issue log at the end of each day. One issue she recorded in the issue log stems from delays in the delivery of resources from a contracted supplier. What tool should the project manager use to determine if corrective action is necessary? | Inspection | Independent estimate | Claims administration | Audit | The scenario suggests the Control Procurements process is underway. Audits are among the tools and techniques of this process and are typically used to evaluate a documented procedure to ensure the procedure is being carried out according to plan and analyzed for improvements. In this situation, an audit can be used to review the schedule for the delivery of material per the contract. The audit results inform the project manager whether changes need to be made to the schedule. If the seller is delinquent I in delivering the material, the audit results will also allow the project manager to determine what, if any, corrective action should be conducted. [PMBOK 6th edition Page, 498]. | تراجع مديرة المشروع سجل الأحداث في نهاية كل يوم. إحدى المشكلات التي سجلتها في سجل الأحداث تنبع من التأخير في تسليم الموارد من مورد متعاقد معه. ما الأداة التي يجب أن تستخدمها مديرة المشروع لتحديد ما إذا كان الإجراء التصحيحي ضروريًا؟ | الفحص | التقدير المستقل | إدارة المطالبات | التدقيق | يشير السيناريو إلى أن عملية مراقبة المشتريات جارية. تعد عمليات التدقيق من بين أدوات وتقنيات هذه العملية وتستخدم عادةً لتقييم إجراء موثق لضمان تنفيذ الإجراء وفقًا للخطة وتحليلها من أجل التحسينات. في هذه الحالة ، يمكن استخدام التدقيق لمراجعة الجدول الزمني لتسليم المواد لكل عقد. توضح نتائج التدقيق مدير المشروع ما إذا كان يلزم إجراء تغييرات على الجدول. إذا تأخر البائع في تسليم المواد ، فإن نتائج التدقيق ستسمح أيضًا لمدير المشروع بتحديد الإجراء التصحيحي ، إن وجد. [PMBOK الطبعة السادسة الصفحة، 498]. | 148 | 5 | False | "19" | Haitham
422 | You are a project manager of a company and your project is currently in the execution phase. In your project there is an issue requires the execution of the contingency plan, which impacts the schedule baseline. As a project manager, what should you do? | Perform risk audit. | Review the cost impact. | Do nothing as this would cause changes to the baselines. | Issue a change request. | The execution of the contingency plan will impact the project schedule, so the next step is to Issue a change request. Change requests are processed for review and disposition through the Perform Integrated Change Control process. [PMBOK 6th edition, Page 115] | أنت مدير مشروع في شركة ومشروعك في مرحلة التنفيذ حاليًا. هناك مشكلة في مشروعك تتطلب تنفيذ خطة الطوارئ ، والتي تؤثر على خط الأساس للوقت كمدير مشروع ، ماذا يجب أن تفعل؟ | قم بإجراء تدقيق المخاطر. | راجع التأثير على التكلفة. | لا تفعل شيئًا لأن هذا قد يتسبب في تغييرات في خطط الأساس. | إصدار طلب تغيير. | سيؤثر تنفيذ خطة الطوارئ على الجدول الزمني للمشروع ، وبالتالي فإن الخطوة التالية هي إصدار طلب التغيير. تتم معالجة طلبات التغيير لمراجعتها والتخلص منها من خلال عملية تنفيذ التحكم المتكامل في التغيير. [PMBOK الطبعة السادسة ، الصفحة 115] | 140 | 5 | False | "20" | Haitham
423 | You have identified a risk that will negatively affect your security project. You and your team have decided to use an older encryption technology because of the high risk associated with the new technology. What type of risk strategy are you using? | Transfer | Exploitation | Mitigation | Avoidance | The Project team avoid new technology because of the high risk associated. [PMBOK 6th edition, Page 443]. | لقد حددت خطرًا سيؤثر سلبًا على مشروع الأمان الخاص بك. قررت أنت وفريقك استخدام تقنية تشفير قديمة بسبب المخاطر العالية المرتبطة بالتكنولوجيا الجديدة. ما نوع استراتيجية المخاطر التي تستخدمها؟ | نقل | استغلال | تخفيف | تجنب | يتجنب فريق المشروع التكنولوجيا الجديدة بسبب المخاطر العالية المرتبطة بها. [PMBOK الطبعة السادسة، الصفحة 443]. | 147 | 3 | False | "19" | Haitham
424 | The project manager hired a team to check the quality, but the project manager cannot obtain stakeholder consensus on the team's composition. What selection criteria can the project manager present to influence consensus? | Knowledge of stakeholder expectations, market landscape, and project scope statement. | Knowledge of the product benchmark, business case and quality assurance. | Knowledge of the stakeholder engagement plan, approval criteria and document specifications. | Knowledge of customer requirements, organizational policies and industry standards and project metrics. | Knowledge of customer requirements, organizational policies and industry standards and project metrics. [PMBOK 6th Page, 332] | استأجر مدير المشروع فريقًا للتحقق من الجودة ، لكن مدير المشروع لا يمكنه الحصول على إجماع أصحاب المصلحة بشأن تكوين الفريق. ما هي معايير الاختيار التي يمكن لمدير المشروع تقديمها للتأثير على الإجماع؟ | معرفة توقعات أصحاب المصلحة ، وطبيعة السوق ، وبيان نطاق المشروع. | معرفة معايير المنتج مسوغ المشروع وتأكيد الجودة. | معرفة خطة إشراك أصحاب المصلحة ومعايير القبول ومواصفات الوثائق. | معرفة متطلبات العملاء والسياسات التنظيمية ومعايير الصناعة ومقاييس المشروع. | معرفة متطلبات العملاء والسياسات التنظيمية ومعايير الصناعة ومقاييس المشروع . [PMBOK 6th الصفحة، 332] | 145 | 4 | False | "19" | Haitham
425 | The project manager had been appointed recently in marketing Project. A team member informs you with a serious concern that impacts the project. You start to record the details, identifies an owner, and sets a realistic date for resolution. What document did the project manager update? | Risk register | Stakeholder register | Change log | Issue log | The issue log will help the project manager effectively track and manage issues, ensuring that they are investigated and resolved [PMBOK 6th edition, Page 96] | تم تعيين مدير المشروع مؤخرًا في مشروع تسويق. أخبرك أحد أعضاء الفريق بمخاوف جدية تؤثر على المشروع. بدأت كمدير مشروع في تسجيل التفاصيل وتحديد المسئولين وتحديد تاريخ واقعي للحل. ما هي الوثيقة التي قام مدير المشروع بتحديثها؟ | سجل المخاطر | سجل أصحاب المصلحة | سجل التغيير | سجل الأحداث | سيساعد سجل الأحداث مدير المشروع على تتبع وإدارة الأحداث بفاعلية ، مما يضمن التحقق منها وحلها. [PMBOK الطبعة السادسة، الصفحة 96] | 140 | 4 | False | "19" | Haitham
426 | You are is a project manager leading huge project with 100 million dollars. Various teams from different countries are involved in this project and the teams need to work cohesively and seamlessly for the success of the project. The task of one team member is highly dependent on that of other team members. Which of the following is important for the overall success of project integration? | Change management | Adherence to professional code of conduct | Detailed definition of the work packages | Communications management plan | The communication management plan is vital for the success of project integration. [PMBOK 6th edition, Page 377]. | أنت مدير مشروع تقود مشروعًا ضخمًا بقيمة 100 مليون دولار. تشارك فرق مختلفة من بلدان مختلفة في هذا المشروع وتحتاج الفرق إلى العمل بشكل متماسك وسلس من أجل نجاح المشروع. تعتمد مهمة أحد أعضاء الفريق بشكل كبير على مهمة أعضاء الفريق الآخرين. أي مما يلي مهم للنجاح الكلي لتكامل المشروع؟ | إدارة التغيير | الالتزام بقواعد السلوك المهني | تعريف مفصل لحزم العمل | خطة إدارة الاتصالات | تعد خطة إدارة الاتصالات مهمة جداً لنجاح تكامل المشروع. [PMBOK الطبعة السادسة ، الصفحة 377]. | 146 | 3 | False | "19" | Haitham
427 | A stakeholder with a high degree of impact now requires more detailed project reports. What should the project manager do? | Meet with the project sponsor to discuss the issue. | Escalate the issue to the project management office. | Work with the project team to prepare a new project charter. | Work with the project team to update the communication management plan. | Since the stakeholder with a high degree of impact requires more detailed project reports, the project manager should work with the project team to update the communication management plan because it includes the stakeholder communication requirement , Information to be communicated, including language, format, content, and level of detail. PMBOK 6th edition page, 377 | يحتاج صاحب المصلحة الذي يتمتع بدرجة عالية من التأثير الآن إلى تقارير أكثر تفصيلاً عن المشروع. ماذا يجب أن يفعل مدير المشروع؟ | لقاء راعي المشروع لمناقشة الموضوع. | تصعيد المشكلة إلى مكتب إدارة المشروع. | العمل مع فريق المشروع لإعداد ميثاق مشروع جديد. | العمل مع فريق المشروع لتحديث خطة إدارة الاتصالات. | نظرًا لأن صاحب المصلحة الذي يتمتع بدرجة عالية من التأثير يتطلب تقارير أكثر تفصيلاً عن المشروع ، يجب على مدير المشروع العمل مع فريق المشروع لتحديث خطة إدارة الاتصالات لأنها تتضمن متطلبات الاتصال مع أصحاب المصلحة ، والمعلومات التي سيتم توصيلها ، بما في ذلك اللغة والشكل والمحتوى ، ومستوى التفاصيل. [PMBOK الطبعة السادسة، الصفحة 377] | 146 | 4 | False | "19" | Haitham
428 | Your project team works in two different cities across the country. The team has been struggling to perform effectively, morale is low and has a difficult time resolving problems. What would be the BEST team development technique to resolve this issue? | Training | Rewards | Mediation | Co-location | Colocation involves placing many or all of the most active project team members in the same physical location to enhance their ability to perform as a team. Colocation strategies can include a team meeting room, common places to post schedules, and other conveniences that enhance communication and a sense of community. [PMBOK 6th edition, Page340 ] | يعمل فريق مشروعك في مدينتين مختلفتين داخل الدولة. كان الفريق يكافح من أجل الأداء بفعالية، والمعنويات منخفضة ويواجه صعوبة في حل المشكلات. ما هي أفضل تقنية لتطوير الفريق لحل هذه المشكلة؟ | التدريب | المكافآت | وساطة | المشاركة بالمكان | تتضمن المشاركة بالمكان وضع العديد من أعضاء فريق المشروع الأكثر نشاطًا أو كلهم ​​في نفس الموقع الفعلي لتعزيز قدرتهم على الأداء كفريق. يمكن أن تتضمن إستراتيجيات المشاركة بالمكان وجود غرف اجتماعات للفريق ، وأماكن مشتركة لمناقشة الجداول الزمنية بأريحية مما يعزز التواصل والشعور بالانتماء إلى المجموعة. [PMBOK الطبعة السادسة، الصفحة 340] | 145 | 4 | False | "20" | Haitham
429 | As a project manager, in which document will you find information about the acceptable level of project and product quality and how to ensure this level of quality in its deliverables and processes? | The Scope Management | Plan Work Performance data | Project Charter | The project management plan | The acceptable level of project and product quality and how to ensure this level of quality in its deliverables and processes are part of the information in the project management plan as it includes the quality management plan as one of its components, so, option (The project management plan) is the right answer. [PMBOK 6th edition, Page 286] | بصفتك مدير مشروع ، في أي مستند ستجد معلومات حول المستوى المقبول لجودة المشروع والمنتج وكيفية ضمان هذا المستوى من الجودة في مخرجاته وعملياته؟ | إدارة النطاق | خطة بيانات أداء العمل | ميثاق المشروع | خطة إدارة المشروع | يعد المستوى المقبول لجودة المشروع والمنتج وكيفية ضمان هذا المستوى من الجودة في مخرجاته وعملياته جزءًا من المعلومات الواردة في خطة إدارة المشروع حيث تتضمن خطة إدارة الجودة كأحد مكوناتها ، لذلك ، الخيار الصحيح هو خطة إدارة المشروع. [PMBOK الطبعة السادسة ، الصفحة 286] | 144 | 3 | False | "20" | Haitham
430 | After contract sign-off , a project manager has been informed him that that the vendor has a bad reputation for delaying the materials delivery and not meet the time agreed in the contract. To ensure the vendor's compliance, what should the project manager do? | Cancel the current contract and select another vendor | Conduct a make-or-buy analysis to verify vendor reliability | Insist on a firm fixed price contract (FFP) with the vendor | Perform periodic inspection of the vendor's work and progress. | To ensure the vendor's compliance, the project manager should perform periodic inspection of the vendor's work and progress to take the corrective action as per the contract at the right time. [PMBOK 6th edition Page, 498]. | بعد توقيع العقد ، تم أبلاغ مدير المشروع بأن البائع لديه سمعة سيئة لتأخيره تسليم المواد وعدم التزامه بالوقت المتفق عليه في العقد. لضمان امتثال البائع ، ماذا يجب أن يفعل مدير المشروع؟ | إلغاء العقد الحالي واختيار بائع آخر | إجراء تحليل الصنع أو الشراء للتحقق من موثوقية البائع | الإصرار على عقد السعر الثابت (FFP) مع البائع | إجراء فحص دوري لأعمال البائع والتقدم المنجز. | لضمان امتثال البائع ، يجب على مدير المشروع إجراء فحص دوري لعمل البائع وانجازه للأعمال وذلك لإتخاذ الإجراء التصحيحي وفقًا للعقد في الوقت المناسب. [PMBOK الطبعة السادسة الصفحة، 498]. | 148 | 5 | False | "18" | Haitham
431 | You are managing a project to construct commercial buildings. During the project kick-off meeting, two project team members had a disagreement around whether to include a specific test within testing scenarios for the new product or not. As the project manager, what should you do? | Reject adding the new test | Add the suggested scenario | Ask each one of them to explain the logic behind his opinion | Postpone the discussion for a later time | If you were to "Add the suggested scenario", or "Reject adding the new test", it will be a premature decision as you didn't discuss the reasoning behind both opinions, and since this is the project kick-off meeting and there's no time pressure for resolving the conflict "Postpone the discussion for later time" seems an appealing approach, if you were to "Ask each one of them to explain the logic behind his opinion, it won't be the right time for such discussion. The best course of action is to "Postpone the discussion for a later time". [PMBOK 6th edition, Page 349]. | أنت تدير مشروعًا لإنشاء مبانٍ تجارية. خلال اجتماع بدء المشروع ، كان هناك خلاف بين اثنين من أعضاء فريق المشروع حول ما إذا كان سيتم تضمين اختبار معين ضمن سيناريوهات الاختبار للمنتج الجديد أم لا. بصفتك مدير المشروع ، ماذا يجب أن تفعل؟ | ارفض إضافة الاختبار الجديد | أضف السيناريو المقترح | اطلب من كل واحد منهم شرح المنطق وراء رأيه | قم بتأجيل المناقشة لوقت لاحق | إذا كنت تريد "إضافة السيناريو المقترح" أو "رفض إضافة الاختبار الجديد"، فسيكون هذا قرارًا سابقًا لأوانه لأنك لم تناقش الأسباب الكامنة وراء كلا الرأيين ، و نظرًا لأن هذا هو الاجتماع الافتتاحي للمشروع ولا يوجد ضغط زمني لحل النزاع "تأجيل المناقشة لوقت لاحق" يبدو نهجاً سليماً، إذا كنت تريد "مطالبة كل واحد منهم بشرح المنطق وراء رأيه، لن يكون الوقت مناسبًا لمثل هذه المناقشة. أفضل قرار تتخذه هو "تأجيل المناقشة لوقت لاحق". [PMBOK الطبعة السادسة، الصفحة 349]. | 145 | 4 | False | "19" | Haitham
432 | You are managing a large engineering project. Your project team works in two different industries across the city. You want to communicate the vision and inspire the project team to achieve high performance. Which of the following skills help the project manager? | Political awareness | Emotional intelligence | Feedback | Leadership | Successful projects require leaders with strong leadership skills. Leadership is the ability to lead a team and inspire them to do their jobs well. It encompasses a wide range of skills, abilities, and actions. Leadership is important through all phases of the project life cycle. There are multiple leadership theories defining leadership styles that should be used as needed for each situation or team. It is especially important to communicate the vision and inspire the project team to achieve high performance. [PMBOK 6th edition, Page 350] | أنت تدير مشروعًا هندسيًا كبيرًا. يعمل فريق مشروعك في مصنعين مختلفين في نفس المدينة. تريد إيصال الرؤية وإلهام فريق المشروع لتحقيق الأداء العالي. أي من المهارات التالية تساعد مدير المشروع؟ | الوعي السياسي | الذكاء العاطفي | ردود الفعل | القيادة | تتطلب المشاريع الناجحة قادة يتمتعون بمهارات قيادية قوية. القيادة هي القدرة على قيادة فريق وإلهامهم للقيام بعملهم بشكل جيد. إنه يشمل مجموعة واسعة من المهارات والقدرات والإجراءات. القيادة مهمة خلال جميع مراحل دورة حياة المشروع. هناك العديد من نظريات القيادة التي تحدد أساليب القيادة التي يجب استخدامها حسب الحاجة لكل موقف أو فريق. من المهم بشكل خاص توصيل الرؤية وإلهام فريق المشروع لتحقيق أداء عالٍ. [PMBOK الطبعة السادسة ، الصفحة 350] | 145 | 4 | False | "20" | Haitham
433 | You are a project manager in an Manufacturing project. You and key stakeholders start conducting a project benefit analysis. Because of the solutions that have not been identified, an engineer from another department has informed you that there are affected systems. As a project manager, what should you do? | Identify all stakeholders | Review the project benefit analysis to consider the additional impact | Update the risk register | Document the issue in the issue log | The issue log is a project document used to identify and monitor issues that occur in the project. The issue log can be updated with any new issues found during the project and described in the scenario because of the solutions that have not been identified causing the system are affected. Making this choice the best answer to the question asked. [PMBOK 6th edition, Page 298] | أنت مدير مشروع في مشروع تصنيع. بدأت أنت وأصحاب المصلحة الرئيسيين في إجراء تحليل فوائد المشروع. بسبب الحلول التي لم يتم تحديدها ، أبلغك مهندس من قسم آخر بوجود أنظمة متأثرة. كمدير مشروع ، ماذا يجب أن تفعل؟ | تحديد جميع أصحاب المصلحة | قم بمراجعة تحليل فوائد المشروع للنظر في التأثير الإضافي | تحديث سجل المخاطر | قم بتوثيق المشكلة في سجل الأحداث | سجل الأحداث هو مستند مشروع يُستخدم لتحديد الأحداث أو المشاكل التي تحدث في المشروع ومراقبتها. يمكن تحديث سجل الأحداث بأي أحداث جديدة يتم العثور عليها أثناء المشروع. وصفها في السيناريو بسبب الحلول التي لم يتم تحديدها والتي تتسبب في تأثر النظام. جعل هذا الاختيار أفضل إجابة على السؤال المطروح. [PMBOK الطبعة السادسة ، الصفحة 298] | 144 | 5 | False | "20" | Haitham
434 | You are a project manager managing a decoration project. Your project team sent confidential information to the subcontractor by mistake. What could have prevented this situation? | Reviewing the stakeholder engagement Plan | Reviewing the Scope management Plan | Review stakeholder register | Reviewing the Communication management Plan | The communications management plan is a component of the project management plan that describes how project communications will be planned, structured, implemented, and monitored for effectiveness. The plan contains the following information: Person responsible for authorizing the release of confidential information; Stakeholder communication requirements; Escalation processes; Timeframe and frequency for the distribution of required information and Person responsible for communicating the information. [PMBOK 6th edition, Page 377] | أنت مدير مشروع تدير مشروع ديكور. أرسل فريق المشروع معلومات سرية إلى مقاول الباطن عن طريق الخطأ. ما الذي كان يمكن أن يمنع هذا الوضع؟ | مراجعة خطة إشراك أصحاب المصلحة | مراجعة خطة إدارة النطاق | مراجعة سجل أصحاب المصلحة | مراجعة خطة إدارة الاتصالات | تعد خطة إدارة الاتصالات أحد مكونات خطة إدارة المشروع التي تصف كيفية تخطيط اتصالات المشروع وهيكلتها وتنفيذها ومراقبتها من أجل الفعالية. تحتوي الخطة على المعلومات التالية: الشخص المسؤول عن تصريح إرسال المعلومات السرية. متطلبات التواصل مع أصحاب المصلحة، عمليات التصعيد، الإطار الزمني والتكرار لتوزيع المعلومات المطلوبة، والشخص المسؤول عن إيصال المعلومات. [PMBOK الطبعة السادسة ، الصفحة 377] | 146 | 4 | False | "20" | Haitham
435 | You are responsible for leading the HR Project. The customer has requested a change in the scope which you have processed through a change request and it is approved from CCB, and the team members Updated the Scope and Schedule baselines to reflect the approved changes. What should you do next? | Inform the sponsor about the approved change request | Implement the approved change request | Update the change log | Inform the impacted stakeholders about the approved change request | After updating the impacted baselines, you should inform the stakeholders about the approved change request. Option ( Inform the sponsor about the approved change request ) is incorrect because the project sponsor is a part of The CCB and has information about the approved change. [PMBOK 6th edition, Page 115] | أنت مسؤول عن قيادة مشروع للموارد البشرية. لقد طلب العميل تغيير النطاق الذي قمت بمعالجته من خلال طلب اغيير وتمت الموافقة عليه من لجنة التحكم بطلبات التغيير، وقام أعضاء الفريق بتحديث خطوط الأساس للنطاق والوقت لتعكس التغييرات المعتمدة. ماذا يجب ان تفعل بعد ذلك؟ | إبلاغ الراعي بطلب التغيير المعتمد | تنفيذ طلب التغيير المعتمد | قم بتحديث سجل التغيير | إبلاغ أصحاب المصلحة المتأثرين بطلب التغيير المعتمد | بعد تحديث خطوط الأساس المتأثرة ، يجب عليك إبلاغ أصحاب المصلحة بطلب التغيير المعتمد. الخيار (إبلاغ الراعي بطلب التغيير المعتمد) غير صحيح لأن راعي المشروع جزء من لجنة التحكم بطلبات التغيير ولديه معلومات حول التغيير المعتمد. [PMBOK الطبعة السادسة ، الصفحة 115] | 140 | 5 | False | "19" | Haitham
436 | A project manager is asked to contribute to a document to describe what is intended to be achieved with a project once it is successfully finished, and how this will be measured. What could be the name of that document? | Project management plan | Change management plan | Statement of work | Benefits management plan | The project benefits management plan is the document that describes how and when the benefits of the project will be delivered, and describes the mechanisms that should be in place to measure those benefits. A project benefit is defined as an outcome of actions, behaviors, products, services, or results that provide value to the sponsoring organization as well as to the project's intended beneficiaries. [PMBOK 6th edition, Page 33] | طلب من مدير المشروع المساهمة في مستند لوصف ماسيتم تحقيقه بمجرد الانتهاء من المشروع بنجاح ، وكيف سيتم قياس ذلك. ماذا يمكن أن يكون اسم تلك الوثيقة؟ | خطة إدارة المشروع | خطة إدارة التغيير | بيان العمل | خطة إدارة الفوائد | خطة إدارة فوائد المشروع هي الوثيقة التي تصف كيف ومتى سيتم تسليم فوائد المشروع ، وتصف الآليات التي ينبغي أن تكون في مكانها الصحيح لقياس تلك الفوائد. تُعرَّف فائدة المشروع على أنها نتيجة للإجراءات أو السلوكيات أو المنتجات أو الخدمات أو النتائج التي توفر قيمة للمؤسسة الراعية وكذلك للمستفيدين من المشروع. [PMBOK الطبعة السادسة ، الصفحة 33] | 140 | 6 | False | "20" | Haitham
437 | Your company has created an electronic network to share information between stakeholders and access to information at any time. Which communication method is used? | Push communication | Multidirectional communication | Interactive communication | Pull communication | An electronic network is a form of Pull communication. [PMBOK 6th edition, Page 374] | أنشأت شركتك شبكة إلكترونية لمشاركة المعلومات بين أصحاب المصلحة والوصول إلى المعلومات في أي وقت. ما هي طريقة الاتصال المستخدمة؟ | الاتصال بالدفع | الاتصال متعدد الاتجاهات | الاتصال التفاعلي | الاتصال بالسحب | الشبكة الإلكترونية هي شكل من أشكال الاتصال بالسحب. [PMBOK الطبعة السادسة ، الصفحة 374] | 146 | 3 | False | "20" | Haitham
438 | As the project manager of a constructing hospitals project, you are determining the accuracy of the deliverables before closing a project. What process should be used to determine this and is an input to formalizing acceptance? | Manage quality. | Control scope. | Accepted deliverables | Control Quality | Validate Scope is the process of formalizing acceptance of the completed project deliverables. The verified deliverables obtained from the Control Quality process are reviewed with the customer or sponsor to ensure they are completed satisfactorily and have received formal acceptance of the deliverables by the customer or sponsor. Verified deliverables is the key inputs of validate scope process and outputs of Control quality process.[PMBOK 6th edition, Page 164] | بصفتك مدير مشروع إنشاء مستشفيات ، فأنت تحدد دقة التسليمات قبل إغلاق المشروع. ما هي العملية التي يجب استخدامها لتحديد ذلك وهل تعتبر مدخلاً لإضفاء الطابع الرسمي على القبول؟ | إدارة الجودة. | التحكم بالنطاق . | التسليمات المقبولة. | التحكم بالجودة. | التحقق من النطاق هو عملية إضفاء الطابع الرسمي على قبول نواتج المشروع المكتملة. تتم مراجعة التسليمات التي تم التحقق منها والتي تم الحصول عليها من عملية التحكم بالجودة مع العميل أو الراعي للتأكد من اكتمالها بشكل مرض وتلقيها قبولًا رسميًا للنواتج من قبل العميل أو الراعي. التسليمات التي تم التحقق منها هي المدخلات الرئيسية لعملية التحقق من النطاق ومخرجات من عملية التحكم بالجودة. [PMBOK الطبعة السادسة، الصفحة 164] | 144 | 5 | False | "19" | Haitham
439 | Situational Awareness is a key interpersonal skill for all effective project managers and means knowing what is going on around you and being able to quickly switch your focus. What another skill is often used in conjunction with Situational Awareness where you the project manager, have to be persuasive in expressing your point and position in order for your project team and stakeholders to react quickly to changing project priorities? | Leadership | Negotiation | Conflict Management | Influencing | Influencing is an interpersonal skill that involves awareness of, and consideration for, the various perspectives in any situation. It helps you gather relevant and critical information in order to address changing project priorities and resolve unexpected project challenges. It is often used in conjunction with the Situational Awareness interpersonal tool.. [PMBOK 6th edition, Page 350] | الوعي بالأوضاع هو مهارة شخصية أساسية لجميع مدراء المشاريع الفعالين ويعني معرفة ما يجري من حولك والقدرة على تحويل تركيزك بسرعة. ما هي المهارة الأخرى التي يتم استخدامها غالبًا مع الوعي بالأوضاع حيث يتعين عليك أنت كمدير مشروع أن تكون مقنعًا في التعبير عن وجهة نظرك وموقفك حتى يتفاعل فريق المشروع وأصحاب المصلحة بسرعة مع تغيير أولويات المشروع؟ | القيادة | التفاوض | فض النزاعات | التأثير | التأثير هو مهارة التعامل مع الآخرين التي تنطوي على إدراك ومراعاة وجهات النظر المختلفة في أي موقف. يساعدك على جمع المعلومات ذات الصلة والحاسمة من أجل معالجة أولويات المشروع المتغيرة وحل تحديات المشروع غير المتوقعة. غالبًا ما يتم استخدامه جنبًا إلى جنب مع أداة الوعي بالأوضاع. [PMBOK الطبعة السادسة، الصفحة 350] | 145 | 4 | False | "19" | Haitham
440 | Risks of quality defect on project deliverables may occurre. In Which category these risks should be included? | External Risk | Commercial Risk | Risk Management Risk | Technical Risk | Risk categories provide a means for grouping individual project risks. A common way to structure risk categories is with a risk breakdown structure (RBS). [PMBOK 6th edition. Page 406] | قد تحدث مخاطر خلل في جودة مخرجات المشروع. في أي فئة يجب إدراج هذه المخاطر؟ | مخاطر خارجية | مخاطر تجارية | مخاطر إدارة المخاطر | مخاطر فنية | توفر فئات المخاطر وسيلة لتجميع مخاطر المشروع الفردية. من الطرق الشائعة لهيكلة فئات المخاطر استخدام هيكل توزيع المخاطر (RBS). [PMBOK الطبعة السادسة. الصفحة 406] | 147 | 3 | False | "20" | Haitham
441 | During the development phase of an IT implementation project, the client refuses to grant the project team access to their database. Since this is essential for configuration of the application, the project deliverables could be impacted. What should the project manager do next? | Discuss it with the project team and update the project schedule. | Review the project statement of work (SOW). | Log it in the risk register. | Update the issue log and meet with the client to review. | Since the client refuses to grant the project team access to their database this is an issue and the project manager should first update the issue log and meet with the client to review and solve it. [PMBOK 6th edition, Page 523] | خلال مرحلة تطوير مشروع تنفيذ تكنولوجيا المعلومات، يرفض العميل منح فريق المشروع حق الوصول إلى قاعدة البيانات الخاصة به. نظرًا لأن هذا ضروري لتكوين التطبيق، فقد تتأثر مخرجات المشروع. ماذا يجب أن يفعل مدير المشروع بعد ذلك؟ | مناقشة ذلك مع فريق المشروع وتحديث الجدول الزمني للمشروع. | مراجعة بيان عمل المشروع (SOW). | تسجيل ذلك في سجل المخاطر. | تحديث سجل الأحداث والإجتماع مع العميل لمراجعته. | نظرًا لأن العميل يرفض منح فريق المشروع حق الوصول إلى قاعدة البيانات الخاصة به ، فهذه مشكلة ويجب على مدير المشروع أولاً تحديث سجل الأحداث والالتقاء بالعميل لمراجعتها وحلها. [PMBOK الطبعة السادسة ، الصفحة 523] | 149 | 4 | False | "20" | Haitham
442 | You want to know which deliverables were produced from the terminated project. Which of the following documentation should you review to obtain this information? | Operational and support documents | Historical Database | Final Product, Service, or Result | Project or phase closure documents | Project or phase closure documents, consisting of formal documentation that indicates completion of the project or phase and the transfer of the completed project or phase deliverables to others, such as an operations group or to the next phase. During project closure, the project manager reviews prior phase documentation, customer acceptance documentation from the Validate Scope process, and the agreement (if applicable) to ensure that all project requirements are completed prior to finalizing the closure of the project. If the project was terminated prior to completion, the formal documentation indicates why the project was terminated and formalizes the procedures for the transfer of the finished and unfinished deliverables of the cancelled project to others.. [PMBOK 6t1 edition, Page 128) | تريد معرفة التسليمات التي تم إنتاجها من المشروع المنتهي. أي من الوثائق التالية يجب عليك مراجعتها للحصول على هذه المعلومات؟ | المستندات التشغيلية والداعمة | قاعدة البيانات التاريخية | المنتج النهائي أو الخدمة أو النتيجة | مستندات إغلاق المشروع أو المرحلة | مستندات إقفال المشروع أو المرحلة ، التي تتكون من وثائق رسمية تشير إلى اكتمال المشروع أو المرحلة ونقل المشروع المكتمل أو تسليمات المرحلة إلى الآخرين ، مثل مجموعة العمليات أو إلى المرحلة التالية. أثناء إغلاق المشروع ، يقوم مدير المشروع بمراجعة وثائق المرحلة السابقة ، ووثائق قبول العميل من عملية التحقق من النطاق ، والاتفاقية (إن وجدت) لضمان إكمال جميع متطلبات المشروع قبل الانتهاء من إغلاق المشروع. إذا تم الغاء المشروع قبل اكماله، تشير الوثائق الرسمية إلى سبب الغاء المشروع وتضفي الطابع الرسمي على إجراءات نقل المخرجات النهائية وغير المكتملة للمشروع الملغى إلى الآخرين. [PMBOK الطبعة السادسة، الصفحة 128] | 140 | 6 | False | "19" | Haitham
443 | You are the project manager of important project. Your project must be completed by September 10 and cannot exceed $12,000. $12,000 is an example of which one of the following? | Management reserve | Scheduled completion date | Assumption | Constraint | Constraints are limitations placed upon the project that the project manager and team must work within. there are scope, schedule and cost constraints. (how much funding has been allocated). and the three constraints are commonly called the triple constraints. [PMBOK 6th edition, Page 253] | أنت مدير مشروع مهم جداً. يجب أن يكتمل مشروعك بحلول 10 سبتمبر ولا يمكن أن يتجاوز 12,000 دولار. 12,000 دولار هي مثال على أي مما يلي؟ | الاحتياطي الإداري | تاريخ الانتهاء المجدول | افتراض | قيد | القيود هي محددات مفروضة على المشروع يجب على مدير المشروع وفريق العمل العمل بها. هناك قيود للنطاق والجدول الزمني والتكلفة. (مقدار التمويل الذي تم تخصيصه). وهذه القيود الثلاثة تسمى عادة القيود الثلاثية. [PMBOK الطبعة السادسة ، الصفحة 253] | 143 | 5 | False | "19" | Haitham
444 | A vendor has a contract to deliver products for a project on the first week of each month. An inspection reveals that some product components are not meeting design requirements. What should the project manager do next? | Conduct an audit of all deliverables and hire another vendor. | Demand the necessary corrections from the vendor and update the progress report. | Request an audit of all deliverables and apply penalties to the vendors. | Insist that the vendor make all necessary corrections and update the risk register. | Because of some product components are not meeting design requirements, the vendor should make all necessary corrections and update the risk register then analyze the impact on project objectives. Options ( Conduct an audit of all deliverables ) not correct because Audit conducts on processes not deliverables. [PMBOK 6th edition Page, 500] | لدى البائع عقد لتسليم منتجات لمشروع في الأسبوع الأول من كل شهر. يكشف الفحص أن بعض مكونات المنتج لا تفي بمتطلبات التصميم. ماذا يجب أن يفعل مدير المشروع بعد ذلك؟ | قم بإجراء تدقيق لجميع المخرجات وتوظيف بائع آخر. | اطلب التصحيحات اللازمة من البائع وقم بتحديث تقرير التقدم. | اطلب مراجعة جميع المخرجات وفرض عقوبات على البائعين. | الإصرار على قيام البائع بإجراء جميع التصحيحات اللازمة وتحديث سجل المخاطر. | نظرًا لأن بعض مكونات المنتج لا تلبي متطلبات التصميم ، يجب على البائع إجراء جميع التصحيحات اللازمة وتحديث سجل المخاطر ثم تحليل التأثير على أهداف المشروع. الخيارات (إجراء تدقيق لجميع النواتج) غير صحيح لأن التدقيق يجري على عمليات ليست قابلة للتسليم. [PMBOK الطبعة السادسة الصفحة، 500] | 148 | 5 | False | "20" | Haitham
445 | Which of the following techniques can ensure that the stakeholders are engaged at appropriate project phases and to obtain or confirm their continued commitment to the success of the project? | Managing project team | Setting ground rules | Performance audits | Stage gate meetings | Stage-gate or phase review meetings give to project stakeholders a chance to review project progress and planned future actions. This gives them a chance to have their voice heard and recorded. The rest of the choices are techniques that are internal to a project. [PMBOK 6th edition, Page 21] | أي من الأساليب التالية يمكن أن يضمن مشاركة أصحاب المصلحة في مراحل المشروع المناسبة والحصول على أو تأكيد التزامهم المستمر بنجاح المشروع؟ | إدارة فريق المشروع | وضع القواعد الأساسية | تدقيقات الأداء | اجتماعات بوابة المرحلة | تمنح اجتماعات بوابة المرحلة أو مراجعة المرحلة لأصحاب المصلحة في المشروع فرصة لمراجعة تقدم المشروع والإجراءات المستقبلية المخطط لها. يمنحهم هذا فرصة لسماع صوتهم وتسجيله. باقي الاختيارات هي تقنيات داخلية للمشروع. [PMBOK الطبعة السادسة ، الصفحة 21] | 140 | 4 | False | "20" | Haitham
446 | What should the project manager refer to evaluate the resources that assign by the project management office (PMO)? | Resource Breakdown Structure (RBS). | Responsibility Assignment Matrix (RAM) | Expert judgment. | Resource management plan. | The resource management plan is the component of the project management plan that provides guidance on how project resources should be evaluated, categorized, allocated, managed, and released. The resource management plan include also the team performance assessment criteria. [PMBOK 6th edition Page, 339]. | ما الذي يجب أن يرجع إليه مدير المشروع لتقييم الموارد التي يعينها مكتب إدارة المشروع (PMO)؟ | هيكل تجزئة الموارد (RBS). | مصفوفة تحديد المسؤولية (RAM). | حكم الخبير. | خطة إدارة الموارد. | تعد خطة إدارة الموارد مكونًا من خطة إدارة المشروع التي توفر إرشادات حول كيفية تقييم موارد المشروع وتصنيفها وتمخصيصها وإدارتها وتسريحها. تتضمن خطة إدارة الموارد أيضًا معايير تقييم أداء الفريق. [PMBOK الطبعة السادسة الصفحة، 339]. | 145 | 3 | False | "19" | Haitham
447 | One of the key stakeholders requested additional features to be added to the product without changing the scope, budget, or schedule. The project manager believes that these features will add great value to the end product. However, these additions will increase project costs and impact the project schedule. Which process should the project manager have followed before including the additional project feature? | Schedule and cost management | Scope and cost management | Collect requirement | Change management | The Change Management used to: 1. Describes how to manage the changes, addresses the change control board (CCB). 2.specifies how the project scope may be changed, the procedure to change the scope, and the requirements to make a change. 3. Ensure that inappropriate changes to the project scope do not occur. [PMBOK 6th edition, Page115] | طلب أحد أصحاب المصلحة الرئيسيين إضافة ميزات إضافية إلى المنتج دون تغيير النطاق أو الميزانية أو الجدول الزمني. يعتقد مدير المشروع أن هذه الميزات ستضيف قيمة كبيرة للمنتج النهائي. ومع ذلك ، فإن هذه الإضافات ستزيد من تكاليف المشروع وتؤثر على الجدول الزمني للمشروع. ما العملية التي يجب على مدير المشروع اتباعها قبل تضمين ميزة المشروع الإضافية؟ | إدارة الجدول الزمني والتكاليف | إدارة النطاق والتكلفة | جمع المتطلبات | إدارة التغيير | تستخدم إدارة التغيير للتالي: 1. تشرح كيفية إدارة التغييرات ، وعمل لجنة التحكم في التغيير (CCB). 2. تحدد كيف يمكن تغيير نطاق المشروع ، وإجراءات تغيير النطاق ، ومتطلبات إجراء التغيير. 3. التأكد من عدم حدوث تغييرات غير مناسبة في نطاق المشروع. [PMBOK الطبعة السادسة، الصفحة115] | 140 | 5 | False | "20" | Haitham
448 | The completion date for a critical milestone is approaching, but a shared team is unable to commit to achieving it on schedule. What should the project manager do to meet the milestone date? | Ask the client to change the milestone date. | Request the additional resources. | Remind the shared team about the milestone's importance. | Approach the shared team's functional manager to request additional support. | The project manager is working in a weak matrix or functional organization. SO the project manager should approach the shared team's functional manager to request additional support. Option ( Remind the shared team about the milestone's importance. ) not good action because they already unable to commit to achieving it on schedule. Option ( Request the additional resources.) not correct because the project manager have no authority and should ask the functional manager for support. Option ( Ask the client to change the milestone date. ) not good practice in such situation. [PMBOK 6th edition, Page 213]. | اقترب موعد الانتهاء من حدث هام ، لكن الفريق المشترك غير قادر على الالتزام بتحقيقه في الموعد المحدد. ما الذي يجب أن يفعله مدير المشروع للوفاء بالتاريخ المحدد؟ | اطلب من العميل تغيير تاريخ الحدث. | اطلب موارد إضافية. | ذكِّر الفريق المشترك بأهمية الحدث. | استهدف المدير الوظيفي للفريق المشترك لطلب دعم إضافي. | يعمل مدير المشروع في مصفوفة ضعيفة أو منظمة وظيفية. لذلك يجب على مدير المشروع الاتصال بالمدير الوظيفي للفريق المشترك لطلب دعم إضافي. الخيار (تذكير الفريق المشترك بأهمية المعلم) ليس إجراءً جيدًا لأنهم بالفعل غير قادرين على الالتزام بتحقيقه في الموعد المحدد. الخيار (طلب موارد إضافية.) غير صحيح لأن مدير المشروع ليس لديه سلطة ويجب أن يطلب الدعم من المدير الوظيفي. الخيار (اطلب من العميل تغيير تاريخ الحدث.) ليس ممارسة جيدة في مثل هذه الحالة. [PMBOK الطبعة السادسة، الصفحة 213]. | 142 | 5 | False | "19" | Haitham
449 | The project manager works in risk management and creating a risk register. The risk register records details of all the risks identified at the beginning and during the life of the project. What tool or technique should the project manager use to generate a list of all possible project risks? | Monte Carlo | Tornado diagram | Probability and impact matrix | Brainstorming | Brainstorming is a data-gathering technique that can be used for identify risk process and The goal of brainstorming is to obtain a comprehensive list of individual project risks and sources of overall project risk. [PMBOK 6th edition page, 414] | يعمل مدير المشروع في إدارة المخاطر وإنشاء سجل للمخاطر. يسجل سجل المخاطر تفاصيل جميع المخاطر التي تم تحديدها في بداية وأثناء عمر المشروع. ما هي الأداة أو التقنية التي يجب على مدير المشروع استخدامها لإنشاء قائمة بجميع مخاطر المشروع المحتملة؟ | مونتي كارلو | مخطط تورنادو | مصفوفة الاحتمالات والأثر | العصف الذهني | العصف الذهني هو أسلوب لجمع البيانات يمكن استخدامه لتحديد عملية المخاطر، والهدف من العصف الذهني هو الحصول على قائمة شاملة بمخاطر المشروع الفردية ومصادر المخاطر الكلية للمشروع. [PMBOK الإصدار السادس، الصفحة 414] | 147 | 3 | False | "19" | Haitham
450 | You have identified a risk that may cause safety concerns for the workers completing the task. You've decided to hire a third party to complete this work because the risk is too great to accept internally. Which risk response is this? | Avoidance | Acceptance | Mitigation | Transference | The transfer involves shifting ownership of a threat to a third party to manage the risk and to bear the impact if the threat occurs. Agreements may be used to transfer ownership and liability for specified risks to another party. A is incorrect because mitigation is any effort to reduce or eliminate the risk. B is incorrect because acceptance means just that: the risk has been accepted. C is incorrect because avoidance is changing the project management plan to avoid the risk altogether. [PMBOK 6th edition, Page 443 ] | لقد حددت خطرًا قد يتسبب في مخاوف تتعلق بسلامة العمال الذين يكملون المهمة. لقد قررت الاستعانة بطرف ثالث لإكمال هذا العمل لأن المخاطرة أكبر من أن تقبل داخليًا. ما هو هذا الرد للمخاطر؟ | تجنب | قبول | تخفيف | نقل | يتضمن نقل المخاطر نقل ملكية التهديد إلى طرف ثالث لإدارة المخاطر وتحمل التأثير في حالة حدوث التهديد. يمكن استخدام الاتفاقيات لنقل الملكية والمسؤولية عن مخاطر محددة إلى طرف آخر. التخفيف غير صحيح لأن التخفيف هو أي جهد لتقليل أو القضاء على المخاطر. القبول غير صحيح لأنه يعني قبول المخاطرة. التجنب غير صحيح لأنه يغير خطة إدارة المشروع لتجنب المخاطر تمامًا. [PMBOK الطبعة السادسة، الصفحة 443] | 147 | 3 | False | "19" | Haitham
451 | You are the project manager of a large IT project. During the implementation phase, you sign a contract to rent an additional server from a local company because of the possibility that the main server may fail due to constant, local-area electrical outages. As a project manager, what strategy are you using? | Transfer | Avoid | Escalate | Mitigate | In risk mitigation, the action is taken to reduce the probability of occurrence and/or impact of a threat. the project manager wants to reduce the probability and impact by renting the generator.[PMBOK 6th edition, Page 443] | أنت مدير مشروع كبير لتقنية المعلومات. أثناء مرحلة التنفيذ ، تقوم بتوقيع عقد لاستئجار خادم إضافي من شركة محلية بسبب احتمال تعطل الخادم الرئيسي بسبب انقطاع التيار الكهربائي المستمر في المنطقة المحلية. كمدير مشروع ، ما هي الاستراتيجية التي تستخدمها؟ | نقل | تجنب | تصعيد | تخفيف | في التخفيف من المخاطر ، يتم اتخاذ الإجراء لتقليل احتمالية حدوث و / أو تأثير التهديد. يريد مدير المشروع تقليل الاحتمالية والتأثير من خلال استئجار الخادم. [PMBOK الطبعة السادسة، الصفحة 443] | 147 | 3 | False | "20" | Haitham
452 | You and your team have done extensive brainstorming and discussions. You have also looked up the organizations process assets and have come up with an exhaustive list of risks. You and your team members feel fairly confident now that you know all the risks. You decide to prioritize the risks and only focus on the high priority ones. A team member indicates that a large number of risks have very low priority. What should you do next? | These risks can be dismissed | Perform Quantitative Risk Analysis | These risks can be accepted | Update risk register | After performing Qualitative Risk Analysis, the Risk Register is updated included watch list which stated the low priority Risks for continued monitoring. [PMBOK 6th edition. Page 427]. | لقد أجريت أنت وفريقك عصف ذهني مكثف ومناقشات. لقد بحثت أيضًا عن أصول عمليات المنظمة وتوصلت إلى قائمة شاملة للمخاطر. تشعر أنت وأعضاء فريقك بالثقة إلى حد ما الآن لأنك تعرفت على كل المخاطر. قررت الأن إعطاء الأولوية للمخاطر والتركيز فقط على المخاطر ذات الأولوية العالية. أشار أحد أعضاء الفريق إلى أن عددًا كبيرًا من المخاطر لها أولوية منخفضة جدًا. ماذا يجب ان تفعل بعد ذلك؟ | يمكن رفض هذه المخاطر | إجراء التحليل الكمي للمخاطر | يمكن قبول هذه المخاطر | تحديث سجل المخاطر | بعد إجراء التحليل النوعي للمخاطر ، يتم تحديث سجل المخاطر ضمن قائمة المراقبة التي حددت المخاطر ذات الأولوية المنخفضة للمراقبة المستمرة. [PMBOK الطبعة السادسة. الصفحة 427]. | 147 | 3 | False | "19" | Haitham
453 | Your project manager has advised that you need to protect the organization from financial risk. In planning a new project, you realize there is a limited scope definition related to the work required to fulfill the contract. What is the best type of contract to choose? | Time and material (T&M) | Cost plus fixed fee (CPFF) | Fixed price incentive fee (FPIF). | Cost plus incentive fee (CPIF). | When you have a project with limited scope, the most suitable type of contract is Cost-reimbursable contracts. This type should be used if the scope of work is expected to change significantly during the execution of the contract. We have two types of Cost-reimbursable contracts in the options given ( Cost plus incentive fee and Cost plus a fixed fee. Both the risk lies on the buyer but Cost plus incentive fee the risk is lower than the cost plus fixed fee where the buyer has to pay a fixed fee along with the cost incurred, but the Cost plus incentive fee the buyer pays the fee based on achieving certain performance objectives mentioned in the contract. [PMBOK 6th edition, Page 472]. | نصحك مدير المشروع بأنك بحاجة إلى حماية المنظمة من المخاطر المالية. عند التخطيط لمشروع جديد ، أدركت أن هناك تعريف محدود لنطاق العمل المطلوب للوفاء بالعقد. ما هو أفضل نوع من العقود يمكن اختياره؟ | الوقت والمواد (T&M). | التكلفة المستردة بالإضافة إلى الرسوم الثابتة (CPFF). | التكلفة الثابتة مع حوافز (FPIF). | التكلفة المستردة بالإضافة إلى الحوافز (CPIF). | عندما يكون لديك مشروع ذو نطاق محدود ، فإن أنسب نوع من العقود هو عقود التكلفة المستردة. يجب استخدام هذا النوع إذا كان من المتوقع أن يتغير نطاق العمل بشكل كبير أثناء تنفيذ العقد. لدينا نوعان من عقود التكلفة القابلة للاسترداد في الخيارات المقدمة (التكلفة المستردة بالإضافة إلى رسوم الحوافز والتكلفة المستردة بالإضافة إلى رسوم ثابتة. تقع كل من المخاطر على عاتق المشتري ولكن التكلفة المستردة بالإضافة إلى رسوم الحوافز ، تكون المخاطر أقل من التكلفة المستردة بالإضافة إلى الرسوم الثابتة حيث يكون المشتري يجب أن يدفع رسمًا ثابتًا مع التكلفة المتكبدة ، ولكن التكلفة المستردة بالإضافة إلى رسوم الحوافز يدفع المشتري الرسوم بناءً على تحقيق أهداف أداء معينة مذكورة في العقد. [PMBOK الطبعة السادسة، الصفحة 472]. | 148 | 3 | False | "20" | Haitham
454 | By the project management information system (PMIS), a project management team is updating a dashboard monthly with information on the project's performance. Which of the following communication methods describes this? | Interactive Communication | Informal communication | Manual communication | Pull Communication | Since (dashboard) is update monthly with information on the project's performance to help the internal and external stakeholders to get the information any time by using the PMIS. its an example of pull communication. [PMBOK 6th edition, Page 374] | من خلال نظام معلومات إدارة المشروع (PMIS) ، يقوم فريق إدارة المشروع بتحديث لوحة قياس الأداء شهريًا بمعلومات عن أداء المشروع. أي من طرق الاتصال التالية تصف هذا؟ | التواصل التفاعلي | التواصل غير الرسمي | الاتصال اليدوي | الاتصال بالسحب | تحديث (لوحة قياس الاداء) شهريًا بمعلومات عن أداء المشروع لمساعدة أصحاب المصلحة الداخليين والخارجيين للحصول على المعلومات في أي وقت باستخدام PMIS. هو مثال على التواصل بسحب البيانات. [PMBOK الطبعة السادسة ، الصفحة 374] | 146 | 3 | False | "19" | Haitham
455 | You are a project manager for an construction project. During the implementation phase, you found that there is a great opportunity and you decide to transfer the ownership of an opportunity to a third party so that it shares some of the benefits if the opportunity occurs. Therefore, a joint venture was made with another company to catch these benefits. Now, you became responsible for the project as a whole. What will your next step be? | Update Resource Management Plan | Update Project Team Assignment | Update Cost Management Plan | Update Communication Management Plan | Due to a joint venture was made So next step should be updated communication management plan because its contains Stakeholder communication requirements , Information to be communicated, including language, format, content, and level of detail, Timeframe and frequency for the distribution of required information and receipt of acknowledgment or response. [PMBOK 6th edition, Page 387] | أنت مدير مشروع انشائي. خلال مرحلة التنفيذ ، وجدت أن هناك فرصة كبيرة وقررت نقل ملكية الفرصة إلى طرف ثالث بحيث يشارك بعض الفوائد في حالة حدوث الفرصة. لذلك ، تم إنشاء مشروع مشترك مع شركة أخرى للاستفادة من هذه الفوائد. الآن ، أصبحت مسؤولاً عن المشروع ككل. ماذا ستكون خطوتك التالية؟ | تحديث خطة إدارة الموارد | تحديث تعيينات فريق المشروع | تحديث خطة إدارة التكلفة | تحديث خطة إدارة الاتصالات | بسبب إنشاء المشروع المشترك يجب أن تكون الخطوة التالية هي تحديث خطة إدارة الاتصالات لأنها تحتوي على متطلبات التواصل مع أصحاب المصلحة والمعلومات التي سيتم توصيلها ، بما في ذلك اللغة والشكل والمحتوى ومستوى التفاصيل والإطار الزمني وتكرار توزيع المعلومات المطلوبة و اقرار استلامها أو الرد. [PMBOK الطبعة السادسة، الصفحة 387] | 146 | 4 | False | "19" | Haitham
456 | A multiphase project that has been executed with internal resources has reached a phase gate. The key project stakeholders want to determine if the phase has met its success criteria, and whether or not the project should progress to the next phase. In addition to the project management plan, which documents will be required? | Agreements including procurement contracts | Lessons learned register and lessons learned repository | Risk register and risk report | Business documents and project charter | The business documents and project charter are needed to determine whether or not the project should progress to the next phase. The project charter will provide the project's success criteria. The business documents include the business case and benefits management plan. The business case documents the business need and the cost-benefit analysis that justifies the project. The benefits management plan is used to measure whether the benefits of the project are being achieved as planned. [PMBOK 6th edition, Page 21] | وصل مشروع متعدد المراحل تم تنفيذه بموارد داخلية إلى نهاية المرحلة. يريد أصحاب المصلحة الرئيسيون في المشروع تحديد ما إذا كانت المرحلة قد استوفت معايير النجاح الخاصة بها، وما إذا كان ينبغي للمشروع التقدم إلى المرحلة التالية أم لا. بالإضافة إلى خطة إدارة المشروع، ما هي المستندات المطلوبة؟ | الاتفاقيات بما في ذلك عقود الشراء | سجل الدروس المستفادة ومستودع الدروس المستفادة | سجل المخاطر وتقرير المخاطر | وثائق العمل وميثاق المشروع | وثائق العمل وميثاق المشروع مطلوبة لتحديد ما إذا كان المشروع يجب أن يتقدم إلى المرحلة التالية أم لا. سيوفر ميثاق المشروع معايير نجاح المشروع. تتضمن وثائق الأعمال دراسة الجدوى وخطة إدارة الفوائد. توثق دراسة الجدوى حاجة العمل وتحليل التكلفة والعائد الذي يبرر المشروع. يتم استخدام خطة إدارة الفوائد لقياس ما إذا كان يتم تحقيق فوائد المشروع كما هو مخطط ام لا. [PMBOK الطبعة السادسة ، الصفحة 21] | 140 | 3 | False | "19" | Haitham
457 | You are a program manager of a project that is halfway through the execution. Because of the increased volatility of prices, one of the vendors asks you to make a price change that will affect the project contract. As a program manager, what should you do next? | Ask the CCB for approval | Implement the approved change | Analyze the impact and Update the Project management plan | Submit a change request and analyze the impact | As a price change will affect the project contract, the project manager should Submit a change request and analyze the impact then take approval from CCB then update affected baselines then Implement the approved change. [PMBOK 6th edition, Page115] | انت مدير برنامج لمشروع في منتصف مرحلة التنفيذ. بسبب التقلب المتزايد في الأسعار ، يطلب أحد البائعين منك إجراء تغيير في السعر من شأنه أن يؤثر على عقد المشروع. كمدير برنامج ، ماذا يجب أن تفعل بعد ذلك؟ | اطلب الموافقة من لجنة التحكم بالتغييرات | تنفيذ التغيير المعتمد | تحليل التأثير وتحديث خطة إدارة المشروع | إرسال طلب تغيير وتحليل التأثير | نظرًا لأن تغيير السعر سيؤثر على عقد المشروع ، يجب على مدير البرنامج إرسال طلب تغيير وتحليل التأثير ثم الحصول على الموافقة من لجنة التحكم بالتغييرات ثم تحديث خطوط الأساس المتأثرة ثم تنفيذ التغيير المعتمد. [PMBOK الطبعة السادسة، الصفحة115] | 140 | 5 | False | "19" | Haitham
458 | While reviewing the statement of work (SOW) for the project, four stakeholders not agree on what the project should include. As a project manager, What should you do? | Document the conflict in the issue log before participating in the development of the project charter. | Include the stakeholders' comments for future reference in the project charter. | Document the stakeholders' points but include the remaining stakeholders' input in final decision making. | Hold a meeting with the four stakeholders to resolve the conflict and reach agreement. | Conflict management is a part of Interpersonal and team skills that can be used for the initiation process. Conflict management can be used to help bring stakeholders into alignment on the objectives, success criteria, high-level requirements, project description, summary milestones, and other elements of the charter. so the project manager should be proactive and meet with the four stakeholders to resolve the conflict and reach an agreement. [PMBOK 6th edition, Page 80] | أثناء مراجعة بيان العمل (SOW) للمشروع ، لم يتفق أربعة من أصحاب المصلحة على ما يجب أن يتضمنه المشروع. كمدير مشروع ، ماذا يجب أن تفعل؟ | توثيق التعارض في سجل الأحداث قبل المشاركة في تطوير ميثاق المشروع. | قم بتضمين تعليقات أصحاب المصلحة للرجوع إليها في المستقبل في ميثاق المشروع. | قم بتوثيق نقاط أصحاب المصلحة ولكن قم بتضمين مدخلات أصحاب المصلحة المتبقين في اتخاذ القرار النهائي. | عقد اجتماع مع أصحاب المصلحة الأربعة لحل النزاع والتوصل إلى اتفاق. | تعد إدارة الصراع جزءًا من المهارات الشخصية والجماعية التي يمكن استخدامها في عملية البدء. يمكن استخدام إدارة الصراع لمساعدة أصحاب المصلحة في المواءمة مع الأهداف ومعايير النجاح والمتطلبات عالية المستوى ووصف المشروع وملخص المعالم والعناصر الأخرى للميثاق. لذلك يجب أن يكون مدير المشروع استباقيًا وأن يجتمع مع أصحاب المصلحة الأربعة لحل النزاع والتوصل إلى اتفاق. [PMBOK الطبعة السادسة ، الصفحة 80] | 145 | 4 | False | "20" | Haitham
459 | A project manager was assigned to a project when the project charter was in development. Which of the following is an input that the project manager will use to develop the project charter? | Enterprise environmental factors and Project Acceptance Criteria | Agreements and Make-or-Buy analysis | Organizational Process Assets and Project Scope Statement | Cost Benefit Analysis and organizational strategies | A business case includes Cost-Benefit Analysis and organizational strategies. [PMBOK 6th edition, Page 68,75] | تم تعيين مدير مشروع عندما كان ميثاق المشروع قيد التطوير. أي مما يلي يعد أحد المدخلات التي سيستخدمها مدير المشروع لتطوير ميثاق المشروع؟ | العوامل البيئية للمؤسسة ومعايير قبول المشروع | الاتفاقيات وتحليل الصنع أو الشراء | أصول العملية التنظيمية وبيان نطاق المشروع | تحليل التكلفة والمنفعة والاستراتيجيات التنظيمية | تتضمن دراسة الجدوى استراتيجيات تحليل التكلفة والمنفعة والاستراتيجيات التنظيمية. [PMBOK الطبعة السادسة ، الصفحة 68،75] | 140 | 2 | False | "20" | Haitham
460 | You are working on a project to construct villa in your city, and you are about to start project planning. As a starting point for initial project planning, what is the first thing you should do? | Conduct a project kick-off meeting to inform and engage stakeholders and gain commitment. | Begin the process of identifying stakeholders so they can be engaged as necessary for project planning. | Develop the project schedule to manage timely completion of the project | Review the project charter to understand the high-level information about the project. | The question states that project planning is about to begin which suggests that project initiation has been completed. The project charter is created during the Develop Project Charter process as part of project initiation. The project team uses the project charter as a starting point for initial project planning. The type and amount of information in the project charter varies depending on the complexity of the project and the information known at the time of its creation. At a minimum, the project charter should define the high-level information about the project that will be elaborated in the various components of the project management plan. [PMBOK 6th edition, Page 81]. | أنت تعمل على مشروع لبناء فيلا في مدينتك ، وأنت على وشك البدء في تخطيط المشروع. كنقطة انطلاق للتخطيط الأولي للمشروع ، ما هو أول شيء يجب عليك فعله؟ | عقد اجتماع إطلاق المشروع لإعلام وإشراك أصحاب المصلحة وكسب الالتزام. | ابدأ عملية تحديد أصحاب المصلحة حتى يمكن إشراكهم عند الضرورة لتخطيط المشروع. | تطوير الجدول الزمني للمشروع لإدارة الانتهاء من المشروع في الوقت المناسب | راجع ميثاق المشروع لفهم المعلومات عالية المستوى حول المشروع. | يشير السؤال إلى أن تخطيط المشروع على وشك البدء مما يشير إلى أن بدء المشروع قد اكتمل. يتم إنشاء ميثاق المشروع أثناء عملية تطوير ميثاق المشروع كجزء من بدء المشروع. يستخدم فريق المشروع ميثاق المشروع كنقطة انطلاق للتخطيط الأولي للمشروع. يختلف نوع وكمية المعلومات في ميثاق المشروع تبعًا لمدى تعقيد المشروع والمعلومات المعروفة وقت إنشائه. كحد أدنى، يجب أن يحدد ميثاق المشروع المعلومات عالية المستوى حول المشروع التي سيتم وضعها في المكونات المختلفة لخطة إدارة المشروع. [PMBOK الطبعة السادسة، الصفحة 81]. | 140 | 3 | False | "20" | Haitham
461 | During the execution phase, the project owner left the project and a new sponsor has been assigned. What should you do next? | Update RACI Chart | Update the Project Management Plan | Update Stakeholder Engagement Plan | Update the stakeholder register | When identifying a new stakeholder during the project, the First step is to update the Stakeholder register. [PMBOK 6th edition, Page 529] | خلال مرحلة التنفيذ ، غادر مالك المشروع وتم تعيين راعي جديد للمشروع. ماذا يجب ان تفعل بعد ذلك؟ | تحديث مخطط توزيع المهام RACI | تحديث خطة إدارة المشروع | تحديث خطة إشراك أصحاب المصلحة | تحديث سجل أصحاب المصلحة | عند تحديد صاحب مصلحة جديد أثناء المشروع ، فإن الخطوة الأولى هي تحديث سجل أصحاب المصلحة. [PMBOK الطبعة السادسة ، الصفحة 529] | 149 | 4 | False | "16" | Haitham
462 | You are a project manager in a infrastructure project. During a review, the site engineer informs you that the concrete production rate has changed over the last three months. What analysis should be conducted? | Control chart | Earned value (EV). | Scatter diagram | Trend analysis | Trend analysis examines project performance over time to determine whether performance is improving or deteriorating. Graphical analysis techniques are valuable for understanding performance to date and for comparing to future performance goals in the form of completion dates. [PMBOK 6th edition, Page 227] | أنت مدير مشروع في مشروع بنية تحتية. أثناء المراجعة ، أخبرك مهندس الموقع أن معدل إنتاج الخرسانة قد تغير خلال الأشهر الثلاثة الماضية. ما هو التحليل الذي يجب إجراؤه؟ | مخطط التحكم | القيمة المكتسبة (EV). | مخطط التشتت | تحليل الاتجاه | يفحص تحليل الاتجاهات أداء المشروع بمرور الوقت لتحديد ما إذا كان الأداء يتحسن أو يتدهور. تعتبر تقنيات التحليل الرسومية ذات قيمة لفهم الأداء الحالي وللمقارنة بأهداف الأداء المستقبلية في شكل تواريخ الإنتهاء. [PMBOK الطبعة السادسة ، الصفحة 227] | 142 | 5 | False | "19" | Haitham
463 | You have recently been assigned as the project manager for a company that has a history of implementing system integration projects and you don't have prior experience. What should you do? | Meet with the sponsor | Review the project charter | Refer to the project statement of work (SOW). | Seek expert judgment | Since you don't have prior experience, so you should seek expert judgment. [PMBOK 6th edition, Page 94] | لقد تم تعيينك مؤخرًا كمدير مشروع لشركة لديها تاريخ في تنفيذ مشاريع تكامل الأنظمة وليس لديك خبرة سابقة. ماذا عليك ان تفعل؟ | الإجتماع مع راعي المشروع | راجع ميثاق المشروع | الرجوع إلى بيان عمل المشروع (SOW). | ابحث عن رأي الخبراء | بسبب أنه ليس لديك خبرة سابقة، لذلك يجب عليك السعي للحصول على رأي الخبراء. [PMBOK الطبعة السادسة ، الصفحة 94] | 140 | 4 | False | "18" | Haitham
464 | You has been assigned as a project manager, you are managing a software development project. As a result of observation and conversation, you notice some of the team members need to improve their skills. What should you do FIRST? | Update Cost Baseline | Schedule training sessions for the team members to optimize their performance. | Acquire new members | Review the Resource Management Plan | The Resource Management Plan include training strategies and methods for developing the project team. [PMBOK 6th edition, Page 319] | لقد تم تعيينك كمدير مشروع ، أنت تدير مشروع تطوير برمجيات. كنتيجة للملاحظة والمحادثة، تلاحظ أن بعض أعضاء الفريق بحاجة إلى تحسين مهاراتهم. ما الذى ينبغى عليك فعله اولا؟ | تحديث خط أساس التكلفة | قم بجدولة جلسات تدريبية لأعضاء الفريق لتحسين أدائهم. | اكتساب أعضاء جدد | راجع خطة إدارة الموارد | تتضمن خطة إدارة الموارد استراتيجيات التدريب وطرق تطوير فريق المشروع. [PMBOK الطبعة السادسة ، الصفحة 319] | 145 | 3 | False | "20" | Haitham
465 | You are a project manager in an IT project. During the deployment of a new system, an unexpected power outage occurs. What should the project manager do? | Risk categorization. | Risk probability and impact assessment. | Perform a qualitative risk analysis . | Refer to the risk register and inform key stakeholder. | As an unexpected power outage occurs, the project manager should first Refer to the risk register and inform key stakeholders to handle this scenario. Risk categorization and Risk probability and impact assessment are T&T in Perform a qualitative risk analysis process, therefore they can be excluded. [PMBOK 6th edition, Page 411, 458]. | أنت مدير مشروع في مشروع تقنية معلومات. أثناء نشر نظام جديد ، حدث انقطاع غير متوقع للتيار الكهربائي. ماذا يجب أن يفعل مدير المشروع؟ | تصنيف المخاطر . | تقييم احتمالية حدوث المخاطر وتأثيرها. | إجراء تحليل نوعي للمخاطر . | الرجوع إلى سجل المخاطر وإبلاغ أصحاب المصلحة الرئيسيين. | عند حدوث انقطاع غير متوقع للتيار الكهربائي، يجب على مدير المشروع الرجوع أولاً إلى سجل المخاطر وإبلاغ أصحاب المصلحة الرئيسيين للتعامل مع هذا السيناريو. تصنيف المخاطر، وتقييم احتمالية حدوث المخاطر وتأثيرها هي أدوات وتقنيات في إجراء عملية تحليل المخاطر النوعية ، وبالتالي يمكن استبعادها. [PMBOK الطبعة السادسة، الصفحة 411، 458]. | 147 | 5 | False | "18" | Haitham
466 | During the middle of the project, the project manager has been exposed to an accident, and a new project manager has been assigned. What should the new project manager do next? | Update organizational process assets (OPA) | Update resource calendar | Update project charter | Update project management plan | Since he is a new project manager, so the communication management plan should be updated. Also, the resource management plan is a component of the project management plan. Option update project charter is incorrect because the sponsor who can update or modify the project charter according to PMBOK. | خلال منتصف المشروع ، تعرض مدير المشروع لحادث ، وتم تعيين مدير مشروع جديد. ماذا يجب أن يفعل مدير المشروع الجديد بعد ذلك؟ | تحديث أصول العملية التنظيمية (OPA) | تحديث تقويم الموارد | تحديث ميثاق المشروع | تحديث خطة إدارة المشروع | نظرًا لأنه مدير مشروع جديد، يجب تحديث خطة إدارة الاتصالات. كما أن خطة إدارة الموارد هي أحد مكونات خطة إدارة المشروع. خيار تحديث ميثاق المشروع غير صحيح لأن الراعي يمكنه تحديث أو تعديل ميثاق المشروع وفقًا لـ PMBOK. | 147 | 4 | False | "20" | Haitham
467 | Using the following values, calculate the Management reserve: Project Budget = 100,000 EAC = 120,000 AC = 5,500 BAC=70,000 | 70000 | 40000 | 100000 | 30000 | The Management reserve = Project Budget - BAC. Therefore, 100,000 - 70,000 = 30,000. [PMBOK 6th edition. Page 267]. | باستخدام القيم التالية ، احسب احتياطي الإدارة: ميزانية المشروع = 100،000 التقدير عند الانتهاء EAC = 120،000 التكلفة الفعلية AC = 5،500 الميزانية عند الاكتمال BAC = 70،000 | 70000 | 40000 | 100000 | 30000 | احتياطي الإدارة = ميزانية المشروع - BAC. لذلك، 100,000 - 70,000 = 30,000 [PMBOK الطبعة السادسة. الصفحة 267]. | 143 | 5 | False | "17" | Haitham
468 | You are in the middle of your project and working on a deliverable which is 85% completed. It is time for the yearly audit. A team of auditors are about to come and verify if you are following the process as defined or not. However, as the deliverable is about to be completed, you check it and measure all dimensions to find any possible dimensional defects. What process is this? | Manage quality | Plan quality management | Control scope | Control quality | In the quality control process, you inspect the deliverable for any possible defects. As you are doing an inspection, you are in the quality control process. Please note that although the quality audit is performed in the manage quality process, it has not started yet and you are doing an inspection, which is a tool of the quality control process. [PMBOK 6th edition, Page 303] | أنت في منتصف مشروعك وتعمل على تسليمات مكتملة بنسبة 85٪. حان الوقت للتدقيق السنوي. فريق من المراجعين على وشك القدوم والتحقق مما إذا كنت تتبع العمليات كما هو محدد أم لا. ومع ذلك ، نظرًا لأن التسليم على وشك الانتهاء ، يمكنك التحقق منه وقياس جميع الأبعاد للعثور على أي عيوب محتملة في الأبعاد. ما هذه العملية؟ | إدارة الجودة | خطة إدارة جودة | التحكم بالنطاق | التحكم بالجودة | في عملية التحكم بالجودة ، تقوم بفحص المنتج بحثًا عن أي عيوب محتملة. أثناء قيامك بالفحص، فأنت في عملية مراقبة الجودة. يرجى ملاحظة أنه على الرغم من إجراء تدقيق الجودة في عملية إدارة الجودة إلا أنه لم يبدأ بعد وأنت تقوم بإجراء فحص ، وهو أداة لعملية مراقبة الجودة. [PMBOK الطبعة السادسة ، الصفحة 303] | 144 | 5 | False | "17" | Haitham
469 | You have been managing a construction new industries project in a developing country, and now you are closing the project. The project completed on schedule and under budget. The general manager of your company heard about the success of your project and wants a summary overview of project performance so that he can talk about your success at the next board meeting. What should you provide to him? | lessons learned register | Lessons learned repository | Project Charter | Final report | The scenario suggests the project has been closed. In other words, the Close Project or Phase process is now complete. The final report is one of the outputs from this process. The final report includes information such as a summary level description of the project, a summary of any risks and issues encountered and how they were addressed, a summary of how the final product, service or result was achieved, and more. Since the vice president wants a summary overview of project results, providing the vice president with the final report will likely meet their needs and is, therefore, of the choices provided, the best answer to the question asked. [PMBOK 6th edition, Page 127] | لقد كنت تدير مشروع إنشاءات صناعات جديدة في دولة نامية ، وأنت الآن تقوم بإغلاق المشروع. اكتمل المشروع في الموعد المحدد وتحت الميزانية. سمع المدير العام لشركتك عن نجاح مشروعك ويريد لمحة موجزة عن أداء المشروع حتى يتمكن من التحدث عن نجاحك في اجتماع مجلس الإدارة التالي. ماذا يجب ان تقدم له؟ | سجل الدروس المستفادة | مستودع الدروس المستفادة | ميثاق المشروع | التقرير النهائي | يشير السيناريو إلى إغلاق المشروع. بمعنى آخر اكتملت عملية إغلاق المشروع أو المرحلة. التقرير النهائي هو أحد مخرجات هذه العملية. يتضمن التقرير النهائي معلومات مثل وصف موجز للمشروع ، وملخصًا لأي مخاطر ومشكلات تمت مواجهتها وكيف تم معالجتها، وملخصًا لكيفية تحقيق المنتج النهائي أو الخدمة أو النتيجة، والمزيد. نظرًا لأن نائب الرئيس يريد لمحة موجزة عن نتائج المشروع ، فإن تزويد نائب الرئيس بالتقرير النهائي من المرجح أن يلبي احتياجاته، وبالتالي هي أفضل إجابة على السؤال المطروح. [PMBOK الطبعة السادسة ، الصفحة 127] | 140 | 6 | False | "20" | Haitham
470 | A project has been initiated that has several project stakeholders from various departments. Some stakeholders are unavailable for the facilitation meeting to discuss end-to-end processes. To satisfy their own personal agenda, the project owner requests that the meeting take place without all stakeholder's present. What should the project manager do? | Discuss stakeholder availability with the sponsor. | Hold a separate meeting with those stakeholders who are unavailable. | Reschedule the meeting to accommodate all stakeholders. | Set up a facilitation meeting without all stakeholders to obtain initial requirements. | Set up a facilitation meeting without all stakeholders to obtain initial requirements, then hold a separate meeting with those stakeholders who are unavailable. Option (Reschedule the meeting to accommodate all stakeholders) not correct because the project owner requests that the meeting take place without all stakeholder's present. [PMBOK 6th edition, Page 514] | تم البدء في مشروع يضم العديد من أصحاب المصلحة في المشروع من مختلف الإدارات. بعض أصحاب المصلحة غير متاحين لاجتماع التيسير (facilitation) لمناقشة العمليات من البداية إلى النهاية. لتلبية جدول أعمالهم الشخصي ، يطلب صاحب المشروع أن يتم الاجتماع دون حضور جميع أصحاب المصلحة. ماذا يجب أن يفعل مدير المشروع؟ | مناقشة توافر أصحاب المصلحة مع الراعي. | اعقد اجتماعًا منفصلاً مع أصحاب المصلحة غير المتاحين. | إعادة جدولة الاجتماع لاستيعاب جميع أصحاب المصلحة. | قم بإعداد اجتماع تيسير بدون حضور جميع أصحاب المصلحة للحصول على المتطلبات الأولية. | قم بإعداد اجتماع تيسير بدون حضور جميع أصحاب المصلحة للحصول على المتطلبات الأولية. ثم أعقد اجتماع منفصل مع أصحاب المصلحة غير المتاحين. الخيار (إعادة جدولة الاجتماع لاستيعاب جميع أصحاب المصلحة) غير صحيح لأن مالك المشروع يطلب أن يتم الاجتماع بدون حضور جميع أصحاب المصلحة. [PMBOK الطبعة السادسة، الصفحة 514] | 149 | 2 | False | "19" | Haitham
471 | A company has recurring quality issues with one of its sole source suppliers. A new project will incur significant penalties from the end users if deliverables are late What should the project manager do? | Escalate the issue to top management | Negotiate with other vendors with better quality-control methods. | Review incoming inspection reports and quality logs | Identify high- level risks prior to developing contingency plans | In the (past projects) ,the company has recurring quality issues with one of its sole source suppliers. in the new project will incur significant penalties from the customer if deliverables are late. So this is high level risk and should be initially take into consideration , then in the planning phase, the project manager should conducts a mitigation plan to reduce this risk such as conduct more tests and Review incoming inspection reports and quality logs. Since its sole source then you don't have any other option to negotiate with other vendors with better quality-control methods.. Therefor you have to consider this risk while you are planning the project. Since you should be proactive so the escalation process to top management is the last decision. [PMBOK 6th edition, Page 442, 443]. | لدى شركة مشكلات جودة متكررة مع أحد مورديها النادرين. سيتعرض المشروع الجديد لعقوبات كبيرة من المستخدمين النهائيين إذا تأخرت التسليمات. ماذا يجب أن يفعل مدير المشروع؟ | تصعيد المشكلة إلى الإدارة العليا | تفاوض مع البائعين الآخرين باستخدام طرق أفضل لمراقبة الجودة. | مراجعة تقارير التفتيش الواردة وسجلات الجودة | تحديد المخاطر عالية المستوى قبل وضع خطط الطوارئ | في (المشاريع السابقة) ، واجهت الشركة مشكلات جودة متكررة مع أحد مورديها الوحيدين. في المشروع الجديد سيتعرض لعقوبات كبيرة من العميل إذا تأخر التسليم. لذا فإن هذا يمثل مخاطرة عالية المستوى ويجب أن يؤخذ في الاعتبار في البداية ، ثم في مرحلة التخطيط ، يجب على مدير المشروع تنفيذ خطة تخفيف لتقليل هذه المخاطر مثل إجراء المزيد من الاختبارات ومراجعة تقارير التفتيش الواردة وسجلات الجودة. نظرًا لأنه مورد نادر ، فليس لديك أي خيار آخر للتفاوض مع البائعين الآخرين باستخدام أساليب أفضل لمراقبة الجودة .. لذلك عليك التفكير في هذه المخاطر أثناء التخطيط للمشروع. نظرًا لأنه يجب أن تكون استباقيًا ، فإن عملية التصعيد إلى الإدارة العليا هي القرار الأخير. [PMBOK الطبعة السادسة ، الصفحة 442 ، 443]. | 147 | 5 | False | "19" | Haitham
472 | During project closure and transferring of the completed project deliverables to the operations department, the construction manager discovers that an audit report from an early project phase is missing. What should the construction manager do? | Ask the operations group to accept the project without the audit report. | Complete project closure and Update the OPA | Remove the audit report from the required project documents and update the project management plan | Inform the operations group about the missing audit report. | Ethically, the project manager must inform the operations group about the missing audit report. [PMBOK 6th edition, Page 127]. | أثناء إغلاق المشروع ونقل تسليمات المشروع المكتملة إلى قسم التشغيل، اكتشف مدير التنفيذ أن تقرير تدقيق من مرحلة مبكرة من المشروع مفقود. ماذا يجب أن يفعل مدير التنفيذ؟ | اطلب من فريق التشغيل قبول المشروع بدون تقرير التدقيق. | استكمال إغلاق المشروع وتحديث OPA | قم بإزالة تقرير المراجعة من مستندات المشروع المطلوبة وقم بتحديث خطة إدارة المشروع | أبلغ فريق التشغيل بتقرير التدقيق المفقود. | أخلاقياً ، يجب على مدير المشروع إبلاغ فريق التشغيل بتقرير التدقيق المفقود. [PMBOK الطبعة السادسة، الصفحة 127]. | 140 | 6 | False | "19" | Haitham
473 | Without consulting the project manager, an operational manager relocate the key project resources in order to assign them operational tasks. Since these resources are now focused on operational tasks rather than deliverables, the deliverables run late. What should the project manager do first? | Ask to have the resources replaced immediately. | Escalate the functional manager's actions to the sponsor. | Extend the project timeline. | Negotiate time allocation to prioritize the resources' workload. | The functional manager removes key project resources in order to assign them operational tasks. The scenario ask what should you do FIRST. The project manager should FIRST Negotiate time allocation to prioritize the resources' workload. It's a strategic way to distribute the work throughout your team to keep your teams busy and productive. [PMBOK 6th edition, Page 357]. | دون استشارة مدير المشروع ، قام مدير تشغيلي بنقل موارد المشروع الرئيسية بهدف تزويدهم بمهام تشغيلية. نظرًا لأن هذه الموارد تركز الآن على المهام التشغيلية بدلاً من التسليمات، فإن التسليمات تأخرت. ما الذي يجب أن يفعله مدير المشروع أولاً؟ | اطلب استبدال الموارد على الفور. | تصعيد إجراءات المدير التشغيلي إلى الراعي. | تمديد الجدول الزمني للمشروع. | التفاوض بشأن تخصيص الوقت لتحديد أولويات عمل الموارد. | السيناريو الحالي هو انه تم نقل موارد المشروع الرئيسية من قبل المدير التشغيلي من أجل تزويدهم بمهام تشغيلية. يسأل السيناريو ما الذي يجب أن تفعله أولاً. يجب على مدير المشروع التفاوض أولاً بشأن تخصيص الوقت لتحديد أولويات عمل الموارد. إنها طريقة إستراتيجية لتوزيع العمل عبر فريقك لإبقاء فرق العمل مشغولة ومنتجة. [PMBOK الطبعة السادسة، الصفحة 357]. | 145 | 4 | False | "16" | Haitham
474 | As you are project manager in the final closing project phase. Which of the following should you as the project manager refer to ensure that requirements approved in the requirements documentation are delivered? | Stakeholder Engagement Assessment Matrix | Scope Management Plan | Project Management Plan | Requirement Traceability Matrix | The requirements traceability matrix is a grid that links product requirements from their origin to the deliverables that satisfy them. The implementation of a requirements traceability matrix helps ensure that each requirement adds business value by linking it to the business and project objectives. It provides a means to track requirements throughout the project life cycle, helping to ensure that requirements approved in the requirements documentation are delivered at the end of the project. Finally, it provides a structure for managing changes to the product scope.. [PMBOK 6th edition, Page 148] | بصفتك مدير المشروع في مرحلة إغلاق المشروع النهائية. أي مما يلي يجب أن تشير إليه بصفتك مدير المشروع لضمان تسليم المتطلبات المعتمدة في وثائق المتطلبات؟ | مصفوفة تقييم مشاركة أصحاب المصلحة | خطة إدارة النطاق | خطة إدارة المشروع | مصفوفة تتبع المتطلبات | مصفوفة تتبع المتطلبات هي شبكة تربط متطلبات المنتج من أصلها إلى المخرجات التي تلبيها. يساعد تنفيذ مصفوفة تتبع المتطلبات على ضمان أن يضيف كل متطلب قيمة عمل من خلال ربطه بأهداف العمل والمشروع. يوفر وسيلة لتتبع المتطلبات طوال دورة حياة المشروع ، مما يساعد على ضمان تسليم المتطلبات المعتمدة في وثائق المتطلبات في نهاية المشروع. أخيرًا ، يوفر هيكلًا لإدارة التغييرات في نطاق المنتج .. [PMBOK الطبعة السادسة، الصفحة 148] | 140 | 6 | False | "20" | Haitham
475 | A project has a senior stakeholder whose input is important, and who needs to be kept informed about the project's status. Rather than receive updates from the project manager, this stakeholder prefers to contact a team member directly. The stakeholder has a connection with this team members that is unrelated to the project and thinks that this is a way to obtain information on the project's true status. What should the project manager do? | Keep the team member properly informed about project status so that the stakeholder receives the same information from both sources. | Leave the connection in place, since the information coming via the team member is unofficial and will not create problems. | Tell the team member not to accept calls from the stakeholder, because these calls have an adverse effect on the team member's productivity. | Ask the stakeholder how the additional information that they feel is missing from current communications may be provided. | The best answer is to ask the stakeholder how the additional information that they feel is missing from current communications may be provided, in order to update the Communication Management Plan. [PMBOK 6th edition, Page 379] | المشروع له صاحب مصلحة كبير تعتبر مدخلاته مهمة ، ويحتاج إلى إطلاعه على حالة المشروع. بدلاً من تلقي التحديثات من مدير المشروع، يفضل صاحب المصلحة هذا الاتصال بأحد أعضاء الفريق مباشرةً. صاحب المصلحة لديه اتصال مع أحد أعضاء هذا الفريق ولكن لا علاقة له بالمشروع ويعتقد أن هذه طريقة للحصول على معلومات حول الحالة الحقيقية للمشروع. ماذا يجب أن يفعل مدير المشروع؟ | اجعل أعضاء الفريق على علم بحالة المشروع بشكل صحيح حتى يتلقى أصحاب المصلحة نفس المعلومات من كلا المصدرين. | اترك الاتصال في مكانه ، لأن المعلومات الواردة عبر عضو الفريق غير رسمية ولن تخلق مشاكل. | أخبر عضو الفريق بعدم قبول المكالمات من أصحاب المصلحة ، لأن هذه المكالمات لها تأثير سلبي على إنتاجية عضو الفريق. | اسأل أصحاب المصلحة عن كيفية تقديم المعلومات الإضافية التي يشعرون أنها مفقودة من الاتصالات الحالية. | أفضل إجابة هي أن تسأل أصحاب المصلحة كيف يمكن توفير المعلومات الإضافية التي يشعرون أنها مفقودة من الاتصالات الحالية ، من أجل تحديث خطة إدارة الاتصالات. [PMBOK الطبعة السادسة ، الصفحة 379] | 146 | 4 | False | "20" | Haitham
476 | You are a project manager in a infrastructure project. What should you do to ensure the successful delivery of the project? | Meet with stakeholders to communicate the schedule budget, and cost impact in the event of a project delay. | Establish a management reserve to handle the unknown risks when occurs | Conduct a team-building activity | Identify the project's risks and necessary success criteria. | Identify the project's risks and the necessary success criteria. [PMBOK 6th edition, Page 417] | أنت مدير مشروع في مشروع بنية تحتية. ما الذي يجب عليك فعله لضمان التسليم الناجح للمشروع؟ | اجتمع مع أصحاب المصلحة لإبلاغهم بميزانية الجدول الزمني وتأثير التكلفة في حالة حدوث تأخير في المشروع. | إنشاء احتياطي إداري للتعامل مع المخاطر غير المعروفة عند حدوثها | قم بنشاط بناء الفريق | تحديد مخاطر المشروع ومعايير النجاح اللازمة. | تحديد مخاطر المشروع ومعايير النجاح اللازمة. [PMBOK الطبعة السادسة ، الصفحة 417] | 147 | 3 | False | "20" | Haitham
477 | The project in execution phase, unidentified stakeholder request a change on project schedule. As a project manager, What should you do first? | Ignore the stakeholder | Meeting with the team and analyze the impact on project constraints | Implement the change | Update Stakeholder Register | Since the Stakeholder Unidentified, then the stakeholder should be identified first and update stakeholder register before analyzing the impact on project constraints. [PMBOK 6th edition, Page 529] | المشروع في مرحلة التنفيذ ، طلب صاحب مصلحة غير محدد تغيير الجدول الزمني للمشروع. بصفتك مدير مشروع ، ما الذي يجب عليك فعله أولاً؟ | تجاهل أصحاب المصلحة | الاجتماع مع الفريق وتحليل التأثير على قيود المشروع | تنفيذ التغيير | تحديث سجل اصحاب المصالح | بما أن صاحب المصلحة غير محدد، يجب تحديد صاحب المصلحة أولاً وتحديث سجل أصحاب المصلحة قبل تحليل التأثير على قيود المشروع. [PMBOK الطبعة السادسة ، الصفحة 529] | 149 | 4 | False | "19" | Haitham
478 | During the control quality process, the quality inspectors have discovered a many number of defects on the deliverables. The project owner told the project manager go proceed to validate scope process for approval. As a project manager, What should you do next? | Validate Scope Process | Ignore the sponsor and direct team to complete the deliverables | Request training for the team members and rework | Evaluate the impact of defects on the project and inform the sponsor | The project manager should first Evaluate the impact of defects on the project and inform the sponsor. [PMBOK 6th edition, Page 305]. | خلال عملية مراقبة الجودة ، اكتشف مفتشو الجودة عددًا من العيوب في المخرجات. أخبر مالك المشروع مدير المشروع بللبدء بعملية التحقق من النطاق وأخذ الموافقة عليها. بصفتك مدير مشروع ، ماذا يجب أن تفعل بعد ذلك؟ | التحقق من صحة عملية النطاق | تجاهل الراعي وتوجيه الفريق لإكمال المخرجات | طلب تدريب أعضاء الفريق وإعادة العمل | تقييم أثر العيوب على المشروع وإبلاغ الراعي | يجب على مدير المشروع أولاً تقييم تأثير العيوب على المشروع وإبلاغ الراعي. [PMBOK الطبعة السادسة، الصفحة 305]. | 144 | 5 | False | "20" | Haitham
479 | You are a construction manager assigned to a new seaport construction project. You want to create WBS but the project is new to your company and there is no previous experience and documentation as a reference. Which of the following tools will help the project manager? | Organizational process assets | Brainstorming | Lessons learned register | Subject matter experts | Since the project is new to your company and there is no previous experience and documentation as a reference. It requires subject matter experts. PMBOK 6th edition, Page 158 ]. | أنت مدير إنشاءات مكلف بمشروع إنشاء ميناء بحري جديد. تريد إنشاء WBS لكن المشروع جديد لشركتك ولا توجد خبرة سابقة أو وثائق كمرجع. أي من الأدوات التالية ستساعد مدير المشروع؟ | أصول العملية التنظيمية | العصف الذهني | تسجيل الدروس المستفادة | الخبراء في الموضوع | نظرًا لأن المشروع جديد على شركتك ولا توجد خبرة سابقة وتوثيق كمرجع. يتطلب في الموضوع. [الطبعة السادسة من PMBOK ، صفحة 158]. | 141 | 3 | False | "20" | Haitham
480 | The project manager is trying to get hand over for a series of marketing materials. The work is rejected by the key stakeholders responsible for sign off because of incorrect use of marketing standards and specification. What should the project manager do before sending materials to the key stakeholders again? | Validate the scope before performing quality control | Create a work breakdown structure before validating the scope | Validate scope before communicating the project status | Perform quality control checks before validating the scope | In the scenario, the work is being validated by the stakeholders, but there are quality concerns noted by the incorrect use of standards. Ideally, the Control Quality process should be completed before the scope can be validated. It is unclear from the scenario whether or not this process has been carried out at all. Regardless, now, when the issues have been found during scope validation, it is essential that before repeating the Validate Scope process for this work, the project manager and the project team conduct the Control Quality process to ensure correctness and proper adherence to the marketing quality standards. Then the scope can be validated based on both correctness and completeness. [PMBOK 6th edition, Page 298]. | يحاول مدير المشروع تسليم سلسلة من المواد التسويقية. تم رفض العمل من قبل أصحاب المصلحة الرئيسيين المسؤولين عن اعتماد التسليمات بسبب الاستخدام غير الصحيح لمعايير التسويق والمواصفات. ما الذي يجب على مدير المشروع فعله قبل إرسال المواد إلى أصحاب المصلحة الرئيسيين مرة أخرى؟ | تحقق من النطاق قبل إجراء مراقبة الجودة | قم بإنشاء هيكل توزيع العمل قبل التحقق من صحة النطاق | تحقق من النطاق قبل الإبلاغ عن حالة المشروع | قم بإجراء فحوصات التحكم يالجودة قبل التحقق من صحة النطاق | في السيناريو ، يتم التحقق من العمل من قبل أصحاب المصلحة ، ولكن هناك مخاوف تتعلق بالجودة تمت ملاحظتها من خلال الاستخدام غير الصحيح للمعايير. من الناحية المثالية ، يجب إكمال عملية التحكم بالجودة قبل التحقق من النطاق. ليس من الواضح من السيناريو ما إذا كانت هذه العملية قد نفذت على الإطلاق أم لا. ولكن عند اكتشاف المشكلات أثناء التحقق من النطاق، من الضروري قبل تكرار عملية التحقق من صحة النطاق أن يقوم مدير المشروع وفريقه بإجراء عملية التحكم بالجودة لضمان الصحة والالتزام المناسب بجودة التسويق والمعايير. ثم يمكن التحقق من صحة النطاق. [PMBOK الطبعة السادسة ، الصفحة 298]. | 144 | 5 | False | "19" | Haitham
481 | Six Sigma methodology incorporates many powerful tools to use in continuous improvement projects and programs. Six Sigma are tools in which of the following processes? | Plan Scope management | Close project or phase | Define Scope | Manage Quality | Six Sigma is the most common quality improvement tools used to analyze and evaluate opportunities for improvement [PMBOK 6th edition, Page 296] | تتضمن منهجية Six Sigma العديد من الأدوات القوية لاستخدامها في مشاريع وبرامج التحسين المستمر. Six Sigma هي من الأدوات التي تستخدم في أي من العمليات التالية؟ | إدارة نطاق الخطة | أغلق المشروع أو المرحلة | تحديد النطاق | إدارة الجودة | Six Sigma هي من أدوات تحسين الجودة الأكثر شيوعًا والمستخدمة لتحليل وتقييم فرص التحسين [PMBOK الإصدار السادس، الصفحة 296] | 144 | 4 | False | "19" | Haitham
482 | You are working in a matrix organization and managing a project. The human resource manager transferred some resources you need from your project to another project without take in consideration the effect of this action on your project. What should you do next? | Escalate this problem to the sponsor | Complete the project without this resources | Update Stakeholder Engagement plan | Negotiate with Functional Manager to assign a new resources | In matrix organizations environment The project manager should effectively negotiate and influence others who are in a position to provide the required team and physical resources for the project. [PMBOK 6th edition, Page 329,330]. | أنت تعمل في منظمة مصفوفية وتدير مشروعًا. نقل مدير الموارد البشرية بعض الموارد التي تحتاجها من مشروعك إلى مشروع آخر دون مراعاة تأثير هذا الإجراء على مشروعك. ماذا يجب ان تفعل بعد ذلك؟ | تصعيد هذه المشكلة إلى الراعي | أكمل المشروع بدون هذه الموارد | تحديث خطة إشراك أصحاب المصلحة | تفاوض مع مدير الموارد البشرية لتعيين موارد جديدة | في بيئة المنظمات المصفوفية، يجب أن يتفاوض مدير المشروع بشكل فعال وأن يؤثر على الآخرين الذين هم في مناصب تسمح لهم بتوفير الفريق المطلوب والموارد المادية للمشروع. [PMBOK الطبعة السادسة، الصفحة 329،330]. | 145 | 4 | False | "20" | Haitham
483 | A buyer sent the quotation (RFQ) to the potential sellers. After a certain days, some potential sellers have questions about the terms and conditions. As a project manager, to ensure that all vendors have a clear and common understanding, what should you do? | Resubmit the RFP. | Send a clarification to the vendors via email. | Conduct one- to-one meeting with vendors. | Conduct a bidder conferences | After receiving a request for quotation (RFQ) and prior to proposal submittal , some potential sellers have questions about the terms and conditions. 50 the project manager should conduct a Bidder conference (also called contractor conferences, vendor conferences, and pre-bid conferences) this meeting between the buyer and prospective sellers prior to proposal submittal. They are used to ensure that all prospective bidders have a clear and common understanding of the procurement and no bidders receive preferential treatment. [PMBOK 6th edition page, 477]. | أرسل المشتري طلب عرض أسعار (RFQ) إلى البائعين المحتملين. بعد عدة أيام، أتت لدى بعض البائعين المحتملين أسئلة حول الشروط والأحكام. بصفتك مدير مشروع، ما الذي يجب عليك فعله للتأكد من أن جميع البائعين لديهم فهم واضح ومشترك؟ | أعد إرسال طلب عرض أسعار. | إرسال توضيح للبائعين عبر البريد الإلكتروني. | عقد اجتماع فردي مع كل بائع من البائعين. | عقد مؤتمر المتقدمين للعطاء | بعد تلقي طلب عرض أسعار (RFQ) وقبل تقديم العرض ، يكون لدى بعض البائعين المحتملين أسئلة حول الشروط والأحكام. يجب على مدير المشروع إجراء مؤتمر للمتقدمين للعطاء (يُطلق عليه أيضًا مؤتمرات المقاولين ومؤتمرات الموردين ومؤتمرات ما قبل العطاء) هذا الاجتماع بين المشتري والبائعين المحتملين قبل تقديم العرض. يتم استخدامه للتأكد من أن جميع مقدمي العطاءات المحتملين لديهم فهم واضح ومشترك للمشتريات ولا يحصل أي مقدم عطاء على معاملة تفضيلية. [PMBOK الطبعة السادسة، الصفحة 477]. | 148 | 3 | False | "19" | Haitham
484 | A project manager is working with the project team to estimate durations for the identified project activities. The team is looking to achieve the most accurate estimate possible. What estimating technique can they use to generate the desired result? | Top-down estimating | Parametric estimating | Analogous estimating | Three-point estimating | Three-point estimating, it uses three estimates (most likely, optimistic, and pessimistic) to calculate the average value of activity duration. It reduces the bias, risks, and uncertainties from the duration calculation. It is more accurate than the analogous technique and Parametric estimating. Analogous estimating is also referred to as top-down estimating. [PMBOK 6th edition, Page 201]. | يعمل مدير المشروع مع فريق المشروع لتقدير مدد أنشطة المشروع المحددة. يتطلع الفريق إلى تحقيق أدق تقدير ممكن. ما هي تقنية التقدير التي يمكنهم استخدامها لتوليد النتيجة المرجوة؟ | التقدير التنازلي | التقدير بالمحددات | التقدير التماثلي | تقدير الثلاث نقاط | تقدير الثلاث نقاط يستخدم ثلاثة تقديرات (الأرجح ، المتفائل ، والمتشائم) لحساب متوسط ​​قيمة مدة النشاط. يقلل هذا التقدير من التحيز والمخاطر والشكوك من حساب المدة. وهو أكثر دقة من التقدير التماثلي والتقدير بالمحددات. يشار إلى التقدير التماثلي أيضًا باسم التقدير التنازلي او التقدير من أعلى إلى أسفل. [PMBOK الطبعة السادسة، الصفحة 201]. | 142 | 3 | False | "19" | Haitham
485 | A tool that provides a visual representation of human resource allocation to a project, number of working hours, and availability on the project over a series of time periods is a: | Resource Breakdown Structure (RBS) | Organization Breakdown Structure (OBS) | Stakeholder Register | Resource Histogram | Resource Histogram shows the required number of hours that will be needed from each department or person for each week or month during the project. [PMBOK 6th edition, Page 719]. | الأداة التي توفر تمثيلاً مرئيًا لتخصيص الموارد البشرية للمشروع، وعدد ساعات العمل، والتوافر في المشروع على مدار سلسلة من الفترات الزمنية هي: | هيكل توزيع الموارد (RBS) | هيكل تنظيم المنظمة (OBS) | سجل أصحاب المصلحة | الرسم البياني للموارد | يوضح الرسم البياني للموارد عدد الساعات المطلوبة من كل قسم أو شخص لكل أسبوع أو شهر خلال المشروع. [PMBOK الطبعة السادسة ، الصفحة 719]. | 145 | 3 | False | "20" | Haitham
486 | After identifying and analyzing risks you and your team start to risk response process, you find a risk which would be difficult for you to manage. You discuss the issue with management and a decision is taken to transfer the management of this risk to your Program manager. What risk response strategy is this? | Transfer | Mitigate | Workaround | Escalate | Moving risk handling to a higher level than the current level is escalation and is one of the strategies used to respond to risks. [PMBOK 6th edition, Page 442]. | بعد تحديد المخاطر وتحليلها ، بدأت أنت وفريقك في عملية الاستجابة للمخاطر. وقد واجهت خطرًا يصعب عليك إدارته. وتمت مناقشة المشكلة مع الإدارة وتم اتخاذ قرار بنقل إدارة هذا الخطر إلى مدير البرنامج الخاص بك. ما هي هذه الإستراتيجية للإستجابة للمخاطر؟ | نقل | تخفيف | الحل | تصعيد | نقل التعامل مع المخاطر لمستوى أعلى من المستوى الحالي يعتبر من التصعيد وهو أحد الإستراتيجيات المستخدمة للإستجابة للمخاطر. [PMBOK الطبعة السادسة، الصفحة 442]. | 147 | 4 | False | "19" | Haitham
487 | The project in closure phase now, what is the activity necessary to transfer the project's products, services, or results to production and/or operations group? | Perform Quality Audit | Complete the preventive and corrective actions | Monitoring implementation of approved changes as they occur | Determine summary budget | The final report is the output of the close project process and provides a summary of the project performance. It can include information such as: Cost objectives, including the acceptable cost range, actual costs ( summary budget ) and reasons for any variances. PMBOK 6th edition Page, 127 | المشروع في مرحلة الإغلاق الآن ، ما هو النشاط الضروري لنقل منتجات المشروع أو خدماته أو نتائجه إلى مجموعة الإنتاج و / أو التشغيل؟ | إجراء تدقيق الجودة | استكمال الإجراءات الوقائية والتصحيحية | مراقبة تنفيذ التغييرات المعتمدة فور حدوثها | تحديد ملخص الميزانية | التقرير النهائي هو ناتج عملية إغلاق المشروع ويقدم ملخصًا لأداء المشروع. يمكن أن تتضمن معلومات مثل: أهداف التكلفة ، بما في ذلك نطاق التكلفة المقبول والتكاليف الفعلية (الميزانية الموجزة) وأسباب أي تباينات. [PMBOK الطبعة السادسة، الصفحة 127] | 140 | 6 | False | "19" | Haitham
488 | You have been recently assigned as a project manager in a big infrastructure project. A strike by local workers occurs due to the lateness workers' payments. That leads to delays in a major component delivery. What is the process the project manager could have been done differently to prevent this type of situation? | Monitor Risk | Identify Stakeholder | Control Scope | Develop Schedule | To prevent this type of situation, we must go to the planning. So the choices that fall into the monitoring and control process group are wrong and identify stakeholder is not related to the question. When developing the schedule, we define milestones regarding event and progress related payments. The timeline development process involves analyzing a what-if scenario as a tool. What-if scenario snalysis is the process of evaluating scenarios in order to predict their positive or negative impact on project objectives. The schedule network analysis is performed using the schedule to account for various scenarios, such as delay in delivery of a major component due to strike. [PMBOK 6th edition, page 213]. | لقد تم تعيينك مؤخرًا كمدير مشروع في مشروع بنية تحتية كبير. يحدث إضراب من قبل العمال المحليين بسبب تأخر دفع رواتبهم. هذا يؤدي إلى تأخير تسليم المكونات الرئيسية. ما هي العملية التي كان يمكن أن يقوم بها مدير المشروع بشكل مختلف لمنع هذا النوع من المواقف؟ | مراقبة المخاطر | تحديد أصحاب المصلحة | التحكم بالنطاق | تطوير الجدول الزمني | لمنع هذا النوع من المواقف ، يجب أن نذهب إلى التخطيط. لذا فإن الاختيارات التي تقع في مجموعة عمليات المراقبة والتحكم خاطئة و تحديد أصحاب المصلحة غير مرتبط بالسؤال. عند تطوير الجدول الزمني ، نحدد المعالم التي تتعلق بالمدفوعات المتعلقة بالحدث والتقدم. تتضمن عملية تطوير الجدول الزمني تحليل سيناريو ماذا لو كأداة. تحليل سيناريوهات ماذا لو هو عملية تقييم السيناريوهات من أجل التنبؤ بتأثيرها الإيجابي أو السلبي على أهداف المشروع. يتم إجراء تحليل شبكة الجدول باستخدام الجدول الزمني لحساب السيناريوهات المختلفة، مثل تأخير تسليم مكون رئيسي بسبب الإضراب. [PMBOK الطبعة السادسة، الصفحة 213]. | 142 | 3 | False | "20" | Haitham
489 | You are working on a complex project which involves multiple team members and sponsors. As a project manager, what should you do before obtaining the project approval and buy-in? | Meet with the stakeholders | Perform a Qualitative and Quantitative risk analysis | Conduct Sensitivity analysis | Complete a stakeholder analysis | Before obtaining the project approval and buy-in, the project manager should complete a stakeholder analysis to align expectations and gain support for the project and facilitate project closure. [PMBOK 6th edition, Page 512]. | أنت تعمل في مشروع معقد يتضمن العديد من أعضاء الفريق والجهات الراعية. بصفتك مدير مشروع ، ما الذي يجب عليك فعله قبل الحصول على الموافقة على المشروع والبدء؟ | لقاء مع أصحاب المصلحة | قم بإجراء تحليل نوعي وكمي للمخاطر | إجراء تحليل الحساسية | أكمال تحليل أصحاب المصلحة | قبل الحصول على الموافقة على المشروع وقبوله، يجب على مدير المشروع إكمال تحليل أصحاب المصلحة لمواءمة التوقعات والحصول على الدعم للمشروع وتسهيل إغلاق المشروع. [PMBOK الطبعة السادسة ، الصفحة 512] | 149 | 2 | False | "20" | Haitham
490 | You have just been assigned as the project manager for an ongoing project in your organization. You have discovered there is no Project Charter that describes the responsibilities and authorities of the project manager. When you talked to your project sponsor about this issue, he told you that your organization has executed many projects in the past without ever using a Project Charter. What will you do? | Create a draft project charter and submit to your supervisor | Create the project charter and inform project team members to ensure common understanding of the key deliverables and their roles and responsibilities | Conduct the project kick-off meeting and inform everyone that the project has started | Discuss the need to have a project charter with the sponsor | The project charter establishes a partnership between the performing and requesting organizations. Projects are initiated by an entity external to the project such as a sponsor, program, or project management office (PMO), or a portfolio governing body chairperson or authorized representative. The project initiator or sponsor is responsible for approve and issue the charter and can take the help of the prospect project manager to develop it. [PMBOK 6th edition, Page 77]. | لقد تم تعيينك للتو كمدير مشروع لمشروع جارٍ في مؤسستك. لقد اكتشفت أنه لا يوجد ميثاق مشروع يصف مسؤوليات وصلاحيات مدير المشروع. عندما تحدثت إلى راعي مشروعك حول هذه المسألة ، أخبرك أن مؤسستك نفذت العديد من المشاريع في الماضي دون استخدام ميثاق المشروع مطلقًا. ماذا ستفعل؟ | أنشئ مسودة ميثاق المشروع وأرسله إلى مشرفك | قم بإنشاء ميثاق المشروع وإبلاغ أعضاء فريق المشروع لضمان فهم مشترك للنتائج الرئيسية وأدوارهم ومسؤولياتهم | عقد اجتماع بدء المشروع وإبلاغ الجميع أن المشروع قد بدأ | ناقش الحاجة إلى وجود ميثاق مشروع مع الراعي | يؤسس ميثاق المشروع شراكة بين المنظمات المنفذة والمنظمات الطالبة للخدمات. تبدأ المشاريع من قبل كيان خارج المشروع مثل الراعي أو البرنامج أو مكتب إدارة المشروع (PMO) أو رئيس المحفظة أو الممثل المعتمد. يكون منشئ المشروع أو الراعي مسؤولاً عن الموافقة على الميثاق وإصداره ويمكنه الاستعانة بمدير المشروع المحتمل لتطويره. [PMBOK الطبعة السادسة، الصفحة 77]. | 140 | 2 | False | "19" | Haitham
491 | You are managing a critical project with frequent changes in requirement. You are in the testing phase of the project, and the customer has requested the addition of a new feature. You have assessed the impact of the change on the triple constraints with your team. What should be your NEXT step? | Update the project management plans and other project documents including project baselines | Look for alternative options including schedule compression techniques like crashing and fast tracking | Raise a change request form and send it for approval to change control board | Analyze the impact of the change on the project's quality objectives and quality planning | Testing is an organized and constructed investigation conducted to provide objective information about the quality of the product or service under test in accordance with the project requirements. The intent of testing is to find errors, defects, bugs, or other nonconformance problems in the product or service. The type, amount, and extent of tests needed to evaluate each requirement are part of the project quality plan and depend on the nature of the project, time, budget, and other constraints. [PMBOK 6th edition, Page 303] | أنت تدير مشروعًا بالغ الأهمية مع تغييرات متكررة في المتطلبات. أنت في مرحلة اختبار المشروع ، وقد طلب العميل إضافة ميزة جديدة. لقد قمت بتقييم تأثير التغيير على القيود الثلاثة مع فريقك. ماذا يجب أن تكون خطوتك التالية؟ | تحديث خطط إدارة المشروع ووثائق المشروع الأخرى بما في ذلك خطط الأساس المرجعية للمشروع | ابحث عن خيارات بديلة بما في ذلك تقنيات ضغط الجدول الزمني مثل حشد الموارد والتتابع السريع | رفع استمارة طلب التغيير وإرسالها للموافقة عليها من لجنة التحكم بالتغيير | تحليل تأثير التغيير على أهداف جودة المشروع وتخطيط الجودة | الاختبار عبارة عن تحقيق منظم ومبني يتم إجراؤه لتوفير معلومات موضوعية حول الجودة المنتج أو الخدمة قيد الاختبار وفقًا لمتطلبات المشروع. الهدف من الاختبار هو العثور على الأخطاء ، العيوب أو الأخطاء أو مشكلات عدم التوافق الأخرى في المنتج أو الخدمة. نوع الاختبارات وكميتها ومداها اللازمة لتقييم كل متطلب هي جزء من خطة جودة المشروع وتعتمد على طبيعة المشروع ، الوقت ، الميزانية والقيود الأخرى. [PMBOK الطبعة السادسة ، الصفحة 303] | 144 | 5 | False | "20" | Haitham
492 | During the review of a control chart, you notice that the process has 3 points between mean and lower control limit and 4 points between upper control limit and specification limit. How will you consider this process? | Cannot be determined | In control | The customer only can take a decision for this process | Unstable | The customer's specification limits is outside the control limit. Therefore, you will take corrective action so as to avoid any possible defect. [PMBOK 6th edition, Page 304] | أثناء مراجعة مخطط التحكم، لاحظت أن العملية لها 3 نقاط بين حد التحكم المتوسط ​​والسفلي و 4 نقاط بين حد التحكم الأعلى وحد المواصفات. كيف ستنظر في هذه العملية؟ | لا يمكن تحديدها | تحت السيطرة | يمكن للعميل فقط اتخاذ قرار لهذه العملية | غير مستقر | حدود مواصفات العميل خارج حدود التحكم. لذلك ، سوف تتخذ إجراءات تصحيحية لتجنب أي عيب محتمل. [PMBOK الطبعة السادسة ، الصفحة 304] | 144 | 5 | False | "19" | Haitham
493 | A recently promoted project manager must facilitate the monthly status update meeting. What should the project manager do to ensure a productive meeting? | Limit attendance to the project team and stakeholders | Avoid or smooth over any disagreements | Carefully read the latest meeting minutes | Circulate a defined agenda | Meeting management is taking steps to ensure meetings meet their intended objectives effective and efficiently. one of the important steps is to prepare and distribute the agenda stating the objectives of the meeting. [PMBOK 6th edition, Page 386] | يجب على مدير المشروع الذي تمت ترقيته مؤخرًا تسهيل الاجتماع الشهري لتحديث الحالة. ماذا يجب أن يفعل مدير المشروع لضمان اجتماع مثمر؟ | قصر الحضور على فريق المشروع وأصحاب المصلحة | تجنب وحل أي خلافات | اقرأ بعناية محضر أخر إجتماع | توزيع محضر معد للإجتماع | تتخذ إدارة الاجتماعات خطوات لضمان تحقيق الاجتماعات للأهداف المرجوة منها بفعالية وكفاءة. تتمثل إحدى الخطوات المهمة في إعداد وتوزيع محضر يوضح أعمال وأهداف الاجتماع. [PMBOK الطبعة السادسة ، الصفحة 386] | 146 | 4 | False | "19" | Haitham
494 | You are a project manager managing a small project for the company XY. A company's financial year-end is coming. A seller delivers most of a project's deliverables but a few defects require correction before the contracted payment can be made. What should the project manager do? | Arrange an extended financial project close until contract closure is completed | Claim penalties for the value of the outstanding payment. | Terminate seller contract. | Pay to the seller with a formal written commitment to complete the work | Because a company's financial year-end is approaching. so the project manager should pay the seller with a formal written commitment to complete the work. [PMBOK 6th edition Page, 499] | أنت مدير مشروع تدير مشروعًا صغيرًا لشركة XY. نهاية السنة المالية للشركة قادمة. يقوم البائع بتسليم معظم مخرجات المشروع ولكن هناك بعض العيوب التي تتطلب التصحيح قبل أن يتم الدفع المتعاقد عليه. ماذا يجب أن يفعل مدير المشروع؟ | تمديد إغلاق المشروع مالياً حتى اكتمال إغلاق العقد. | مطالبة بغرامات عن قيمة المدفوعات المستحقة. | إنهاء عقد البائع. | الدفع للبائع مع التزام كتابي رسمي لإتمام العمل. | لأن نهاية السنة المالية للشركة تقترب. يجب على مدير المشروع أن يدفع للبائع مع التزامه كتابيًا ورسميًا لإكمال العمل. [PMBOK الطبعة السادسة الصفحة، 499] | 148 | 5 | False | "18" | Haitham
495 | As project manager, what is the proper techniques help to identify and analyze risks? | Probability and impact matrix. | SWOT Analysis | Monte Carol | Expert Judgment | Expert Judgment is a technique used in all risk processes except Monitor Risk. [PMBOK 6th edition. Page 396] | كمدير للمشروع ، ما هو الأسلوب المناسب التي يساعد في تحديد المخاطر وتحليلها؟ | مصفوفة الاحتمالات والأثر. | تحليل SWOT | مونتي كارول | حكم خبير | حكم الخبراء هو أسلوب يستخدم في جميع عمليات المخاطر باستثناء مراقبة المخاطر. [PMBOK 6th edition. الصفحة 396] | 147 | 3 | False | "19" | Haitham
496 | As you are a project manager of the construct infrastructure Project. Your project is behind Schedule and the sponsor suggests reducing the time for quality assurance testing. What should the project manager do first? | Perform quality audit | Perform quality control measurements. | Change the quality requirements | Follow the Quality Management Plan | The Project manager should Follow The quality management plan because It describes how applicable policies, procedures, and guidelines will be implemented to achieve the quality objectives. It describes the activities and resources necessary for the project management team to achieve the quality objectives set for the project include Quality control and quality management activities planned for the project. [PMBOK 6th edition, Page 286] | بما أنك مدير مشروع إنشاء البنية التحتية. مشروعك متأخر عن الجدول الزمني ويقترح الراعي تقليل وقت اختبار ضمان الجودة. ما الذي يجب أن يفعله مدير المشروع أولاً؟ | قم بإجراء تدقيق الجودة | قم بإجراء قياسات مراقبة الجودة. | تغيير متطلبات الجودة | اتبع خطة إدارة الجودة | يجب على مدير المشروع اتباع خطة إدارة الجودة لأنها تصف كيفية تنفيذ السياسات والإجراءات والإرشادات المعمول بها لتحقيق أهداف الجودة. يصف الأنشطة والموارد اللازمة لفريق إدارة المشروع لتحقيق أهداف الجودة المحددة للمشروع بما في ذلك التحكم بالجودة وأنشطة إدارة الجودة المخطط لها للمشروع. [PMBOK الطبعة السادسة ، الصفحة 286] | 144 | 5 | False | "20" | Haitham
497 | A project is initiated, and the planning is complete. As a project manager, you are about to conduct the kick-off meeting with all stakeholders before start execution phase, and you feel that the strategic directions for the project need to be presented first. Who should present this topic? | customer | Project manager | Functional manager | Project sponsor | The project sponsor Is the person presenting the organization's strategy ( strategic directions ) during the kick-off meeting. [PMBOK 6th edition, Page 86]. | تم بدأ المشروع، واكتمل التخطيط. بصفتك مديرًا للمشروع ، أنت على وشك إجراء الاجتماع الافتتاحي مع جميع أصحاب المصلحة قبل بدء مرحلة التنفيذ، وتشعر أن الاتجاهات الإستراتيجية للمشروع يجب أن تُعرض أولاً. من يجب أن يقدم هذا الموضوع؟ | العميل | مدير المشروع | المدير الوظيفي | راعي المشروع | راعي المشروع هو الشخص الذي يعرض استراتيجية المنظمة (التوجهات الاستراتيجية) خلال الاجتماع الافتتاحي. [PMBOK 6th edition، Page 86]. | 140 | 3 | False | "19" | Haitham
498 | The change control board (CCB) is evaluating a recently submitted change request. The project sponsor wants to deferring the request until a later date. Another stakeholder is in favor of denying. The project manager and other stakeholders feel to approve the request. The Project manager is unsure how to proceed since there is disagreement among the stakeholders what should the project manager do? | Approve the request as the project manager has authority to decide for the group | Approve the request as the project sponsor has the final say | Defer the request until all of the stakeholders are in agreement | Consult the project management plan | The question indicates that the perform integrated change request control process is underway, to reffer to project management plan is the best choice since it's contain change management plan. [PMBOK 6th edition, Page 115]. | تقوم لجنة التحكم في التغيير (CCB) بتقييم طلب التغيير المقدم مؤخرًا. يريد راعي المشروع تأجيل الطلب حتى تاريخ لاحق. صاحب مصلحة آخر يؤيد الرفض. يشعر مدير المشروع وأصحاب المصلحة الآخرون بالموافقة على الطلب. مدير المشروع غير متأكد من كيفية المضي قدمًا نظرًا لوجود خلاف بين أصحاب المصلحة ، ماذا يجب أن يفعل مدير المشروع؟ | قم بالموافقة على الطلب حيث أن مدير المشروع لديه سلطة اتخاذ القرار للمجموعة | الموافقة على الطلب لأن راعي المشروع له الكلمة الأخيرة | تأجيل الطلب حتى يتفق جميع أصحاب المصلحة | الرجوع لخطة إدارة المشروع | يشير السؤال إلى أن عملية التحكم في طلب التغيير المتكامل جارية ، والرجوع إلى خطة إدارة المشروع هي الخيار الأفضل لأنها تحتوي على خطة إدارة التغيير. [PMBOK 6th edition، Page 115]. | 140 | 5 | False | "20" | Haitham
499 | The Project team members and the professional experts are working on a design development project. A project manager discovers an enhancement that will improve the design. What should the project manager do? | Document this discovery, and present it to an stakeholders | Ask the subject matter expert (SME) to implement the enhancement | Ignore the enhancement as no changes are allowed | Ask the change control board (CCB) to review the enhancement. | Since the enhancement may impact the project baseline, so the next step. ask the change control board (CCB) to review the enhancement and make a decision. [PMBOK 6th edition, Page 115] | يعمل أعضاء فريق المشروع والخبراء المحترفون على مشروع تطوير التصميم. يكتشف مدير المشروع تحسينًا من شأنه تحسين التصميم. ماذا يجب أن يفعل مدير المشروع؟ | توثيق هذا الاكتشاف وتقديمه إلى أصحاب المصلحة | اطلب من الخبير المتخصص تنفيذ التحسين | تجاهل التحسين حيث لا يسمح بإجراء أي تغييرات | اطلب من لجنة التحكم في التغيير (CCB) مراجعة التحسين. | نظرًا لأن التحسين قد يؤثر على خط الأساس للمشروع ، فإن الخطوة التالية. اطلب من لجنة التحكم في التغيير (CCB) مراجعة التحسين واتخاذ قرار. [PMBOK الطبعة السادسة ، الصفحة 115] | 140 | 5 | False | "19" | Haitham
500 | You are managing a complex construction project and you request a seven-year schedule for this project. Although multiple brainstorming sessions with your project team, you struggle to provide detail for the project management plan. This causes a delay in obtaining the project management plan approvals. As a project manager, what should you have done to avoid this situation? | Use decomposition techniques | Used subject matter expert to develop the detailed schedule. | Created a high level Gantt chart to represent the milestone only | Used the rolling wave planning technique for activity planning | Since the project manager struggles to provide details for the project management plan, so the project manager should have used iterative planning to avoid this situation. Recurring planning is a method in which the work that will be accomplished in the near term is accurately planned and the work that will be executed in the remote periods is planned at a high level until more details are clear that enables it to be carefully re-planned in the coming periods. [PMBOK 6th edition, Page 185]. | أنت تدير مشروع بناء معقد وتطلب جدولاً مدته سبع سنوات لهذا المشروع. على الرغم من جلسات العصف الذهني المتعددة مع فريق المشروع ، إلا أنك تكافح من أجل توفير تفاصيل لخطة إدارة المشروع. يتسبب هذا في تأخير الحصول على الموافقات على خطة إدارة المشروع. بصفتك مدير مشروع ، ما الذي كان يجب عليك فعله لتجنب هذا الموقف؟ | استخدام تقنيات التفكيك | الاستعانة بخبير في الموضوع لتطوير الجدول الزمني المفصل. | إنشاء مخطط جانت عالي المستوى لتمثيل الحدث الرئيسي فقط | استخدام تقنية التخطيط المتكرر لتخطيط الأنشطة | نظرًا لأن مدير المشروع يكافح لتوفير التفاصيل لخطة إدارة المشروع ، لذلك كان ينبغي على مدير المشروع استخدام التخطيط المتكرر لتجنب هذا الموقف. التخطيط المتكرر هو أسلوب يتم فيه تخطيط العمل الذي سيتم إنجازه على المدى القريب بدقة ويتم تخطيط الأعمال التي سيتم تنفيذها في الفترات البعيدة بمستوى عالي الى حين وضوح تفاصيل أكثر تمكن من اعادة تخطيطها بدقة في الفترات القادمة. [الطبعة السادسة من PMBOK ، صفحة 185]. | 142 | 3 | False | "19" | Haitham
501 | An approved change request adds an incentive to a lump sum contract if the contractor is able to maintain the current baseline schedule. What should now be updated? | Schedule baseline. | Scope baseline. | Project management plan. | Cost baseline. | If the contractor is able to maintain the current baseline schedule, so you will not update the schedule baseline. He not mentioned that the scope will be affected. Only the cost baseline will be updated due to this approved change request. No need to update the whole project management plan because you update the affected plan or baseline only. [PMBOK 6th edition Page, 115] | يضيف طلب التغيير المعتمد حافزًا إلى عقد مبلغ مقطوع إذا كان المقاول قادرًا على الحفاظ على جدول الأساس الحالي. ما الذي يجب تحديثه الآن؟ | خط الأساس المرجعي للوقت. | خط الأساس المرجعي للنطاق. | خطة إدارة المشروع. | خط الأساس المرجعي للتكلفة. | إذا كان المقاول قادرًا على الحفاظ على الجدول الأساسي الحالي ، فلن تقوم بتحديث خط الأساس للجدول. ولم يذكر أن النطاق سيتأثر. سيتم تحديث أساس التكلفة فقط بسبب طلب التغيير المعتمد هذا. لا حاجة لتحديث خطة إدارة المشروع بالكامل لأنك تقوم بتحديث الخطة أو الأساس المتأثر فقط. [PMBOK الطبعة السادسة الصفحة، 115] | 140 | 5 | False | "20" | Haitham
502 | A Project manager is estimating an activity duration in the project schedule. As per the following data, what is the activity's expected time? - Optimistic time (O) is three weeks. - Pessimistic time (P) is seven weeks. - Most likely time (M) is five weeks. | 7 weeks. | 6 weeks | 3 weeks. | 5 weeks | The formula for three-point estimate (based on triangular distribution) is: Estimate = (Optimistic + (Most Likely ) + Pessimistic)/3. = ( 3+7+5) / 3 = 5 weeks . Note: to estimate activity duration, use triangular distribution, while the cost estimation you can use triangular or beta distribution. [PMBOK 6th edition, Page 201]. | يقوم مدير المشروع بتقدير مدة نشاط في جدول المشروع. حسب البيانات التالية ما هو الوقت المتوقع للنشاط؟ - زمن التفاؤل (O) ثلاثة أسابيع. - زمن التشاؤم (P) سبعة أسابيع. - الوقت المرجح (M) هو خمسة أسابيع. | 7 أسابيع | 6 أسابيع | 3 أسابيع | 5 أسابيع | معادلة تقدير النقاط الثلاث (على أساس التوزيع الثلاثي) هي التقدير = (متفائل + الأرجح + متشائم) \ 3 = (3 + 7 + 5) \ 3 = 5 أسابيع. ملاحظة: لتقدير مدة النشاط ، استخدم التوزيع الثلاثي ، بينما يمكن استخدام التوزيع الثلاثي أو توزيع بيتا لتقدير التكلفة. [PMBOK الطبعة السادسة ، الصفحة 201]. | 142 | 3 | False | "20" | Haitham
503 | You are a project manager in a construction project. During a review, the project team member identifies a quality issue that may cause the product to be rejected by the customer. However, the project sponsor wants to deliver the product. As a project manager, what should you do? | Ensure that the product meets customer requirements | Deliver the product | Update the issue log | Review the quality checklist | The Quality Issue may or may not cause the product to be rejected by the customer. SO, the project manager should first Review the quality checklist. Quality checklist used to verify that a set of required steps has been performed or to check if a list of requirements has been satisfied. Quality checklists should incorporate the acceptance criteria Included In the scope baseline. After reviewing the Quality checklist by the project manager and verifying the existence of an issue, the issue must then be presented to the customer and If he not accept the product, then it must be recorded in the issue log to start track and find the solution. [PMBOK 6th edition, Page 302]. | أنت مدير مشروع في مشروع بناء. أثناء المراجعة، اكتشف عضو من فريق المشروع مشكلة جودة قد تتسبب في رفض العميل للمنتج. ومع ذلك ، فإن راعي المشروع يريد تسليم المنتج. كمدير مشروع ، ماذا يجب أن تفعل؟ | تأكد من أن المنتج يلبي متطلبات العملاء | تسليم المنتج | قم بتحديث سجل المشكلة | راجع قائمة التحقق من الجودة | قد تتسبب مشكلة الجودة أو لا في رفض العميل للمنتج. لذا ، يجب على مدير المشروع أولاً مراجعة قائمة فحص الجودة. يتم استخدام قائمة فحص الجودة للتحقق من تنفيذ مجموعة من الخطوات المطلوبة أو للتحقق مما إذا تم استيفاء قائمة المتطلبات. يجب أن تتضمن قوائم فحص الجودة معايير القبول المدرجة في خط الأساس للنطاق. بعد مراجعة قائمة فحص الجودة من قبل مدير المشروع وبعد التحقق من وجود مشكلة، يجب بعد ذلك عرض المشكلة على العميل وإذا لم يقبل المنتج ، فيجب تسجيله في سجل الأحداث لبدء التتبع والعثور على الحل . [PMBOK الطبعة السادسة، الصفحة 302]. | 144 | 5 | False | "19" | Haitham
504 | As a project manager for a huge project, you conduct a kick-off meeting to inform and engage stakeholders and gain commitment to the project. In which process group are you currently? | Executing | Monitoring and Controlling | Closing | Planning | The project kick-off meeting Is usually associated with the end of planning and the start of executing. Its purpose is to communicate the objectives of the project, gain the commitment of the team for the project, and explain the roles and responsibilities of each stakeholder [PMBOK 6th edition, Page 86] | بصفتك مدير مشروع لمشروع ضخم ، فإنك تعقد اجتماعًا أوليًا لإعلام أصحاب المصلحة وإشراكهم وكسب الالتزام بالمشروع. في أي مجموعة عمليات أنت حاليا؟ | التنفيذ | التحكم والمراقبة | الإغلاق | التخطيط | عادة ما يرتبط اجتماع بدء المشروع بنهاية التخطيط وبداية التنفيذ. الغرض منه هو إيصال أهداف المشروع ، وكسب التزام الفريق بالمشروع ، وشرح الأدوار والمسؤوليات لكل صاحب مصلحة. (PMBOK الطبعة السادسة، الصفحة 86] | 140 | 3 | False | "20" | Haitham
505 | During the implementation phase, the project manager identifies a new project activity that will not affect the project deadline. What should the project manager do next step? | Ask the sponsor to approve the new activity. | Update the schedule baseline and Begin working on the new task immediately | Update the change log and update the schedule baseline | Create a change request. | The question scenario indicates that the Perform Integrated change request control process should be conducted due to add new activity and study the impact of change request on project objective. [PMBOK 6th edition, Page 115]. | أثناء مرحلة التنفيذ ، حدد مدير المشروع نشاطًا جديدًا لن يؤثر على الموعد النهائي للمشروع. ماذا يجب أن يفعل مدير المشروع كخطوة تالية؟ | اطلب من الراعي الموافقة على النشاط الجديد | قم بتحديث خط الأساس للجدول وابدأ العمل على المهمة الجديدة على الفور | قم بتحديث سجل التغيير وقم بتحديث خط الأساس للجدول الزمني | إنشاء طلب تغيير | سيناريو السؤال يشير إلى أنه يجب إجراء عملية التحكم في طلب التغيير المتكامل بسبب إضافة نشاط جديد ودراسة تأثير طلب التغيير على هدف المشروع. [PMBOK الطبعة السادسة، الصفحة 115]. | 140 | 5 | False | "19" | Haitham
506 | A project status report shows that: The earned value (EV) is 30 The schedule performance index (SPI) is .93. The cost performance index (CPI) is 1.05. In what area should the project manager implement corrective actions? | Project cost. | Resource management. | Communication management | Project schedule. | The cost performance index (CPI) is 1.05 ( The project is under budget ). The schedule performance Index (SPI) Is .93. ( the project is behind schedule ) so the project manager should focus on the project schedule and implement corrective actions to return the schedule back. [PMBOK 6th edition. Page 267]. | يوضح تقرير حالة المشروع أن: القيمة المكتسبة (EV) هي 30 مؤشر أداء الجدول (SPI) هو 93. مؤشر أداء التكلفة (CPI) هو 1.05. في أي منطقة يجب على مدير المشروع تنفيذ الإجراءات التصحيحية؟ | تكلفة المشروع. | إدارة الموارد. | إدارة الاتصالات | الجدول الزمنى للمشروع. | مؤشر أداء التكلفة (CPI) هو 1.05 (المشروع تحت الميزانية). مؤشر أداء الجدول (SPI) هو 93. (المشروع متأخر عن الجدول الزمني) لذلك يجب على مدير المشروع التركيز على الجدول الزمني للمشروع وتنفيذ الإجراءات التصحيحية لإعادة الجدول الزمني مرة أخرى. [PMBOK الطبعة السادسة. الصفحة 267]. | 143 | 5 | False | "18" | Haitham
507 | A project manager uses the schedule from a similar project to estimate the cost of the project activities for a new project. Which method was used to derive the estimates? | Bottom-up estimating. | Parametric estimating. | Expert judgment | Analogous estimating. | Since schedule from a similar project used, so the method is Analogous estimates. Analogous estimates are usually done In the initial stages of the project when limited Information is known. Analogous cost estimating is generally less costly and time-consuming compared to other methods, but it is also less accurate. [PMBOK 6th edition. Page 244]. | يستخدم مدير المشروع الجدول الزمني من مشروع مماثل لتقدير تكلفة أنشطة المشروع لمشروع جديد. ما هي الطريقة التي تم استخدامها للحصول على التقديرات؟ | التقدير التصاعدي. | تقدير حدودي. | حكم خبير | تقدير مماثل. | بما أنه استخدم جدول زمني من مشروع مماثل ، فإن الطريقة هي التقدير المماثل. عادة ما يتم إجراء التقدير المماثل في المراحل الأولى من المشروع عندما تكون المعلومات محدودة. يعتبر تقدير التكلفة المماثل عمومًا أقل تكلفة ويستغرق وقتًا طويلاً مقارنة بالطرق الأخرى ، ولكنه أيضًا أقل دقة. [PMBOK الطبعة السادسة ، الصفحة 244]. | 143 | 3 | False | "19" | Haitham
508 | After contract sign-off, a project manager learns that the supplier has a reputation of not delivering according to the contract. To ensure the vendor's compliance, what should the project manager do? | Cancel the current contract and select another vendor | Conduct a make-or-buy analysis to verify vendor reliability | Insist on a firm fixed price contract (FFP) with the vendor | Perform periodic inspection of the vendor's work and progress. | To ensure the supplier's compliance, the project manager should perform a periodic inspection of the vendor's work and progress to take the corrective action as per the contract at the right time. [PMBOK 6th edition Page, 498]. | بعد توقيع العقد ، علم مدير المشروع أن المورد لديه سمعة بعدم التسليم وفقًا للعقد. لضمان امتثال البائع ، ماذا يجب أن يفعل مدير المشروع؟ | إلغاء العقد الحالي واختيار بائع آخر | قم بإجراء تحليل الصنع أو الشراء للتحقق من موثوقية البائع | الإصرار على عقد ثابت السعر (FFP) مع البائع | إجراء فحص دوري لأعمال البائع والتقدم المنجز. | لضمان امتثال المورد ، يجب على مدير المشروع إجراء فحص دوري لأعمال البائع والتقدم المنجز لاتخاذ الإجراء التصحيحي وفقًا للعقد في الوقت المناسب. [PMBOK الطبعة السادسة الصفحة، 498]. | 148 | 5 | False | "20" | Haitham
509 | You are managing a project a local government project which has BAC $120,000 and supposes to finish in 6 months. After four months, the project manager confirmed that the project is 55 % complete . To date, $90,000 has been spent. What is the EV, SV, and CV? | EV= $60,000 SV= -$14,000 CV= -$24,000 | EV= $60,00 SV= $24,000 CV= $14.000 | EV= $66,000 SV= -$24,000 CV= -$14,000 | EV= $66,000 SV= -$14,000 CV= -$24,000 | Since 55% of the project is complete , So EV= 55% * 120,000 = $66,000 and PV = 4 / 6 *120,000 = 80,000. So SV = EV - PV = 66,000 - 80,000 = - $14,000 And CV = EV - AC = 66,000 - 90,000 = - $24,000 [PMBOK 6th edition. Page 267]. | أنت تدير مشروعًا تابعًا للحكومة المحلية تبلغ تكلفته 120,000 دولار ويفترض أن ينتهي في 6 أشهر. بعد أربعة أشهر ، أكد مدير المشروع أن المشروع قد اكتمل بنسبة 55٪. حتى الآن ، تم إنفاق 90,000$ ما هي EV و SV و CV؟ | EV = 60,000 دولار SV = -14,000 دولار CV = -24,000 دولار | EV = 60,000 دولار SV = 24,000 دولار CV = 14,000 دولار | EV = 66,000 دولار SV = -24,000 دولار CV = 14,000 دولار | EV = 66,000 دولار SV = -14,000 دولار CV = -24,000 دولار | بما أن 55٪ من المشروع مكتمل ، EV = 55٪ * 120,000 = دولار 66,000 PV = 4 / 6 * 120,000 = 80,000 دولار SV = EV-PV = 66,000-80,000 = -14,000 دولار CV = EV - AC = 66,000 - 90,000 = -24,000 دولار [PMBOK الطبعة السادسة، الصفحة 267]. | 143 | 5 | False | "19" | Haitham
510 | Which of the following risk analysis techniques can help you to investigate the likelihood that each specific risk will occur? | Monte Carlo | Risk categorization | Probability and Impact matrix | Risk Probability and Impact Assessment | Risk probability assessment considers the likelihood that a specific risk will occur. Risk impact assessment considers the potential effect on one or more project objectives such as schedule, cost, quality, or performance. Impacts will be negative for threats and positive for opportunities. [PMBOK 6th edition, Page 423]. | أي من تقنيات تحليل المخاطر التالية يمكن أن تساعدك على التحقيق في احتمالية حدوث كل خطر محدد؟ | مونتي كارلو | تصنيف المخاطر | مصفوفة الاحتمالات والأثر | تقييم احتمالية المخاطر وتأثيرها | تقييم احتمال وقوع المخاطر يأخذ في الاعتبار احتمال حدوث خطر معين. يأخذ تقييم تأثير المخاطر في الاعتبار التأثير المحتمل على واحد أو أكثر من أهداف المشروع مثل الجدول الزمني أو التكلفة أو الجودة أو الأداء. ستكون التأثيرات سلبية بالنسبة للتهديدات وإيجابية للفرص. [PMBOK الطبعة السادسة، الصفحة 423]. | 147 | 3 | False | "19" | Haitham
511 | The change control board just approved a change request to modify two of the major deliverables. In which process will this change be implemented? | Close Project or Phase | Monitor and Control Project Work | Perform Integrated Change Control | Direct and Manage Project Work | An approved change request for corrective actions, preventive actions, and defect repairs will be implemented in the Direct and Manage Project Work process. [PMBOK 6th edition, Page 92]. | وافقت لجنة التحكم في التغيير للتو على طلب تغيير لتعديل اثنين من المخرجات الرئيسية. في أي عملية سيتم تنفيذ هذا التغيير؟ | أغلق المشروع أو المرحلة | مراقبة ومراقبة أعمال المشروع | أداء مراقبة التغيير المتكامل | توجيه وإدارة أعمال المشروع | سيتم تنفيذ طلب التغيير المعتمد كاالإجراءات التصحيحية والإجراءات الوقائية وإصلاحات العيوب في عملية توجيه وإدارة عمل المشروع. [PMBOK الطبعة السادسة، الصفحة 92]. | 140 | 4 | False | "20" | Haitham
512 | You are a project manager who is in charge of an important project for your company. When the SPI=0.85 and CPI=1.15. How is the project performing? | The project is on schedule and under budget | The project is ahead of schedule and under budget | The project is behind schedule and over budget | The project is behind schedule and within budget | If SPI=0.85 is less than 1 that means is bad and the project is behind schedule. If CP1=1.15 is larger than 1 that means is good or the cost is within budget. [PMBOK 6th edition. Pages 263, 267]. | أنت مدير مشروع مسؤول عن مشروع مهم لشركتك. عندما يكون SPI = 0.85 CPI = 1.15 كيف هو أداء المشروع؟ | المشروع في الموعد المحدد وتحت الميزانية | المشروع سابق للجدول الزمني وتحت الميزانية | المشروع متأخر عن الجدول الزمني والميزانية | المشروع متأخر عن الجدول الزمني وضمن الميزانية | إذا كان SPI = 0.85 أقل من 1 ، فهذا يعني أنه سيئ وأن المشروع متأخر عن الجدول الزمني. إذا كان CPI = 1.15 أكبر من 1 ، فهذا يعني أنه جيد أو التكلفة في حدود الميزانية. [PMBOK الطبعة السادسة. الصفحات 263 ، 267]. | 143 | 5 | False | "20" | Haitham
513 | To compare different vendors and rate their proposals, as a project manager, what should you use? | Bid documents | Bidder conferences | A contract | Evaluation criteria | Evaluation criteria used to compare different subcontractors and rate their proposals. The buyer seeks to ensure that the proposal selected will offer the best quality for the services required. [PMBOK 6th edition Page. 478. 479] | لمقارنة البائعين المختلفين وتقييم عروضهم ، بصفتك مدير مشروع ، ما الذي يجب عليك استخدامه؟ | وثائق العطاء | مؤتمرات المتقدمين للعطاء | العقد | معيار التقييم | تستخدم معايير التقييم لمقارنة مختلف المتعاقدين من الباطن وتقييم عروضهم. يسعى المشتري إلى التأكد من أن العرض الذي تم اختياره سيقدم أفضل جودة للخدمات المطلوبة. [PMBOK الطبعة السادسة الصفحة. 478. 479] | 148 | 3 | False | "19" | Haitham
514 | During the initiation phase, the project manager classifying a list of project stakeholders and discovers an interested stakeholder with certain authority. How should the project manager manage this stakeholder? | Keep satisfied | Manage Closely | Monitor | Keep informed | The stakeholder is interested in the project with little authority so you will keep him Informed. [PMBOK 6th edition, Page 512] | أثناء مرحلة البدء ، صنف مدير المشروع قائمة أصحاب المصلحة في المشروع وأكتشف صاحب مصلحة مهتم بالمشروع مع سلطة محددة. كيف يجب أن يدير مدير المشروع صاحب المصلحة هذا؟ | ابق راض | إدارة عن كثب | مراقب | ابق على اطلاع | صاحب المصلحة مهتم بالمشروع مع قليل من السلطة لذلك سوف تبقيه على اطلاع. [PMBOK الطبعة السادسة ، الصفحة 512] | 149 | 4 | False | "20" | Haitham
515 | The project manager near to complete to project, unidentified stakeholder request a change on project scope. As a project manager for that project, What should you do first step? | Ignore the stakeholder | Meeting with the team and analyze the impact on project constraints | Implement the change | Update stakeholder register | Since the stakeholder is unidentified, the stakeholder should be identified first and update stakeholder register before analyzing the impact on project constraints. [PMBOK 6th edition, Page 529] | مدير المشروع على وشك الانتهاء من المشروع ، طلب صاحب مصلحة غير محدد تغيير نطاق المشروع. بصفتك مدير مشروع لهذا المشروع ، ما الخطوة الأولى التي يجب عليك القيام بها؟ | تجاهل أصحاب المصلحة | الاجتماع مع الفريق وتحليل التأثير على قيود المشروع | تنفيذ التغيير | تحديث سجل اصحاب المصالح | نظرًا لأن صاحب المصلحة غير محدد ، يجب تحديد صاحب المصلحة أولاً وتحديث سجل أصحاب المصلحة قبل تحليل التأثير على قيود المشروع. [PMBOK الطبعة السادسة ، الصفحة 529] | 149 | 5 | False | "20" | Haitham
516 | A program manager informs the project manager that their project was terminated. The project manager want to inform the stakeholders and team members about this. To what document should the project manager refer? | Change Management Plan | Responsibility assignment matrix (RAM) | Resources Management Plan | Communication management plan | The project manager should refer to communication management plan to inform the stakeholders and team management about the project termination decision. Because communication management plan includes who & when & why should send the information. [PMBOK 6th edition, Page 377] | يقوم مدير البرنامج بإبلاغ مدير المشروع بإنهاء مشروعه. يريد مدير المشروع إبلاغ أصحاب المصلحة وأعضاء الفريق بهذا. إلى أي وثيقة يجب أن يشير مدير المشروع؟ | خطة إدارة التغيير | مصفوفة إسناد المسؤولية (RAM) | خطة إدارة الموارد | خطة إدارة الاتصالات | يجب على مدير المشروع الرجوع إلى خطة إدارة الاتصالات لإبلاغ أصحاب المصلحة وإدارة الفريق بقرار إنهاء المشروع. لأن خطة إدارة الاتصالات تتضمن من ومتى ولماذا يرسل المعلومات. [PMBOK الطبعة السادسة ، الصفحة 377] | 146 | 5 | False | "20" | Haitham
517 | A new team member has been assigned to a project team. This resource is used to a different delivery method that is less productive and does not enforce the deadline. The new delivery method is integrated so low productivity personnel have larger impact on the overall productivity of team performance. What strategy can the project manager apply to resolve the conflict with the new resource? | Force / Direct | compromise / Reconcile | Smooth / Accommodate | Collaborate / Problem solve | Collaborate / Problem-solving is the best conflict resolution technique to resolve the conflict with the new resource. [PMBOK 6th edition, Page 349]. | تم تعيين عضو جديد في فريق المشروع. يستخدم هذا المورد طريقة تسليم مختلفة أقل إنتاجية ولا تؤثر على الموعد النهائي. تم دمج طريقة التسليم الجديدة بحيث يكون للأفراد ذوي الإنتاجية المنخفضة تأثير أكبر على الإنتاجية الإجمالية لأداء الفريق. ما هي الإستراتيجية التي يمكن لمدير المشروع تطبيقها لحل التعارض مع المورد الجديد؟ | القوة / التوجيه | تسوية / توافق | تجانس / استيعاب | التعاون / حل المشكلة | التعاون / حل المشكلات هو أفضل أسلوب لحل النزاعات لحل التعارض مع المورد الجديد. [PMBOK الطبعة السادسة ، الصفحة 349]. | 145 | 4 | False | "17" | Haitham
518 | As a project manager for a huge construction project, the project is being fast-tracked because the stakeholders committed to the schedule baseline. Some construction activities must be initiated before all basic scope specifications are completely developed. What type of contract should the procurement manager negotiate? | Cost plus fixed fee (CPFF). | Firm fixed price (FFP). | Fixed price incentive fee (FPIF) | Cost plus incentive fee (CPIF). | The project scope not well defined so you can easily remove option Fixed Price incentive Fee Contracts (FPIF) and Firm fixed-price contract (FFP). Option Cost Plus Incentive Fee Contracts (CPIF) Is the Best because this type Provides low risk for the buyer from CPFF.T he risk also lies with the buyer: however, this risk Is lower than the Cost Plus Fixed Fee where the buyer has to pay a fixed fee along with the cost Incurred. CPMBOK 6th edition, Page 472) | بصفتك مدير مشروع لمشروع بناء ضخم ، يتم تتبع المشروع بسرعة لأن أصحاب المصلحة ملتزمون بخط الأساس للجدول الزمني. يجب الشروع في بعض أنشطة البناء قبل تطوير جميع المواصفات الأساسية للنطاق بالكامل. ما نوع العقد الذي يجب أن يتفاوض عليه مدير المشتريات؟ | التكلفة بالإضافة إلى المبلغ الثابت (CPFF). | السعر المحدد (FFP). | السعر الثابت مع قيمة تحفيزية (FPIF) | التكلفة بالإضافة إلى قيمة تحفيزية (CPIF). | كون نطاق المشروع غير محدد جيدًا يمكن بسهولة إزالة الخيار السعر الثابت مع قيمة تحفيزية (FPIF) والخيار السعر المحدد (FFP). الخيار عقود التكلفة بالإضافة إلى قيمة تحفيزية (CPIF) هي الأفضل لأن هذا النوع يوفر مخاطر منخفضة للمشتري من CPFF. تقع المخاطر أيضًا على المشتري: ومع ذلك ، فإن هذه المخاطر تكون أقل من عقود التكلفة بالإضافة إلى المبلغ الثابت (CPFF) حيث يتعين على المشتري دفع رسوم ثابتة مع التكلفة المتكبدة. [CPMBOK الطبعة السادسة، الصفحة 472] | 148 | 3 | False | "20" | Haitham
519 | You need a public opinion as part of the requirements gathering process for your project. You selected a wide variety of people for your study and want to use a requirements gathering technique that can produce results quickly. Which technique is best suited for this scenario? | Observations | Brainstorming | Group Creativity Techniques | Questionnaires and Surveys | Questionnaires and Surveys are written sets of questions designed to quickly accumulate information from a wide number of respondents with quick turnaround time.[PMBOK 6th edition, Page 143) | أنت بحاجة إلى رأي عام كجزء من عملية جمع المتطلبات لمشروعك. لقد اخترت مجموعة متنوعة من الأشخاص لدراستك وترغب في استخدام تقنية جمع المتطلبات التي يمكن أن تؤدي إلى نتائج سريعة. ما هي التقنية الأنسب لهذا السيناريو؟ | الملاحظات | العصف الذهني | تقنيات إبداع المجموعة | الاستبيانات والاستطلاعات | الاستبيانات والاستطلاعات عبارة عن مجموعات مكتوبة من الأسئلة مصممة لتجميع المعلومات بسرعة من عدد كبير من المستجيبين في وقت استجابة سريع. [PMBOK الطبعة السادسة، الصفحة 143] | 141 | 3 | False | "19" | Haitham
520 | A project consists of 5 activities, A, B, C, D, and E. Task A begins on day 1 and will take two days to complete. Task B will take 6 days to complete and can not begin until task A is finished. Task C will take 4 days to complete, cannot begin before task A is finished, and must be completed before task D begins. Task D will take 8 days to complete and cannot begin until task B is finished. Task E will take 1 day to complete and cannot begin until task D is finished. What is the duration of the critical path? | 19 days. | 20 days. | 15 days. | 17 days | Path ( 1 ) A-B-E-D= 17 Days Path ( 2) A-C-D-E= 15 Days So, the duration of the critical path is 17 days. [PMBOK 6th edition, Page 210, 211]. | يتكون المشروع من 5 أنشطة ، A و B و C و D و E. تبدأ المهمة (A) في اليوم الأول وستستغرق يومين لإكمالها. ستستغرق المهمة B ستة أيام لتكتمل ولا يمكن أن تبدأ حتى تنتهي المهمة A. ستستغرق المهمة C أربعة أيام حتى تكتمل، ولا يمكن أن تبدأ قبل انتهاء المهمة A ، ويجب إكمالها قبل بدء المهمة D. ستستغرق المهمة D ثمانية أيام حتى تكتمل ولا يمكن أن تبدأ حتى تنتهي المهمة B. ستستغرق المهمة E يومًا واحدًا حتى تكتمل ولا يمكن أن تبدأ حتى تنتهي المهمة D. ما هي مدة المسار الحرج؟ | 19 يومًا. | 20 يوم. | 15 يوم. | 17 يومًا | المسار (1): A-B-E-D = 17 المسار (2): A-C-D-E = 15 إذن مدة المسار الحرج 17 يومًا. [PMBOK الطبعة السادسة، الصفحة 210، 211]. | 142 | 3 | False | "19" | Haitham
521 | You are a project manager for a website design development project. An issue appears on a project and one of your project team remember that this issue has occurred before, but cannot remember the solution. Which of the following options should you refer first to find the solution? | Checklist | Issue management procedure | Organizational Strategy | Organizational process assets | The organizational process assets include Issue and defect management procedures defining issue and defect controls, issue and defect identification and resolution, and action item tracking. Issue and defect management database(s) containing historical issue and defect status, issue and defect resolution, and action item results. [PMBOK 6th edition, Page 94]. | أنت مدير مشروع لتطوير تصميم مواقع الويب. تظهر مشكلة في مشروع ويتذكر أحد أعضاء فريق المشروع أن هذه المشكلة حدثت من قبل، ولكن لا يمكنه تذكر الحل. أي من الخيارات التالية يجب أن ترجع له أولاً للعثور على الحل؟ | قائمة التدقيق | إجراءات إدارة القضية | الإستراتيجية التنظيمية | أصول العملية التنظيمية | تتضمن أصول العملية التنظيمية إجراءات إدارة المشكلات والعيوب التي تحدد ضوابط المشكلة والعيوب ، وتحديد المشكلات والعيوب وحلها ، وتتبع عنصر العمل. قاعدة بيانات إدارة المشكلات والعيوب التي تحتوي على المشكلات التاريخية وحالة العيب وحل المشكلات والعيوب ونتائج عنصر الإجراء. [PMBOK الطبعة السادسة، الصفحة 94]. | 140 | 4 | False | "18" | Haitham
522 | As a project manager, what should you do FIRST if the project sponsor decided to conduct certain changes to the project scope without consulting you? | Update the project management plan to involve the changes. | Negotiate with the project sponsor to make the changes in the next phase of the project | Identify this as a risk and implement risk response strategies | Assess the impact of the change in the project scope. | Before updating the project management plan, the project manager should first Assess the impact of the change In the project scope. [PMBOK 6th edition, Page 170 ]. | بصفتك مدير مشروع ، ما الذي يجب عليك فعله أولاً إذا قرر راعي المشروع إجراء تغييرات معينة على نطاق المشروع دون استشارتك؟ | قم بتحديث خطة إدارة المشروع لإدخال التغييرات. | تفاوض مع راعي المشروع لإجراء التغييرات في المرحلة التالية من المشروع | حدد هذا على أنه خطر وقم بتنفيذ استراتيجيات الاستجابة للمخاطر | قيم تأثير التغيير في نطاق المشروع. | قبل تحديث خطة إدارة المشروع ، يجب على مدير المشروع أولاً تقييم تأثير التغيير في نطاق المشروع. [PMBOK الطبعة السادسة، الصفحة 170]. | 141 | 5 | False | "16" | Haitham
523 | A quality control member informs a project manager about a one-week schedule delay to complete the testing phase. What should the project manager do next? | Crash the schedule. | Negotiate with the customer for a change in the schedule. | Take corrective action to minimize the impact of delay | Check whether this task is on the critical path. | Before you take corrective measures, determine the Impact of the delay. For example, if the task has 3 weeks float, you do not need other options. [PMBOK 6th edition, Page 210]. | قام عضو مراقبة الجودة بإبلاغ مدير المشروع بتأخير الجدول الزمني لمدة أسبوع واحد لإكمال مرحلة الاختبارات. ماذا يجب أن يفعل مدير المشروع بعد ذلك؟ | حشد الموارد في الجدول الزمني. | التفاوض مع العميل لتغيير الجدول. | اتخذ إجراءات تصحيحية لتقليل تأثير التأخير | تحقق مما إذا كانت هذه المهمة على المسار الحرج. | قبل اتخاذ الإجراءات التصحيحية ، حدد تأثير التأخير. على سبيل المثال ، إذا كانت المهمة تحتوي على 3 أسابيع ، فلن تحتاج إلى خيارات أخرى. [PMBOK الطبعة السادسة، الصفحة 210]. | 142 | 5 | False | "20" | Haitham
524 | After finishing the planning phase of a project, but before execution, the project manager needs to communicate and gain commitment on project objectives. What should the project manager do next? | Send the project management plan to all stakeholders via email. | Call each stakeholder to explain their roles and responsibilities. | Ask the project sponsor to communicate the plan to all stakeholders. | Conduct a kick-off meeting with all stakeholders. | Since the project manager needs to communicate and gain commitment, so project kick-off meeting is required. The project kick-off meeting is usually associated with the end of planning and the start of executing. It's purpose is to communicate the objectives of the project, gain the commitment of the team for the project, and explain the roles and responsibilities of each stakeholder. [PMBOK 6th edition, Page 86]. | بعد الانتهاء من مرحلة التخطيط للمشروع ، ولكن قبل التنفيذ ، يحتاج مدير المشروع إلى التواصل والحصول على الالتزام بأهداف المشروع. ماذا يجب أن يفعل مدير المشروع بعد ذلك؟ | أرسل خطة إدارة المشروع إلى جميع أصحاب المصلحة عبر البريد الإلكتروني. | الإتصال بكل صاحب مصلحة لشرح أدواره ومسؤولياته. | اطلب من راعي المشروع توصيل الخطة لجميع أصحاب المصلحة. | عقد اجتماع إطلاق المشروع مع جميع أصحاب المصلحة. | نظرًا لأن مدير المشروع يحتاج إلى التواصل والحصول على الالتزام ، فإن اجتماع بدء المشروع مطلوب. عادة ما يرتبط اجتماع إطلاق المشروع بنهاية التخطيط وبداية التنفيذ. والغرض منه هو إيصال أهداف المشروع ، وكسب التزام الفريق بالمشروع ، وشرح أدوار ومسؤوليات كل صاحب مصلحة. [PMBOK الطبعة السادسة، الصفحة 86]. | 140 | 3 | False | "20" | Haitham
525 | After completing some work required to develop your project team members, such as training and improving competencies. What will you do next? | Team building activities | Staff assignments | WBS dictionary elements | Team performance assessments | You are in Develop Team Process, and the Team Performance Assessments is output from Develop Team Process. [PMBOK 6th edition, Page 336] | بعد الانتهاء من بعض الأعمال المطلوبة لتطوير أعضاء فريق المشروع الخاص بك ، مثل التدريب وتحسين الكفاءات. ماذا ستفعل بعد ذلك؟ | أنشطة بناء الفريق | تعيينات الموظفين | عناصر قاموس WBS | تقييمات أداء الفريق | أنت في عملية تطوير الفريق ، وتقييمات أداء الفريق هي من مخرجات هذه العملية. [PMBOK الطبعة السادسة، الصفحة 336]. | 145 | 4 | False | "18" | Haitham
526 | You are a project manager in a critical project for your organization. You have a project with a budget of 200,000 SR. The duration of the project is 30 months, and the work is evenly distributed throughout the duration. After 15 months, you review the project's progress and you find that 60% of the work is completed and 110,000 SR has been spent. Determine the estimate at completion assuming the future cost performance is the same as the past cost performance. | 100,000 SR | 190,000 SR | 120,000 SR | 183,486 SR | Due to that future cost performance is same as the past cost performance we should apply the following formula: EAC = BAC / CPI BAC=200,000 EV=200,000 * 60% = 120,000 CPI = EV / AC = 120,000 / 110,000 = 1.09 EAC = 200,000 / 1.09 = 183,486 SR. [PMBOK 6th edition. Page 267]. | أنت مدير مشروع في مشروع مهم لمؤسستك. لديك مشروع بميزانية 200,000 ريال. مدة المشروع 30 شهرًا ، ويتم توزيع العمل بالتساوي طوال المدة. بعد 15 شهرًا ، قمت بمراجعة تقدم المشروع ووجدت أن 60٪ من العمل قد اكتمل وتم إنفاق 110,000 ريال سعودي. أحسب التقدير عند الانتهاء على افتراض أن أداء التكلفة المستقبلية هو نفسه أداء التكلفة السابق. | 100,000 ريال | 190,000 ريال | 120,000 ريال | 183,486 ريال | نظرًا لأن أداء التكلفة المستقبلية مماثل لأداء التكلفة السابقة ، يجب علينا تطبيق المعادلة التالية: EAC = BAC / CPI BAC = 200.000 EV = 200,000 * 60٪ = 120,000 CPI = EV / AC = 120,000 / 110,000 = 1.09 EAC = 200, 000 / 1.09 = 183,486 ريال [PMBOK الطبعة السادسة. الصفحة 267]. | 143 | 5 | False | "20" | Haitham
527 | You are leading a construction new commercial project to install new door frames in an office building. Currently, you are about to start the development of the assumption log for the project. What should you do first? | Review the project scope statement | Start the Identify Stakeholders process as the assumption log is an output of this process | Review the project management plan | Read the project business case | The assumption log is a project document used to record all assumptions and constraints throughout the project life cycle. The assumption log is created as an output of the Develop Project Charter process, as such limited information is available to create this project document. High-level strategic and operational assumptions and constraints are normally identified in the business case before the project is initiated and will flow into the project charter. Lower-level activity and task assumptions are generated throughout the project. The assumption log is used to record all assumptions and constraints throughout the project life cycle. Therefore, of the available options, the project business case is the best source of information to use in the development of the assumption log. [PMBOK 6th edition, Page 77] | أنت تقود مشروعًا تجاريًا جديدًا لإنشاء إطارات أبواب جديدة في مبنى إداري. حاليًا ، أنت على وشك البدء في تطوير سجل الافتراضات للمشروع. ما الذى ينبغى عليك فعله اولا؟ | راجع بيان نطاق المشروع | ابدأ عملية تحديد أصحاب المصلحة حيث أن سجل الافتراضات هو أحد مخرجات هذه العملية | مراجعة خطة إدارة المشروع | اقرأ مسوغ المشروع | سجل الافتراضات هو مستند المشروع الذي يستخدم لتسجيل جميع الافتراضات والقيود طوال دورة حياة المشروع. يتم إنشاء سجل الافتراضات كمخرجات لعملية تطوير ميثاق المشروع، حيث تتوفر هذه المعلومات المحدودة لإنشاء وثيقة المشروع هذه. عادة ما يتم تحديد الافتراضات والقيود الاستراتيجية والتشغيلية رفيعة المستوى في دراسة الجدوى قبل بدء المشروع وسوف تنعكس في ميثاق المشروع. يتم إنشاء المستوى الأدنى من الإفتراضات للأنشطة والمهام خلال المشروع. يتم استخدام سجل الافتراضات لتسجيل جميع الافتراضات والقيود طوال دورة حياة المشروع. لذلك من بين الخيارات المتاحة، يعد مسوغ المشروع أفضل مصدر للمعلومات لاستخدامها في تطوير سجل الافتراضات. [PMBOK الطبعة السادسة، الصفحة 77] | 140 | 2 | False | "20" | Haitham
528 | You, as a project manager, are in the process of midway review at the end of the first year of a $50K project. The earned value analysis shows that the PV is $25K, the EV is $20K, and the AC is $30K. What can be determined from these figures? | The project should be terminated as there is no solution to fix it. | The project is under budget but ahead of schedule. | The project is going normally, and it will be managed and closed normally. | The project is going slower than planned. | From the question it's clear that: EV < AC & PV. So, the Project over budget and behind schedule. Then, the project is going slower than planned is the best choice. [PMBOK 6th edition, Pages 263, 267]. | أنت، كمدير مشروع ، في طور المراجعة في منتصف الطريق في نهاية السنة الأولى لمشروع بقيمة 50 ألف دولار. يُظهر تحليل القيمة المكتسبة أن القيمة المخططة PV تساوي 25 ألف دولار ، و القيمة المكتسبة EV تبلغ 20 ألف دولار ، و التكلفة الفعلية AC تساوي 30 ألف دولار. ما الذي يمكن تحديده من هذه الأرقام؟ | يجب الغاء المشروع حيث لا يوجد حل لإصلاحه. | المشروع تحت الميزانية ولكن سابق للجدول الزمني. | يسير المشروع بشكل طبيعي ، وسيتم إدارته وإغلاقه بشكل طبيعي. | يسير المشروع أبطأ مما هو مخطط له. | من السؤال يتضح أن: EV < AC & PV. لذلك ، المشروع متجاوز للميزانية ومتأخر عن الجدول الزمني. بذلك ، يسير المشروع أبطأ مما هو مخطط له، هو الخيار الأفضل. [PMBOK الطبعة السادسة الصفحة 263، 267]. | 143 | 5 | False | "18" | Haitham
529 | A project team is in the process of obtaining supplier responses, selecting a supplier, and awarding a contract. For this purpose, the team is using some predefined selection criteria to evaluate the bids and select the most appropriate supplier. Which process of project management is the project team working on? | Plan Procurement Management | Control Procurements | Proposal Evaluation | Conduct Procurements | The activities are part of the "conduct procurement" process, which includes obtaining supplier responses, selecting a supplier, and awarding a contract based on selection criteria to qualified supplier. Although the team is working on proposal evaluation, option (proposal evaluation) is not a process, but a tool. [PMBOK 6th edition Page, 482]. | فريق المشروع بصدد الحصول على ردود الموردين ، واختيار المورد ، وتوقيع العقد. لهذا الغرض ، يستخدم الفريق بعض معايير الاختيار المحددة مسبقًا لتقييم العطاءات واختيار المورد الأنسب. ما هي عملية إدارة المشروع التي يعمل عليها فريق المشروع؟ | خطة إدارة المشتريات | التحكم بالمشتريات | تقييم العروض | إدارة المشتريات | تعد الأنشطة المذكورة في السؤال جزءًا من عملية "إدارة المشتريات" والتي تتضمن الحصول على ردود الموردين ، واختيار المورد ، ووتوقيع العقد بناءً على معايير الاختيار للمورد المؤهل. على الرغم من أن الفريق يعمل على تقييم العروض، فإن الخيار (تقييم العروض) ليس عملية ولكنه أداة. [PMBOK الطبعة السادسة الصفحة، 482]. | 148 | 4 | False | "19" | Haitham
530 | You have been asked to begin writing the project scope management plan. You are gathering the necessary documents to begin this process. Which of the following is required to do this? | Focus groups | Risk management plan | Requirement traceability chart | Quality management plan | The way the project and product scope will be managed can be influenced by how the organization’s quality policy, methodologies, and standards are implemented on the project. It will be needed when developing a scope management plan. [PMBOK 6th edition, Page 135 ]. | لقد طُلب منك البدء في كتابة خطة إدارة نطاق المشروع. أنت تجمع المستندات اللازمة لبدء هذه العملية. أي مما يلي مطلوب للقيام بذلك؟ | مجموعات التركيز | خطة إدارة المخاطر | مخطط تتبع المتطلبات | خطة إدارة الجودة | يمكن أن تتأثر الطريقة التي سيتم بها إدارة نطاق المشروع والمنتج بكيفية تنفيذ سياسة الجودة والمنهجيات والمعايير الخاصة بالمنظمة في المشروع. وستكون هناك حاجة إليها عند تطوير خطة إدارة النطاق. [PMBOK الطبعة السادسة، الصفحة 135]. | 141 | 3 | False | "20" | Haitham
531 | The project has reached a stage where work is being done in seven countries. Project team members need to know in which currency they are to report their cost data. Which of the following should they reference? | Cost baseline | Cost estimates | Cost breakdown structure | Cost management plan | The cost management plan provides information and guidance on how the project manager and project team will plan, structure, account, and control the project costs. The contents of the plan vary based on the needs of the particular project. The project in the scenario is operating in many countries and currencies. To align all the project documents and communications, it is important for this project cost management plan to detail the currencies to be used, when, in which circumstances, and other pertinent requirements of the project. [PMBOK 6th edition, Page 238] | وصل المشروع إلى مرحلة حيث يجري العمل في سبعة بلدان. يحتاج أعضاء فريق المشروع إلى معرفة العملة التي سيبلغون بها عن بيانات التكلفة الخاصة بهم. أي مما يلي يجب أن يشيروا إليه؟ | خط الأساس للتكلفة | تقديرات التكلفة | هيكل توزيع التكلفة | خطة إدارة التكلفة | توفر خطة إدارة التكلفة معلومات وإرشادات حول كيفية قيام مدير المشروع وفريق المشروع بالتخطيط والهيكل والحساب والتحكم في تكاليف المشروع. تختلف محتويات الخطة بناءً على احتياجات المشروع المعين. المشروع في السيناريو يعمل في العديد من البلدان والعملات. لمواءمة جميع مستندات واتصالات المشروع ، من المهم لخطة إدارة تكاليف المشروع هذه أن توضح بالتفصيل العملات التي سيتم استخدامها ومتى وفي أي ظروف ومتطلبات أخرى ذات صلة بالمشروع. [PMBOK الطبعة السادسة ، الصفحة 238] | 143 | 3 | False | "20" | Haitham
532 | As you project manager, you have submitted the cost baseline to the sponsor. After a review, the sponsor tells you that the amount you have estimated for a certain month is more than the funds the sponsor can disburse you for that month. What do you think the sponsor will advise you to do next? | To remove some of the work scope for that month | To motivate the project team to do the work of that month without being fully paid for it | To reduce the cost estimates of the activities for that month | To reschedule the work of that month | Rescheduling work for the period where funds are lower than estimated will be required in this situation. Removal of scope is not a correct option. It will be tough to motivate people to work without being paid and this may not be legally ok also. Reducing the estimates is also not an option as this will mean that the original estimates were incorrect, and this option will require a change request which will impact the cost baseline. [PMBOK 6th edition. Page 269]. | بصفتك مدير المشروع ، قمت بإرسال خط الأساس المرجعي للتكلفة إلى راعي المشروع. بعد المراجعة ، أخبرك الراعي أن المبلغ الذي قدرته لشهر معين هو أكثر من الأموال التي يمكن للراعي صرفها لك لهذا الشهر. ماذا تعتقد أن الراعي سوف ينصحك أن تفعله بعد ذلك؟ | لإزالة بعض نطاق العمل لذلك الشهر | لتحفيز فريق المشروع على القيام بأعمال ذلك الشهر دون دفع كامل مستحقاتهم مقابل ذلك | لتقليل تقديرات التكلفة للأنشطة لذلك الشهر | لإعادة جدولة عمل ذلك الشهر | إعادة جدولة العمل للفترة التي يكون فيها التمويل أقل من التكلفة المقدرة ستكون مطلوبة في هذه الحالة. إزالة النطاق ليس خيارًا صحيحًا. سيكون من الصعب تحفيز الناس على العمل دون الحصول على كامل أجرهم ، وقد لا يكون هذا مقبولًا من الناحية القانونية أيضًا. إن تقليل التقديرات ليس خيارًا أيضًا لأن هذا سيعني أن التقديرات الأصلية كانت غير صحيحة، وسيتطلب هذا الخيار طلب تغيير سيؤثر على خط الأساس المرجعي للتكلفة. [PMBOK الطبعة السادسة. الصفحة 269]. | 143 | 5 | False | "19" | Haitham
533 | You are managing a project which has BAC 90,000 $ and supposes to finish in 9 months. Five months have passed; however, four months of the work have been completed. To date, you have spent 60% of the budget. What are the EV, CPI, and SPI? | EV= 30,000 CPI = 0.74 SPI = 0.9 | EV= 35,000 CPI = 0.74 SPI = 0.9 | EV= 35,000 CPI = 0.74 SPI = 2 | EV= 40,000 CPI = 0.74 SPI = 0.8 | EV= 4 / 9 * 90,000 = $ 40,000 AC = 0.6 * 90,000 = 54,000 $ PV = 5 / 9 * 90,000 = 50,000 $ CPI = 40,000 / 54,000 = 0.74 SPI = 40,000 / 50,000 = 0.8. [PMBOK 6th edition. Page 267]. | أنت تدير مشروعًا ميزانيته BAC تساوي 90,000 دولار، ويفترض أن ينتهي في غضون 9 أشهر. خمسة أشهر مرت. ومع ذلك، تم الانتهاء من أربعة أشهر من العمل. لقد أنفقت حتى الآن 60٪ من الميزانية. ما هي القيمة المكتسبة EV و مؤشر أداء التكلفة CPI ومؤشر أداء الجدول الزمني SPI؟ | EV= 30,000 CPI = 0.74 SPI = 0.9 | EV= 35,000 CPI = 0.74 SPI = 0.9 | EV= 35,000 CPI = 0.74 SPI = 2 | EV= 40,000 CPI = 0.74 SPI = 0.8 | القيمة المكتسبة EV = 4 \ 9 * 90,000 = 40,000 دولار التكلفة الفعلية AC = 0.6 * 90,000 = 54,000 دولار القيمة المخططة PV = 5 / 9 * 90,000 = 50,000 دولار مؤشر التكلفة CPI = 40,000 / 54,000 = 0.74 مؤشر الجدول الزمني SPI = 40,000 / 50,000 = 0.8. [PMBOK الطبعة السادسة. الصفحة 267]. | 143 | 5 | False | "20" | Haitham
534 | Within your project team, you notice that emotions are at a high due to competition among the team members. People are quick to react rather than understanding each other's needs and responding appropriately. Due to this, team members you are struggling to meet your project goals and results. You are also disturbed about this and speak to your sponsor who advises you to attend a certain training. What training is this likely to be? | Active listening | Team building | Goal setting and results management | Emotional Intelligence | Emotional intelligence is the ability to identify, assess, and manage the personal emotions of oneself and other people, as well as the collective emotions of groups of people. The team can use emotional intelligence to reduce tension and increase cooperation by identifying, assessing, and controlling the sentiments of project team members, anticipating their actions, acknowledging their concerns, and following up on their issues.[PMBOK 6th edition, Page 349] | داخل فريق مشروعك ، لاحظت أن الانفعالات مرتفعة بسبب المنافسة بين أعضاء الفريق. يستجيبوا الأشخاص بسرعة بدلاً من فهم احتياجات بعضهم البعض والاستجابة بشكل مناسب. نتيجة لذلك ، يتصارع أعضاء الفريق لتحقيق أهداف مشروعك ونتائجه. أنت أيضًا منزعج من هذا الأمر وتحدثت إلى راعي المشروع الذي نصحك بحضور تدريب معين. ما هو التدريب المحتمل أن يكون؟ | الاستماع الفعال | بناء الفريق | تحديد الأهداف وإدارة النتائج | الذكاء العاطفي | الذكاء العاطفي هو القدرة على تحديد وتقييم وإدارة المشاعر الشخصية للذات وللآخرين ، بالإضافة إلى المشاعر الجماعية لمجموعات من الناس. يمكن للفريق استخدام الذكاء العاطفي لتقليل التوتر وزيادة التعاون من خلال تحديد وتقييم والسيطرة على مشاعر أعضاء فريق المشروع ، وتوقع أفعالهم ، والاعتراف بمخاوفهم ، ومتابعة قضاياهم. [PMBOK الطبعة السادسة، الصفحة 349] | 145 | 4 | False | "18" | Haitham
535 | In your project, your project team starts testing an mechanical component created during a project, the test failed. The cost of such testing is usually classified as: | Appraisal cost | Internal failure cost | External failure cost | Appraisal and internal failure costs | A failed test incurs both appraisal cost and internal failure cost. [PMBOK 6th edition. Page 283] | في مشروعك ، يبدأ فريق المشروع الخاص بك في اختبار مكون ميكانيكي تم إنشاؤه أثناء المشروع ، وفشل الاختبار. عادة ما يتم تصنيف تكلفة هذا الاختبار على النحو التالي: | تكلفة تقييم | تكلفة الفشل الداخلي | تكلفة الفشل الخارجي | تكاليف التقييم والفشل الداخلي | يصنف الاختبار الفاشل على أنه تكلفة تقييم وتكلفة فشل داخلي. [PMBOK الطبعة السادسة. الصفحة 283] | 144 | 5 | False | "20" | Haitham
536 | You have just been moved onto a project that is well into the project implementation phase. You then realize that no stakeholder register exists for the project. Since you are new to the organization, you want to ensure that you use its templates for documents. Therefore, you search for a template for a stakeholder registered in the: | Enterprise environmental factors | Stakeholder management plan | Project management plan | Organizational process assets | Organizational process assets are inputs in Identify Stakeholders process and include Stakeholder register templates. [PMBOK 6th edition, Page 510] | لقد تم نقلك للتو إلى مشروع دخل مرحلة التنفيذ. أدرك أنه لا يوجد سجل لأصحاب المصلحة في المشروع. نظرًا لأنك جديد في المؤسسة، فأنت تريد التأكد من استخدام قوالب المستندات الخاصة بها. لذلك ستبحث عن نموذج سجل أصحاب المصلحة في: | العوامل البيئية للمؤسسة | خطة إدارة أصحاب المصلحة | خطة إدارة المشروع | أصول العملية التنظيمية | أصول العملية التنظيمية هي مدخلات في عملية تحديد أصحاب المصلحة وتتضمن قوالب سجلات أصحاب المصلحة. [PMBOK الطبعة السادسة ، الصفحة 510] | 149 | 4 | False | "19" | Haitham
537 | Sony is so good at assembling those types of knowledge, that if someone with no experience is hired, it would take two years to match his skill. This type of knowledge is known as: | Explicit knowledge | Embedded knowledge | Experience knowledge | Tacit knowledge | Knowledge is commonly split into "explicit" (knowledge that can be readily codified using words, pictures, and numbers) and "tacit" (knowledge that is personal and difficult to express, such as beliefs, insights, experience, and "know-how"). [PMBOK 6th edition, Page 100] | تعد سوني كشركة جيدة جدًا في تجميع هذه الأنواع من المعارف بحيث إذا تم التعاقد مع شخص ليس لديه خبرة ، فسوف يستغرق الأمر عامين لمطابقة مهارته. يُعرف هذا النوع من المعرفة باسم: | معرفة صريحة | المعرفة المضمنة | معرفة الخبرة | المعرفة الضمنية | تنقسم المعرفة عادة إلى "صريحة" (معرفة يمكن تقنينها بسهولة باستخدام الكلمات والصور والأرقام) و "ضمنية" (المعرفة الشخصية التي يصعب التعبير عنها ، مثل المعتقدات والرؤى والخبرة والدراية الفنية). [PMBOK الطبعة السادسة، الصفحة 100] | 140 | 4 | False | "19" | Haitham
538 | You are project manager and working with your customers on completing deliverables in seaport project. Which of the following stakeholders can modify and make changes in the project charter? | The project customer | All stakeholders | The team members | The project sponsor | The sponsor is the only person who can modify and make changes In the project charter. [PMBOK 6th edition, Page 114] | أنت مدير المشروع وتعمل مع عملائك على إكمال التسليمات في مشروع الميناء. أي من أصحاب المصلحة التاليين يمكنه تعديل ميثاق المشروع وإجراء تغييرات عليه؟ | عميل المشروع | جميع أصحاب المصلحة | أعضاء الفريق | راعي المشروع | الراعي هو الشخص الوحيد الذي يمكنه التعديل وإجراء التغييرات في ميثاق المشروع. [PMBOK الطبعة السادسة ، الصفحة 114] | 140 | 6 | False | "20" | Haitham
539 | As part of the initiation process, what should the project manager do prior to the planning stage? | Define the project sign-off criteria and create a risk register. | Start gathering requirements and plan the kick-off meeting. | Acquire the resources and determine the budget. | Develop the project charter and identify the stakeholders. | in the initiation phase, the project manager should Develop the project charter and identify the stakeholders prior to the planning stage. [PMBOK 6th edition, Page 77]. | كجزء من عملية البدء ، ما الذي يجب على مدير المشروع فعله قبل مرحلة التخطيط؟ | تحديد معايير الموافقة على المشروع وإنشاء سجل للمخاطر. | ابدأ في جمع المتطلبات وخطط لاجتماع البداية. | الحصول على الموارد وتحديد الميزانية. | تطوير ميثاق المشروع وتحديد أصحاب المصلحة. | في مرحلة البدء ، يجب على مدير المشروع تطوير ميثاق المشروع وتحديد أصحاب المصلحة قبل مرحلة التخطيط. [PMBOK الطبعة السادسة، الصفحة 77]. | 140 | 2 | False | "19" | Haitham
540 | You are managing a project in which your team members are uncertain as to how much time will be needed for each activity. Which of the following techniques is considered the most useful in this case? | Critical Path Method (CPM) | Arrow Diagramming Method (ADM) | Precedence Diagramming Method (PDM) | Three-point estimating | Three-point estimating ( triangular distribution )is the technique used for time measurement in case of uncertainties. Optimistic, pessimistic, and most likely are taken into consideration. [PMBOK 6th edition, Page 201]. | أنت تدير مشروعًا فيه أعضاء فريقك غير متأكدين من الوقت المطلوب لكل نشاط. أي من الأساليب التالية يعتبر الأكثر فائدة في هذه الحالة؟ | طريقة المسار الحرج (CPM) | طريقة الرسم بالأسهم (ADM) | طريقة الرسم بالأسبقية (PDM) | تقدير الثلاث نقاط | التقدير ثلاثي النقاط (التوزيع الثلاثي) هو التقنية المستخدمة لقياس الوقت في حالة عدم اليقين. ويؤخذ بعين الإعتبار التقييم المتفائل والمتشائم والأرجح. [PMBOK الطبعة السادسة ، الصفحة 201]. | 142 | 3 | False | "20" | Haitham
541 | A local contractor is unable to meet a delivery date. The project team did not anticipate this new threat to the supply of the product. Importing this product will cost the project twice the price that the local vendor charges. What should the project manager use to fund this effort? | Contingency reserve | Project budget reserve | Risk response reserve | Management reserve | The Project manager will use the management reserve to fund this effort because its unidentified risk occurred. [PMBOK 6th edition, Page 246, 405] | المقاول المحلي غير قادر على تلبية تاريخ التسليم. لم يتوقع فريق المشروع هذا التهديد الجديد لتوريد المنتج. سيكلف استيراد هذا المنتج المشروع ضعف السعر الذي يفرضه البائع المحلي. ما الذي يجب أن يستخدمه مدير المشروع لتمويل هذا التوريد؟ | احتياطي الطوارئ | احتياطي ميزانية المشروع | احتياطي الاستجابة للمخاطر | الاحتياطي الإداري | سيستخدم مدير المشروع الاحتياطي الإداري لتمويل هذا التوريد بسبب حدوث مخاطر غير محددة. [PMBOK الطبعة السادسة، الصفحة 246، 405] | 147 | 5 | False | "16" | Haitham
542 | When an organization identifies an opportunity to which it would like to respond, it often initiates a: | Project scope statement | Enterprise Environmental Factors | Lessons learned knowledge base | Feasibility study | A feasibility study is often initiated to help an organization decide whether it should undertake a project. The project scope statement is the output from define scope process and is developed during the planning phase. Enterprise Environmental Factors and Lessons learned knowledge base not to help decide if a project should be undertaken. [PMBOK 6th edition, Page 29]. | عندما تحدد منظمة ما فرصة ترغب في الاستجابة لها ، فإنها غالبًا ما تبدأ بـ : | بيان نطاق المشروع | العوامل البيئية للمؤسسة | قواعد المعرفة للدروس المستفادة | دراسة الجدوى | غالبًا ما يتم البدء في دراسة الجدوى لمساعدة المنظمة على تحديد ما إذا كان ينبغي عليها تنفيذ مشروع. بيان نطاق المشروع هو الناتج من تحديد عملية النطاق ويتم تطويره خلال مرحلة التخطيط. لا تساعد قاعدة المعرفة الخاصة بالعوامل البيئية والدروس المستفادة في تحديد ما إذا كان ينبغي تنفيذ المشروع أم لا. [PMBOK الطبعة السادسة. الصفحة 29]. | 140 | 2 | False | "16" | Haitham
543 | You have been asked to provide cost estimates for a project which would be to complete plumber installation in building. As a project manager, you have had past experience in similar projects in your previous organization. The organization you have joined also has recently done a similar project. There is an urgency in providing the estimate as mandated by executive management. What estimation technique would you adopt? | Use Bottom-up Estimating | Use Parametric Estimating technique | Ask your previous organization for the estimates | Use Analogous Estimating | Analogous estimating relies on previous similar projects as the basis of estimation. So, it relies on historical information. This technique is used when there is a limited amount of detailed information like during the early phases of the project. It is less costly and less time-consuming. As time is a constraint as stated in the question, this is the best choice. [PMBOK 6th edition. Page 244]. | لقد طُلب منك تقديم تقديرات التكلفة لمشروع إكمال تركيب التمديدات الصحية في المبنى. بصفتك مدير مشروع ، لديك خبرة سابقة في مشاريع مماثلة في مؤسستك السابقة. وايضاً قامت المنظمة التي انضممت إليها مؤخرًا بمشروع مماثل. هناك حاجة ملحة لتقديم التقدير كما هو مطلوب من قبل الإدارة التنفيذية. ما هي تقنية التقدير التي ستتبناها؟ | استخدم التقدير التصاعدي | استخدم تقنية التقدير بالمحددات | اسأل مؤسستك السابقة عن التقديرات | استخدم التقدير المماثل | يعتمد التقدير المماثل على مشاريع سابقة مماثلة كأساس للتقدير. لذلك ، فهو يعتمد على المعلومات التاريخية. يتم استخدام هذه التقنية عندما يكون هناك كم محدود من المعلومات التفصيلية مثل الوضع في المراحل المبكرة من المشروع. إنها أقل تكلفة وأقل استهلاكاً للوقت. بما أن الوقت يعتبر من القيود كما هو مذكور في السؤال ، فهذا هو الخيار الأفضل. [PMBOK الطبعة السادسة. الصفحة 244]. | 143 | 3 | False | "19" | Haitham
544 | You are a project manager in a manufacturing company. You want to analyze the output of a production line which manufactures water bottles. You want to determine whether the variations in the jobs are inherent to the process or if the process is in need of adjustment. Which of the following tools would be most useful? | Trend analysis | Pareto charts | Statistical sampling | Control charts | Control charts are a graphical display of the results over time of a process. They are used to determine if the process is in control or in need of adjustment. Control charts are used to determine whether or not a process is stable or has predictable performance. [PMBOK 6th edition, Page 304 ] | أنت مدير مشروع في شركة تصنيع. تريد تحليل ناتج خط الإنتاج الذي يصنع زجاجات مياه. تريد تحديد ما إذا كانت الاختلافات في الوظائف متأصلة في العملية أو إذا كانت العملية بحاجة إلى تعديل. أي من الأدوات التالية ستكون مفيدة للغاية؟ | تحليل الاتجاه | مخططات باريتو | أخذ العينات الإحصائية | مخططات التحكم | مخططات التحكم هي عرض رسومي للنتائج بمرور الوقت للعملية. يتم استخدامها لتحديد ما إذا كانت العملية تحت السيطرة أو بحاجة إلى تعديل. تُستخدم مخططات التحكم لتحديد ما إذا كانت العملية مستقرة أم لا ولها أداء يمكن التنبؤ به . [PMBOK الطبعة السادسة ، الصفحة 304] | 144 | 5 | False | "19" | Haitham
545 | Project manager is in the process of obtaining sellers responses, selecting a seller and awarding a contract. Which of the following is most likely to include a procurement statement of work (SOW) and request for proposal (RFP)? | Project Management plan | Procurement management | Plan quality reports | Procurement documentation | The question suggests that the Conduct Procurements process is underway. Procurement documentation provides a written record used in reaching the legal agreement and can include bid documents, procurement statement of work. From the available options, only the procurement documentation contains all of the elements specified in the question. [PMBOK 6th edition, Page 485]. | مدير المشروع بصدد الحصول على ردود البائعين، اختيار البائع، وتوقيع العقد. أي مما يلي من المرجح أن يتضمن بيان عمل المشتريات (SOW) وطلب تقديم العروض (RFP)؟ | خطة إدارة المشروع | إدارة المشتريات | تقارير خطة الجودة | وثائق المشتريات | يشير السؤال إلى أن عملية إجراء المشتريات جارية. توفر وثائق المشتريات سجلاً مكتوبًا يستخدم في الوصول إلى الاتفاقية القانونية ويمكن أن تتضمن مستندات العطاء وبيان عمل المشتريات. من بين الخيارات المتاحة، تحتوي وثائق المشتريات فقط على جميع العناصر المحددة في السؤال. [PMBOK الطبعة السادسة، الصفحة 485]. | 148 | 4 | False | "20" | Haitham
546 | One of the key stakeholder asks the project manager to add a new product feature. The project manager is unsure who have the authority to approve this request. To what document should the project manager refer? | RACI Matrix | Change Log | Organizational process assets ( OPA ) | Change Management Plan | The change management plan provides the direction for managing the change control process and documents the roles and responsibilities of the change control board (CCB). RACI Matrix is used to illustrate the connections between work packages, or activities, and project team members. so the correct answer is change management plan. [PMBOK 6th edition, Page 116]. | طلب أحد أصحاب المصلحة الرئيسيين مدير المشروع لإضافة ميزة جديدة للمنتج. مدير المشروع غير متأكد من لديه السلطة للموافقة على هذا الطلب. إلى أي وثيقة يجب أن يرجع مدير المشروع؟ | مصفوفة RACI | سجل التغيير | أصول العملية التنظيمية (OPA) | خطة إدارة التغيير | توفر خطة إدارة التغيير التوجيه لإدارة عملية التحكم في التغيير وتوثيق أدوار ومسؤوليات لجنة التحكم في التغيير (CCB). تُستخدم مصفوفة RACI لتوضيح الروابط بين حزم العمل أو الأنشطة وأعضاء فريق المشروع. لذا فإن الإجابة الصحيحة هي تغيير خطة الإدارة. [PMBOK الطبعة السادسة، الصفحة 116]. | 140 | 5 | False | "20" | Haitham
547 | You are developing a budget for your airport project. You don't want to use indirect costs in determining the budget. Where should you specify the information regarding indirect costs? | Activity Cost Estimates | Project schedule | Scope baseline | Basis of Estimates | The Basis of Estimates contains the assumptions made when dealing with inclusion or exclusion of direct or indirect costs in the project budget.[PMBOK 6th edition, Page 247] | أنت تقوم بتطوير ميزانية لمشروعك وهو عبارة عن مطار. لا تريد استخدام التكاليف غير المباشرة في تحديد الميزانية. أين يجب أن تحدد المعلومات المتعلقة بالتكاليف غير المباشرة؟ | تقديرات تكلفة النشاط | الجدول الزمنى للمشروع | خط الأساس للنطاق | أسس التقديرات | تحتوي أسس التقديرات على الافتراضات التي تم إجراؤها عند التعامل مع إدراج أو استبعاد التكاليف المباشرة أو غير المباشرة في ميزانية المشروع. [PMBOK الطبعة السادسة، الصفحة 247] | 143 | 3 | False | "20" | Haitham
548 | You are in the process of executing a project that deals with laying out fiber cables connecting two cities. You have been reporting progress on a monthly basis. This month, due to unplanned vacations, many of the staff have not turned up at work. This has caused a delay in the schedule. You decide to check if the schedule variance is within the allowable threshold. What document should you refer to? | Project Management Plan | Project Schedule Network Diagram | Activity Definition | Schedule Management Plan | The acceptable schedule variances are defined in the Schedule Management Plan. [PMBOK 6th edition, Page 182] | أنت بصدد تنفيذ مشروع تمديد كابلات ألياف تربط بين مدينتين. يتم رفع تقارير تقدم الأعمال شهرياً. هذا الشهر ، بسبب الإجازات غير المخطط لها، لم يحضر العديد من الموظفين إلى العمل. وقد تسبب هذا في تأخير الجدول الزمني. قررت التحقق مما إذا كان التباين في الجدول الزمني ضمن الحد المسموح به أم لا. ما الوثيقة التي يجب أن ترجع لها؟ | خطة إدارة المشروع | المخطط الشبكي لجدول المشروع | تعريف النشاط | خطة إدارة الجدول الزمني | يتم تحديد حد التباين المقبول للجدول الزمني في خطة إدارة الجدول الزمني. [PMBOK الطبعة السادسة، الصفحة 182] | 142 | 3 | False | "20" | Haitham
549 | This tool of the Control Quality process is used to aid organize data when performing inspections and collecting information on defects: | Histogram | Cause and effect diagram | Scatter diagrams | Check sheets | Check sheets are also known as tally sheets and are used to organize facts in a manner that will facilitate the effective collection of useful data about a potential quality problem. [ PMBOK 6th edition, Page 302 ] | تُستخدم هذه الأداة في عملية التحكم بالجودة للمساعدة في تنظيم البيانات عند إجراء عمليات التفتيش وجمع المعلومات عن العيوب: | الرسم البياني | مخطط السبب والأثر | مخططات التشتت | قوائم التحقق | تُعرف قوائم التحقق أيضًا باسم قوائم التعداد (قوائم تالي) وتُستخدم لتنظيم الحقائق بطريقة تسهل الجمع الفعال للبيانات المفيدة حول مشكلة الجودة المحتملة. [PMBOK الطبعة السادسة ، الصفحة 302] | 144 | 5 | False | "20" | Haitham
550 | As you work to prepare your quality management plan for your project. Which of the following can help you to have an overview of the tests required to verify requirements? | Use a checklist | Review the quality metrics | Review project scope statement | Review the requirements traceability matrix | The requirements traceability matrix links product requirements to deliverables and helps to ensure each requirement in the requirements documentation is tested. The matrix provides an overview of the tests required to verify the requirements. ( PM BOK Guide 6th Edition, page 280 ) | أثناء عملك على إعداد خطة إدارة الجودة لمشروعك. أي مما يلي يمكن أن يساعدك في الحصول على نظرة عامة على الاختبارات المطلوبة للتحقق من المتطلبات؟ | استخدام قائمة التحقق | مراجعة مقاييس الجودة | مراجعة بيان نطاق المشروع | مراجعة مصفوفة تتبع المتطلبات | تربط مصفوفة تتبع المتطلبات متطلبات المنتج بالمخرجات وتساعد على ضمان اختبار كل متطلب في وثائق المتطلبات. توفر المصفوفة لمحة عامة عن الاختبارات المطلوبة للتحقق من المتطلبات. [PMBOK الطبعة السادسة، الصفحة 280]. | 144 | 3 | False | "19" | Haitham
551 | You have completed resource planning and acquired resources. You have improved the team competency and performance. Now you wish to track the performance of individual members and optimize the team's performance. Which process will you perform? | Team building | Develop Team | Control Resources | Manage Team | Track the performance of individual members and optimize the team's performance are performed in the Manage Team process. [PMBOK 6th edition, Page 345]. | لقد أكملت تخطيط الموارد واكتسبت الموارد. لقد قمت بتحسين كفاءة الفريق وأدائه. أنت الآن ترغب في تتبع أداء الأعضاء الفرديين وتحسين أداء الفريق. ما هي العملية التي ستقوم بها؟ | بناء الفريق | تطوير الفريق | التحكم بالموارد | إدارة الفريق | تتبع أداء الأعضاء الفرديين وتحسين أداء الفريق يتم تنفيذه في عملية إدارة الفريق. [PMBOK الطبعة السادسة ، الصفحة 345]. | 145 | 4 | False | "18" | Haitham
552 | Which process ensures that the assigned physical resources are available to the project at the right time and in the right place? | Plan Resource Management | Acquire Resources | Manage Team | Control resources | Control Resources is the process of ensuring that the physical resources assigned and allocated to the project are available as planned, as well as monitoring the planned versus actual utilization of resources and taking corrective action as necessary. The key benefit of this process is ensuring that the assigned resources are available to the project at the right time and in the right place and are released when no longer needed. [PMBOK 6th edition, Page 352] | ما هي العملية التي تضمن أن الموارد المادية المخصصة متاحة للمشروع في الوقت المناسب وفي المكان المناسب؟ | خطة إدارة الموارد | اكتساب الموارد | إدارة الفريق | التحكم بالموارد | التحكم بالموارد هي عملية التأكد من أن الموارد المادية المعينة والمخصصة للمشروع متاحة كما هو مخطط لها ، بالإضافة إلى مراقبة الاستخدام المخطط له مقابل الاستخدام الفعلي للموارد واتخاذ الإجراءات التصحيحية حسب الضرورة. تتمثل الفائدة الرئيسية لهذه العملية في ضمان توفر الموارد المخصصة للمشروع في الوقت المناسب وفي المكان المناسب وتحريرها عند عدم الحاجة إليها. [PMBOK الطبعة السادسة ، الصفحة 352] | 145 | 5 | False | "20" | Haitham
553 | The business case documents the business needs and the cost-benefit analysis that justify the project. The summary of how the project has achieved the business needs identified in the business case is documented in the: | Project WBS | Project Scope Statement | Project charter | Project final report | The summary of how the project has achieved the business needs identified in the business case is included in a project's final report. The other choices are either project initiating or planning documents. (PMBOK 6th edition, Page 128] | يوثق مسوغ المشروع احتياجات العمل وتحليل التكلفة ووالمنفعة والذي يبرر للبدء بالمشروع. يتم توثيق ملخص كيفية تحقيق المشروع لاحتياجات العمل المحددة في دراسة الجدوى في: | هيكل تجزئة العمل WBS للمشروع | بيان نطاق المشروع | ميثاق المشروع | التقرير النهائي للمشروع | يتم تضمين ملخص كيفية تحقيق المشروع لاحتياجات العمل المحددة في دراسة الجدوى في التقرير النهائي للمشروع. الخيارات الأخرى هي إما وثائق بدء للمشروع أو للتخطيط. [PMBOK الطبعة السادسة ، الصفحة 128] | 140 | 6 | False | "19" | Haitham
554 | What is the process used to ensures that agreed-upon risk responses are executed as planned? | Plan Risk management | Identify Risk | Monitor Risk | Implement Risk Responses | Implement Risk Responses is the process of implementing agreed-upon risk response plans. The key benefit of this process is that it ensures that agreed-upon risk responses are executed as planned to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities. [PMBOK 6th edition, Page 449] | ماهي العملية التي تستخدم لتنفيذ استجابات المخاطر المتفق عليها كما هو مخطط لها؟ | خطة إدارة المخاطر | تحديد المخاطر | مراقبة المخاطر | تنفيذ استجابات المخاطر | تنفيذ الاستجابات للمخاطر هي عملية تنفيذ خطط الاستجابة للمخاطر المتفق عليها. تتمثل الميزة الرئيسية لهذه العملية في أنها تضمن تنفيذ استجابات المخاطر المتفق عليها كما هو مخطط لها لمعالجة التعرض لمخاطر المشروع بشكل عام ، وتقليل تهديدات المشروع الفردية ، وزيادة فرص المشروع الفردية. [PMBOK الطبعة السادسة ، الصفحة 449] | 147 | 4 | False | "20" | Haitham
555 | As you are project manager, in which of the following techniques are used to determine the type, format of information needed and the communication needs of the project stakeholders? | Communication models | Communication Method; | Root Cause Analysis | Communication requirements analysis | Analysis of communication requirements determines the information needs of the project stakeholders. These requirements are defined by combining the type and format of information needed with an analysis of the value of that information. [PMBOK 6th edition, Pages 369] | نظرًا لأنك مدير مشروع تدير المشروع، أي من الأساليب التالية يستخدم لتحديد نوع المعلومات المطلوبة وشكلها واحتياجات الاتصال لأصحاب المصلحة في المشروع؟ | نماذج الاتصال | طريقة الاتصال | تحليل السبب الجذري | تحليل متطلبات الاتصال | يحدد تحليل متطلبات الاتصال الاحتياجات المعلوماتية لأصحاب المصلحة في المشروع. يتم تحديد هذه المتطلبات من خلال الجمع بين نوع وشكل المعلومات المطلوبة مع تحليل قيمة تلك المعلومات. [PMBOK الطبعة السادسة، الصفحة 369] | 146 | 4 | False | "20" | Haitham
556 | You are construction manager and meeting with the seller's project manager to review their construction work. In this review, your focus is on the deliverables and a site walkthrough. What is this known as? | Performance review | Earned value analysis | Audit | Inspection | This is an inspection. An inspection is a structured review of the work being performed by the contractor. This may involve a simple review of the deliverables or an actual physical review of the work itself. On a construction/engineering/infrastructure project, inspections involve walkthroughs of the site by both the buyer and the contractor to ensure a mutual understanding of the work in progress. Ina performance review, resources, cost, schedule, and quality will be reviewed. Audits are related to the procurement process. [PMBOK 6th edition, Page 498] | أنت مدير التشييد واجتمعت مع مدير مشروع البائع لمراجعة أعمال البناء الخاصة بهم. في هذه المراجعة ينصب تركيزك على المخرجات وجولات الموقع. ما هي هذه التقنية؟ | مراجعة الأداء | تحليل القيمة المكتسبة | التدقيق | الفحص | هذا يعتبر فحص. الفحص هو مراجعات منظمة للعمل الذي يقوم به المقاول. قد يتضمن ذلك مراجعة بسيطة للنتائج أو مراجعة فعلية للعمل نفسه. في مشروع البناء / الهندسة / البنية التحتية، يشمل الفحص عمليات الجولات التفتيشية للموقع من قبل المشتري والمقاول لضمان الفهم المتبادل للعمل الجاري. في مراجعة الأداء، يتم مراجعة الموارد والتكلفة والجدول الزمني والجودة. كما ترتبط عمليات التدقيق بعملية الشراء. [PMBOK الطبعة السادسة، الصفحة 498] | 148 | 5 | False | "19" | Haitham
557 | You are project manager managing a heavy equipment manufacturing project. During the execution phase, an unexpected issue occurred and need to procure a new piece of machinery. As a project manager, from where may the necessary funds be obtained? | Contingency reserve. | Project sponsor. | Cost Baseline. | Management reserve. | Since the issue is Unforeseen, then the Management reserves should be used. Management reserves are an amount of the project budget withheld for management control purposes and are reserved for unforeseen work that is within scope of the project. Management reserves are intended to address the unknown unknowns that can affect a project. [PMBOK 6th edition page, 252] | أنت مدير مشروع تدير مشروعًا لتصنيع المعدات الثقيلة. خلال مرحلة التنفيذ ، حدثت مشكلة غير متوقعة وتحتاج إلى شراء آلة جديدة. كمدير للمشروع ، من أين يمكن الحصول على الأموال اللازمة؟ | احتياطي الطوارئ. | راعي المشروع. | خط الأساس المرجعي للتكلفة. | الاحتياطي الإداري. | نظرًا لأن المشكلة غير متوقعة، فيجب استخدام الإحتياطي الإداري. الإحتياطي الإداري هو مبلغ من ميزانية المشروع محتجزة لأغراض التحكم الإدارية وهي محجوزة للعمل غير المتوقع الذي يقع في نطاق المشروع. يهدف الإحتياطي الإداري إلى معالجة الحدث المجهول - المجهول الذي يمكن أن يؤثر على المشروع. [PMBOK الطبعة السادسة، الصفحة 252] | 143 | 3 | False | "19" | Haitham
558 | The director of PMO requests from the project managers to start calculating the cost contingency reserve for the project works. As a project manager, how should you calculate contingency reserves? | Trend analysis | What-if scenario analysis | Earned value analysis | Percentage of the estimated cost | The contingency reserve may be a percentage of the estimated cost, a fixed number, or maybe developed by using quantitative analysis methods such as Monte Carlo Analysis, Decision Tree Analysis and EMV (Expected Monetary Value).. [PMBOK 6th edition, Page 427] | يطلب مدير مكتب إدارة المشاريع من مديري المشاريع البدء في حساب احتياطي طوارئ التكلفة لأعمال المشروع. بصفتك مدير مشروع ، كيف يجب أن تحسب احتياطي الطوارئ؟ | تحليل الاتجاه | تحليل سيناريو ماذا لو | تحليل القيمة المكتسبة | نسبة من التكلفة التقديرية | قد يكون احتياطي الطوارئ نسبة مئوية من التكلفة المقدرة ، أو رقمًا ثابتًا ، أو ربما يتم تطويره باستخدام طرق التحليل الكمي مثل تحليل مونت كارلو ، وتحليل شجرة القرار و القيمة النقدية المتوقعة EMV. [PMBOK الطبعة السادسة، الصفحة 427] | 147 | 3 | False | "20" | Haitham
559 | You are a project manager of a project. During the preparing and planning phase, you and your team members start identify the definition of probability of events occurring and the impact. What process is this? | Perform qualitative risk analysis | Identify risks | Perform quantitative risk analysis | Plan risk management | In the plan risk management process, you define the definition of risk probability and its impact. [PMBOK 6th edition, Page 407] | أنت مدير مشروع. أثناء مرحلة الإعداد والتخطيط، بدأت أنت وأعضاء فريقك في تعريف احتمالية وقوع الأحداث والتأثير. ما هذه العملية؟ | إجراء التحليل النوعي للمخاطر | تحديد المخاطر | إجراء التحليل الكمي للمخاطر | خطة إدارة المخاطر | في عملية التخطيط لإدارة المخاطر، تقوم بتعريف احتمالية المخاطر وتأثيرها. [PMBOK الطبعة السادسة ، الصفحة 407] | 147 | 3 | False | "19" | Haitham
560 | As a project manager, you are in the process of confirming the formal acceptance of the seller's work, finalizing open claims, Updating records to reflect final results, and archiving lessons learned recently captured about the seller's performance. Which of the following processes are you performing? | Control Procurements | Monitor and Control Project Work | Conduct Procurements | Close Project or Phase | The scenario presented describes administrative closure activities, which occur as part of the Close Project or Phase process. While procurements are closed through the Control Procurements process, administrative closure of procurements occurs through the Close Project or Phase process. Activities related to the completion of the contractual agreements applicable to the project or project phase such as: Confirming the formal acceptance of the seller's work, Finalizing open claims, Updating records to reflect final results, and Archiving such information for future use. [PMBOK 6th edition, Page 123] | بصفتك مدير مشروع ، فأنت بصدد تأكيد القبول الرسمي لعمل البائع ، وإنهاء المطالبات المفتوحة ، وتحديث السجلات لتعكس النتائج النهائية ، وأرشفة الدروس المستفادة التي تم التقاطها مؤخرًا حول أداء البائع. أي من العمليات التالية تقوم بتنفيذها؟ | مراقبة المشتريات | مراقبة والتحكم بأعمال المشروع | إدارة المشتريات | أغلق المشروع أو المرحلة | يصف السيناريو المقدم أنشطة الإغلاق الإداري، والتي تحدث كجزء من عملية إغلاق المشروع أو المرحلة. بينما يتم إغلاق المشتريات من خلال عملية التحكم بالمشتريات، يحدث الإغلاق الإداري للمشتريات من خلال عملية إغلاق المشروع أو المرحلة. الأنشطة المتعلقة بإنجاز الاتفاقات التعاقدية المطبقة على مرحلة المشروع أو المشروع مثل: تأكيد القبول الرسمي لعمل البائع ، وإنهاء المطالبات المفتوحة ، وتحديث السجلات لتعكس النتائج النهائية ، وأرشفة هذه المعلومات للاستخدام المستقبلي. [PMBOK الطبعة السادسة ، الصفحة 123] | 140 | 6 | False | "20" | Haitham
561 | As a project manager, in which document will you find information about Project Scope Description, Project Deliverables, and Project Exclusions? | Stakeholder register | Change log | Project charter | Scope baseline | Project scope description, project deliverables and project exclusions included in scope statement which a part of scope baseline. [PMBOK 6th edition, Page 161) | بصفتك مدير مشروع ، في أي مستند ستجد معلومات حول وصف نطاق المشروع وتسليمات المشروع واستثناءات المشروع؟ | سجل أصحاب المصلحة | سجل التغيير | ميثاق المشروع | خط الأساس المرجعي للنطاق | وصف نطاق المشروع ، وتسليمات المشروع واستثناءات المشروع تكون مدرجة في بيان النطاق الذي يعتبر جزءًا من خط الأساس المرجعي للنطاق. [PMBOK الطبعة السادسة ، الصفحة 161] | 141 | 3 | False | "19" | Haitham
562 | As project manager managing project, which of the following is an inputs for initiation processes? | Expert judgment | Requirements traceability matrix | Project management plan | Organizational process assets | Organizational process assets are inputs for developing the project charter process and identify the stakeholder process. [PMBOK 6th edition, Page 79]. | كمدير مشروع تدير مشروع، أي من التالي يعتبر من المدخلات لعمليات البدء؟ | حكم الخبير | مصفوفة تتبع المتطلبات | خطة إدارة المشروع | أصول العملية التنظيمية | أصول العملية التنظيمية هي مدخل لتطوير عملية ميثاق المشروع وتحديد عملية أصحاب المصلحة. [PMBOK الطبعة السادسة ، الصفحة 79]. | 140 | 2 | False | "16" | Haitham
563 | In which of the following types of contracts does the buyer have the maximum cost risk? | Fixed Price | Time and Material | Cost Plus Incentive Fee | Cost Reimbursable, | In a cost-reimbursable type of contract, the buyer has the maximum risk because the total cost of the project remains unknown. This is usually used when the buyer is not able to come up with a complete contract statement of work and has limited understanding. cost-plus fixed fee is the maximum cost risk for the buyer and included in cost reimbursable contract. In a Fixed Price Contract, the buyer has the least cost risk because any additional cost over and above the negotiated price has to be borne by the seller. [PMBOK 6th edition Page, 472]. | في أي من أنواع العقود التالية يتحمل المشتري أقصى مخاطر التكلفة؟ | السعر الثابت | الوقت والمواد | التكلفة بالإضافة إلى رسوم الحوافز | التكلفة المستردة | في عقد التكلفة المستردة، يتحمل المشتري أقصى قدر من المخاطر لأن التكلفة الإجمالية للمشروع لا تزال غير معروفة. يستخدم هذا عادةً عندما لا يكون المشتري قادرًا على تقديم بيان عمل كامل للعقد ولديه فهم محدود. التكلفة بالإضافة إلى الرسوم الثابتة هي الحد الأقصى لمخاطر التكلفة بالنسبة للمشتري ويتم تضمينها في عقد التكلفة القابلة للاسترداد. في عقد السعر الثابت، يتحمل المشتري أقل مخاطر للتكلفة لأن أي تكلفة إضافية تزيد عن السعر المتفاوض عليه يجب أن يتحمله البائع. [PMBOK الطبعة السادسة الصفحة، 472]. | 148 | 3 | False | "19" | Haitham
564 | A project manager notices that there is limited participation and contribution from a new team member. What should the project manager do? | Review the roles and responsibilities of each team member. | Discuss the situation with the project sponsor. | Write a complaint to the human resources department. | Discipline the new team member. | The Project manager should first (Discipline - Correction - Direction) the new team member because of his limited participation and contribution. Option (Review the roles and responsibilities of each team member) not correct because the project manager notices that there is limited participation and contribution from a new team member only not all the team members. The project manager should be proactive so option (Discuss the situation with the project sponsor & Write a complaint to the human resources department) not a good practices as a first step. [PMBOK 6th edition, Page 347]. | لاحظ مدير المشروع أن هناك مشاركة ومساهمة محدودة من عضو جديد في الفريق. ماذا يجب أن يفعل مدير المشروع؟ | راجع أدوار ومسؤوليات كل عضو في الفريق. | ناقش الوضع مع راعي المشروع. | اكتب شكوى إلى إدارة الموارد البشرية. | ضبط عضو الفريق الجديد. | يجب على مدير المشروع أولاً (الضبط - التصحيح - التوجيه) عضو الفريق الجديد بسبب مشاركته ومساهمته المحدودة. الخيار (مراجعة أدوار ومسؤوليات كل عضو في الفريق) غير صحيح لأن مدير المشروع لاحظ أن هناك مشاركة ومساهمة محدودة من العضو الجديد في الفريق فقط وليس كل أعضاء الفريق. يجب أن يكون مدير المشروع استباقيًا، لذلك الخيار (ناقش الموقف مع راعي المشروع و اكتب شكوى إلى قسم الموارد البشرية) ليس من الممارسات الجيدة كخطوة أولى. [PMBOK الطبعة السادسة، الصفحة 347]. | 145 | 4 | False | "19" | Haitham
565 | As project manager managing project, A conflict between the requirements is best resolved in favor of the: | Sponsor | Team members | Project manager's boss | Customer | The conflict between the requirements should always be resolved in favor of the Customer. [PMBOK 6th edition, Page 348]. | بصفتك مدير مشروع يدير المشروع ، من الأفضل حل التضارب بين المتطلبات لصالح: | راعي المشروع | أعضاء الفريق | رئيس مدير المشروع | العميل | يجب دائمًا حل التضارب بين المتطلبات لصالح العميل. [PMBOK الطبعة السادسة ، الصفحة 348]. | 145 | 4 | False | "19" | Haitham
566 | You are the project manager of a project to solve customer service problems in your marketing company. During the execution phase, several quality defects have been discovered, causing customer concern. You would like to create a chart showing the frequency of problems and the causes that have the largest number of defects. Which tool shows defects by volume from greatest to least? | Flowchart | Matrix diagrams | Ishikawa Diagram | Pareto Chart | A Pareto chart is a specific type of histogram that ranks causes or Issues by their overall influence. A Pareto chart assists in prioritizing corrective actions as the issues with the greatest impact are displayed in order. [PMBOK 6th edition, Page 293]. | أنت مدير مشروع لحل مشاكل خدمة العملاء في شركة التسويق الخاصة بك. خلال مرحلة التنفيذ تم اكتشاف العديد من عيوب الجودة، مما تسبب في قلق العملاء. ترغب في إنشاء مخطط يوضح تكرار المشكلات والأسباب التي بها أكبر عدد من العيوب. ما الأداة التي تعرض العيوب بالحجم من الأكبر إلى الأقل؟ | المخططات الإنسيابية | المخططات المصفوفية | مخطط إيشيكاوا | مخطط باريتو | مخطط باريتو هو نوع معين من أنواع المدرج التكراري (histogram) الذي يصنف الأسباب أو المشكلات حسب تأثيرها العام. يساعد مخطط باريتو في تحديد أولويات الإجراءات التصحيحية حيث يتم عرض المشكلات ذات التأثير الأكبر بالترتيب. [PMBOK الطبعة السادسة ، الصفحة 293]. | 144 | 4 | False | "20" | Haitham
567 | As project manager managing project, You are in the process of finalizing all activities for the project, phase, or contract. Which of the following documents include information about objectives of Scope, Quality and Cost and the criteria used to evaluate them? | Risk Register | Project Charter | Scope Management Plan | Final Report | Final Report includes information about Objectives of Scope, Quality and Cost and the criteria used to evaluate them. [PMBOK 6th edition, Page 127] | بصفتك مدير مشروع يدير المشروع ، فأنت بصدد إنهاء جميع الأنشطة الخاصة بالمشروع أو المرحلة أو العقد. أي من المستندات التالية تتضمن معلومات حول أهداف النطاق والجودة والتكلفة والمعايير المستخدمة لتقييمها؟ | سجل المخاطر | ميثاق المشروع | خطة إدارة النطاق | التقرير النهائي | يتضمن التقرير النهائي معلومات حول أهداف النطاق والجودة والتكلفة والمعايير المستخدمة لتقييمها. [PMBOK الطبعة السادسة ، الصفحة 127] | 140 | 6 | False | "19" | Haitham
568 | As project manager managing project, in which of the following estimating technique that uses a statistical relationship between historical data and project parameters to calculate the activity duration? | Three-Point estimating | Bottom-up estimating | Top-down estimating | Parametric estimating | Parametric estimating is an estimating technique in which an algorithm is used to calculate cost or duration based on historical data and project parameters. Parametric estimating uses a statistical relationship between historical data and other variables (e.g., square footage in construction) to calculate an estimate for activity parameters, such as cost, budget, and duration. (PMBOK 6th edition, Page 200] | كمدير مشروع، في أي من أساليب التقدير التالية تستخدم علاقة إحصائية بين البيانات التاريخية ومعلمات المشروع لحساب مدة النشاط؟ | تقدير الثلاث نقاط | التقدير التصاعدي | التقدير التنازلي | التقدير بالمحددات | التقدير البارامترى أو بالمحددات هو أسلوب تقدير يتم فيه استخدام خوارزمية لحساب التكلفة أو المدة بناءً على البيانات التاريخية ومحددات المشروع. يستخدم التقدير البارامتري علاقة إحصائية بين البيانات التاريخية والمتغيرات الأخرى (على سبيل المثال ، القدم المربعة في البناء) لحساب تقدير محددات النشاط، مثل التكلفة والميزانية والمدة. [PMBOK الطبعة السادسة ، الصفحة 200] | 142 | 3 | False | "19" | Haitham
569 | A project manager for a application development project has collected the work performance data and used the requirements documentation and requirements traceability matrix to generate the work performance information regarding variances in the project work compared to the baseline. What process is the project manager performing? | Validate Scope | Manage Quality | Direct and Manage Project Work | Control Scope | It is important to understand how work performance data is transformed into work performance information. Work performance data is produced as a result of project execution. The work performance data can then be analyzed during various controlling processes to produce work performance information. Work performance information is only produced as an output from Monitoring and Controlling processes group. In this scenario, the question suggests that a variance analysis has been performed using work performance data in order to produce work performance information. Thus, it can be concluded that the process underway is part of the Monitoring and Controlling Process Group, and the two answer choices representing executing processes can be eliminated. Both the Validate Scope and Control Scope processes produce work performance information, but since the project manager reviews the variance in project work compared to baselines, so the correct choice is Control Scope process. [PMBOK 6th edition, Page 170 ]. | قام مدير مشروع لمشروع تطوير تطبيق، بجمع بيانات أداء العمل واستخدم وثائق المتطلبات ومصفوفة تتبع المتطلبات لإنشاء معلومات أداء العمل فيما يتعلق بالتباينات في عمل المشروع مقارنة بخط الأساس. ما هي العملية التي يقوم بها مدير المشروع؟ | التحقق من النطاق | إدارة الجودة | توجيه وإدارة أعمال المشروع | التحكم بالنطاق | من المهم فهم كيفية تحويل بيانات أداء العمل إلى معلومات أداء العمل. يتم إنتاج بيانات أداء العمل كنتيجة لتنفيذ المشروع. يمكن بعد ذلك تحليل بيانات أداء العمل أثناء عمليات التحكم المختلفة لإنتاج معلومات أداء العمل. يتم إنتاج معلومات أداء العمل فقط كمخرجات من مجموعة عمليات المراقبة والتحكم. في هذا السيناريو ، يشير السؤال إلى أنه تم إجراء تحليل التباين باستخدام بيانات أداء العمل من أجل إنتاج معلومات أداء العمل. وبالتالي ، يمكن استنتاج أن العملية الجارية هي جزء من مجموعة عمليات المراقبة والتحكم ، ويمكن التخلص من خياري الإجابة اللذين يمثلان عمليات التنفيذ. تنتج عمليتا التحقق من النطاق و التحكم بالنطاق معلومات أداء العمل، ولكن بما أن مدير المشروع يراجع التباين في عمل المشروع مقارنة بخطوط الأساس فإن الخيار الصحيح هو عملية التحكم بالنطاق. [PMBOK الطبعة السادسة، الصفحة 170]. | 141 | 5 | False | "18" | Haitham
570 | Your project sponsor has Informed you that you have to consider the external limitations during the develop schedule process. This is an example of: | Assumptions | Regulations | Standards | Constraints | The external limitation is an example of Constraints [PMBOK 6th edition, Page 207]. | أبلغك راعي مشروعك أنه يجب عليك مراعاة المحددات الخارجية أثناء عملية تطوير الجدول الزمني. هذا مثال على: | الافتراضات | اللوائح | المعايير | القيود | المحددات الخارجية هي مثال على القيود [PMBOK الطبعة السادسة، الصفحة 207]. | 142 | 3 | False | "20" | Haitham
571 | As project manager managing project, you are in the process of creating tailored reports for project stakeholders. You are reviewing various plans and project documents but find something important missing in order to get the details to do this. What could it be? | The scope baseline | Issues escalated downward from the program level | Issues escalated upward to the program level | Work performance reports | The work performance report Is tailored as per stakeholder needs in the manage communications process. Work performance reports are circulated to the project stakeholders through this process as defined in the communications management plan. Examples of work performance reports include status reports and progress reports. Work performance reports can contain earned value graphs and information, trend lines and forecasts, reserve burndown charts, defect histograms, contract performance information, and risk summaries. They can be presented as dashboards, heat reports, stop light charts, or other representations useful for creating awareness and generating decisions and actions.[PMBOK 6th edition, Page 382] | بصفتك مدير مشروع يدير المشروع ، فأنت بصدد إنشاء تقارير مخصصة لأصحاب المصلحة في المشروع. أنت تقوم بمراجعة الخطط ووثائق المشروع المختلفة ولكنك تجد شيئًا مهمًا مفقودًا للحصول على التفاصيل للقيام بذلك. ماذا يمكن أن يكون؟ | خط الأساس للنطاق | المشاكل المصعدة للأسفل من مستوى البرنامج | المشاكل المصعدة لأعلى لمستوى البرنامج | تقارير أداء العمل | يتم تخصيص تقرير أداء العمل وفقًا لاحتياجات أصحاب المصلحة في عملية إدارة الاتصالات. يتم توزيع تقارير أداء العمل على أصحاب المصلحة في المشروع من خلال هذه العملية على النحو المحدد في خطة إدارة الاتصالات. تتضمن أمثلة تقارير أداء العمل تقارير الوضع الحالي وتقارير الأداء. يمكن أن تحتوي تقارير أداء العمل على رسوم بيانية ومعلومات للقيمة المكتسبة، وخطوط الاتجاه والتنبؤات، ومخططات الاحتياطي المتبقي، ومخططات العيوب، ومعلومات أداء العقد، وملخصات المخاطر. يمكن تقديمها على شكل لوحات أداء، أو تقارير مطبوعة، أو مخططات توقف، أو تمثيلات أخرى مفيدة لخلق الوعي وتوليد القرارات والإجراءات. [PMBOK الطبعة السادسة، الصفحة 382] | 146 | 4 | False | "19" | Haitham
572 | A Project Manager is in the process of preparing a plan that documents how the procurement process will be managed: from developing procurement documents to contract closure. She is also going through project requirements and scope documents with the team and discussing different contract types to decide the one most suitable for the project. According to you, which process of procurement management is the Project Manager in? | Conduct Procurements | Control Procurements | Close Procurements | Plan Procurement Management | The Project Manager is in the 'plan procurement management' process, and she is preparing the procurement management plan with her team. Contract types are also important tools of this process, which is carried at the planning stage of the project. [PMBOK 6th edition, Page 466] | مديرة مشروع في طور إعداد خطة توثق كيفية إدارة عملية الشراء، من تطوير مستندات الشراء إلى إقفال العقد. كما أنها تقوم بمراجعة متطلبات المشروع ووثائق النطاق مع الفريق وتناقش أنواع العقود المختلفة لتحديد النوع الأكثر ملاءمة للمشروع. حسب رأيك ، ما هي العملية من عمليات إدارة المشتريات التي تعمل عليها مديرة المشروع؟ | إدارة المشتريات | التحكم بالمشتريات | إغلاق المشتريات | خطة إدارة المشتريات | تعمل مديرة المشروع في عملية "التخطيط لإدارة المشتريات" ، وتقوم بإعداد خطة إدارة المشتريات مع فريقها. تعد أنواع العقود أيضًا أدوات مهمة لهذه العملية ، والتي يتم تنفيذها في مرحلة التخطيط للمشروع. [PMBOK الطبعة السادسة ، الصفحة 466] | 148 | 3 | False | "20" | Haitham
573 | You are a project manager for a application design project. Which of the following data representation techniques that can be used in understanding and estimating the cost of quality for a process? | Logical data model | Matrix diagrams | Prioritization matrix | Process maps | Flowcharts are also referred to as process maps because they display the sequence of steps and the branching possibilities that exist for a process that transforms one Or more inputs into one or more outputs. Flowcharts may prove useful in understanding and estimating the cost of quality for a process. [PMBOK 6th edition, Page 284] | أنت مدير مشروع لمشروع تصميم تطبيق. أي من تقنيات تمثيل البيانات التالية يمكن استخدامها في فهم وتقدير تكلفة الجودة لعملية ما؟ | نموذج البيانات المنطقية | المخططات المصفوفية | مصفوفة تحديد الأولويات | خرائط العمليات | يشار إلى المخططات الانسيابية أيضًا باسم خرائط العمليات لأنها تعرض تسلسل الخطوات وإمكانيات التفرع الموجودة لعملية تقوم بتحويل مدخل واحد أو أكثر إلى واحد أو أكثر من المخرجات. قد تكون المخططات الانسيابية مفيدة في فهم وتقدير تكلفة الجودة لعملية ما. [PMBOK الطبعة السادسة ، الصفحة 284] | 144 | 3 | False | "20" | Haitham
574 | You have overheard two functional managers arguing about the impacts that your project will have on their departments. What is your best response? | Do nothing | Inform the managers that the project sponsors already consider impact when they decided to implement the project | Put in advance requests for resources from each department | Analyze and report to each manager the impact your project will have on their departments in terms of time and resources required and the enterprise priority of your project. | Analyze and report to each manager the impact your project will have on their departments. This will not only help the functional managers to plan proactively for those times of resources will be required by your project, it will also ease hostility and promote cooperation among staff. PMI's Code of Conduct mandates that project managers act in good faith and provide timely and accurate information to affected stakeholders. [PMI Code of Ethics and Professional Conduct] [Prof. Responsibility] [PMBOK 6th edition, Page 523] | لقد سمعت بالصدفة مديرين وظيفيين يتجادلان حول تأثيرات مشروعك على أقسامهم. ما هو أفضل رد لك؟ | لا تفعل شيئا | أبلغ المديرين أن رعاة المشروع يفكرون بالفعل في التأثير عندما قرروا تنفيذ المشروع | تقديم طلبات مسبقة للحصول على الموارد من كل قسم | قم بتحليل وإبلاغ كل مدير بالتأثير الذي سيحدثه مشروعك على إداراتهم من حيث الوقت والموارد المطلوبة وأولوية مشروعك بالنسبة للمنظمة. | قم بتحليل وإبلاغ كل مدير بالتأثير الذي سيحدثه مشروعك على أقسامهم. لن يساعد ذلك المديرين الفنيين على التخطيط بشكل استباقي للأوقات التي يتطلب فيها مشروعك الموارد فحسب، بل سيخفف أيضًا من العداء ويعزز التعاون بين الموظفين. تلزم مدونة قواعد السلوك الخاصة بمعهد إدارة المشاريع PMI مديري المشاريع بالتصرف بحسن نية وتقديم معلومات دقيقة وفي الوقت المناسب لأصحاب المصلحة المتضررين. [مدونة الأخلاق والسلوك المهني لدى معهد إدارة المشاريع] [المسؤولية المهنية] [PMBOK الطبعة السادسة، الصفحة 523] | 149 | 4 | False | "18" | Haitham
575 | A large construction project for a logistics company will require the expenditure of a large amount of capital. The finance group works with the project manager to set project limits when expenses will be incurred in a given project and to determine whether there are ways to smooth out or level the spending to avoid a single large expenditure in one quarter and none in the next. This is an example of: | Levelized Billing | A financial review | Rescheduling | Funding Limit Reconciliation | Large variations in the periodic expenditure of funds are usually undesirable for organizational operations. Therefore, the expenditure of funds is reconciled with the funding limits set by the customer or performing organization on the disbursement of funds for the project. [PMBOK 6th edition, Page 253] | سيتطلب مشروع بناء كبير لشركة لوجستية إنفاق مبلغ كبير من رأس المال. تعمل المجموعة المالية مع مدير المشروع لوضع حدود للمشروع عند بدء المصروفات ولتحديد ما إذا كانت هناك طرق لتجانس الإنفاق أو تسويته لتجنب النفقات الكبيرة في أحد الأرباع خلال العام وعدم وجود إنفاق عالي في الربع الذي يليه. هذا مثال على: | الفواتير المستوية | مراجعة مالية | إعادة جدولة | الملائمة مع حدود التمويل | عادة ما تكون الاختلافات الكبيرة في الإنفاق الدوري للأموال غير مرغوب فيها للعمليات في المنظمة. لذلك تتم ملائمة إنفاق الأموال مع حدود التمويل التي وضعها العميل أو المؤسسة المنفذة والتي تصرف الأموال للمشروع. [PMBOK الطبعة السادسة ، الصفحة 253] | 143 | 3 | False | "20" | Haitham
576 | Calculation of late finish dates and late start dates for the uncompleted portion of the project is called. | Schedule compression | An arrow diagram | A forward pass | A backward pass | Calculation of late finish dates and late start dates for the uncompleted portion of the project is called a backward pass. [PMBOK 6th edition, Page 210] | حساب تواريخ الانتهاء المتأخرة وتواريخ البدء المتأخرة للجزء الغير مكتمل من المشروع، يسمى بـ: | ضغط الجدول الزمني | مخطط الأسهم | المسار الأمامي | المسار العكسي | يُطلق على حساب تواريخ الانتهاء المتأخرة وتواريخ البدء المتأخرة للجزء غير المكتمل من المشروع باسم المسار العكسي. [PMBOK الطبعة السادسة ، الصفحة 210] | 142 | 3 | False | "19" | Haitham
577 | While rating a proposal, one of the requirements was: "The proposed project manager needs to be a certified Project Management Professional, PMP®" This is an example of: | Constraints | Assumptions | Good practice | Source Selection Criteria | This is an example of source selection criteria used to rate or score proposals. [PMBOK 6th edition, Page 478] | أثناء تقييم العروض، كان أحد المتطلبات: "يجب أن يكون مدير المشروع المقترح محترف معتمد في إدارة المشاريع PMP®". هذا مثال على: | القيود | الافتراضات | ممارسة جيدة | معايير اختيار المصدر | هذا مثال على معايير اختيار المصدر المستخدمة لتقييم أو تسجيل الدرجات لعروض المتنافسين. [PMBOK الطبعة السادسة، الصفحة 478] | 148 | 3 | False | "19" | Haitham
578 | A decision tree is a Perform Quantitative Risk Analysis technique. A decision tree is represented by a Decision Tree Diagram. The decision tree describes a situation under consideration, the implications of each of the available choices, and the possible scenarios. A Decision Tree Diagram shows how to make a decision among alternative capital strategies known as: | Alternative nodes | Question points | Checkpoints | Decision nodes | The decision points are known as decision nodes. The decision tree incorporates the cost of each available choice, the possibilities of each of the available choices, and possible scenarios. It shows how to make a decision among alternative capital strategies (decision nodes) when the environment is not known with certainty. [PMBOK 6th edition, Page 435] | شجرة القرار هي تقنية تنفيذ التحليل الكمي للمخاطر. يتم تمثيل شجرة القرار بواسطة مخطط شجرة القرار. تصف شجرة القرار موقف قيد الدراسة، والآثار المترتبة على كل من الخيارات المتاحة، والسيناريوهات المحتملة. يوضح مخطط شجرة القرار كيفية اتخاذ قرار بين استراتيجيات مالية بديلة تعرف باسم: | العقد البديلة | نقاط السؤال | نقاط تفتيش | عقد القرار | تُعرف نقاط القرار باسم عقد القرار. تتضمن شجرة القرار تكلفة كل خيار متاح وإمكانيات كل من الخيارات المتاحة والسيناريوهات المحتملة. يوضح كيفية اتخاذ قرار بين استراتيجيات مالية بديلة (عقد القرار) عندما لا تكون البيئة الحالية وضحة. [PMBOK الطبعة السادسة ، الصفحة 435] | 147 | 3 | False | "20" | Haitham
579 | Which of the following processes deals with maintaining the integrity of baselines by releasing only approved changes for incorporation into the project management plan? | Direct and Manage Project Work | Develop Project Management Plan | Monitor and Control Project Work | Perform Integrated Change Control | Maintaining the integrity of baselines is done in the Perform Integrated Change Control process. This process is conducted from project inception through project completion. [PMBOK 6th edition, Page 113] | أي من العمليات التالية تعمل على المحافظة على صحة خطط الأساس المرجعية من خلال إصدار التغييرات المعتمدة فقط لإدراجها في خطة إدارة المشروع؟ | توجيه وإدارة أعمال المشروع | تطوير خطة إدارة المشروع | التحكم ومراقبة أعمال المشروع | تنفيذ التحكم المتكامل بالتغييرات | يتم الحفاظ على صحة خطط الأساس في عملية تنفيذ التحكم المتكامل بالتغييرات. تتم هذه العملية من بداية المشروع وحتى اكتماله. [PMBOK الطبعة السادسة، الصفحة 113]. | 140 | 5 | False | "19" | Haitham
580 | The Manage Stakeholder Engagement process is a very important project management process. An ineffective effort in this process can sabotage the whole project. Which of the following is the key benefit of this process? | It makes the Manage Communications process redundant. | It produces the stakeholder engagement plan. | Lessons learned are documented during this process. | It increases support and minimizes resistance from stakeholders. | Lessons learned can be documented during any project management process. The key benefit of the Manage Stakeholder Engagement process is that it allows the project manager to increase support and minimize resistance from stakeholders, significantly increasing the changes to achieve project success. [PMBOK 6th edition, Page 523] | تعد عملية إدارة مشاركة أصحاب المصلحة عملية مهمة للغاية لإدارة المشروع. الجهد غير الفعال في هذه العملية يمكن أن يخرب المشروع بأكمله. أي مما يلي هو الفائدة الرئيسية لهذه العملية؟ | يجعل عملية إدارة الاتصالات زائدة عن الحاجة. | ينتج خطة إشراك أصحاب المصلحة. | يتم توثيق الدروس المستفادة خلال هذه العملية. | يزيد الدعم ويقلل من مقاومة أصحاب المصلحة. | يمكن توثيق الدروس المستفادة خلال أي عملية خلال إدارة مشروع. تتمثل الميزة الرئيسية لعملية إدارة مشاركة أصحاب المصلحة في أنها تتيح لمدير المشروع زيادة الدعم وتقليل المقاومة من أصحاب المصلحة ، مما يزيد بشكل كبير من التغييرات لتحقيق نجاح المشروع. [PMBOK الطبعة السادسة ، الصفحة 523] | 149 | 4 | False | "19" | Haitham
581 | In projects where there is a gap between the real business requirements and the stated business requirements, agile methods are extremely helpful. Agile methods provide a solution to this problem by: | Completing the project quickly so that gap is significantly reduced. | Replacing the project manager with a scrum master in order to execute the project. | Eliminating the documentation altogether from the project manage approach. | Purposefully building and reviewing prototypes and release version refine requirements. | Agile methods purposefully build and review prototypes and release versions in order to refine the requirements. As a result, scope is defined and redefined throughout the project. [PMBOK 6th edition, Page 133] [Prof. Responsibility] | في المشاريع التي توجد فيها فجوة بين متطلبات العمل الحقيقية ومتطلبات العمل المذكورة، تكون المنهجيات الرشيقة مفيدة للغاية. توفر المنهجيات الرشيقة حلاً لهذه المشكلة عن طريق: | استكمال المشروع بسرعة بحيث تقل الفجوة بشكل كبير. | استبدال مدير المشروع بـ سكرم ماستر Scrum Master من أجل تنفيذ المشروع. | إزالة الوثائق تمامًا من نهج إدارة المشروع. | بناء النماذج الأولية ومراجعتها بشكل هادف وإصدار متطلبات تحسين الإصدارات. | تعمل المنهجيات الرشيقة على بناء النماذج الأولية ومراجعتها بشكل هادف وإصدار متطلبات تحسين الإصدارات. نتيجة لذلك ، يتم تحديد النطاق وإعادة تعريفه خلال كامل المشروع. [PMBOK الطبعة السادسة، الصفحة 133] [المسئولية المهنية] | 141 | 3 | False | "20" | Haitham
582 | Ahmad is the project manager for a shopping mall construction project which is in its fourth month of execution. According to the project contract, Ahmad can only issue project invoices when the project is 25%, 50%, 75% and 100% complete in terms of the approved project schedule. Recently the 25% milestone has been reached and Ahmad is ready to issue his first invoice. According to the contract, the project must be completed in 12 months. What is the project’s SPI? | 0.25 | 0.33 | 1.33 | 0.75 | Since the 25% schedule milestone has been achieved, the project’s earned schedule (ES) is 25%. Further the project is in its third month of execution so the actual time is 33.33% (i.e. 4 months / 12 months). SPI = ES / AT = 25% / 33.33% = 0.75 [PMBOK 6th edition, Page 233] | أحمد هو مدير مشروع بناء مركز تجاري في الشهر الرابع من تنفيذه. وفقًا لعقد المشروع ، لا يمكن لأحمد إصدار فواتير المشروع إلا عندما يكتمل المشروع بنسبة 25٪ و 50٪ و 75٪ و 100٪ من حيث الجدول الزمني المعتمد للمشروع. تم الوصول مؤخرًا إلى نسبة 25٪، وأصبح أحمد مستعدًا لإصدار فاتورته الأولى. وفقًا للعقد ، يجب الانتهاء من المشروع خلال 12 شهرًا. ما هو SPI للمشروع؟ | 0.25 | 0.33 | 1.33 | 0.75 | منذ أن تم تحقيق 25٪ من الجدول الزمني ، فإن الجدول الزمني المكتسب للمشروع (ES) هو 25٪. علاوة على ذلك ، فإن المشروع في الشهر الثالث من التنفيذ وبالتالي فإن الوقت الفعلي هو 33.33٪ (أي 4 أشهر / 12 شهرًا). SPI = ES / AT = 25٪ / 33.33٪ = 0.75 [PMBOK الطبعة السادسة ، الصفحة 233] | 142 | 5 | False | "20" | Haitham
583 | Visiting a construction site to ensure the completed work is the same work specified in the requirements is: | Milestone | Variance Analysis | Requirements traceability | Scope validation | Inspection is a scope validation technique that includes activities (such as measuring, examining, and verifying) to determine whether work and deliverables meet requirements and product acceptance criteria. [PMBOK 6th edition, Page 163] | زيارة موقع البناء للتأكد من أن العمل المنجز هو نفس العمل المحدد في المتطلبات هو: | معلم أو حدث هام | تحليل التباين | تتبع المتطلبات | التحقق من النطاق | التفتيش هو أسلوب للتحقق من النطاق يتضمن أنشطة (مثل القياس والفحص والتحقق) لتحديد ما إذا كان العمل والتسليمات تفي بالمتطلبات ومعايير قبول المنتج. [PMBOK الطبعة السادسة ، الصفحة 163] | 141 | 5 | False | "20" | Haitham
584 | While reviewing project procurement and accounting records for your project, you discover there is a pattern of unauthorized expenses by a specific resource. These expenses are not within the scope of the project and were somewhat camouflaged within a number of large and complicated expense reports. What do you do? | If the total expenses are less than 1% of the project budget do nothing | Fire the resource | Confront the resource | Notify the appropriate management immediately | Notify the appropriate management of the unauthorized expenses. Project managers are required by PMI's Code of Ethics to report any unethical or illegal behaviors or activities to the appropriate management. Not doing so violates the PMI code. [PMI Code of Ethics and Professional Conduct] [Prof. Responsibility] [PMBOK 6th edition, Page 492] | أثناء مراجعة سجلات المشتريات والمحاسبة لمشروعك ، تكتشف أن هناك نمطًا من النفقات غير المصرح بها من قبل مورد معين. هذه النفقات ليست ضمن نطاق المشروع وقد تم تمويهها إلى حد ما في عدد من تقارير النفقات الكبيرة والمعقدة. ماذا عليك أن تفعل؟ | إذا كانت النفقات الإجمالية أقل من 1٪ من ميزانية المشروع فلا تفعل شيئًا | أطرد المورد | واجه المورد | قم بإخطار الإدارة المناسبة على الفور | إخطار الإدارة المناسبة بالنفقات غير المصرح بها. يطلب من مديري المشاريع بموجب مدونة الأخلاقيات الخاصة بمعهد إدارة المشاريع الإبلاغ عن أي سلوكيات أو أنشطة غير أخلاقية أو غير قانونية إلى الإدارة المناسبة. عدم القيام بذلك ينتهك كود PMI. [مدونة الأخلاق والسلوك المهني لدى معهد إدارة المشاريع] [المسؤولية المهنية] [PMBOK الطبعة السادسة، الصفحة 492] | 148 | 5 | False | "20" | Haitham
585 | A project to design and build a new building is canceled after the project has been underway for some time. What process is employed to document what work was done and to what extent it was completed? | Validate Scope | Control Scope | Control Quality | Close Project or Phase | If the project is terminated early, the Close Project or Phase process should establish and document the level and extent of completion. [PMBOK 6th edition, Page 121] | تم إلغاء مشروع تصميم وبناء مبنى جديد بعد أن استمر المشروع لبعض الوقت. ما هي العملية المستخدمة لتوثيق ما تم إنجازه وإلى أي مدى تم الانتهاء منه؟ | التحقق من النطاق | التحكم بالنطاق | التحكم بالجودة | أغلاق المشروع أو المرحلة | إذا تم إنهاء المشروع مبكرًا ، فيجب أن تبدأ عملية إغلاق المشروع أو المرحلة ويتم توثيق مستوى ومدى الإنجاز. [PMBOK الطبعة السادسة ، الصفحة 121] | 140 | 6 | False | "20" | Haitham
586 | You are managing a project that requires an environmental permit to do work. The approval is in the final stages. A confidential, reliable report is brought to your notice. The report indicates there is a high risk of an environmental hazard due to the project. Your manager tells you it is better to keep quiet at this stage since losses from terminating the project might be very high. You must: | Send an email to your manager documenting the matter and disclaimer ownership of the project. | Wait for the project to start and see if the information in the report is true. | Keep quiet about the matter since you will follow your man instructions. | Inform the necessary authorities of the hazard, even if it means canceled the project. | The best option is to inform the necessary authorities about the report so that the right decision can be made, even if it means the project will be cancelled. [PMI Code of Ethics and Professional Conduct] [Prof. Responsibility] [PMBOK 6th edition, Page 90] | أنت تدير مشروعًا يتطلب تصريحًا بيئيًا للقيام بالعمل. الموافقات في المراحل النهائية. تم إحضار تقرير سري وموثوق إليك، يشير التقرير إلى وجود مخاطر بيئية عالية بسبب المشروع. يخبرك مديرك أنه من الأفضل التزام الصمت في هذه المرحلة لأن الخسائر من إنهاء المشروع قد تكون عالية جدًا. يجب عليك أن: | أرسل بريدًا إلكترونيًا إلى مديرك لتوثيق الأمر وإخلاء المسؤولية عن المشروع. | انتظر حتى يبدأ المشروع وتحقق مما إذا كانت المعلومات الواردة في التقرير صحيحة. | ابق هادئًا بشأن هذا الأمر لأنك ستتبع تعليمات مديرك. | إبلاغ الجهات المختصة بالمخاطر، حتى لو كانت تعني إلغاء المشروع. | الخيار الأفضل هو إبلاغ السلطات اللازمة بالتقرير حتى يمكن اتخاذ القرار الصحيح ، حتى لو كان ذلك يعني إلغاء المشروع. [مدونة الأخلاق والسلوك المهني لمعهد إدارة المشاريع] [المسؤولية المهنية] [PMBOK الطبعة السادسة، الصفحة 90] | 140 | 4 | False | "20" | Haitham
587 | A Work Breakdown Structure is a hierarchical illustration of all the work to be done in a project. A WBS component does not represent: | Products | Results | Services | Project activities | Upper level WBS components are decomposed into more easily managed elements and can be process- or product-oriented. The lowest level of the WBS is the work packages. The project activities are obtained by further decomposing the work packages. The activities become a part of the project schedule and not the WBS. [PMBOK 6th edition, Page 156] | هيكل تقسيم العمل عبارة عن توضيح هرمي لجميع الأعمال التي يتعين القيام بها في المشروع. مكونات الـ WBS لا تضهر: | المنتجات | النتائج | الخدمات | أنشطة المشروع | تفكك مكونات هيكل تجزئة العمل WBS ذات المستوى العلوي إلى عناصر تتم إدارتها بسهولة أكبر ويمكن أن تكون موضوعة على أساس العمليات أو المنتجات. أدنى مستوى من WBS هو حزم العمل. يتم الحصول على أنشطة المشروع من خلال مزيد من التفكيك لحزم العمل. تصبح الأنشطة جزءًا من جدول المشروع وليست من الـ WBS. [PMBOK الطبعة السادسة ، الصفحة 156] | 141 | 3 | False | "19" | Haitham
588 | Which of the following is not a Risk Diagramming technique? | Influence diagrams | Decision trees | Tornado diagram | Control charts | Control charts is not a Risk Diagramming technique, it's a control technique used in Quality Management. [PMBOK 6th edition, Page 395] | أي مما يلي لا يعد تقنية لتمثيل المخاطر برسم بياني؟ | مخططات التأثير | شجرة القرار | مخطط تورنادو | مخططات التحكم | مخططات التحكم ليست تقنية تخطيط مخاطر ، إنها تقنية تحكم مستخدمة في إدارة الجودة. [PMBOK الطبعة السادسة ، الصفحة 395] | 147 | 3 | False | "19" | Haitham
589 | The Cost of Quality principle includes: | The costs involved when changes are made to the requirements | The cost of deploying a project configuration management system | The costs associated with eliminating requirements | The costs of ensuring conformance to requirements | Quality costs are the total costs incurred by investment in preventing nonconformance to requirements, appraising the product or service for conformance to requirements, and failing to meet requirements (rework). [PMBOK 6th edition, Pages 240] | يشمل مبدأ تكلفة الجودة ما يلي: | التكاليف المتضمنة عند إجراء تغييرات على المتطلبات | تكلفة تطبيق نظام إدارة تكوين المشروع | التكاليف المرتبطة بإلغاء المتطلبات | تكاليف ضمان التوافق مع المتطلبات | تكاليف الجودة هي إجمالي التكاليف التي تصرف لمنع عدم المطابقة للمتطلبات ، وتقييم المنتج أو الخدمة للتوافق مع المتطلبات ، والفشل في تلبية المتطلبات (إعادة العمل). [PMBOK الطبعة السادسة، الصفحة 240] | 143 | 3 | False | "19" | Haitham
590 | You are working for a large project organization with several project managers working on 15 projects. All project managers submit their status reports at month’s end. One of your fellow project managers, Nada, has reported an error in the past two months. From discussions with one of her project’s team members who is also working on one of your projects, you realize Nada is deliberately misreporting the project’s status to inflate her performance for the annual performance appraisal next month. The month end review meeting is in two days, and you are preparing your own presentation for it. What should you say about her status report? | Since there is no direct relationship between your project and hers, there is no need to intervene in this issue. | Prepare a brief of what you have discussed with her team member and report the inconsistency in the meeting. | Send an email to her boss asking to check the contents of her report. | Investigate and verify the blame before reporting the incorrect status to the appropriate management. | Investigate and verify the blame before reporting the incorrect status to the appropriate management. Project managers are required by PMI's Code of Ethics to provide truthful and accurate information, and to report errors and omissions of others to the appropriate management. [PMI Code of Ethics and Professional Conduct] [Prof. Responsibility] [PMBOK 6th edition, Page 105] | أنت تعمل في شركة مشاريع كبيرة مع العديد من مدراء المشاريع الذين يعملون في 15 مشروعًا. يرسل جميع مدراء المشاريع تقارير حالة المشاريع الخاصة بهم في نهاية الشهر. رفعت ندى، إحدى مدراء المشاريع من زملائك، خطأ في الشهرين الماضيين. من خلال المناقشات مع أحد أعضاء فريق مشروعها الذي يعمل أيضًا على أحد مشاريعك، أدركت أن ندى تعمدت تقديم تقارير خاطئة عن حالة المشروع لتضخيم أدائها من أجل تقييم الأداء السنوي الشهر المقبل. سيكون اجتماع مراجعة نهاية الشهر بعد يومين ، وأنت تقوم بإعداد العرض التقديمي الخاص بك له. ماذا يجب أن تقول عن تقرير حالتها؟ | نظرًا لعدم وجود علاقة مباشرة بين مشروعك ومشروعها ، فلا داعي للتدخل في هذه القضية. | قم بإعداد موجز لما ناقشته مع عضو فريقها وأبلغ عن التناقض في الاجتماع. | أرسل بريدًا إلكترونيًا إلى رئيسها تطلب فيه التحقق من محتويات تقريرها. | البحث والتحقق من الخطأ الوارد قبل الإبلاغ عن الحالة غير الصحيحة إلى الإدارة المناسبة. | البحث والتحقق من الخطأ الوارد قبل الإبلاغ عن الحالة غير الصحيحة إلى الإدارة المناسبة. يطلب من مديري المشاريع بموجب مدونة الأخلاقيات الخاصة بمعهد إدارة المشاريع تقديم معلومات صادقة ودقيقة ، والإبلاغ عن أخطاء وسهو الآخرين إلى الإدارة المناسبة. [مدونة الأخلاق والسلوك المهني لدى معهد إدارة المشاريع] [المسؤولية المهنية] [PMBOK الطبعة السادسة، الصفحة 105] | 140 | 5 | False | "20" | Haitham
591 | You are in the middle of a risk assessment meeting with key stakeholders, customers and project team leaders. While identifying and assessing risks, you realize that two key stakeholders are overemphasizing the impact of a risk. What is the best step to take to avoid unfairness or bias when assessing risks? | Implement assumptions analysis to explore the validity of assumptions. | Develop a risk response strategy to eliminate threats. | Perform sensitivity analysis to establish which risks have the most impact on the project. | Engage a neutral facilitator to support the Perform Qualitative Risk Analysis process. | Engaging a neutral facilitator to support the Perform Qualitative Risk Analysis process should help address bias. [PMBOK 6th edition, Page 420] | أنت في منتصف اجتماع لتقييم المخاطر مع أصحاب المصلحة الرئيسيين والعملاء وقادة فريق المشروع. أثناء تحديد وتقييم المخاطر ، تدرك أن اثنين من أصحاب المصلحة الرئيسيين يبالغون في التأكيد على تأثير المخاطر. ما هي أفضل خطوة يجب اتخاذها لتجنب عدم الصحة أو التحيز عند تقييم المخاطر؟ | تنفيذ تحليل الافتراضات لاستكشاف صحة الافتراضات. | تطوير استراتيجية الاستجابة للمخاطر للقضاء على التهديدات. | قم بإجراء تحليل الحساسية لتحديد المخاطر التي لها أكبر تأثير على المشروع. | قم بإشراك ميسّر محايد لدعم عملية إجراء التحليل النوعي للمخاطر. | يجب أن يساعد إشراك ميسّر محايد لدعم عملية إجراء التحليل النوعي للمخاطر في معالجة التحيز. [PMBOK الطبعة السادسة ، الصفحة 420] | 147 | 3 | False | "20" | Haitham
592 | There is a heavy demand for new houses in your city's expensive neighborhood. Turner, a construction company, has employed you as a project manager to assess the benefit of building new energy-efficient houses in that neighborhood, even though it takes more expensive technology to build such houses. You have started gathering data to perform a detailed payback analysis to submit a report to your management. Since the full financial impact of building energy-efficient houses is difficult to estimate, you would like to prepare a rough cost benefit analysis and include it with the report. Which of the following describes the effort you are undertaking in this scenario? | You are developing a cost management plan to provide as an input to the Estimate Costs process. | You are developing a risk management plan to provide as an input to the Perform Quantitative Risk Analysis process. | You are developing a cost-benefit analysis to provide as an input to the Plan Risk Management process. | You are developing a business case to provide as an input to the Develop Project Charter process. | An organization's business need may arise due to advances in technology, a demand from the market or a legal requirement. The business need and cost-benefit analysis are documented in a business case. A business case determines whether the project is worth the investment. Payback analysis is also part of a business case. The business case and other documents are used as an input to the Develop Project Charter process. Hence, you are making efforts to build a business case as input to the Develop Project Charter process. [PMBOK 6th edition, Page 77] | هناك طلب كبير على المنازل الجديدة في الأحياء الباهظة الثمن في مدينتك. لقد وظفتك شركة تيرنر، وهي شركة إنشاءات، كمدير مشروع لتقييم فائدة بناء منازل جديدة موفرة للطاقة في هذا الحي، على الرغم من أن بناء مثل هذه المنازل يتطلب تقنية أكثر تكلفة. لقد بدأت في جمع البيانات لإجراء تحليل مفصل للمردود لتقديم تقرير إلى إدارتك. نظرًا لأنه من الصعب تقدير التأثير المالي الكامل لبناء منازل موفرة للطاقة، فأنت ترغب في إعداد تحليل تقريبي لمزايا التكلفة وتضمينه في التقرير. أي مما يلي يصف الجهد الذي تبذله في هذا السيناريو؟ | أنت بصدد تطوير خطة إدارة تكلفة لتقديمها كمدخل لعملية تقدير التكاليف. | أنت بصدد تطوير خطة لإدارة المخاطر لتقديمها كمدخل لعملية تحليل المخاطر الكمية. | أنت تقوم بتطوير تحليل التكلفة والمنفعة لتقديمه كمدخل لعملية خطة إدارة المخاطر. | أنت تطور مسوغ المشروع لتقديمه كمدخل لعملية تطوير ميثاق المشروع. | قد تنشأ حاجة العمل في المنظمة بسبب التقدم في التكنولوجيا ، أو الطلب من السوق أو المتطلبات القانونية. يتم توثيق حاجة العمل وتحليل التكلفة والمنفعة في مسوغ العمل. يحدد مسوغ العمل ما إذا كان المشروع يستحق الاستثمار. تحليل الاسترداد هو أيضًا جزء من مسوغ العمل. يُستخدم مسوغ العمل والمستندات الأخرى كمدخل لعملية تطوير ميثاق المشروع. بالتالي فأنت تبذل جهودًا لبناء مسوغ العمل لإدخاله في عملية تطوير ميثاق المشروع. [PMBOK الطبعة السادسة، الصفحة 77] | 140 | 2 | False | "20" | Haitham
593 | Ali is in the execution phase of a residential housing construction project. He has been informed of major scope changes from stakeholders in the middle of the project. These changes involve regulatory requirements from local authorities that may affect not only the scope but also the cost and duration of the project. What is the first step that Ali should take in considering these changes? | Meet with the change control board to solicit some ideas on the new project plan | Add new tasks to the project plan and assign resources to account for regulatory changes | Escalate the scope changes to the sponsor and steering committee for their decision | Create a report detailing the impact of scope changes on project parameters such as cost, quality, and schedule | Any scope changes in a project must go through the Integrated Change Control process to determine the impact on project parameters such as cost, quality and schedule. The changes must then be presented to the Change Control Board for their review. Then, all approved changes must be planned, and resources must be allocated. Therefore, the first step for Ali is to create a report detailing the impact of scope changes on project parameters such as cost, quality and schedule. [PMBOK 6th edition, Page 115] | علي في مرحلة تنفيذ مشروع بناء سكني. وقد تم إبلاغه بالتغييرات الرئيسية في النطاق من أصحاب المصلحة في منتصف المشروع. تتضمن هذه التغييرات متطلبات تنظيمية من السلطات المحلية قد تؤثر ليس فقط على نطاق المشروع ولكن أيضًا على تكلفة ومدة المشروع. ما هي الخطوة الأولى التي يجب أن يتخذها علي عند التفكير في هذه التغييرات؟ | الإلتقاء بلجنة التحكم في التغيير للحصول على بعض الأفكار حول خطة المشروع الجديدة | أضافة مهام جديدة إلى خطة المشروع وقم بتعيين الموارد لحساب التغييرات التنظيمية | تصعيد تغييرات النطاق إلى الراعي واللجنة التنفيذية لاتخاذ قرارهم | إنشاء تقرير يوضح بالتفصيل تأثير تغييرات النطاق على عوامل المشروع مثل التكلفة والجودة والجدول الزمني | يجب أن تمر أي تغييرات في النطاق في المشروع بعملية التحكم المتكامل في التغيير لتحديد التأثير على عوامل المشروع مثل التكلفة والجودة والجدول الزمني. يجب بعد ذلك تقديم التغييرات إلى لجنة مراقبة التغيير لمراجعتها. بعد ذلك ، يجب تخطيط جميع التغييرات المعتمدة ، وتخصيص الموارد. لذلك فإن الخطوة الأولى لـعلي هي إنشاء تقرير يوضح بالتفصيل تأثير تغييرات النطاق على عوامل المشروع مثل التكلفة والجودة والجدول الزمني. [PMBOK الطبعة السادسة ، الصفحة 115] | 140 | 5 | False | "19" | Haitham
594 | Amal is worried about her project because many of her tasks are moving slowly, and two critical tasks may slip. She conducts a thorough resource analysis and finds out that there are five people who will be free next week. She would like to assign those people to finish her tasks early and prevent the project completion date from slipping. This is an example of: | Management reserves | Resource leveling | Fast tracking | Crashing | Adding more resources to scheduled tasks in order to compress the task durations is called crashing. [PMBOK 6th edition, Page 215] | تشعر أمل بالقلق بشأن مشروعها لأن العديد من مهامها تتحرك ببطء، وقد يتأخر عملان مهمان. أجرت تحليلاً شاملاً للموارد واكتشفت أن هناك خمسة أشخاص سيكونون متاحين الأسبوع المقبل. إنها ترغب في تعيين هؤلاء الأشخاص لإنهاء مهامها مبكرًا ومنع تأخير تاريخ انتهاء المشروع. هذا مثال على: | الاحتياطي الإداري | تسوية الموارد | التتبع السريع | حشد الموارد | يُطلق على إضافة المزيد من الموارد إلى المهام المجدولة بهدف الإسراع فيها ووتقليل مدة تنفيذها حشد الموارد. [PMBOK الطبعة السادسة ، الصفحة 215] | 142 | 3 | False | "20" | Haitham
595 | Haitham is managing a construction project. He is using his communication, interpersonal and management skills to keep the key project stakeholders engaged with the project. Which of the following activities is not related to the Manage Stakeholder Engagement process? | Addressing and resolving issues | Confirming the stakeholders' continued commitment | Negotiating and communicating with the stakeholders | Developing the stakeholder engagement plan | The stakeholder engagement plan is developed during the Plan Stakeholder Engagement process. However, the stakeholder engagement plan might get updated during the Manage Stakeholder Engagement process. [PMBOK 6th edition, Pages 516, 529] | هيثم يدير مشروع بناء. إنه يستخدم مهارات الاتصال والمهارات الشخصية والإدارية لديه للحفاظ على مشاركة أصحاب المصلحة الرئيسيين في المشروع. أي من الأنشطة التالية لا يرتبط بعملية إدارة مشاركة أصحاب المصلحة؟ | معالجة وحل القضايا | تأكيد الالتزام المستمر لأصحاب المصلحة | التفاوض والتواصل مع أصحاب المصلحة | تطوير خطة إشراك أصحاب المصلحة | يتم تطوير خطة إشراك أصحاب المصلحة خلال عملية التخطيط لإشراك أصحاب المصلحة. ومع ذلك، قد يتم تحديث خطة إشراك أصحاب المصلحة أثناء عملية إدارة مشاركة أصحاب المصلحة. [PMBOK الطبعة السادسة، الصفحة 516 ، 529] | 149 | 4 | False | "20" | Haitham
596 | You are working on a waste management project that, upon completion, will be turned over to the local municipality for steady-state operation. Parking of trucks and other vehicles has become a serious problem because no parking area was allotted to you on the main dumping site. As a result, your trucks are parked on nearby roadsides. One of the fleet supervisors informs you that close to the main site, there is a large tract of land a local charity owns. Many locals park their cars on this tract of land. What should you do? | Since the piece of land is already used as parking, you can park your trucks over there. | Don’t park the trucks on that piece of land because it will be a violation of other’s property rights. | Check the local parking laws. | Ask the supervisor to get contact information of the local charity. | You must not use someone's property without permission, even if others are doing the same thing. The best option is to call the charity and ask for their permission. [PMI Code of Ethics and Professional Conduct] [Prof. Responsibility] | أنت تعمل في مشروع إدارة النفايات الذي سيتم تسليمه إلى البلدية المحلية عند الإنتهاء منه لتشغيله بإستقرار. أصبح وقوف الشاحنات والمركبات الأخرى مشكلة خطيرة لأنه لم يتم تخصيص مكان لوقوف السيارات لك في موقع رمي النفايات الرئيسي. نتيجة لذلك، يتم إيقاف شاحناتك على جوانب الطرق القريبة. أعلمك أحد مشرفي الأسطول أنه بالقرب من الموقع الرئيسي، توجد مساحة كبيرة من الأرض تمتلكها جمعية خيرية محلية. يوقف العديد من السكان المحليين سياراتهم على هذه الأرض. ماذا عليك ان تفعل؟ | نظرًا لأن قطعة الأرض مستخدمة بالفعل كموقف سيارات ، يمكنك إيقاف شاحناتك هناك. | لا تقم بإيقاف الشاحنات على قطعة الأرض هذه لأنها ستكون انتهاكًا لحقوق ملكية الآخرين. | تحقق من قوانين وقوف السيارات المحلية. | اطلب من المشرف الحصول على معلومات الاتصال بالمؤسسة الخيرية المحلية. | يجب عدم استخدام ممتلكات شخص ما دون إذن، حتى لو كان الآخرون يفعلون نفس الشيء. الخيار الأفضل هو الاتصال بالمؤسسة الخيرية وطلب الإذن منها. [مدونة الأخلاق والسلوك المهني لدى معهد إدارة المشاريع] [المسئولية المهنية] | 149 | 4 | False | "17" | Haitham
597 | You have managed a highway construction project, which is intended to improve transportation between north and south regions of the country. In the execution phase, you received many complaints from stakeholders, including the highway transportation agency. At least half these complaints were regarding the quality of the Asphalt layers of the road, and the nonconformance to the quality levels incorporated in the project quality management plan. So far, you have successfully fixed all the reported issues, but you are concerned by this recurrent event. What should you do to avoid future similar issues? | Initiate a defect repair to repair the road | Initiate a change request to update the project quality management plan | Initiate a corrective action to bring the future quality of the road in line with the project management plan | Initiate a preventive action to reduce the probability of negative consequences associated with the poor quality of the road | There is no need to update the quality management plan since the problem is with the workmanship and not with the quality management plan. The scenario is asking for an action that will ensure future compliance, i.e. a preventive action. Note that since all of the reported defects have been fixed, there is no need for any corrective action or defect repair at this stage. [PMBOK 6th edition, Page 96] | لقد أدرت مشروع إنشاء طريق سريع يهدف إلى تحسين النقل بين المناطق الشمالية والجنوبية من البلاد. في مرحلة التنفيذ ، تلقيت العديد من الشكاوى من أصحاب المصلحة ، بما في ذلك وكالة النقل على الطرق السريعة. كانت نصف هذه الشكاوى على الأقل تتعلق بجودة طبقات الأسفلت للطريق ، وعدم التوافق مع مستويات الجودة المدرجة في خطة إدارة جودة المشروع. لقد نجحت حتى الآن في إصلاح جميع المشكلات المبلغ عنها ، ولكنك تشعر بالقلق حيال هذا الحدث المتكرر. ما الذي يجب عليك فعله لتجنب مشاكل مماثلة في المستقبل؟ | الشروع في إصلاح الخلل لإصلاح الطريق | بدء طلب تغيير لتحديث خطة إدارة جودة المشروع | الشروع في اتخاذ إجراء تصحيحي لجعل الجودة المستقبلية للطريق تتماشى مع خطة إدارة المشروع | ابدأ في إجراء وقائي لتقليل احتمالية حدوث عواقب سلبية مرتبطة بجودة الطريق الرديئة | ليست هناك حاجة لتحديث خطة إدارة الجودة لأن المشكلة تكمن في جودة تنفيذ العمل وليس في خطة إدارة الجودة. يتطلب السيناريو إجراء يضمن الامتثال المستقبلي للجودة مثل الإجراءات الوقائية. لاحظ أنه نظرًا لأنه تم إصلاح جميع العيوب المبلغ عنها ، فلا داعي لأي إجراء تصحيحي أو إصلاح عيب في هذه المرحلة. [PMBOK الطبعة السادسة ، الصفحة 96] | 140 | 4 | False | "20" | Haitham
598 | Changes in projects are inevitable. Therefore, project managers must develop or use a system to manage and control changes. There are four types of changes that need to be controlled in a project: Project changes, deliverable changes, process changes, and baseline changes. The impact of each of these changes must be evaluated, and approved or rejected changes must be communicated to all stakeholders, as and when required. Which of the following helps control these changes? | Configuration control and Control chart | Control chart and Cost control | Change control and Control chart | Configuration control and Change control | Configuration control is focused on the specification of both the processes and deliverables, whereas change control is focused on project changes and the product baselines. A configuration control process and change control system must be implemented to handle all those changes. [PMBOK 6th edition, Page 115] | التغييرات في المشاريع أمر لا مفر منه. لذلك يجب على مدراء المشاريع تطوير أو استخدام نظام لإدارة التغييرات والتحكم فيها. هناك أربعة أنواع من التغييرات التي يجب التحكم فيها في المشروع: تغييرات المشروع ، وتغييرات التسليمات، وتغييرات العمليات ، وتغييرات خطوط الأساس. يجب تقييم تأثير كل من هذه التغييرات، ويجب إبلاغ التغييرات المعتمدة أو المرفوضة إلى جميع أصحاب المصلحة عند الحاجة. أي مما يلي يساعد في التحكم في هذه التغييرات؟ | مخطط التحكم والتحكم في التكوين | مخطط التحكم والتحكم بالتكاليف | التحكم بالتغيير ومخطط التحكم | التحكم في التكوين والتحكم في التغيير | يركز التحكم في التكوين على مواصفات كل من العمليات والتسليمات، بينما يركز التحكم في التغيير على تغييرات المشروع وخطوط الأساس للمنتج. يجب تنفيذ عملية التحكم في التكوين ونظام التحكم في التغيير للتعامل مع كل هذه التغييرات. [PMBOK الطبعة السادسة ، الصفحة 115] | 140 | 5 | False | "20" | Haitham
599 | Two of your expert team members have been in a heated argument over the use of a new software product for your research project. Recently, you noticed that the argument, instead of increasing creativity, is causing conflict between the team members. To prevent the conflict from escalating, you want to resolve it by open dialogue and evaluating alternatives. All the following statements about conflict are false except: | Scarce resources cannot be a source of a conflict. | Personal work style cannot be a source of a conflict. | Reducing the amount of conflict is not desirable. | Conflict is inevitable in a project environment. | Conflict is inevitable in a project environment. The other statements are incorrect. [PMBOK 6th edition, Page 348] | دخل اثنان من أعضاء فريق الخبراء لديك في جدال حاد حول استخدام منتج برمجي جديد لمشروعك البحثي. لقد لاحظت مؤخرًا أن الجدال يتسبب في حدوث صراع بين أعضاء الفريق بدلاً من زيادة الإبداع. لمنع تصعيد الصراع، تريد حله من خلال الحوار المفتوح وتقييم البدائل. جميع العبارات التالية حول الصراع خاطئة باستثناء: | لا يمكن أن تكون ندرة الموارد مصدراً للصراع. | لا يمكن أن يكون أسلوب العمل الشخصي مصدر للصراع. | تقليل حجم الصراع غير مرغوب فيه. | الصراع أمر لا مفر منه في بيئة المشروع. | الصراع أمر لا مفر منه في بيئة المشروع. العبارات الأخرى غير صحيحة. [PMBOK الطبعة السادسة ، الصفحة 348] | 145 | 4 | False | "19" | Haitham
600 | The customer requests a change to the project that would increase the project risk. Which of the following should you do first? | Talk to the customer about the impact of the change | Change the risk management plan | Include the expected monetary value of the risk in the new cost estimate | Analyze the change‘s impact of the change with the team | Your first step is to assess the impact of the change with the team. Then you can determine possible options, after which you can meet with management. [PMBOK 6th Edition, Page 115] | يطلب العميل إجراء تغيير في المشروع من شأنه زيادة مخاطر المشروع. أي مما يلي يجب أن تفعله أولاً؟ | تحدث إلى العميل حول تأثير التغيير | تغيير خطة إدارة المخاطر | قم بتضمين القيمة النقدية المتوقعة للمخاطر في تقدير التكلفة الجديد | حلل تأثير التغيير مع الفريق | خطوتك الأولى هي تقييم تأثير التغيير مع الفريق. ثم يمكنك تحديد الخيارات الممكنة ، وبعد ذلك يمكنك مقابلة الإدارة. [PMBOK الطبعة السادسة، الصفحة 115] | 140 | 5 | False | "19" | Haitham

## Sheet3
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Questions | Answer A | Answer B | Answer C | Answer Correct | Questions Ar | Answer A Ar | Answer B Ar | Answer C Ar | Answer Correct Ar | Chapter | Process Group | Free Quiz | Exam No.
William is the project manager of the civil Project. He and the project team have identified a risk event in the project with a high probability of occurrence and the risk event has a high-cost impact on the project. William discusses the risk event with Virginia, the primary project customer, and she decides that the requirements surrounding the risk event should be removed from the project. The removal of the requirements does affect the project scope, but it can release the project from high-risk exposure. What risk response has been enacted in this project? | Mitigation | Transference | Acceptance | Avoidance | William is the project manager of the civil Project. He and the project team have identified a risk event in the project with a high probability of occurrence and the risk event has a high-cost impact on the project. William discusses the risk event with Virginia, the primary project customer, and she decides that the requirements surrounding the risk event should be removed from the project. The removal of the requirements does affect the project scope, but it can release the project from high-risk exposure. What risk response has been enacted in this project? | Mitigation | Transference | Acceptance | Avoidance | Risk Management | Executing | False | "16"
Risk event should be removed from your project. The removal of the requirements does affect your project scope, but it can release the project from high-risk exposure. What risk response has been enacted in this project? | Mitigation | Transference | Acceptance | Avoidance | Risk event should be removed from your project. The removal of the requirements does affect your project scope, but it can release the project from high-risk exposure. What risk response has been enacted in this project? | Mitigation | Transference | Acceptance | Avoidance | Risk Management | Planning | False | "19"
A local contractor is unable to meet a delivery date. The project team did not anticipate this new threat to the supply of the product. Importing this product will cost the project twice the price that the local vendor charges. What should the project manager use to fund this effort? | Contingency reserve | Project budget reserve | Risk response reserve | Management reserve | A local contractor is unable to meet a delivery date. The project team did not anticipate this new threat to the supply of the product. Importing this product will cost the project twice the price that the local vendor charges. What should the project manager use to fund this effort? | Contingency reserve | Project budget reserve | Risk response reserve | Management reserve | Risk Management | Monitoring and Controlling | False | "16"
You are a project manager in an construction project. You and your team planned, identified, analyzed risks and planned risk responses for your project. During the implementation phase, an unidentified risk occurs. How will you fund to face this risk? | Cost baseline | Contingency Reserve | Risk Mitigation | Management Reserve | You are a project manager in an construction project. You and your team planned, identified, analyzed risks and planned risk responses for your project. During the implementation phase, an unidentified risk occurs. How will you fund to face this risk? | Cost baseline | Contingency Reserve | Risk Mitigation | Management Reserve | Risk Management | Executing | False | "17"
Mustafa is a project manager of the civil project for your organization. In this project, you are currently performing quantitative risk analysis. The tool and technique you are using is a simulation where the project model is computed many times with the input values chosen at random for each iteration and Outputs representing the range of possible outcomes for the project. The goal is to create a probability distribution from the iterations for the project schedule. What technique will you use with this simulation? | Pareto charts | Expected Monetary Value | Cause and effect diagram | Monte Carlo Technique | Mustafa is a project manager of the civil project for your organization. In this project, you are currently performing quantitative risk analysis. The tool and technique you are using is a simulation where the project model is computed many times with the input values chosen at random for each iteration and Outputs representing the range of possible outcomes for the project. The goal is to create a probability distribution from the iterations for the project schedule. What technique will you use with this simulation? | Pareto charts | Expected Monetary Value | Cause and effect diagram | Monte Carlo Technique | Risk Management | Planning | False | "18"
To create a probability distribution from the iterations for the project schedule. What technique will you use with this simulation? | Pareto charts | Expected Monetary Value | Cause and effect diagram | Monte Carlo Technique | To create a probability distribution from the iterations for the project schedule. What technique will you use with this simulation? | Pareto charts | Expected Monetary Value | Cause and effect diagram | Monte Carlo Technique | Risk Management | Planning | False | "20"
You are working in a matrix organization and managing a construction project. The functional manager moved some resources you need from your project to another project. What should you do next? | Update stakeholder engagement plan | Escalate this problem to the sponsor | Complete the project without this resources | Negotiate with functional manager to assign a new resources | You are working in a matrix organization and managing a construction project. The functional manager moved some resources you need from your project to another project. What should you do next? | Update stakeholder engagement plan | Escalate this problem to the sponsor | Complete the project without this resources | Negotiate with functional manager to assign a new resources | Resources Management | Executing | False | "18"
You are working in a matrix organization and managing a project. The human resource manager transferred some resources you need from your project to another project without take in consideration the effect of this action on your project. What should you do next? | Escalate this problem to the sponsor | Complete the project without this resources | Update Stakeholder Engagement plan | Negotiate with Functional Manager to assign a new resources | You are working in a matrix organization and managing a project. The human resource manager transferred some resources you need from your project to another project without take in consideration the effect of this action on your project. What should you do next? | Escalate this problem to the sponsor | Complete the project without this resources | Update Stakeholder Engagement plan | Negotiate with Functional Manager to assign a new resources | Resources Management | Executing | False | "20"
As project manager managing project, in which of the following inputs for initiation processes? | Expert judgment | Requirements traceability matrix | Project management plan | Organizational process assets | As project manager managing project, in which of the following inputs for initiation processes? | Expert judgment | Requirements traceability matrix | Project management plan | Organizational process assets | Integration Management | Initiating | False | "16"
You are a project manager for a website design development project. An issue appears on a project and one of your project team remember that this issue has occurred before, but cannot remember the solution. Which of the following options should you refer first to find the solution? | Checklist | Issue management procedure | Organizational Strategy | Organizational process assets | You are a project manager for a website design development project. An issue appears on a project and one of your project team remember that this issue has occurred before, but cannot remember the solution. Which of the following options should you refer first to find the solution? | Checklist | Issue management procedure | Organizational Strategy | Organizational process assets | Integration Management | Executing | False | "18"
During an audit, it was noted that only 20 percent of completed projects had documented lessons learned. What should the project manager have updated to document this? | Quality process Assets. | Stakeholder responsibility matrix. | Change control documentation. | Organizational process assets | During an audit, it was noted that only 20 percent of completed projects had documented lessons learned. What should the project manager have updated to document this? | Quality process Assets. | Stakeholder responsibility matrix. | Change control documentation. | Organizational process assets | Quality Management | Executing | False | "20"
You have just been moved onto a project that is well into the project implementation phase. You then realize that no stakeholder register exists for the project. Since you are new to the organization, you want to ensure that you use its templates for documents. Therefore, you search for a template for a stakeholder registered in the: | Enterprise environmental factors | Stakeholder management plan | Project management plan | Organizational process assets | You have just been moved onto a project that is well into the project implementation phase. You then realize that no stakeholder register exists for the project. Since you are new to the organization, you want to ensure that you use its templates for documents. Therefore, you search for a template for a stakeholder registered in the: | Enterprise environmental factors | Stakeholder management plan | Project management plan | Organizational process assets | Stakeholder Management | Executing | False | "19"
After contract sign-off , a project manager has been informed him that that the vendor has a bad reputation for delaying the materials delivery and not meet the time agreed in the contract. To ensure the vendor's compliance, what should the project manager do? | Cancel the current contract and select another vendor | Conduct a make-or-buy analysis to verify vendor reliability | Insist on a firm fixed price contract (FFP) with the vendor | Perform periodic inspection of the vendor's work and progress. | After contract sign-off , a project manager has been informed him that that the vendor has a bad reputation for delaying the materials delivery and not meet the time agreed in the contract. To ensure the vendor's compliance, what should the project manager do? | Cancel the current contract and select another vendor | Conduct a make-or-buy analysis to verify vendor reliability | Insist on a firm fixed price contract (FFP) with the vendor | Perform periodic inspection of the vendor's work and progress. | Procurement Management | Monitoring and Controlling | False | "18"
After contract sign-off, a project manager learns that the supplier has a reputation of not delivering according to the contract. To ensure the vendor's compliance, what should the project manager do? | Cancel the current contract and select another vendor | Conduct a make-or-buy analysis to verify vendor reliability | Insist on a firm fixed price contract (FFP) with the vendor | Perform periodic inspection of the vendor's work and progress. | After contract sign-off, a project manager learns that the supplier has a reputation of not delivering according to the contract. To ensure the vendor's compliance, what should the project manager do? | Cancel the current contract and select another vendor | Conduct a make-or-buy analysis to verify vendor reliability | Insist on a firm fixed price contract (FFP) with the vendor | Perform periodic inspection of the vendor's work and progress. | Procurement Management | Monitoring and Controlling | False | "20"
You often has to deal with change requests to expand or reduce the project scope. Changes in project scope impact a variety of project documents. In this context, approved change requests can impact all of the following except: | Cost Estimates | Project Management Plan | Project Deliverables | Project Charter | You often has to deal with change requests to expand or reduce the project scope. Changes in project scope impact a variety of project documents. In this context, approved change requests can impact all of the following except: | Cost Estimates | Project Management Plan | Project Deliverables | Project Charter | Scope Management | Monitoring and Controlling | False | "19"
Martin is a project manager in an infrastructure project. After finalizing all activities for the project, which of the following documents will help him in this process? | Stakeholder Register | Verified deliverables | Probability and Impact Matrix | Project Charter | Martin is a project manager in an infrastructure project. After finalizing all activities for the project, which of the following documents will help him in this process? | Stakeholder Register | Verified deliverables | Probability and Impact Matrix | Project Charter | Integration Management | Closing | False | "16"
During the Kick- off meeting, the CEO did not accept a project management plan. What should you refer to persuade the CEO? | Cost benefit analysis | Project management plan | SOW Bottom of Form | Project charter | During the Kick- off meeting, the CEO did not accept a project management plan. What should you refer to persuade the CEO? | Cost benefit analysis | Project management plan | SOW Bottom of Form | Project charter | Integration Management | Planning | False | "18"
Nancy's project is in execution. Nancy is currently planning to execute the Manage Stakeholder Engagement process. She has gathered the project documents such as the issue log, the change log, the stakeholder register, the lessons learned register and the necessary organizational process assets. Which of the following is a key input to this process that is still missing from this list? | Expert Judgment | Communication Skills | Change requests | Project Management Plan | Nancy's project is in execution. Nancy is currently planning to execute the Manage Stakeholder Engagement process. She has gathered the project documents such as the issue log, the change log, the stakeholder register, the lessons learned register and the necessary organizational process assets. Which of the following is a key input to this process that is still missing from this list? | Expert Judgment | Communication Skills | Change requests | Project Management Plan | Stakeholder Management | Executing | False | "17"
You have recently been assigned to lead a project that is halfway into execution. The project has many stakeholders, and you are trying to determine how to engage them effectively. Which of the following will best help you in this effort? | Scope Management Plan | Project Charter | Change Management Plan | Project Management Plan | You have recently been assigned to lead a project that is halfway into execution. The project has many stakeholders, and you are trying to determine how to engage them effectively. Which of the following will best help you in this effort? | Scope Management Plan | Project Charter | Change Management Plan | Project Management Plan | Stakeholder Management | Executing | False | "16"
Which document defines how the project is to be executed, monitored, controlled, and closed? | Project scope | Project charter | Project management information system | Project management plan | Which document defines how the project is to be executed, monitored, controlled, and closed? | Project scope | Project charter | Project management information system | Project management plan | Integration Management | Planning | False | "19"
You and your team are currently developing the project charter and are looking for valuable inputs you can use to complete it using all of the following inputs in the "Develop Project Charter process" except? | Business case | Enterprise environmental factors | Agreements | Project management plan | You and your team are currently developing the project charter and are looking for valuable inputs you can use to complete it using all of the following inputs in the "Develop Project Charter process" except? | Business case | Enterprise environmental factors | Agreements | Project management plan | Integration Management | Initiating | False | "17"
You have been hired for a new project, and the project charter has already been approved. What documentation is needed to prepare for the kick-off meeting? | Quality management plan | Scope management plan | Business case | Project management plan | You have been hired for a new project, and the project charter has already been approved. What documentation is needed to prepare for the kick-off meeting? | Quality management plan | Scope management plan | Business case | Project management plan | Integration Management | Planning | False | "20"
You have recently been assigned as a project manager to manage a project that was terminated five months ago because of funding related issues, but which has since been re-initiated. You want to find out the exact reasons for the termination of the project. You also want to know which deliverables were produced from the terminated project. Which of the following documentation should you review to obtain this information? | Operational and support documents | Historical Database | Final Product, Service, or Result | Project or phase closure documents | You have recently been assigned as a project manager to manage a project that was terminated five months ago because of funding related issues, but which has since been re-initiated. You want to find out the exact reasons for the termination of the project. You also want to know which deliverables were produced from the terminated project. Which of the following documentation should you review to obtain this information? | Operational and support documents | Historical Database | Final Product, Service, or Result | Project or phase closure documents | Integration Management | Closing | False | "17"
You also want to know which deliverables were produced from the terminated project. Which of the following documentation should you review to obtain this information? | Operational and support documents | Historical Database | Final Product, Service, or Result | Project or phase closure documents | You also want to know which deliverables were produced from the terminated project. Which of the following documentation should you review to obtain this information? | Operational and support documents | Historical Database | Final Product, Service, or Result | Project or phase closure documents | Integration Management | Closing | False | "19"
The project manager is busy with an important milestone, and after that, he have to deliver a deliverable to the client. Since the client is known for his difficult behavior, management is worried whether the client will accept the deliverable. Therefore, they tell him to check the product acceptance criteria again before calling the client. What document will the PM look at to get this information.? | Control Chart | WBS dictionary | WBS | Project scope statement | The project manager is busy with an important milestone, and after that, he have to deliver a deliverable to the client. Since the client is known for his difficult behavior, management is worried whether the client will accept the deliverable. Therefore, they tell him to check the product acceptance criteria again before calling the client. What document will the PM look at to get this information.? | Control Chart | WBS dictionary | WBS | Project scope statement | Scope Management | Planning | False | "19"
You are a project manager who takes over a project during the execution phase. You would like to know more about project deliverables, the work required to complete those deliverables, project constraints, and assumptions. Which of the following documents would be MOST useful? | Work Breakdown Structure (WBS) | Activity List | Requirements Documentation | Project Scope Statement | You are a project manager who takes over a project during the execution phase. You would like to know more about project deliverables, the work required to complete those deliverables, project constraints, and assumptions. Which of the following documents would be MOST useful? | Work Breakdown Structure (WBS) | Activity List | Requirements Documentation | Project Scope Statement | Scope Management | Executing | False | "20"
Which of the following business documents that Justify why the project is authorized? | Project management plan | Project charter | Scope statement of work | Business case | Which of the following business documents that Justify why the project is authorized? | Project management plan | Project charter | Scope statement of work | Business case | Integration Management | Initiating | False | "18"
You are a project manager during the initiation phase. Which of the following documents will help you while developing the project charter? | Brainstorming | Final report | Project Management Plan | Business case | You are a project manager during the initiation phase. Which of the following documents will help you while developing the project charter? | Brainstorming | Final report | Project Management Plan | Business case | Integration Management | Initiating | False | "19"
A project manager updating a dashboard monthly with information on the project's performance using project management information system (PMIS). Which of the following communication methods describes this? | Manual communication | Interactive Communication. | Informal communication. | Pull Communication. | A project manager updating a dashboard monthly with information on the project's performance using project management information system (PMIS). Which of the following communication methods describes this? | Manual communication | Interactive Communication. | Informal communication. | Pull Communication. | Communication Management | Planning | False | "16"
Your company has created an electronic network to share information between stakeholders and access to information at any time. Which communication method is used? | Push communication | Multidirectional communication | Interactive communication | Pull communication | Your company has created an electronic network to share information between stakeholders and access to information at any time. Which communication method is used? | Push communication | Multidirectional communication | Interactive communication | Pull communication | Communication Management | Planning | False | "20"
By the project management information system (PMIS), a project management team is updating a dashboard monthly with information on the project's performance. Which of the following communication methods describes this? | Interactive Communication | Informal communication | Manual communication | Pull Communication | By the project management information system (PMIS), a project management team is updating a dashboard monthly with information on the project's performance. Which of the following communication methods describes this? | Interactive Communication | Informal communication | Manual communication | Pull Communication | Communication Management | Planning | False | "19"
You are a project manager in an Construction project. During the work, an unexpected resource shortage occurs. What should the project manager do? | Perform a qualitative risk analysis | Risk categorization | Risk probability and impact assessment | Refer to the risk register and inform key stakeholders | You are a project manager in an Construction project. During the work, an unexpected resource shortage occurs. What should the project manager do? | Perform a qualitative risk analysis | Risk categorization | Risk probability and impact assessment | Refer to the risk register and inform key stakeholders | Risk Management | Monitoring and Controlling | False | "20"
You are a project manager in a communication project. During the deployment of a new system, an unexpected power outage occurs. What should the project manager do? | Risk categorization | Risk probability and impact assessment | Perform a qualitative risk analysis | Refer to the risk register and inform key stakeholders | You are a project manager in a communication project. During the deployment of a new system, an unexpected power outage occurs. What should the project manager do? | Risk categorization | Risk probability and impact assessment | Perform a qualitative risk analysis | Refer to the risk register and inform key stakeholders | Risk Management | Executing | False | "18"
The relevant stakeholders inspected the deliverables and found that that there has been a change in the company strategy. Therefore, important changes must be made to the requirements. The project manager believes that these changes make the deliverables unstable. What should the project manager do? | Request the details about the new requirements, evaluate them with the project team, and recommend whether to continue or close the project. | Evaluate the impact on the project, coordinate with the sponsor and close the project. | Evaluate and incorporate the changes to the project management plan to start executing them. | Request that the stakeholders specify the new requirements and present them to the change control board (CCB). | The relevant stakeholders inspected the deliverables and found that that there has been a change in the company strategy. Therefore, important changes must be made to the requirements. The project manager believes that these changes make the deliverables unstable. What should the project manager do? | Request the details about the new requirements, evaluate them with the project team, and recommend whether to continue or close the project. | Evaluate the impact on the project, coordinate with the sponsor and close the project. | Evaluate and incorporate the changes to the project management plan to start executing them. | Request that the stakeholders specify the new requirements and present them to the change control board (CCB). | Integration Management | Monitoring and Controlling | False | "20"
A project manager has received reports from a supplier that he is over capacity, which may delay his delivery. What should the project manager update next? | Schedule Baseline. | Stakeholder engagement plan. | Issue log. | Risk register. | A project manager has received reports from a supplier that he is over capacity, which may delay his delivery. What should the project manager update next? | Schedule Baseline. | Stakeholder engagement plan. | Issue log. | Risk register. | Risk Management | Monitoring and Controlling | False | "19"
You are in the execution phase of a project to build a building. The project team develops a new response for an existing risk that will reduce the schedule by 20 days. What document should the project manager update? | Schedule management plan. | Risk breakdown structure (PBS). | Risk management plan. | Risk register. | You are in the execution phase of a project to build a building. The project team develops a new response for an existing risk that will reduce the schedule by 20 days. What document should the project manager update? | Schedule management plan. | Risk breakdown structure (PBS). | Risk management plan. | Risk register. | Risk Management | Executing | False | "18"
During the implementation phase, one of your project team has told you that the Concrete delivery will be delayed one week. As a project manager, what document should you refer to FIRST? | Plan Risk management plan | Issue Log | Risk Response | Risk Register | During the implementation phase, one of your project team has told you that the Concrete delivery will be delayed one week. As a project manager, what document should you refer to FIRST? | Plan Risk management plan | Issue Log | Risk Response | Risk Register | Risk Management | Executing | False | "20"
You are in the execution phase of a project to build a stadium. The project team develops a new response for an existing risk that will reduce the schedule by 20 days. What document should the project manager update? | Risk breakdown structure (PBS). | Risk management plan | Schedule management plan | Risk register | You are in the execution phase of a project to build a stadium. The project team develops a new response for an existing risk that will reduce the schedule by 20 days. What document should the project manager update? | Risk breakdown structure (PBS). | Risk management plan | Schedule management plan | Risk register | Risk Management | Planning | False | "16"
Which of the following is an output of the Create WBS process? | Project scope statement | Decomposition | Requirements documentation | Scope baseline | Which of the following is an output of the Create WBS process? | Project scope statement | Decomposition | Requirements documentation | Scope baseline | Scope Management | Planning | False | "18"
During managing stakeholder expectations, at the end of the design phase, you found one of the key stakeholders complain of one of work package still not complete. You do not agree and review with him the WBS dictionary but the stakeholder is still unsatisfied. What is the next document you should review? | Requirement management plan | Scope management plan | WBS | Scope Baseline | During managing stakeholder expectations, at the end of the design phase, you found one of the key stakeholders complain of one of work package still not complete. You do not agree and review with him the WBS dictionary but the stakeholder is still unsatisfied. What is the next document you should review? | Requirement management plan | Scope management plan | WBS | Scope Baseline | Scope Management | Planning | False | "20"
If the project deliverables didn't meet the agreed-upon acceptance criteria. What should the project manager reference to verity this with the contractor? | Quality log | Request for proposal (RFP). | Procurement management plan | Statement of work (SOW). | If the project deliverables didn't meet the agreed-upon acceptance criteria. What should the project manager reference to verity this with the contractor? | Quality log | Request for proposal (RFP). | Procurement management plan | Statement of work (SOW). | Procurement Management | Planning | False | "18"
The project manager didn't accepted the deliverables because don't meet the agreed-upon acceptance criteria. What should the project manager reference to verify this with the contractor? | Request for proposal (RFP). | Procurement management plan | Quality log | Statement of work (SOW). | The project manager didn't accepted the deliverables because don't meet the agreed-upon acceptance criteria. What should the project manager reference to verify this with the contractor? | Request for proposal (RFP). | Procurement management plan | Quality log | Statement of work (SOW). | Procurement Management | Planning | False | "20"
A project manager is working with the project team to estimate durations for the identified project activities. The team is looking to achieve the most accurate estimate possible. What estimating technique can they use to generate the desired result? | Top-down estimating | Parametric estimating | Analogous estimating | Three-point estimating | A project manager is working with the project team to estimate durations for the identified project activities. The team is looking to achieve the most accurate estimate possible. What estimating technique can they use to generate the desired result? | Top-down estimating | Parametric estimating | Analogous estimating | Three-point estimating | Schedule Management | Planning | False | "19"
You are managing a project in which your team members are uncertain as to how much time will be needed for each activity. Which of the following techniques is considered the most useful in this case? | Critical Path Method (CPM) | Arrow Diagramming Method (ADM) | Precedence Diagramming Method (PDM) | Three-point estimating | You are managing a project in which your team members are uncertain as to how much time will be needed for each activity. Which of the following techniques is considered the most useful in this case? | Critical Path Method (CPM) | Arrow Diagramming Method (ADM) | Precedence Diagramming Method (PDM) | Three-point estimating | Schedule Management | Planning | False | "20"
Suzi is the project manager on a civil project. When she hears that her project has run into a snag due to weeks of bad weather on the job site, she says "No problem, we have insurance that covers cost overruns due to weather." What risk response strategy did she use? | Sharing | Avoidance | Mitigation | Transference | Suzi is the project manager on a civil project. When she hears that her project has run into a snag due to weeks of bad weather on the job site, she says "No problem, we have insurance that covers cost overruns due to weather." What risk response strategy did she use? | Sharing | Avoidance | Mitigation | Transference | Risk Management | Planning | False | "17"
You have identified a risk that may cause safety concerns for the workers completing the task. You've decided to hire a third party to complete this work because the risk is too great to accept internally. Which risk response is this? | Avoidance | Acceptance | Mitigation | Transference | You have identified a risk that may cause safety concerns for the workers completing the task. You've decided to hire a third party to complete this work because the risk is too great to accept internally. Which risk response is this? | Avoidance | Acceptance | Mitigation | Transference | Risk Management | Planning | False | "19"
A senior project manager is working on monitoring the progress of the schedule. To determine whether performance is getting better or worse, he analyzes project performance over time. What technique is the project manager using? | Performance reviews | Variance analysis | Inspection | Trend Analysis | A senior project manager is working on monitoring the progress of the schedule. To determine whether performance is getting better or worse, he analyzes project performance over time. What technique is the project manager using? | Performance reviews | Variance analysis | Inspection | Trend Analysis | Schedule Management | Monitoring and Controlling | False | "16"
You are a project manager in a infrastructure project. During a review, the site engineer informs you that the concrete production rate has changed over the last three months. What analysis should be conducted? | Control chart | Earned value (EV). | Scatter diagram | Trend analysis | You are a project manager in a infrastructure project. During a review, the site engineer informs you that the concrete production rate has changed over the last three months. What analysis should be conducted? | Control chart | Earned value (EV). | Scatter diagram | Trend analysis | Schedule Management | Monitoring and Controlling | False | "19"
The project manager near to complete to project, unidentified stakeholder request a change on project scope. As a project manager for that project, What should you do first step? | Ignore the stakeholder | Meeting with the team and analyze the impact on project constraints | Implement the change | Update Stakeholder Register | The project manager near to complete to project, unidentified stakeholder request a change on project scope. As a project manager for that project, What should you do first step? | Ignore the stakeholder | Meeting with the team and analyze the impact on project constraints | Implement the change | Update Stakeholder Register | Stakeholder Management | Monitoring and Controlling | False | "20"
The project in execution phase, unidentified stakeholder request a change on project schedule. As a project manager, What should you do first? | Ignore the stakeholder | Meeting with the team and analyze the impact on project constraints | Implement the change | Update Stakeholder Register | The project in execution phase, unidentified stakeholder request a change on project schedule. As a project manager, What should you do first? | Ignore the stakeholder | Meeting with the team and analyze the impact on project constraints | Implement the change | Update Stakeholder Register | Stakeholder Management | Executing | False | "19"
The customer has requested a change in the scope which you have processed through a change request and it is approved from CCB. Now, you are in the process of implementing this change into the project. In which of the following processes do you implement the approved change? | Perform integrated change control | Monitor and control project work | Control scope | Direct and manage project work | The customer has requested a change in the scope which you have processed through a change request and it is approved from CCB. Now, you are in the process of implementing this change into the project. In which of the following processes do you implement the approved change? | Perform integrated change control | Monitor and control project work | Control scope | Direct and manage project work | Integration Management | Monitoring and Controlling | False | "16"
You are working on a critical deliverable encounter a major change that affects the schedule baseline and the next milestone deliverable. You have assessed the impact of the change on the project constraints with your team, and the change control board just approved a change request. In which process will this change be implemented? | Perform integrated change control | Monitor and control project work | Develop project management plan | Direct and manage project work | You are working on a critical deliverable encounter a major change that affects the schedule baseline and the next milestone deliverable. You have assessed the impact of the change on the project constraints with your team, and the change control board just approved a change request. In which process will this change be implemented? | Perform integrated change control | Monitor and control project work | Develop project management plan | Direct and manage project work | Integration Management | Executing | False | "19"
The change control board just approved a change request to modify two of the major deliverables. In which process will this change be implemented? | Close Project or Phase | Monitor and Control Project Work | Perform Integrated Change Control | Direct and Manage Project Work | The change control board just approved a change request to modify two of the major deliverables. In which process will this change be implemented? | Close Project or Phase | Monitor and Control Project Work | Perform Integrated Change Control | Direct and Manage Project Work | Integration Management | Executing | False | "20"
Ahmad is a project manager working for a construction company. As part of his current project, he oversees the inspection of deliverables, measuring them against documented requirements and acceptance criteria for obtaining the stakeholders' formal acceptance of the project deliverables. What project management process is he performing? | Control Quality | Manage Quality | Control Scope | Validate Scope | Ahmad is a project manager working for a construction company. As part of his current project, he oversees the inspection of deliverables, measuring them against documented requirements and acceptance criteria for obtaining the stakeholders' formal acceptance of the project deliverables. What project management process is he performing? | Control Quality | Manage Quality | Control Scope | Validate Scope | Scope Management | Monitoring and Controlling | False | "18"
Your project is complete and the product is ready to be delivered. The client inspects the deliverable and accepts it. What process is this? | Close project or phase | Close procurement | Control Quality | Validate scope | Your project is complete and the product is ready to be delivered. The client inspects the deliverable and accepts it. What process is this? | Close project or phase | Close procurement | Control Quality | Validate scope | Scope Management | Monitoring and Controlling | False | "20"
After the project charter is approved, what should you do NEXT? | Prepare Project Scope Statement | Scope baseline | Prepare a business case | Prepare Scope Management Plan | After the project charter is approved, what should you do NEXT? | Prepare Project Scope Statement | Scope baseline | Prepare a business case | Prepare Scope Management Plan | Scope Management | Planning | False | "17"
A construction manager is leading a project to study the feasibility of constructing a tower. The project needs to be analyzed from a technical, economic, and social point of view. The construction manager has created the project charter on behalf of the project sponsor, and it is now approved. Which of the following processes should be performed next? | Develop Project Charter | Scope Baseline | Identify Risks | Plan Scope Management | A construction manager is leading a project to study the feasibility of constructing a tower. The project needs to be analyzed from a technical, economic, and social point of view. The construction manager has created the project charter on behalf of the project sponsor, and it is now approved. Which of the following processes should be performed next? | Develop Project Charter | Scope Baseline | Identify Risks | Plan Scope Management | Scope Management | Planning | False | "19"
Midway of your project and working on a deliverable which is 90% completed. It is time for the yearly audit. A team of auditors are about to come and verify if you are following the process as defined or not. However, as the deliverable is about to be completed, you check it and measure all dimensions to find any possible dimensional defects. What process is this? | Manage quality | Plan quality management | Control scope | Control quality | Midway of your project and working on a deliverable which is 90% completed. It is time for the yearly audit. A team of auditors are about to come and verify if you are following the process as defined or not. However, as the deliverable is about to be completed, you check it and measure all dimensions to find any possible dimensional defects. What process is this? | Manage quality | Plan quality management | Control scope | Control quality | Quality Management | Monitoring and Controlling | False | "19"
You are in the middle of your project and working on a deliverable which is 85% completed. It is time for the yearly audit. A team of auditors are about to come and verify if you are following the process as defined or not. However, as the deliverable is about to be completed, you check it and measure all dimensions to find any possible dimensional defects. What process is this? | Manage quality | Plan quality management | Control scope | Control quality | You are in the middle of your project and working on a deliverable which is 85% completed. It is time for the yearly audit. A team of auditors are about to come and verify if you are following the process as defined or not. However, as the deliverable is about to be completed, you check it and measure all dimensions to find any possible dimensional defects. What process is this? | Manage quality | Plan quality management | Control scope | Control quality | Quality Management | Monitoring and Controlling | False | "17"
As a project manager, what should you use to compare different suppliers and rate their proposals? | Bid documents | Bidder conferences | A contract. | Evaluation criteria | As a project manager, what should you use to compare different suppliers and rate their proposals? | Bid documents | Bidder conferences | A contract. | Evaluation criteria | Procurement Management | Planning | False | "17"
To compare different vendors and rate their proposals, as a project manager, what should you use? | Bid documents | Bidder conferences | A contract | Evaluation criteria | To compare different vendors and rate their proposals, as a project manager, what should you use? | Bid documents | Bidder conferences | A contract | Evaluation criteria | Procurement Management | Planning | False | "19"
Which of the following is neither an input to nor an output of the Develop Project Charter process? | A project charter | A business case | Benefits management plan | Expert Judgment | Which of the following is neither an input to nor an output of the Develop Project Charter process? | A project charter | A business case | Benefits management plan | Expert Judgment | Integration Management | Initiating | False | "20"
As project manager, what a proper the following techniques help to identify and analyze risks? | Probability and impact matrix. | SWOT Analysis | Monte Carol | Expert Judgment | As project manager, what a proper the following techniques help to identify and analyze risks? | Probability and impact matrix. | SWOT Analysis | Monte Carol | Expert Judgment | Risk Management | Planning | False | "19"
You are a project manager for a company that provides catering services for events, each of which is managed as a project. The company is awarded a contract to cater a conference for 1,500 participants. The conference organizer conducts an inspection of the delivered food and beverages and discovers that 10 out of 10.000 soft drink bottles were out of date. Based on that, the conference organizer rejects the entire delivery. The project manager's company is now faced with replacement costs, the loss of credibility, and disrupted logistics. To what cost of quality (COQ) category do these costs belong? | Internal failure. | Appraisal. | Prevention | External failure. | You are a project manager for a company that provides catering services for events, each of which is managed as a project. The company is awarded a contract to cater a conference for 1,500 participants. The conference organizer conducts an inspection of the delivered food and beverages and discovers that 10 out of 10.000 soft drink bottles were out of date. Based on that, the conference organizer rejects the entire delivery. The project manager's company is now faced with replacement costs, the loss of credibility, and disrupted logistics. To what cost of quality (COQ) category do these costs belong? | Internal failure. | Appraisal. | Prevention | External failure. | Quality Management | Planning | False | "19"
In a conference call, the project manager failed the delivery date. Based on that, the conference organizer rejects the entire delivery. The project manager's company is now faced with replacement costs, the loss of credibility, and disrupted logistics. To what cost of quality (COQ) category do these costs belong? | Internal failure. | Appraisal. | Prevention | External failure. | In a conference call, the project manager failed the delivery date. Based on that, the conference organizer rejects the entire delivery. The project manager's company is now faced with replacement costs, the loss of credibility, and disrupted logistics. To what cost of quality (COQ) category do these costs belong? | Internal failure. | Appraisal. | Prevention | External failure. | Quality Management | Planning | False | "20"
A project manager managing a project with extreme weather expected soon. The project is over budget, and the project sponsor can not provide additional funding. To achieve the milestone before the extreme weather begins, which of the following techniques should the project manager use? | Resource leveling | Crashing | What-if scenario analysis | Fast-tracking | A project manager managing a project with extreme weather expected soon. The project is over budget, and the project sponsor can not provide additional funding. To achieve the milestone before the extreme weather begins, which of the following techniques should the project manager use? | Resource leveling | Crashing | What-if scenario analysis | Fast-tracking | Schedule Management | Planning | False | "19"
Which of the following techniques should a project manager use to optimize and reduce the duration of a project? | Simulation | Critical path method | Resource leveling | Fast-tracking | Which of the following techniques should a project manager use to optimize and reduce the duration of a project? | Simulation | Critical path method | Resource leveling | Fast-tracking | Schedule Management | Planning | False | "20"
When an organization identifies an opportunity to which it would like to respond, it often initiates a: | Project scope statement | Enterprise Environmental Factors | Lessons learned knowledge base | Feasibility study | When an organization identifies an opportunity to which it would like to respond, it often initiates a: | Project scope statement | Enterprise Environmental Factors | Lessons learned knowledge base | Feasibility study | Integration Management | Initiating | False | "16"
A project sponsor ask the project manager to obtain a summary of the performance of a project that recently closed. What document can the project manager provide the sponsor and contain this information? | Work performance information | Project management plan | Work performance report | Final report | A project sponsor ask the project manager to obtain a summary of the performance of a project that recently closed. What document can the project manager provide the sponsor and contain this information? | Work performance information | Project management plan | Work performance report | Final report | Integration Management | Closing | False | "18"
You have been managing a construction new industries project in a developing country, and now you are closing the project. The project completed on schedule and under budget. The general manager of your company heard about the success of your project and wants a summary overview of project performance so that he can talk about your success at the next board meeting. What should you provide to him? | lessons learned register | Lessons learned repository | Project Charter | Final report | You have been managing a construction new industries project in a developing country, and now you are closing the project. The project completed on schedule and under budget. The general manager of your company heard about the success of your project and wants a summary overview of project performance so that he can talk about your success at the next board meeting. What should you provide to him? | lessons learned register | Lessons learned repository | Project Charter | Final report | Integration Management | Closing | False | "20"
You are managing a project with project teams in different geographical locations. During project execution, the customer requests a major scope change. The project manager wants to communicate and get approval for this change. What is the BEST communication method for this purpose? | Pull communication | Push communication | Static Communication | Interactive communication | You are managing a project with project teams in different geographical locations. During project execution, the customer requests a major scope change. The project manager wants to communicate and get approval for this change. What is the BEST communication method for this purpose? | Pull communication | Push communication | Static Communication | Interactive communication | Communication Management | Planning | False | "17"
Markus is working on an international project which involves 150 team members and the project budget is $1,400,000. The weekly status meeting is conducted worldwide and is scheduled for Wednesday at 5:00 PM and the duration of the meeting is two hours. All of the team members globally communicate using the video conferencing unit at their location. What kind of communication method is this? | Pull communication | Push communication | Push Pull communication | Interactive communication | Markus is working on an international project which involves 150 team members and the project budget is $1,400,000. The weekly status meeting is conducted worldwide and is scheduled for Wednesday at 5:00 PM and the duration of the meeting is two hours. All of the team members globally communicate using the video conferencing unit at their location. What kind of communication method is this? | Pull communication | Push communication | Push Pull communication | Interactive communication | Communication Management | Planning | False | "20"
A project manager wants to recruit another team member to replace an engineer who retired. What document should capture this change? | Ground rules | Organizational process Assets. | Project management plan. | Responsibility assignments matrix (RAM) | A project manager wants to recruit another team member to replace an engineer who retired. What document should capture this change? | Ground rules | Organizational process Assets. | Project management plan. | Responsibility assignments matrix (RAM) | Resources Management | Planning | False | "19"
The customer wants to remove certain characteristics from the product. The project manager submits a change request which is approved by the change control board (CCB). What should the project manager do next? | Update the risk register. | Update the project charter. | Update the issue log. | Update the project management plan. | The customer wants to remove certain characteristics from the product. The project manager submits a change request which is approved by the change control board (CCB). What should the project manager do next? | Update the risk register. | Update the project charter. | Update the issue log. | Update the project management plan. | Integration Management | Monitoring and Controlling | False | "16"
In your project, the Schedule Performance Index SPI is 0.7, and Cost Performance Index CPI 1.1. You analyzed the baseline and decided to return the schedule back to meet the baseline. You will: | Terminate the project. | Check with your sponsor. | Check tasks which can be removed from baseline. | Check options of crashing or fast-tracking the project. | In your project, the Schedule Performance Index SPI is 0.7, and Cost Performance Index CPI 1.1. You analyzed the baseline and decided to return the schedule back to meet the baseline. You will: | Terminate the project. | Check with your sponsor. | Check tasks which can be removed from baseline. | Check options of crashing or fast-tracking the project. | Schedule Management | Monitoring and Controlling | False | "17"
An experienced engineer is hired to supervise a subcontractor hired for a project. The experienced engineer uses an effective cost control technique, but it is not the agreed-upon technique for the project. This causes conflicts with the integration group reconciling the monthly reports. What should the project manager do? | Force the new employee to follow the agreed-upon technique. | Initiate a change request to resolve the issue. | Search for solutions that are similar to the existing technique. | Emphasize the advantage of the new method and change the technique with which costs are managed. | An experienced engineer is hired to supervise a subcontractor hired for a project. The experienced engineer uses an effective cost control technique, but it is not the agreed-upon technique for the project. This causes conflicts with the integration group reconciling the monthly reports. What should the project manager do? | Force the new employee to follow the agreed-upon technique. | Initiate a change request to resolve the issue. | Search for solutions that are similar to the existing technique. | Emphasize the advantage of the new method and change the technique with which costs are managed. | Cost Management | Monitoring and Controlling | False | "18"
You are managing a project that is in its first month of execution. In one of the meetings, a key stakeholder asks for some changes to be made in the ongoing work. The stakeholder is asking for the changes to be implemented immediately. You realize that the changes being asked for will require update the Project Management Plan and the Scope baseline, which have already been baselined. As a Project manager, which is the best course of action? | Make the changes as they are being asked for by a key stakeholder | Refuse to make the changes as it is a deviation from approved | Scope Analyze the impact of the changes on triple constraints | Generate a change request and submit it to Integrated change control | You are managing a project that is in its first month of execution. In one of the meetings, a key stakeholder asks for some changes to be made in the ongoing work. The stakeholder is asking for the changes to be implemented immediately. You realize that the changes being asked for will require update the Project Management Plan and the Scope baseline, which have already been baselined. As a Project manager, which is the best course of action? | Make the changes as they are being asked for by a key stakeholder | Refuse to make the changes as it is a deviation from approved | Scope Analyze the impact of the changes on triple constraints | Generate a change request and submit it to Integrated change control | Integration Management | Monitoring and Controlling | False | "17"
A change request has been approved to add additional scope to a project. The change will increase the project duration by one month and will increase the budget by $50,000. What should the project manager do next? | Add resources to bring the schedule back on track. | Implement the approved change by following the project management plan. | Use management reserves to cover the cost of the change. | Communicate the change to the relevant stakeholders. | A change request has been approved to add additional scope to a project. The change will increase the project duration by one month and will increase the budget by $50,000. What should the project manager do next? | Add resources to bring the schedule back on track. | Implement the approved change by following the project management plan. | Use management reserves to cover the cost of the change. | Communicate the change to the relevant stakeholders. | Integration Management | Monitoring and Controlling | False | "18"
You are managing a project with a budget of $9,000, and $1,500 has been spent. However, you only completed $1,000 worth of work. Your schedule says that you should have completed 50% of the work. What is the estimate at completion (EAC)? | $13,500 (Based on original project Budget). | $9,000 (Based on original project Budget). | $9,000 (Based on performance data). | $13,500 (Based on performance data). | You are managing a project with a budget of $9,000, and $1,500 has been spent. However, you only completed $1,000 worth of work. Your schedule says that you should have completed 50% of the work. What is the estimate at completion (EAC)? | $13,500 (Based on original project Budget). | $9,000 (Based on original project Budget). | $9,000 (Based on performance data). | $13,500 (Based on performance data). | Cost Management | Monitoring and Controlling | False | "16"
Which of these types of precedence relationships is least commonly used in the Precedence Diagramming Method? | Start to Start | Finish to Finish | Finish to Start | Start to Finish | Which of these types of precedence relationships is least commonly used in the Precedence Diagramming Method? | Start to Start | Finish to Finish | Finish to Start | Start to Finish | Schedule Management | Planning | False | "17"
Increasing the number of resources in order to crash a project schedule does not always cut the time by the same factor. In worst cases, too many resources assigned to an activity may actually increase the activity duration. This is because: | Decrease in cost budget | Funding limit reconciliation | Additional risk introduced due to crashing | Required additional coordination | Increasing the number of resources in order to crash a project schedule does not always cut the time by the same factor. In worst cases, too many resources assigned to an activity may actually increase the activity duration. This is because: | Decrease in cost budget | Funding limit reconciliation | Additional risk introduced due to crashing | Required additional coordination | Schedule Management | Planning | False | "18"
You are a project manager in an IT project. You and key stakeholders start conducting a project benefit analysis. Because of the solutions that have not been identified, an engineer from another department has informed you that there are affected systems. As a project manager, what should you do? | Update the risk register | Identify all stakeholders | Review the project benefit analysis to consider the additional impact | Document the issue in the issue log. | You are a project manager in an IT project. You and key stakeholders start conducting a project benefit analysis. Because of the solutions that have not been identified, an engineer from another department has informed you that there are affected systems. As a project manager, what should you do? | Update the risk register | Identify all stakeholders | Review the project benefit analysis to consider the additional impact | Document the issue in the issue log. | Risk Management | Monitoring and Controlling | False | "18"
A change request has been approved by the change control board CCB. You want to make sure that this change has been implemented correctly. Which process will ensure this? | Direct and Manage Project Work. | Mange Quality. | Monitor and Control Protect Work. | Control Quality. | A change request has been approved by the change control board CCB. You want to make sure that this change has been implemented correctly. Which process will ensure this? | Direct and Manage Project Work. | Mange Quality. | Monitor and Control Protect Work. | Control Quality. | Quality Management | Monitoring and Controlling | False | "16"
As part of earned value management (EVM), The budget at completion (BAC) for the project is SAR 100,000 and the estimate at completion (EAC) is SAR 130,000. If the schedule performance index (SPI) is equal to 1.0. What is the cost performance index (CPI)? | Equal to 1.2 | Greater than 1.0 | Equal to 1.0 | Less than 1.0 | As part of earned value management (EVM), The budget at completion (BAC) for the project is SAR 100,000 and the estimate at completion (EAC) is SAR 130,000. If the schedule performance index (SPI) is equal to 1.0. What is the cost performance index (CPI)? | Equal to 1.2 | Greater than 1.0 | Equal to 1.0 | Less than 1.0 | Cost Management | Monitoring and Controlling | False | "17"
The RACI chart is an example of a responsibility assignment matrix (RAM). The letters R and C in ?RACI? stand for: | Resource and consultant | Responsible and categorize | Resource and consult | Responsible and consult | The RACI chart is an example of a responsibility assignment matrix (RAM). The letters R and C in ?RACI? stand for: | Resource and consultant | Responsible and categorize | Resource and consult | Responsible and consult | Resources Management | Planning | False | "20"
Project costs are estimated for all project activities and are aggregated to establish a cost baseline. Which of the following statements about the cost baseline is not true? | The project cost performance is measured against the cost baseline. | The cost baseline is an output of the determine budget process. | The cost baseline is in the form of an ?S? curve. | The cost baseline includes all authorized budgets, including management reserves. | Project costs are estimated for all project activities and are aggregated to establish a cost baseline. Which of the following statements about the cost baseline is not true? | The project cost performance is measured against the cost baseline. | The cost baseline is an output of the determine budget process. | The cost baseline is in the form of an ?S? curve. | The cost baseline includes all authorized budgets, including management reserves. | Cost Management | Planning | False | "16"
As the project manager of a large project, you are determining the accuracy of the deliverables before closing a project. What process should be used to determine this and is an input to formalizing acceptance? | Accepted deliverables | Manage quality | Control scope | Control quality | As the project manager of a large project, you are determining the accuracy of the deliverables before closing a project. What process should be used to determine this and is an input to formalizing acceptance? | Accepted deliverables | Manage quality | Control scope | Control quality | Scope Management | Monitoring and Controlling | False | "16"
You are calculates the amount of float on various paths in the network diagram to determine the minimum project duration. Which tool or technique you are using to do this? | Three-point estimating | Critical chain method | Parametric estimating | Critical path method | You are calculates the amount of float on various paths in the network diagram to determine the minimum project duration. Which tool or technique you are using to do this? | Three-point estimating | Critical chain method | Parametric estimating | Critical path method | Cost Management | Monitoring and Controlling | False | "19"
Julia is currently recruiting her project team. She has carried out various interviews and has shortlisted potential candidates. Now, according to the project communication management plan, she has to submit the shortlisted profiles to the project client (customer) for approval. Only then, can she formally hire the approved candidates for the project. The submission of the profiles to the client will go through which of the following processes? | Manage Stakeholder Engagement | Acquire Resources | Plan Resource Management | Manage Communications | Julia is currently recruiting her project team. She has carried out various interviews and has shortlisted potential candidates. Now, according to the project communication management plan, she has to submit the shortlisted profiles to the project client (customer) for approval. Only then, can she formally hire the approved candidates for the project. The submission of the profiles to the client will go through which of the following processes? | Manage Stakeholder Engagement | Acquire Resources | Plan Resource Management | Manage Communications | Communication Management | Executing | False | "16"
Haitham is managing a software development project. The buyer of the product is an external entity. During the project?s execution, Haitham finds that a new operations manager was hired in the customer organization. The new manager is now a key stakeholder. Which of the following documents is least likely to be updated because of the addition of this new stakeholder? | Stakeholder register | Risk register | Stakeholder engagement plan | Issue log | Haitham is managing a software development project. The buyer of the product is an external entity. During the project?s execution, Haitham finds that a new operations manager was hired in the customer organization. The new manager is now a key stakeholder. Which of the following documents is least likely to be updated because of the addition of this new stakeholder? | Stakeholder register | Risk register | Stakeholder engagement plan | Issue log | Stakeholder Management | Planning | False | "20"
A project manager must stress the importance of collecting and documenting lessons learned through the project lifecycle. One good way to collect this information is during weekly status meetings. Usually, weekly status meetings, if not managed properly, end up in firefighting since most of the time, attention goes to the burning issues. How can you ensure that the lessons-learned gathering does not get missed in such a situation? | Record the minutes of the meeting | Do not discuss burning issues in weekly status meetings | Replace status update meetings with one-on-one meetings with the team members | Add a lessons-learned agenda item | A project manager must stress the importance of collecting and documenting lessons learned through the project lifecycle. One good way to collect this information is during weekly status meetings. Usually, weekly status meetings, if not managed properly, end up in firefighting since most of the time, attention goes to the burning issues. How can you ensure that the lessons-learned gathering does not get missed in such a situation? | Record the minutes of the meeting | Do not discuss burning issues in weekly status meetings | Replace status update meetings with one-on-one meetings with the team members | Add a lessons-learned agenda item | Communication Management | Executing | False | "17"
As part of the Estimate Costs process, a project manager obtained access to certain commercially available databases to get resource cost rate information. Such published commercial information is considered what type of input? | Historical information | Organizational process asset | HR Input | Enterprise environmental factor | As part of the Estimate Costs process, a project manager obtained access to certain commercially available databases to get resource cost rate information. Such published commercial information is considered what type of input? | Historical information | Organizational process asset | HR Input | Enterprise environmental factor | Cost Management | Planning | False | "17"
The term Progressive Elaboration incorrectly represents which of the following? | Rolling wave planning | Detailing out the product requirements developed during the initiation process | Production of fabrication and construction drawings from the design drawings for a chemical plant. | Changes to project scope | The term Progressive Elaboration incorrectly represents which of the following? | Rolling wave planning | Detailing out the product requirements developed during the initiation process | Production of fabrication and construction drawings from the design drawings for a chemical plant. | Changes to project scope | Schedule Management | Planning | False | "19"
No matter how good you are in communicating, information distribution to stakeholders as planned is a challenging task. Many tools and techniques are used during the Manage Communications process except: | Project reporting | Communication technologies | Communication skills | Work performance reports | No matter how good you are in communicating, information distribution to stakeholders as planned is a challenging task. Many tools and techniques are used during the Manage Communications process except: | Project reporting | Communication technologies | Communication skills | Work performance reports | Communication Management | Executing | False | "18"
During execution, a project manager identifies a major obstacle that is delay progress. An escalation to the client's project manager has gone unanswered, and project progress is worsening each week. What should the project manager do? | Inform the supervisor of the client's project manager | Follow the escalation matrix in the project management plan, and escalate it to the next level | Escalate the issue directly to the steering committee | Revise the communication management plan | During execution, a project manager identifies a major obstacle that is delay progress. An escalation to the client's project manager has gone unanswered, and project progress is worsening each week. What should the project manager do? | Inform the supervisor of the client's project manager | Follow the escalation matrix in the project management plan, and escalate it to the next level | Escalate the issue directly to the steering committee | Revise the communication management plan | Communication Management | Executing | False | "19"
A project manager has just started planning his project. If he has only limited information about the project, he should use the following technique to estimate the duration for each activity using historical data from a similar project: | Four-point estimating | Three-point estimating | Parametric estimating | Analogous estimating | A project manager has just started planning his project. If he has only limited information about the project, he should use the following technique to estimate the duration for each activity using historical data from a similar project: | Four-point estimating | Three-point estimating | Parametric estimating | Analogous estimating | Schedule Management | Planning | False | "20"
You have been appointed as a project manager for a new project. After several months, you find that the accounting department has reject all charges because the project was not approved. What should the project manager have done to prevent this? | Obtained the fund needed to start the project | Planned the resources necessary to start the project | Verified that the business case was authorized by the project initiator | Get the project charter approval from the project sponsor | You have been appointed as a project manager for a new project. After several months, you find that the accounting department has reject all charges because the project was not approved. What should the project manager have done to prevent this? | Obtained the fund needed to start the project | Planned the resources necessary to start the project | Verified that the business case was authorized by the project initiator | Get the project charter approval from the project sponsor | Integration Management | Initiating | False | "17"
During the planning phase of your project, the project and product requirements have been identified by the project team. Which of the following tools and techniques will be used to accomplish this? | Network diagram, benchmarking, and project scope statement. | Mind mapping, affinity diagram, and brainstorming. | Observations conversations, trend analysis, and work breakdown structure (WBS). | Observations conversations, benchmarking, and affinity diagram. | During the planning phase of your project, the project and product requirements have been identified by the project team. Which of the following tools and techniques will be used to accomplish this? | Network diagram, benchmarking, and project scope statement. | Mind mapping, affinity diagram, and brainstorming. | Observations conversations, trend analysis, and work breakdown structure (WBS). | Observations conversations, benchmarking, and affinity diagram. | Scope Management | Planning | False | "16"
You are the project manager of a Construction project. The project sponsor has information about the project which is behind schedule and over budget, but he wants more details about the progress of the project. As a project manager, what should you provide to the project sponsor about the status of the project? | Work performance information | Work performance data | Earned value report | Work performance report | You are the project manager of a Construction project. The project sponsor has information about the project which is behind schedule and over budget, but he wants more details about the progress of the project. As a project manager, what should you provide to the project sponsor about the status of the project? | Work performance information | Work performance data | Earned value report | Work performance report | Communication Management | Executing | False | "20"
A stakeholder informs the project manager that they don't receive the weekly project status reports, even though they participated in the project kick-off meeting. What should the project manager do? | Forward the latest report to this stakeholder. | Adjust the stakeholder register to include this stakeholder | Escalate this issue to the project sponsor. | Review the communication management plan. | A stakeholder informs the project manager that they don't receive the weekly project status reports, even though they participated in the project kick-off meeting. What should the project manager do? | Forward the latest report to this stakeholder. | Adjust the stakeholder register to include this stakeholder | Escalate this issue to the project sponsor. | Review the communication management plan. | Communication Management | Executing | False | "19"
The Control Procurements process receives a very important input from the Direct and Manage Project Work process. Which one is it? | Approved change requests | Procurement documents | Agreements | Work performance data | The Control Procurements process receives a very important input from the Direct and Manage Project Work process. Which one is it? | Approved change requests | Procurement documents | Agreements | Work performance data | Procurement Management | Monitoring and Controlling | False | "16"
You are working as a project manager for a high-yield crop development project. Data from the weather agency shows an unfavorable weather pattern for the next few months. As a senior project manager, you want to assess the schedule?s feasibility under adverse conditions and provide some insights to your team. That way, your team can prepare some reserves and plan risk responses if unfavorable conditions exist during execution. Which of the following techniques should you use to simulate risks and other sources of uncertainty to calculate possible schedule outcomes? | Pareto charts | Variance analysis | Crashing | Monte Carlo analysis | You are working as a project manager for a high-yield crop development project. Data from the weather agency shows an unfavorable weather pattern for the next few months. As a senior project manager, you want to assess the schedule?s feasibility under adverse conditions and provide some insights to your team. That way, your team can prepare some reserves and plan risk responses if unfavorable conditions exist during execution. Which of the following techniques should you use to simulate risks and other sources of uncertainty to calculate possible schedule outcomes? | Pareto charts | Variance analysis | Crashing | Monte Carlo analysis | Schedule Management | Planning | False | "16"
What does a Cost Performance Index (CPI) of more than 1.0 indicate? | The project is over budget | The project is right on budget | The project is ahead of schedule | The project is under budget | What does a Cost Performance Index (CPI) of more than 1.0 indicate? | The project is over budget | The project is right on budget | The project is ahead of schedule | The project is under budget | Cost Management | Monitoring and Controlling | False | "19"
Which of the following components of a project scope statement is useful in reducing scope creep? | Acceptance criteria | Deliverables | Scope description | Exclusions | Which of the following components of a project scope statement is useful in reducing scope creep? | Acceptance criteria | Deliverables | Scope description | Exclusions | Scope Management | Planning | False | "17"
While analyzing a project, the project manager calculated the ratio of the Earned Value (EV) to the Actual Costs (AC) and obtained a value of 1.2. The project manager decided this was an unfavorable condition for the project and decided to take corrective action. What is your view? | The project manager is correct. The ratio of EV to AC is the Cost Performance Index and a ratio greater than 1 is unfavorable to the project | The project manager is not correct. The ratio of EV to AC is the Cost Variance and a ratio greater than 1 is favorable to the project | The project manager is correct. The ratio of EV to AC is the Cost Variance and a ratio greater than 1 is unfavorable to the project | The project manager is not correct. The ratio of EV to AC is the Cost Performance Index and a ratio greater than 1 is favorable to the project | While analyzing a project, the project manager calculated the ratio of the Earned Value (EV) to the Actual Costs (AC) and obtained a value of 1.2. The project manager decided this was an unfavorable condition for the project and decided to take corrective action. What is your view? | The project manager is correct. The ratio of EV to AC is the Cost Performance Index and a ratio greater than 1 is unfavorable to the project | The project manager is not correct. The ratio of EV to AC is the Cost Variance and a ratio greater than 1 is favorable to the project | The project manager is correct. The ratio of EV to AC is the Cost Variance and a ratio greater than 1 is unfavorable to the project | The project manager is not correct. The ratio of EV to AC is the Cost Performance Index and a ratio greater than 1 is favorable to the project | Cost Management | Monitoring and Controlling | False | "20"
Ahmad has worked for a retail company as a project manager. With his positive thinking and strong managerial skills, he turned many potentially disastrous projects into successes. Because of his expertise, his employer?s senior executives offered him a group project manager position for a newly started environmental project. However, Ahmad learned that, in his newly assigned project, he might have to offer bribes to obtain government licenses. What should Ahmad do in such a situation? | Accept the offer because project managers must obey their higher-ups | Accept the position and offer bribes because project managers must complete projects on time and within budget | Investigate to find out if it is customary to offer bribes in that part of the country | Reject the offer because project managers should not engage in an unethical conduct | Ahmad has worked for a retail company as a project manager. With his positive thinking and strong managerial skills, he turned many potentially disastrous projects into successes. Because of his expertise, his employer?s senior executives offered him a group project manager position for a newly started environmental project. However, Ahmad learned that, in his newly assigned project, he might have to offer bribes to obtain government licenses. What should Ahmad do in such a situation? | Accept the offer because project managers must obey their higher-ups | Accept the position and offer bribes because project managers must complete projects on time and within budget | Investigate to find out if it is customary to offer bribes in that part of the country | Reject the offer because project managers should not engage in an unethical conduct | Integration Management | Initiating | False | "18"
You are managing a heavy equipment manufacturing project that involves many mechanical, electrical, and IT staff. Your team prepared a schedule network diagram using duration estimates with dependencies and constraints. Your team also calculated the critical path for the project using late and early values. Today, your project office has indicated to you that some of the resources you had planned for the project will be unavailable. To deal with this, you explore the possibility of modifying the schedule to account for limited resources. What is your best possible step in such a situation? | Perform Resource Leveling to account for limited resources | Use crashing or fast tracking to level resources across the project | Apply leads and lags to develop a viable schedule | Recalculate critical path after applying the resource constraints | You are managing a heavy equipment manufacturing project that involves many mechanical, electrical, and IT staff. Your team prepared a schedule network diagram using duration estimates with dependencies and constraints. Your team also calculated the critical path for the project using late and early values. Today, your project office has indicated to you that some of the resources you had planned for the project will be unavailable. To deal with this, you explore the possibility of modifying the schedule to account for limited resources. What is your best possible step in such a situation? | Perform Resource Leveling to account for limited resources | Use crashing or fast tracking to level resources across the project | Apply leads and lags to develop a viable schedule | Recalculate critical path after applying the resource constraints | Schedule Management | Planning | False | "17"
Salwa has to brief her key project stakeholders on the recent approved changes to the project scope. Which of the following project documents will provide essential input to Salwa for preparing her presentation? | Change request form | Change control procedures | Issue management procedures | Change log | Salwa has to brief her key project stakeholders on the recent approved changes to the project scope. Which of the following project documents will provide essential input to Salwa for preparing her presentation? | Change request form | Change control procedures | Issue management procedures | Change log | Integration Management | Monitoring and Controlling | False | "19"
While creating the probability and impact matrix, what should the project manager and his team consider to support the project risk analysis? | Project scope and project deliverables. | Project quality and resources. | Contingency reserve for budget and schedule. | Possible effects on the objectives of the project. | While creating the probability and impact matrix, what should the project manager and his team consider to support the project risk analysis? | Project scope and project deliverables. | Project quality and resources. | Contingency reserve for budget and schedule. | Possible effects on the objectives of the project. | Quality Management | Planning | False | "16"
A project manager joins a global project that will be supported by virtual teams in different time zones. How should the project manager share information in this situation? | Review the responsibility assignments matrix (RAM) to understand the virtual teams' roles | Use the resource breakdown structure (RBS) to set up the virtual teams. | Communicate the work breakdown structure(WBS) to the virtual team members. | Employ project communication and technical tools to adapt to the virtual teams. | A project manager joins a global project that will be supported by virtual teams in different time zones. How should the project manager share information in this situation? | Review the responsibility assignments matrix (RAM) to understand the virtual teams' roles | Use the resource breakdown structure (RBS) to set up the virtual teams. | Communicate the work breakdown structure(WBS) to the virtual team members. | Employ project communication and technical tools to adapt to the virtual teams. | Communication Management | Executing | False | "20"
A functional manager for the organization is also the direct supervisor for one of the team members on a current project. The functional manager requests that the project manager provide a weekly summary of the team member's work performance. The functional manager and the project manager are not in the same geographical area. What should the project manager do? | Make a phone call at the end of the week to quickly debrief the functional manager on the tasks performed. | Hold a weekly meeting with the functional manager to review the tasks performed. | Deny the functional manager's request and escalate the situation to the steering committee. | Draft a weekly email to the functional manager with a short list of the tasks performed. | A functional manager for the organization is also the direct supervisor for one of the team members on a current project. The functional manager requests that the project manager provide a weekly summary of the team member's work performance. The functional manager and the project manager are not in the same geographical area. What should the project manager do? | Make a phone call at the end of the week to quickly debrief the functional manager on the tasks performed. | Hold a weekly meeting with the functional manager to review the tasks performed. | Deny the functional manager's request and escalate the situation to the steering committee. | Draft a weekly email to the functional manager with a short list of the tasks performed. | Communication Management | Executing | False | "19"
A project manager is meeting with the steering committee to obtain approval to deploy a develop software solution. After ten minutes of explaining why the solution is ready for deployment, the project manager is told to better prepare and return with more facts. What should the project manager do to improve their approach? | Email the steering committee explaining why the solution is ready for deployment. | Ask the sponsor to directly obtain approval from the steering committee. | Ask the project administrator to explain that user acceptance testing was completed then present this to the steering committee. | Review the communication management plan and present that all deliverables have been developed and are ready for deployment. | A project manager is meeting with the steering committee to obtain approval to deploy a develop software solution. After ten minutes of explaining why the solution is ready for deployment, the project manager is told to better prepare and return with more facts. What should the project manager do to improve their approach? | Email the steering committee explaining why the solution is ready for deployment. | Ask the sponsor to directly obtain approval from the steering committee. | Ask the project administrator to explain that user acceptance testing was completed then present this to the steering committee. | Review the communication management plan and present that all deliverables have been developed and are ready for deployment. | Communication Management | Executing | False | "20"
Which of the following items can be defined by creating the Cost Management Plan of a project? | Level of accuracy and Work Packages | Rules of Performance Measurement and Rewards | Units of Measure and Quality Metrics | Control Thresholds and Units of Measure | Which of the following items can be defined by creating the Cost Management Plan of a project? | Level of accuracy and Work Packages | Rules of Performance Measurement and Rewards | Units of Measure and Quality Metrics | Control Thresholds and Units of Measure | Cost Management | Planning | False | "18"
You have recently taken over a troubled automobile project, which has gone out of control. The project team missed many deadlines, and stakeholders were displeased with the project?s progress. As an experienced project manager, your first priority is to align the schedule with the project plan. You would like to use what-if scenario analysis to see how various factors affected the project schedule so you can develop a plan to reduce the impact of adverse conditions on the project schedule in the future. What would be your next course of action be, once you determine the factors that created schedule overruns? | Prepare a resource breakdown structure to identify resources used | Update activity lists to incorporate new activities into the schedule | Develop project schedule network diagrams to determine the total slack | Generate change requests for a corrective action | You have recently taken over a troubled automobile project, which has gone out of control. The project team missed many deadlines, and stakeholders were displeased with the project?s progress. As an experienced project manager, your first priority is to align the schedule with the project plan. You would like to use what-if scenario analysis to see how various factors affected the project schedule so you can develop a plan to reduce the impact of adverse conditions on the project schedule in the future. What would be your next course of action be, once you determine the factors that created schedule overruns? | Prepare a resource breakdown structure to identify resources used | Update activity lists to incorporate new activities into the schedule | Develop project schedule network diagrams to determine the total slack | Generate change requests for a corrective action | Schedule Management | Monitoring and Controlling | False | "18"
The Company CEO is asking you to make a presentation on your project, which has been in progress for 18 months to over 50 identified internal and external stakeholders. You have been conducting such presentations and holding meetings regularly on this critical project. You should begin by? | Deciding on the general form of the presentation | Determining the objective | Defining the audience | Circulating issues to be discussed | The Company CEO is asking you to make a presentation on your project, which has been in progress for 18 months to over 50 identified internal and external stakeholders. You have been conducting such presentations and holding meetings regularly on this critical project. You should begin by? | Deciding on the general form of the presentation | Determining the objective | Defining the audience | Circulating issues to be discussed | Communication Management | Executing | False | "19"
The Requirements Traceability Matrix helps in tracing all the following except: | Requirements to project objectives | Requirements to project scope | Requirements to test strategy | Requirements to project risk | The Requirements Traceability Matrix helps in tracing all the following except: | Requirements to project objectives | Requirements to project scope | Requirements to test strategy | Requirements to project risk | Scope Management | Planning | False | "18"
You are managing a IT project. After identifying risks, you start the qualitative risk analysis process and now you are going to prioritize them. Which of the following techniques you are going to use? | Tornado diagram. | Scatter diagram. | Sensitive analysis. | Probability and impact matrix. | You are managing a IT project. After identifying risks, you start the qualitative risk analysis process and now you are going to prioritize them. Which of the following techniques you are going to use? | Tornado diagram. | Scatter diagram. | Sensitive analysis. | Probability and impact matrix. | Risk Management | Planning | False | "16"
Fatimah can bid on two projects. Project A has a 50 percent return on investment while Project B has a 20 percent return on investment. Project A?s scope of work is complex, and Fatimah?s organization does not have the necessary skills and experience to do this project. However, Project B?s scope of work falls within the strengths of Fatimah?s organization. Which project must Fatimah bid on? | None as this is a conflict of interest situation | Both since the overall profit will be higher | Project A since the return on investment is the highest | Project B since the organization has the required skills | Fatimah can bid on two projects. Project A has a 50 percent return on investment while Project B has a 20 percent return on investment. Project A?s scope of work is complex, and Fatimah?s organization does not have the necessary skills and experience to do this project. However, Project B?s scope of work falls within the strengths of Fatimah?s organization. Which project must Fatimah bid on? | None as this is a conflict of interest situation | Both since the overall profit will be higher | Project A since the return on investment is the highest | Project B since the organization has the required skills | Integration Management | Initiating | False | "19"
A recently promoted project manager must mange the weekly status update meeting. What should the project manager do to ensure a productive meeting? | Limit attendance to the project team and stakeholders | Avoid or smooth over any disagreements | Carefully read the latest meeting minutes | Circulate a defined agenda in advance | A recently promoted project manager must mange the weekly status update meeting. What should the project manager do to ensure a productive meeting? | Limit attendance to the project team and stakeholders | Avoid or smooth over any disagreements | Carefully read the latest meeting minutes | Circulate a defined agenda in advance | Communication Management | Executing | False | "20"
You are in the Validate Scope process of your electronic goods manufacturing project. While reviewing some products, you have noticed that the tolerance for one product is 0.01 percent less than what was listed in the requirements documentation. This deviation may not be a problem for the customers, and it may not impair the product?s operation. What is your best immediate action in such a situation? | Change the project management plan to allow for small deviation | Reject all products and restart the project | Discuss with your team about the quality testing | Notify the stakeholders about the deviation | You are in the Validate Scope process of your electronic goods manufacturing project. While reviewing some products, you have noticed that the tolerance for one product is 0.01 percent less than what was listed in the requirements documentation. This deviation may not be a problem for the customers, and it may not impair the product?s operation. What is your best immediate action in such a situation? | Change the project management plan to allow for small deviation | Reject all products and restart the project | Discuss with your team about the quality testing | Notify the stakeholders about the deviation | Scope Management | Monitoring and Controlling | False | "17"
A stakeholder with a high degree of impact now requires more detailed project reports. What should the project manager do? | Meet with the project sponsor to discuss the issue. | Escalate the issue to the project management office. | Work with the project team to prepare a new project charter. | Work with the project team to update the communication management plan. | A stakeholder with a high degree of impact now requires more detailed project reports. What should the project manager do? | Meet with the project sponsor to discuss the issue. | Escalate the issue to the project management office. | Work with the project team to prepare a new project charter. | Work with the project team to update the communication management plan. | Communication Management | Executing | False | "19"
You just completed the first phase of a multi-phase project. You have calculated earned value measurements and found that the current CPI is 0.79 and the current SPI is 0.98. Your next phase plan should focus first on which element of the project: | Quality | Resources | Schedule | Cost | You just completed the first phase of a multi-phase project. You have calculated earned value measurements and found that the current CPI is 0.79 and the current SPI is 0.98. Your next phase plan should focus first on which element of the project: | Quality | Resources | Schedule | Cost | Cost Management | Monitoring and Controlling | False | "19"
You are a project manager managing a decoration project. Your project team sent confidential information to the subcontractor by mistake. What could have prevented this situation? | Reviewing the stakeholder engagement Plan | Reviewing the Scope management Plan | Review stakeholder register | Reviewing the Communication management Plan | You are a project manager managing a decoration project. Your project team sent confidential information to the subcontractor by mistake. What could have prevented this situation? | Reviewing the stakeholder engagement Plan | Reviewing the Scope management Plan | Review stakeholder register | Reviewing the Communication management Plan | Communication Management | Executing | False | "20"
You are a project manager for an construction project. During the implementation phase, you found that there is a great opportunity and you decide to transfer the ownership of an opportunity to a third party so that it shares some of the benefits if the opportunity occurs. Therefore, a joint venture was made with another company to catch these benefits. Now, you became responsible for the project as a whole. What will your next step be? | Update Resource Management Plan | Update Project Team Assignment | Update Cost Management Plan | Update Communication Management Plan | You are a project manager for an construction project. During the implementation phase, you found that there is a great opportunity and you decide to transfer the ownership of an opportunity to a third party so that it shares some of the benefits if the opportunity occurs. Therefore, a joint venture was made with another company to catch these benefits. Now, you became responsible for the project as a whole. What will your next step be? | Update Resource Management Plan | Update Project Team Assignment | Update Cost Management Plan | Update Communication Management Plan | Communication Management | Executing | False | "19"
Your project team has recently identified a risk in the software development project and decided not to change the project management plan to deal with the risk. The risk response strategy that your team used in this scenario is an example of: | Mitigate | Transfer | Avoid | Acceptance | Your project team has recently identified a risk in the software development project and decided not to change the project management plan to deal with the risk. The risk response strategy that your team used in this scenario is an example of: | Mitigate | Transfer | Avoid | Acceptance | Risk Management | Planning | False | "17"
As a project manager, what is the estimating technique should be used to estimate a project cost using a firm-fixed-price contract? | Parametric Estimating | Analogous Estimating | Program Evaluation and Review Technique (PERT) | Bottom-up Estimating | As a project manager, what is the estimating technique should be used to estimate a project cost using a firm-fixed-price contract? | Parametric Estimating | Analogous Estimating | Program Evaluation and Review Technique (PERT) | Bottom-up Estimating | Cost Management | Planning | False | "19"
Which of the following is not an example of parametric estimating? | Activity duration estimated based on the number of drawings multiplied by the number of labor hours per drawing. | Activity duration estimated based on the number of labor hours per meter for cable installation. | Activity duration estimated based on the square footage in construction. | Activity duration estimated based on the actual duration of a similar, previous project. | Which of the following is not an example of parametric estimating? | Activity duration estimated based on the number of drawings multiplied by the number of labor hours per drawing. | Activity duration estimated based on the number of labor hours per meter for cable installation. | Activity duration estimated based on the square footage in construction. | Activity duration estimated based on the actual duration of a similar, previous project. | Schedule Management | Planning | False | "18"
Which document describes the project's deliverables and the work required to create those deliverables? | Project authorization document | Project scope management plan | Project charter | Project scope statement | Which document describes the project's deliverables and the work required to create those deliverables? | Project authorization document | Project scope management plan | Project charter | Project scope statement | Scope Management | Planning | False | "19"
A project charter that formally authorized a project was created. The project charter documented the initial requirements to satisfy stakeholders' needs and expectations. How often should the project charter be revised? | At the beginning, middle, and end of a project | Once a month | As required by the PMO | Project charter is usually not updated during the course of the project. | A project charter that formally authorized a project was created. The project charter documented the initial requirements to satisfy stakeholders' needs and expectations. How often should the project charter be revised? | At the beginning, middle, and end of a project | Once a month | As required by the PMO | Project charter is usually not updated during the course of the project. | Integration Management | Initiating | False | "20"
A project can be authorized by any of the following except: | The PMO | The sponsor | The portfolio steering committee | The project manager | A project can be authorized by any of the following except: | The PMO | The sponsor | The portfolio steering committee | The project manager | Integration Management | Initiating | False | "18"
You have been asked by your project manager to help create a chart that illustrates the project resources that will be working on each work package. What would be the best type of chart to use? | WBS | Milestone chart | Project organization chart | RACI chart | You have been asked by your project manager to help create a chart that illustrates the project resources that will be working on each work package. What would be the best type of chart to use? | WBS | Milestone chart | Project organization chart | RACI chart | Resources Management | Planning | False | "18"
You are working with your customers on completing deliverables in your electronic parts manufacturing project. Since these parts will be exported to other countries, they will need more testing before your customers accept them. In this scenario, which of the following statements about the completed deliverables is correct? | Completed deliverables not accepted by customers must be forwarded to the close project or phase process. | Deliverables formally accepted by customers must be moved to organizational process assets. | Deliverables formally accepted by customers are forwarded to the validate scope process. | Completed deliverables not accepted by customers must require a change request for defect repair. | You are working with your customers on completing deliverables in your electronic parts manufacturing project. Since these parts will be exported to other countries, they will need more testing before your customers accept them. In this scenario, which of the following statements about the completed deliverables is correct? | Completed deliverables not accepted by customers must be forwarded to the close project or phase process. | Deliverables formally accepted by customers must be moved to organizational process assets. | Deliverables formally accepted by customers are forwarded to the validate scope process. | Completed deliverables not accepted by customers must require a change request for defect repair. | Scope Management | Monitoring and Controlling | False | "18"
All the following are tools of the Control Schedule process except: | Critical Path Method | Schedule compression | Leads and lags | Parametric estimating | All the following are tools of the Control Schedule process except: | Critical Path Method | Schedule compression | Leads and lags | Parametric estimating | Schedule Management | Monitoring and Controlling | False | "20"
A project has a senior stakeholder whose input is important, and who needs to be kept informed about the project's status. Rather than receive updates from the project manager, this stakeholder prefers to contact a team member directly. The stakeholder has a connection with this team members that is unrelated to the project and thinks that this is a way to obtain information on the project's true status. What should the project manager do? | Keep the team member properly informed about project status so that the stakeholder receives the same information from both sources. | Leave the connection in place, since the information coming via the team member is unofficial and will not create problems. | Tell the team member not to accept calls from the stakeholder, because these calls have an adverse effect on the team member's productivity. | Ask the stakeholder how the additional information that they feel is missing from current communications may be provided. | A project has a senior stakeholder whose input is important, and who needs to be kept informed about the project's status. Rather than receive updates from the project manager, this stakeholder prefers to contact a team member directly. The stakeholder has a connection with this team members that is unrelated to the project and thinks that this is a way to obtain information on the project's true status. What should the project manager do? | Keep the team member properly informed about project status so that the stakeholder receives the same information from both sources. | Leave the connection in place, since the information coming via the team member is unofficial and will not create problems. | Tell the team member not to accept calls from the stakeholder, because these calls have an adverse effect on the team member's productivity. | Ask the stakeholder how the additional information that they feel is missing from current communications may be provided. | Communication Management | Executing | False | "20"
As a project manager, you are working on high rise building project. You are struggling to arrange your first meeting with project resources. What should you do to ensure resource collaboration? | Obtain the general manager's authorization | Obtain Business case approval from the project sponsor | Meet with each stakeholder individually | Obtain project charter approval | As a project manager, you are working on high rise building project. You are struggling to arrange your first meeting with project resources. What should you do to ensure resource collaboration? | Obtain the general manager's authorization | Obtain Business case approval from the project sponsor | Meet with each stakeholder individually | Obtain project charter approval | Integration Management | Initiating | False | "19"
Main Sponsor is really interested in reviewing the key performance indicators of the project. Where will you find this information for the project? | KPI is part of the change control tool | KPI can be part of organizational process assets | KPI is included in the project charter in the business case section | KPI is included in the project charter as success criteria | Main Sponsor is really interested in reviewing the key performance indicators of the project. Where will you find this information for the project? | KPI is part of the change control tool | KPI can be part of organizational process assets | KPI is included in the project charter in the business case section | KPI is included in the project charter as success criteria | Integration Management | Initiating | False | "20"
A recently promoted project manager must facilitate the monthly status update meeting. What should the project manager do to ensure a productive meeting? | Limit attendance to the project team and stakeholders | Avoid or smooth over any disagreements | Carefully read the latest meeting minutes | Circulate a defined agenda | A recently promoted project manager must facilitate the monthly status update meeting. What should the project manager do to ensure a productive meeting? | Limit attendance to the project team and stakeholders | Avoid or smooth over any disagreements | Carefully read the latest meeting minutes | Circulate a defined agenda | Communication Management | Executing | False | "19"
A project manager needed to shorten a project schedule and decided to employ crashing, a schedule compression technique. Which of the following activities would not be an example of crashing? | Paying to expedite delivery activities | Bringing in additional resources | Approving overtime | Reducing project scope | A project manager needed to shorten a project schedule and decided to employ crashing, a schedule compression technique. Which of the following activities would not be an example of crashing? | Paying to expedite delivery activities | Bringing in additional resources | Approving overtime | Reducing project scope | Schedule Management | Planning | False | "19"
_______________ is the authorized budget for the work scheduled to be completed on an activity or WBS component. | Earned value | Midpoint cost | Interim cost | Planned value | _______________ is the authorized budget for the work scheduled to be completed on an activity or WBS component. | Earned value | Midpoint cost | Interim cost | Planned value | Cost Management | Monitoring and Controlling | False | "20"
Decision tree analysis is used to calculate the average outcome when the future includes scenarios that may or may not happen. What are a decision node?s inputs and outputs? | Input: Cost of each decision; Output: Probability of occurrence | Input: Scenario probability; Output: Expected Monetary Value (EMV) | Input: Cost of each decision; Output: Payoff | Input: Cost of each decision; Output: Decision made | Decision tree analysis is used to calculate the average outcome when the future includes scenarios that may or may not happen. What are a decision node?s inputs and outputs? | Input: Cost of each decision; Output: Probability of occurrence | Input: Scenario probability; Output: Expected Monetary Value (EMV) | Input: Cost of each decision; Output: Payoff | Input: Cost of each decision; Output: Decision made | Risk Management | Planning | False | "18"
As you are project manager managing project, in which of the following techniques are used to determine the type, format of information needed and the communication needs of the project stakeholders? | Communication models | Communication Method; | Root Cause Analysis | Communication requirements analysis | As you are project manager managing project, in which of the following techniques are used to determine the type, format of information needed and the communication needs of the project stakeholders? | Communication models | Communication Method; | Root Cause Analysis | Communication requirements analysis | Communication Management | Executing | False | "20"
Which of the following project processes would you use to monitor the implementation of approved changes? | Control Scope | Perform Integrated Change Control | Validate Scope | Monitor and Control Project Work | Which of the following project processes would you use to monitor the implementation of approved changes? | Control Scope | Perform Integrated Change Control | Validate Scope | Monitor and Control Project Work | Integration Management | Initiating | False | "18"
You and your team have compiled your project's activity list, determined how the activities should be performed, and analyzed the schedule. You are preparing information for the project sponsor to highlight the identified activities that may create a delay in the overall project schedule. Which of the following would be most useful in this situation? | Project calendars | Activity attributes | Duration estimates | Project schedule network diagrams | You and your team have compiled your project's activity list, determined how the activities should be performed, and analyzed the schedule. You are preparing information for the project sponsor to highlight the identified activities that may create a delay in the overall project schedule. Which of the following would be most useful in this situation? | Project calendars | Activity attributes | Duration estimates | Project schedule network diagrams | Schedule Management | Planning | False | "20"
The project you are working on has received an invoice from a vendor for US$17,500. However, your team believes the correct total due is US$15,300. When you notify the vendor, the vendor still insists on US$17,500. What is the best course of action now? | Pay $15,300 | File a lawsuit | Pay $17,500 | Negotiate with the vendor | The project you are working on has received an invoice from a vendor for US$17,500. However, your team believes the correct total due is US$15,300. When you notify the vendor, the vendor still insists on US$17,500. What is the best course of action now? | Pay $15,300 | File a lawsuit | Pay $17,500 | Negotiate with the vendor | Procurement Management | Monitoring and Controlling | False | "17"
Which of the following statements is correct regarding the kickoff meeting? | Just to inform and engage stakeholders | Just to get the commitment | Just to inform | Kickoff meeting is conducted not only to inform but also to engage and gain commitment from stakeholders | Which of the following statements is correct regarding the kickoff meeting? | Just to inform and engage stakeholders | Just to get the commitment | Just to inform | Kickoff meeting is conducted not only to inform but also to engage and gain commitment from stakeholders | Integration Management | Planning | False | "16"
As project manager managing project, you are in the process of creating tailored reports for project stakeholders. You are reviewing various plans and project documents but find something important missing in order to get the details to do this. What could it be? | The scope baseline | Issues escalated downward from the program level | Issues escalated upward to the program level | Work performance reports | As project manager managing project, you are in the process of creating tailored reports for project stakeholders. You are reviewing various plans and project documents but find something important missing in order to get the details to do this. What could it be? | The scope baseline | Issues escalated downward from the program level | Issues escalated upward to the program level | Work performance reports | Communication Management | Executing | False | "19"
(EEF) enterprise environmental factors play an important role during the development of the project charter. It includes some elements such as: | Organizational standard policies, processes, and procedures | Templates (e.g., project charter template) | Historical information and lessons learned . | Organizational culture and political climate | (EEF) enterprise environmental factors play an important role during the development of the project charter. It includes some elements such as: | Organizational standard policies, processes, and procedures | Templates (e.g., project charter template) | Historical information and lessons learned . | Organizational culture and political climate | Integration Management | Initiating | False | "19"
A project progressing on time and within budget is 40 days away from achieving its main milestone. The project manager then learns that a key component to achieve this milestone will be unavailable for 60 days. What should the project manager do? | Send an amended progress report to all stakeholders. | Notify stakeholders at the next project status meeting. | Revise the risk management plan. | Update the issue log. | A project progressing on time and within budget is 40 days away from achieving its main milestone. The project manager then learns that a key component to achieve this milestone will be unavailable for 60 days. What should the project manager do? | Send an amended progress report to all stakeholders. | Notify stakeholders at the next project status meeting. | Revise the risk management plan. | Update the issue log. | Integration Management | Executing | False | "16"
Analysis of project spending against project budget and calculation of the percentage complete of tasks currently underway are examples of: | Control Chart | PERT analysis | Expert judgment | Performance reviews | Analysis of project spending against project budget and calculation of the percentage complete of tasks currently underway are examples of: | Control Chart | PERT analysis | Expert judgment | Performance reviews | Cost Management | Monitoring and Controlling | False | "18"
Which of the following is true about risks? | A risk usually has a single cause and, if it occurs, may have one or more effects. | A risk usually has a single cause and, if it occurs, usually has a single effect. | A risk usually has more than one cause, and if it occurs, usually has a single effect. | A risk may have one or more causes, and, if it occurs, may have one or more effects. | Which of the following is true about risks? | A risk usually has a single cause and, if it occurs, may have one or more effects. | A risk usually has a single cause and, if it occurs, usually has a single effect. | A risk usually has more than one cause, and if it occurs, usually has a single effect. | A risk may have one or more causes, and, if it occurs, may have one or more effects. | Risk Management | Planning | False | "19"
Which of the following is not an example of a work performance report? | Status report | Progress report | Project dashboard | Project charter | Which of the following is not an example of a work performance report? | Status report | Progress report | Project dashboard | Project charter | Integration Management | Monitoring and Controlling | False | "20"
A project manager planning the risk responses for his project. He ask the project team to perform more tests on some of the critical applications being developed to minimize the problems during the user acceptance testing phase. This Risk Response is an example of: | Risk Avoidance | Risk Transference | Risk Acceptance | Risk Mitigation | A project manager planning the risk responses for his project. He ask the project team to perform more tests on some of the critical applications being developed to minimize the problems during the user acceptance testing phase. This Risk Response is an example of: | Risk Avoidance | Risk Transference | Risk Acceptance | Risk Mitigation | Risk Management | Planning | False | "20"
You are a project manager in a construction project. The project is ahead of schedule and under budget. A key stakeholder suggests a change to include a value-added feature that wouldn't impact project schedule and cost. What should you do next? | Advise the stakeholder that, since the project is under budget. the feature will be added | Advise the stakeholder that changes shouldn't be implemented when a project is behind schedule. | Update the project management plan to include the new feature. | Evaluate the change's impact with the project team. | You are a project manager in a construction project. The project is ahead of schedule and under budget. A key stakeholder suggests a change to include a value-added feature that wouldn't impact project schedule and cost. What should you do next? | Advise the stakeholder that, since the project is under budget. the feature will be added | Advise the stakeholder that changes shouldn't be implemented when a project is behind schedule. | Update the project management plan to include the new feature. | Evaluate the change's impact with the project team. | Integration Management | Executing | False | "17"
During the kick-off meeting, who should present the executing strategy of the project? | Project Management Team | Project Sponsor | Directive PMO | Project manager | During the kick-off meeting, who should present the executing strategy of the project? | Project Management Team | Project Sponsor | Directive PMO | Project manager | Integration Management | Executing | False | "18"
A first-time project manager created a Work Breakdown Structure (WBS) where the deliverables had different levels of decomposition. What would your comment on this be? | This is incorrect. All deliverables need to have the same level of decomposition. | This is incorrect. Only deliverables under different branches can have different levels of decomposition. | This is fine. The focus of the WBS is not the deliverables but the tasks involved. | This is fine. Different deliverables can have different levels of decomposition, depending on the work involved. | A first-time project manager created a Work Breakdown Structure (WBS) where the deliverables had different levels of decomposition. What would your comment on this be? | This is incorrect. All deliverables need to have the same level of decomposition. | This is incorrect. Only deliverables under different branches can have different levels of decomposition. | This is fine. The focus of the WBS is not the deliverables but the tasks involved. | This is fine. Different deliverables can have different levels of decomposition, depending on the work involved. | Scope Management | Planning | False | "20"
You are managing a project for a customer that has just gone bankrupt and is subject to liquidation proceedings. There are several outstanding invoices this customer has not paid to your company. What should you do now? | Go into alternate dispute resolution | Do nothing | Send the invoices to the bankruptcy attorneys | Contact the appropriate management at your company for advice how to proceed | You are managing a project for a customer that has just gone bankrupt and is subject to liquidation proceedings. There are several outstanding invoices this customer has not paid to your company. What should you do now? | Go into alternate dispute resolution | Do nothing | Send the invoices to the bankruptcy attorneys | Contact the appropriate management at your company for advice how to proceed | Integration Management | Executing | False | "19"
You have just received notice that the organization you have worked for as a project manager has gone bankrupt. All employees have 72 hours? notice of termination. What is the best course of action for the two projects you are managing? | Conduct a project closeout meeting | Leave the office today | Raise a claim for and on behalf of all the employees and contractors who were participating in the project | Follow company directives | You have just received notice that the organization you have worked for as a project manager has gone bankrupt. All employees have 72 hours? notice of termination. What is the best course of action for the two projects you are managing? | Conduct a project closeout meeting | Leave the office today | Raise a claim for and on behalf of all the employees and contractors who were participating in the project | Follow company directives | Integration Management | Executing | False | "20"
The Actual Cost (AC) is the total cost actually incurred and recorded in accomplishing work performed for an activity or work breakdown structure component. What is the upper limit for the AC? | 50 percent over and above the Planned Value (PV) | The Actual Cost (AC) is limited to the Planned Value (PV) | 100 percent over and above the Planned Value (PV) | There is no upper limit for the Actual Cost (AC) | The Actual Cost (AC) is the total cost actually incurred and recorded in accomplishing work performed for an activity or work breakdown structure component. What is the upper limit for the AC? | 50 percent over and above the Planned Value (PV) | The Actual Cost (AC) is limited to the Planned Value (PV) | 100 percent over and above the Planned Value (PV) | There is no upper limit for the Actual Cost (AC) | Cost Management | Monitoring and Controlling | False | "17"
Which of the following is neither an input nor an output of the Direct and Manage Project Work process? | Approved change requests | Change requests | Deliverables | Approved deliverables | Which of the following is neither an input nor an output of the Direct and Manage Project Work process? | Approved change requests | Change requests | Deliverables | Approved deliverables | Integration Management | Executing | False | "16"
A detailed milestone list is created as an output of which process? | Develop Schedule | Sequence Activities | Develop Project Charter | Define Activities | A detailed milestone list is created as an output of which process? | Develop Schedule | Sequence Activities | Develop Project Charter | Define Activities | Schedule Management | Planning | False | "16"
As a project manager, you are responsible for determining and delivering the required levels of both grade and quality. Select which of the following statements you disagree with. | Grade relates to the product's characteristics | Quality relates to the customer requirements | Quality and grade of a product must be carefully managed | Grade relates to the customer requirements | As a project manager, you are responsible for determining and delivering the required levels of both grade and quality. Select which of the following statements you disagree with. | Grade relates to the product's characteristics | Quality relates to the customer requirements | Quality and grade of a product must be carefully managed | Grade relates to the customer requirements | Quality Management | Planning | False | "17"
You are leading your team in the preparation of your project schedule and are currently sequencing the activities and determining which type of precedence relationship exists between them. Which of the following is the most commonly used type of precedence relationship that you will use? | Start-to-start | Finish-to-finish | Start-to-finish | Finish-to-start | You are leading your team in the preparation of your project schedule and are currently sequencing the activities and determining which type of precedence relationship exists between them. Which of the following is the most commonly used type of precedence relationship that you will use? | Start-to-start | Finish-to-finish | Start-to-finish | Finish-to-start | Schedule Management | Planning | False | "17"
A project scope statement is defined with project deliverables, constraints, and assumptions associated with the project objectives. What should the project manager do next? | Take a formal acceptance of the completed project deliverables. | Monitoring the status of the project and product scope and managing changes to the scope baseline. | Determine the products, services, and results to be delivered. | Establish a hierarchical breakdown of the total scope to be carried out by the project team. | A project scope statement is defined with project deliverables, constraints, and assumptions associated with the project objectives. What should the project manager do next? | Take a formal acceptance of the completed project deliverables. | Monitoring the status of the project and product scope and managing changes to the scope baseline. | Determine the products, services, and results to be delivered. | Establish a hierarchical breakdown of the total scope to be carried out by the project team. | Scope Management | Planning | False | "16"
Ali is a Project Manager of a project in which team members have a dual reporting structure. In addition to reporting to him, they also report to their functional manager. Also, the team members are expected to do the project work along with department work. Ali is working in which form of organization? | Functional | Tight Matrix | Projectized | Matrix | Ali is a Project Manager of a project in which team members have a dual reporting structure. In addition to reporting to him, they also report to their functional manager. Also, the team members are expected to do the project work along with department work. Ali is working in which form of organization? | Functional | Tight Matrix | Projectized | Matrix | Integration Management | Executing | False | "17"
The total budget of a 12 month project is SAR 2 million. The project's first three months indicates a cost to date of SAR 500,000 and the earned value is SAR 525,000, and the total amount spent till now is SAR 550,000. What is the project status? | Ahead of schedule and under budget. | Behind schedule and over schedule. | On schedule and on budget. | Ahead of schedule and over budget. | The total budget of a 12 month project is SAR 2 million. The project's first three months indicates a cost to date of SAR 500,000 and the earned value is SAR 525,000, and the total amount spent till now is SAR 550,000. What is the project status? | Ahead of schedule and under budget. | Behind schedule and over schedule. | On schedule and on budget. | Ahead of schedule and over budget. | Cost Management | Monitoring and Controlling | False | "18"
The project manager of a strategic project was approached by the CEO who expressed concern that the project will not be worth the investment. What document should the project manager ask the CEO to review? | Cost management plan | Signed project charter | Company's business plan | Approved business case | The project manager of a strategic project was approached by the CEO who expressed concern that the project will not be worth the investment. What document should the project manager ask the CEO to review? | Cost management plan | Signed project charter | Company's business plan | Approved business case | Integration Management | Initiating | False | "20"
During half of the implementation phase, you notice that a competitor will release the same product into the marketplace. What should you do next? | Update the project charter | Advise the sponsor to cancel the project | Stakeholders analysis | Cost benefit analysis | During half of the implementation phase, you notice that a competitor will release the same product into the marketplace. What should you do next? | Update the project charter | Advise the sponsor to cancel the project | Stakeholders analysis | Cost benefit analysis | Integration Management | Executing | False | "18"
You are over budget and it is impossible to complete the project with the given budget. Therefore, you submit a change request which your management approves. After approval, you update the cost baseline and update other project documents. The document used to register any changes occur during the project execution is known as: | Risk register | RACI matrix | Issue log | Change log | You are over budget and it is impossible to complete the project with the given budget. Therefore, you submit a change request which your management approves. After approval, you update the cost baseline and update other project documents. The document used to register any changes occur during the project execution is known as: | Risk register | RACI matrix | Issue log | Change log | Integration Management | Executing | False | "19"
A project manager is preparing a kick-off meeting for a new service assessment. A high-level description of the service has been provided. What should the project manager do next? | Develop the project charter. | Create the work breakdown structure (WBS). | Develop the responsible, accountable, consult, and inform (RACI) matrix. | Define the project scope statement. | A project manager is preparing a kick-off meeting for a new service assessment. A high-level description of the service has been provided. What should the project manager do next? | Develop the project charter. | Create the work breakdown structure (WBS). | Develop the responsible, accountable, consult, and inform (RACI) matrix. | Define the project scope statement. | Scope Management | Planning | False | "17"
You are the project manager for a large construction project. You want to understand the process for preparing a project scope statement and how formal acceptance of the completed project deliverables will be obtained. Which of the following will you have to reference? | The requirements management plan | The stakeholder management plan | The quality management plan | The scope management plan | You are the project manager for a large construction project. You want to understand the process for preparing a project scope statement and how formal acceptance of the completed project deliverables will be obtained. Which of the following will you have to reference? | The requirements management plan | The stakeholder management plan | The quality management plan | The scope management plan | Scope Management | Planning | False | "18"
You are administering a contract on your project. Your sponsor asks you to give him the list of paid invoices to the seller. He wants a report containing information about the total amount collected by the seller as part of project execution. What documentation would you review in order to provide your sponsor with the report? | Performance Reports | Project Management Plan | Statement of Work | Work Performance Data | You are administering a contract on your project. Your sponsor asks you to give him the list of paid invoices to the seller. He wants a report containing information about the total amount collected by the seller as part of project execution. What documentation would you review in order to provide your sponsor with the report? | Performance Reports | Project Management Plan | Statement of Work | Work Performance Data | Procurement Management | Monitoring and Controlling | False | "19"
You are managing a complex project with many stakeholders each with their own interest in the project. You have begun the process of monitoring overall project stakeholder relationships. Your goal is to increase the efficiency and effectiveness of stakeholder engagement activity. What process are you are engaged in? | Manage Communications | Monitor Communications | Manage Stakeholder Engagement | Monitor Stakeholder Engagement | You are managing a complex project with many stakeholders each with their own interest in the project. You have begun the process of monitoring overall project stakeholder relationships. Your goal is to increase the efficiency and effectiveness of stakeholder engagement activity. What process are you are engaged in? | Manage Communications | Monitor Communications | Manage Stakeholder Engagement | Monitor Stakeholder Engagement | Stakeholder Management | Monitoring and Controlling | False | "18"
You are a project manager managing an IT project. During project closure, customer agreement cannot be achieved through negotiations. What should the project manager do next? | Unresolved claims may be subject to litigation | Start the closing phase | Inform project team members | Seek arbitration following the alternative dispute resolution ADR procedures | You are a project manager managing an IT project. During project closure, customer agreement cannot be achieved through negotiations. What should the project manager do next? | Unresolved claims may be subject to litigation | Start the closing phase | Inform project team members | Seek arbitration following the alternative dispute resolution ADR procedures | Procurement Management | Monitoring and Controlling | False | "16"
A project manager wants to ensure sufficient stakeholder participation throughout a project's life cycle. What should the project manager include in the stakeholder engagement plan? | Feedback from stakeholders on project operations. | Change requests initiated by stakeholders. | Stakeholder power/interest grid. | Desired and current stakeholder engagement levels. | A project manager wants to ensure sufficient stakeholder participation throughout a project's life cycle. What should the project manager include in the stakeholder engagement plan? | Feedback from stakeholders on project operations. | Change requests initiated by stakeholders. | Stakeholder power/interest grid. | Desired and current stakeholder engagement levels. | Stakeholder Management | Planning | False | "19"
Mervat an IT project manager, is in the planning phase of a shopping website development project. A junior project manager, who has worked under her authority, started developing procedures for maintaining the integrity of cost and schedule performance baselines in the project. Where should the junior project manager store these procedures? | In the project resource management plan | In the project scope statement | In the project communications management plan | In the project management plan | Mervat an IT project manager, is in the planning phase of a shopping website development project. A junior project manager, who has worked under her authority, started developing procedures for maintaining the integrity of cost and schedule performance baselines in the project. Where should the junior project manager store these procedures? | In the project resource management plan | In the project scope statement | In the project communications management plan | In the project management plan | Integration Management | Planning | False | "17"
During a weekly status meeting, a team member informs the project manager that the design submitted to the local government for approval has been rejected due to an error in the blueprint. Resubmission of the design will require an additional two weeks. What should the project manager do first? | Review the reject submission and begin working on the resubmission | Add another layer of review for future projects to avoid similar problems | Inform the project sponsor and look for support | Update the issue log and identify the possible cause of the error | During a weekly status meeting, a team member informs the project manager that the design submitted to the local government for approval has been rejected due to an error in the blueprint. Resubmission of the design will require an additional two weeks. What should the project manager do first? | Review the reject submission and begin working on the resubmission | Add another layer of review for future projects to avoid similar problems | Inform the project sponsor and look for support | Update the issue log and identify the possible cause of the error | Integration Management | Executing | False | "20"
During a risk audit, it was found that some risks were not analyzed correctly. It was suspected that risk-related information were not properly reviewed before concluding characteristics of risks like probability, etc. What could have been done to prevent this issue? | Risk probability and impact assessment | Effective interviews during the risk identification process | Analysis of other risk parameters | Risk data quality assessment | During a risk audit, it was found that some risks were not analyzed correctly. It was suspected that risk-related information were not properly reviewed before concluding characteristics of risks like probability, etc. What could have been done to prevent this issue? | Risk probability and impact assessment | Effective interviews during the risk identification process | Analysis of other risk parameters | Risk data quality assessment | Risk Management | Monitoring and Controlling | False | "17"
During the execution phase, a project manager discovers that team members have started to work on task that are coming directly from the customer. What should the project manager do? | Split the project into two projects to keep the scopes separate and bill the client separately. | Continue working on tasks that have already been started and revise the baseline | Hold a risk review board meeting and add the tasks that have already been started to the risk log. | Stop the work that is outside the project scope statement and submit a change request. | During the execution phase, a project manager discovers that team members have started to work on task that are coming directly from the customer. What should the project manager do? | Split the project into two projects to keep the scopes separate and bill the client separately. | Continue working on tasks that have already been started and revise the baseline | Hold a risk review board meeting and add the tasks that have already been started to the risk log. | Stop the work that is outside the project scope statement and submit a change request. | Integration Management | Executing | False | "18"
You are a project manager and have just assigned to the project in the execution phase. A project is in jeopardy. It is behind schedule and resources are limited. What is the first action you should take? | Hold a project team meeting. | Review the work performance report. | Ask management for additional resources. | Revise the project management plan | You are a project manager and have just assigned to the project in the execution phase. A project is in jeopardy. It is behind schedule and resources are limited. What is the first action you should take? | Hold a project team meeting. | Review the work performance report. | Ask management for additional resources. | Revise the project management plan | Integration Management | Executing | False | "19"
A project manager for a large, ongoing project is under a tight deadline to finish each of the project's three phases. The executives have decided to increase the budget and time to ensure their standards are met. The project manager has updated the schedule to reflect the increases. What should the project manager do next? | Update the success criteria in the scope management plan. | Review the requirements in the quality management plan. | Add the tasks mentioned to the schedule management plan. | Communicate the updated schedule to the stakeholder. | A project manager for a large, ongoing project is under a tight deadline to finish each of the project's three phases. The executives have decided to increase the budget and time to ensure their standards are met. The project manager has updated the schedule to reflect the increases. What should the project manager do next? | Update the success criteria in the scope management plan. | Review the requirements in the quality management plan. | Add the tasks mentioned to the schedule management plan. | Communicate the updated schedule to the stakeholder. | Integration Management | Executing | False | "20"
Your customer wants to remove certain attributes from the product. You submits a change request which is approved by the change control board ( CCB ). What should you do next? | Update the project charter. | Update the Issue log. | Update the risk register. | Update the project management plan. | Your customer wants to remove certain attributes from the product. You submits a change request which is approved by the change control board ( CCB ). What should you do next? | Update the project charter. | Update the Issue log. | Update the risk register. | Update the project management plan. | Integration Management | Executing | False | "19"
In the middle of the design phase of a software development project, the project manager realizes that planned tasks will be delivered late. What should the project manager do first? | Revise the task delivery dates in the project management plan. | Assume the delay, and report it during the next stakeholder meeting. | Email stakeholders about the delay, and update the project management plan. | Update the issue log. | In the middle of the design phase of a software development project, the project manager realizes that planned tasks will be delivered late. What should the project manager do first? | Revise the task delivery dates in the project management plan. | Assume the delay, and report it during the next stakeholder meeting. | Email stakeholders about the delay, and update the project management plan. | Update the issue log. | Integration Management | Executing | False | "20"
A project manager is running a complex transformation project. During a team briefing, the lead resource raises a concern that a critical milestone is being affected because tasks are taking longer than expected. What should the project manager do? | Increase the number of resources to ensure that milestones are achieved | Review the project management plan to identify how the estimates were built | Inform the project sponsor of the expected delay and potential impact | Identify corrective actions and raise the issue to the change control board CCB if needed | A project manager is running a complex transformation project. During a team briefing, the lead resource raises a concern that a critical milestone is being affected because tasks are taking longer than expected. What should the project manager do? | Increase the number of resources to ensure that milestones are achieved | Review the project management plan to identify how the estimates were built | Inform the project sponsor of the expected delay and potential impact | Identify corrective actions and raise the issue to the change control board CCB if needed | Schedule Management | Monitoring and Controlling | False | "19"
A project manager is executing a new office building. Which of the following activities might the project manager and the team conduct during the Monitor and Control Project Work process? | Implementing approved change requests to achieve the project's objectives | Transfer the ownership of deliverables to the assigned stakeholders | Prepare and share the final project report according to the communications management plan | Comparing actual project performance against the project management plan | A project manager is executing a new office building. Which of the following activities might the project manager and the team conduct during the Monitor and Control Project Work process? | Implementing approved change requests to achieve the project's objectives | Transfer the ownership of deliverables to the assigned stakeholders | Prepare and share the final project report according to the communications management plan | Comparing actual project performance against the project management plan | Integration Management | Monitoring and Controlling | False | "16"
As a project manager, if you want to determine the best corrective action in terms of cost in case of project deviations, which of the following data analysis techniques should you use? | Trend analysis | Variance analysis | Earned value analysis | Cost-benefit analysis | As a project manager, if you want to determine the best corrective action in terms of cost in case of project deviations, which of the following data analysis techniques should you use? | Trend analysis | Variance analysis | Earned value analysis | Cost-benefit analysis | Integration Management | Monitoring and Controlling | False | "17"
A stakeholder requests a change to the project. The project manager wants to avoid wasting the change control board (CCB) time and decides to approve the change themself. What should the project manager do to make sure they can approve this change? | Request that all stakeholders vote before making a decision. | Review the change with all stakeholders. | Obtain the customer's approval before implementation. | Verify that the change does not affect the project baseline. | A stakeholder requests a change to the project. The project manager wants to avoid wasting the change control board (CCB) time and decides to approve the change themself. What should the project manager do to make sure they can approve this change? | Request that all stakeholders vote before making a decision. | Review the change with all stakeholders. | Obtain the customer's approval before implementation. | Verify that the change does not affect the project baseline. | Integration Management | Monitoring and Controlling | False | "18"
After a project's first status meeting, the team realizes that the tasks are more complex than the project leader programmed . What should the project manager do to address this? | Make changes to the original plan. | Hire more people for the critical path. | Use the fast tracking technique | Prepare a change request. | After a project's first status meeting, the team realizes that the tasks are more complex than the project leader programmed . What should the project manager do to address this? | Make changes to the original plan. | Hire more people for the critical path. | Use the fast tracking technique | Prepare a change request. | Integration Management | Executing | False | "19"
Alan is a project manager, he joins a project that is involved with an industry in which he have little experience. An urgent issue is raised on the software development portion of the project. From whom should the project manager request direction? | Development team | Project management office | All Stakeholders | Internal subject matter experts | Alan is a project manager, he joins a project that is involved with an industry in which he have little experience. An urgent issue is raised on the software development portion of the project. From whom should the project manager request direction? | Development team | Project management office | All Stakeholders | Internal subject matter experts | Integration Management | Executing | False | "20"
Which of the following soft skills helps to reduce misunderstandings and improves communication and knowledge sharing? | Leadership | Political awareness | Lessons learned register | Active listening | Which of the following soft skills helps to reduce misunderstandings and improves communication and knowledge sharing? | Leadership | Political awareness | Lessons learned register | Active listening | Integration Management | Executing | False | "19"
During the development of the scope management plan, a stakeholder requests the addition of pilot technology into the project scope to assist with the product marketing. What should the project manager do? | Use the project reserve for the pilot technology. | Review the scope baseline with the stakeholder. | Increase the project budget with the cost of the pilot technology. | Include the stakeholder in the scope planning meetings. | During the development of the scope management plan, a stakeholder requests the addition of pilot technology into the project scope to assist with the product marketing. What should the project manager do? | Use the project reserve for the pilot technology. | Review the scope baseline with the stakeholder. | Increase the project budget with the cost of the pilot technology. | Include the stakeholder in the scope planning meetings. | Scope Management | Planning | False | "20"
A project manager has just been assigned in the middle of the execution phase. The project is delayed and two important stakeholders are not cooperating with project objectives. Documentation states not to interact directly with either stakeholder, leaving this role to the company's chief information officer . What should the project manager do? | Perform a root cause analysis and escalate to the two important stakeholders. | Perform a data analysis and review the stakeholders' roles and responsibilities matrix. | Perform a stakeholder analysis and escalate the issue to upper management. | Perform an assumption and constraint analysis and review the stakeholder engagement plan. | A project manager has just been assigned in the middle of the execution phase. The project is delayed and two important stakeholders are not cooperating with project objectives. Documentation states not to interact directly with either stakeholder, leaving this role to the company's chief information officer . What should the project manager do? | Perform a root cause analysis and escalate to the two important stakeholders. | Perform a data analysis and review the stakeholders' roles and responsibilities matrix. | Perform a stakeholder analysis and escalate the issue to upper management. | Perform an assumption and constraint analysis and review the stakeholder engagement plan. | Stakeholder Management | Planning | False | "20"
Team members on a life cycle replacement project are consumed to frequently changing requirements even without formal approval. What should the project manager do? | Review the cost baseline with team members, and ask that any changes to requirements with cost are captured | Review the configuration management plan to identify what items will be changed and the frequency of the change | Ask the project sponsor to provide directions to the project team with regard to the frequency of any changes to requirements | Develop and implement a change management plan to define how changes will be addressed and controlled | Team members on a life cycle replacement project are consumed to frequently changing requirements even without formal approval. What should the project manager do? | Review the cost baseline with team members, and ask that any changes to requirements with cost are captured | Review the configuration management plan to identify what items will be changed and the frequency of the change | Ask the project sponsor to provide directions to the project team with regard to the frequency of any changes to requirements | Develop and implement a change management plan to define how changes will be addressed and controlled | Integration Management | Monitoring and Controlling | False | "19"
A project manager has completed his project on time and within budget. An unexpected complaint from a customer regarding the project's scope raised. It turns out that the customer wanted a much simpler solution. What should the project manager have done differently? | Defined project scope with the customer. | Controlled scope with the help of the project team. | Validated project scope with stakeholders. | Collect requirements with the customer. | A project manager has completed his project on time and within budget. An unexpected complaint from a customer regarding the project's scope raised. It turns out that the customer wanted a much simpler solution. What should the project manager have done differently? | Defined project scope with the customer. | Controlled scope with the help of the project team. | Validated project scope with stakeholders. | Collect requirements with the customer. | Scope Management | Planning | False | "16"
You have recently been assigned to manage a project that is midway into execution. The project is behind schedule and under budget, but the customer is not happy with the performance of the project. What is the FIRST thing you should do? | Renegotiate the contract. | Reschedule baselines. | Discuss it with the project team. | Meet with the customer. | You have recently been assigned to manage a project that is midway into execution. The project is behind schedule and under budget, but the customer is not happy with the performance of the project. What is the FIRST thing you should do? | Renegotiate the contract. | Reschedule baselines. | Discuss it with the project team. | Meet with the customer. | Integration Management | Executing | False | "20"
You are managing the changes made to the scope baseline. The causes of variances and the corrective action chosen should be included in: | Recommended corrective action | Scope management plan | Risk Register | Lessons learned register | You are managing the changes made to the scope baseline. The causes of variances and the corrective action chosen should be included in: | Recommended corrective action | Scope management plan | Risk Register | Lessons learned register | Scope Management | Monitoring and Controlling | False | "19"
Michel is managing a project. The project is about three-fourths done when the site engineer reports that due to inherent complexities in a specific task, the deliverables would be delayed. This would involve additional analysis and then implementation. He requests that this new work be added to the scope and also the time required to be added to the schedule. You and the site engineer have analyzed the impact of this change to cost, and have written up a change request and requested approval from the change control board. Just today, you have received approval from the change control board - what should be the immediate course of action? | Perform Quality Assurance | Ascertain the impact of this change to scope, schedule and cost before making any change | Start work immediately | Make sure that the scope baseline and schedule baseline are updated to reflect the approved change before implementing the change. | Michel is managing a project. The project is about three-fourths done when the site engineer reports that due to inherent complexities in a specific task, the deliverables would be delayed. This would involve additional analysis and then implementation. He requests that this new work be added to the scope and also the time required to be added to the schedule. You and the site engineer have analyzed the impact of this change to cost, and have written up a change request and requested approval from the change control board. Just today, you have received approval from the change control board - what should be the immediate course of action? | Perform Quality Assurance | Ascertain the impact of this change to scope, schedule and cost before making any change | Start work immediately | Make sure that the scope baseline and schedule baseline are updated to reflect the approved change before implementing the change. | Integration Management | Executing | False | "19"
A project's primary focus is on schedule. To monitor this, the project manager requests monthly progress reports from the contractor. What should the project manager ask the contractor to include in these reports? | Schedule attributes. | Work breakdown structure (WBS) | Network chart. | Gantt chart. | A project's primary focus is on schedule. To monitor this, the project manager requests monthly progress reports from the contractor. What should the project manager ask the contractor to include in these reports? | Schedule attributes. | Work breakdown structure (WBS) | Network chart. | Gantt chart. | Schedule Management | Monitoring and Controlling | False | "20"
You have been hired as a project manager for a new project. After several weeks, you discover that the accounting department has declined all charges because the project was not approved. What should the project manager have done to prevent this? | Planned the resources necessary to start the project | Verified that the business case was authorized by the project initiator | Obtained the fund needed to start the project | Obtained the project charter approval from the project sponsor | You have been hired as a project manager for a new project. After several weeks, you discover that the accounting department has declined all charges because the project was not approved. What should the project manager have done to prevent this? | Planned the resources necessary to start the project | Verified that the business case was authorized by the project initiator | Obtained the fund needed to start the project | Obtained the project charter approval from the project sponsor | Integration Management | Initiating | False | "19"
A recently appointed project manager is in constant conflict with a senior manager. Since this is not ideal for the team, the project manager wants to resolve this. What should the project manager do? | Escalate the issue to the project sponsor. | Seek guidance from the other project managers. | Enlist the help of a neutral mediator. | Request a scheduled face-to-face meetings with the senior manager. | A recently appointed project manager is in constant conflict with a senior manager. Since this is not ideal for the team, the project manager wants to resolve this. What should the project manager do? | Escalate the issue to the project sponsor. | Seek guidance from the other project managers. | Enlist the help of a neutral mediator. | Request a scheduled face-to-face meetings with the senior manager. | Resources Management | Monitoring and Controlling | False | "18"
After defining project goals and objectives. The PMO conducts a meeting with stakeholders to align expectations. What result indicates that the project is moving forward correctly? | Statement of work (SOW) | Kick-off meeting | Business case | Key deliverables | After defining project goals and objectives. The PMO conducts a meeting with stakeholders to align expectations. What result indicates that the project is moving forward correctly? | Statement of work (SOW) | Kick-off meeting | Business case | Key deliverables | Integration Management | Executing | False | "20"
Your project is currently in the execution phase. The team members have been implemented a change request without going through the CCB. As a project manager, what should you do? | Do nothing | Update the project management plan | Update the change log | Send the change request to CCB for approval | Your project is currently in the execution phase. The team members have been implemented a change request without going through the CCB. As a project manager, what should you do? | Do nothing | Update the project management plan | Update the change log | Send the change request to CCB for approval | Integration Management | Executing | False | "19"
You are working with your team on estimating how much time each activity will take. One of the documents you are using contains information on categories of labor, material, and equipment required to complete your project. You are also interested to see skill levels of your labor, any certifications required, and grade levels your supplies. Which of the following documents would you primarily refer to for this purpose? | Risk breakdown structure | Organizational breakdown structure | Work breakdown structure | Resource breakdown structure | You are working with your team on estimating how much time each activity will take. One of the documents you are using contains information on categories of labor, material, and equipment required to complete your project. You are also interested to see skill levels of your labor, any certifications required, and grade levels your supplies. Which of the following documents would you primarily refer to for this purpose? | Risk breakdown structure | Organizational breakdown structure | Work breakdown structure | Resource breakdown structure | Schedule Management | Planning | False | "18"
You are preparing two documents for risk management. One contains sources of overall project risk and also summary information on individual risks. The second describes individual risks identified. What name should you give to the first document? | Requirements traceability matrix | Risk register | Risk management plan | Risk report | You are preparing two documents for risk management. One contains sources of overall project risk and also summary information on individual risks. The second describes individual risks identified. What name should you give to the first document? | Requirements traceability matrix | Risk register | Risk management plan | Risk report | Risk Management | Planning | False | "16"
The mitigation plan is failed to deal with the issue that occurred three weeks ago because of unavailable resources, and has negatively impacted the schedule. What should the project manager have done to prevent this? | Sent out status reports to stakeholders. | Updated the risk mitigation plan. | Updated the risk management plan. | Conducted stand-up meetings to communicate project status. | The mitigation plan is failed to deal with the issue that occurred three weeks ago because of unavailable resources, and has negatively impacted the schedule. What should the project manager have done to prevent this? | Sent out status reports to stakeholders. | Updated the risk mitigation plan. | Updated the risk management plan. | Conducted stand-up meetings to communicate project status. | Integration Management | Executing | False | "20"
You are a Project manager developing the project charter. Which of the Following are you using in this Process? | Project Management Plan | Deliverables | Stakeholder register | letters of intent | You are a Project manager developing the project charter. Which of the Following are you using in this Process? | Project Management Plan | Deliverables | Stakeholder register | letters of intent | Integration Management | Initiating | False | "20"
During project execution, it is noticed that the actual expenditure is too high compared to baseline cost estimates. What should the project manager do next? | Revisit project scope and cut high-cost items. | Review historical data to get new cost estimates. | Review assumption log to understand which cost assumptions were wrong. | Update cost forecasts and discuss the options with the project sponsor. | During project execution, it is noticed that the actual expenditure is too high compared to baseline cost estimates. What should the project manager do next? | Revisit project scope and cut high-cost items. | Review historical data to get new cost estimates. | Review assumption log to understand which cost assumptions were wrong. | Update cost forecasts and discuss the options with the project sponsor. | Cost Management | Monitoring and Controlling | False | "17"
During project closure and transferring of the completed project deliverables to the operation department, the project manager discovers that an audit report from an early project phase is missing. What should the project manager do? | Remove the audit report from the required project documents and update the project management plan. | Ask the operation department representative to accept the project without the audit report. | Complete project closure and update the OPA | Inform the operation department representative about the missing audit report. | During project closure and transferring of the completed project deliverables to the operation department, the project manager discovers that an audit report from an early project phase is missing. What should the project manager do? | Remove the audit report from the required project documents and update the project management plan. | Ask the operation department representative to accept the project without the audit report. | Complete project closure and update the OPA | Inform the operation department representative about the missing audit report. | Integration Management | Closing | False | "16"
One of the project risks is likely to cause, a negative impact of SAR 15,000 with a probability of 50%. At the same time, there is a possibility of saving SAR 10,000 by choosing alternate resources, this has a likelihood of 25%. What is the Expected Monetary Value (EMV) of the project? | SAR -7,500 | SAR -25,000 | SAR 2,500 | SAR -5,000 | One of the project risks is likely to cause, a negative impact of SAR 15,000 with a probability of 50%. At the same time, there is a possibility of saving SAR 10,000 by choosing alternate resources, this has a likelihood of 25%. What is the Expected Monetary Value (EMV) of the project? | SAR -7,500 | SAR -25,000 | SAR 2,500 | SAR -5,000 | Risk Management | Planning | False | "17"
A project manager has been hired to develop a product for a multinational company. While writing the key deliverables for the project charter, the project manager has two technology options and is unsure of which to use. One is safer and the other is cheaper. What should the project manager do to determine the key deliverables for the project? | Establish requirements with the project sponsor. | Use the cheaper technology in order to maintain the budget. | Choose the best option based on the project manager's experience. | Meet with the client to understand their technological requirements. | A project manager has been hired to develop a product for a multinational company. While writing the key deliverables for the project charter, the project manager has two technology options and is unsure of which to use. One is safer and the other is cheaper. What should the project manager do to determine the key deliverables for the project? | Establish requirements with the project sponsor. | Use the cheaper technology in order to maintain the budget. | Choose the best option based on the project manager's experience. | Meet with the client to understand their technological requirements. | Scope Management | Planning | False | "18"
You have been assigned as a project manager of a new project to be executed out of Orlando. The project is being implemented in an area with many hurricanes. What is the best risk response strategy appropriate for this project? | Accept | Enhance | Avoid | Transfer | You have been assigned as a project manager of a new project to be executed out of Orlando. The project is being implemented in an area with many hurricanes. What is the best risk response strategy appropriate for this project? | Accept | Enhance | Avoid | Transfer | Risk Management | Planning | False | "18"
A project earned value = SAR 40,000 , Actual Cost = SAR 50,000 , and BAC = SAR 200,000. What is the Estimate To Complete (ETC) for the project if the work is performed at the budgeted rate? | SAR 200,000 | SAR 210 | SAR 250,000 | SAR 160,000 | A project earned value = SAR 40,000 , Actual Cost = SAR 50,000 , and BAC = SAR 200,000. What is the Estimate To Complete (ETC) for the project if the work is performed at the budgeted rate? | SAR 200,000 | SAR 210 | SAR 250,000 | SAR 160,000 | Cost Management | Monitoring and Controlling | False | "19"
A project manager has just completed the project management plan for a construction project. This is a high-visibility project for many stakeholders across multiple functional departments and level of understanding. What can the project manager do to ensure approval of the project management plan? | Develop a stakeholder register and then select the most important stakeholder to obtain their approval. | Ask the project sponsor to approve the project management plan as a first step, then communicate this to other stakeholders to help approve the project . | Conduct interviews with each stakeholders separately in order to obtain approval of the project management plan individually. | Organize a meeting for stakeholders and provide the appropriate information to obtain their approval. | A project manager has just completed the project management plan for a construction project. This is a high-visibility project for many stakeholders across multiple functional departments and level of understanding. What can the project manager do to ensure approval of the project management plan? | Develop a stakeholder register and then select the most important stakeholder to obtain their approval. | Ask the project sponsor to approve the project management plan as a first step, then communicate this to other stakeholders to help approve the project . | Conduct interviews with each stakeholders separately in order to obtain approval of the project management plan individually. | Organize a meeting for stakeholders and provide the appropriate information to obtain their approval. | Integration Management | Monitoring and Controlling | False | "20"
A project manager is managing a project to build a telecommunications tower. The project requires a crane, but the crane previously booked for this project receives a last-minute reassignment to a higher-priority government project. What should the project manager do first? | Review the service agreement with the vendor. | Prepare resolution for the situation. | Escalate the solution to stakeholders. | Add this to the issue log. | A project manager is managing a project to build a telecommunications tower. The project requires a crane, but the crane previously booked for this project receives a last-minute reassignment to a higher-priority government project. What should the project manager do first? | Review the service agreement with the vendor. | Prepare resolution for the situation. | Escalate the solution to stakeholders. | Add this to the issue log. | Resources Management | Monitoring and Controlling | False | "19"
A project manager is currently developing the project schedule for a mandatory regulatory project. The project manager is receiving input from different stakeholders and finds that many of them are estimating completion times that are longer than the established end date. What should the project manager do next? | Apply crashing to the project management plan in order to reduce the extension of the proposed schedule. | Remind the stakeholders about the project constraints and request a revision of their inputs. | Identify a new critical path that could guarantee the project's completion by the end date. | Notify the sponsor and request to modify the end date to accommodate the proposed schedule. | A project manager is currently developing the project schedule for a mandatory regulatory project. The project manager is receiving input from different stakeholders and finds that many of them are estimating completion times that are longer than the established end date. What should the project manager do next? | Apply crashing to the project management plan in order to reduce the extension of the proposed schedule. | Remind the stakeholders about the project constraints and request a revision of their inputs. | Identify a new critical path that could guarantee the project's completion by the end date. | Notify the sponsor and request to modify the end date to accommodate the proposed schedule. | Schedule Management | Planning | False | "19"
The project manager had been appointed recently in marketing Project. A team member informs you with a serious concern that impacts the project. You start to record the details, identifies an owner, and sets a realistic date for resolution. What document did the project manager update? | Risk register | Stakeholder register | Change log | Issue log | The project manager had been appointed recently in marketing Project. A team member informs you with a serious concern that impacts the project. You start to record the details, identifies an owner, and sets a realistic date for resolution. What document did the project manager update? | Risk register | Stakeholder register | Change log | Issue log | Integration Management | Executing | False | "19"
Rework is an example of? | Cost of the contingency reserve | Cost of Conformance | External Failure Costs | Cost of quality | Rework is an example of? | Cost of the contingency reserve | Cost of Conformance | External Failure Costs | Cost of quality | Quality Management | Planning | False | "18"
During a project status meeting, a team member informs the project manager of an unexpected increase in the price of an essential component required to complete the deliverable. What should the project manager do? | Include the increased price in the project budget. | Refer to the procurement management plan. | Update the risk management plan to adapt to the new scenario. | Analyze the impact of the price increase on the project. | During a project status meeting, a team member informs the project manager of an unexpected increase in the price of an essential component required to complete the deliverable. What should the project manager do? | Include the increased price in the project budget. | Refer to the procurement management plan. | Update the risk management plan to adapt to the new scenario. | Analyze the impact of the price increase on the project. | Cost Management | Monitoring and Controlling | False | "20"
While controlling project work, the team discovers that the schedule performance index (SPI) is 0.8 and the cost performance index (CPI) is 0.95 . If the schedule for this project is a priority and no additional resources are available, what should the project manager do? | Use resource smoothing. | Use crashing. | Use resource levelling. | Use fast tracking. | While controlling project work, the team discovers that the schedule performance index (SPI) is 0.8 and the cost performance index (CPI) is 0.95 . If the schedule for this project is a priority and no additional resources are available, what should the project manager do? | Use resource smoothing. | Use crashing. | Use resource levelling. | Use fast tracking. | Schedule Management | Monitoring and Controlling | False | "19"
A resources can't be retained for the full project life cycle and there is no additional budget available. What should the project manager do to ensure effective project delivery while utilizing resources within budgeted limits? | Move budgeted funds from other project areas to mitigate any risk of gaps in assignments. | Create a budget change request for stakeholders before presenting project progress. | Identify those resources who can likely perform all necessary project tasks, and remove resources that are specialized. | Schedule similar tasks around the same time to limit the duration of resources' engagement. | A resources can't be retained for the full project life cycle and there is no additional budget available. What should the project manager do to ensure effective project delivery while utilizing resources within budgeted limits? | Move budgeted funds from other project areas to mitigate any risk of gaps in assignments. | Create a budget change request for stakeholders before presenting project progress. | Identify those resources who can likely perform all necessary project tasks, and remove resources that are specialized. | Schedule similar tasks around the same time to limit the duration of resources' engagement. | Schedule Management | Planning | False | "20"
Which of the following technique can be used to identify the key issues and suitable alternatives to be prioritized as a set of decisions for implementation? | Requirements traceability matrix | A responsibility assignment matrix (RAM) | Stakeholder engagement assessment matrix | Prioritization matrix | Which of the following technique can be used to identify the key issues and suitable alternatives to be prioritized as a set of decisions for implementation? | Requirements traceability matrix | A responsibility assignment matrix (RAM) | Stakeholder engagement assessment matrix | Prioritization matrix | Quality Management | Planning | False | "19"
Which of the following techniques can ensure that the stakeholders are engaged at appropriate project phases and to obtain or confirm their continued commitment to the success of the project? | Managing project team | Setting ground rules | Performance audits | Stage gate meetings | Which of the following techniques can ensure that the stakeholders are engaged at appropriate project phases and to obtain or confirm their continued commitment to the success of the project? | Managing project team | Setting ground rules | Performance audits | Stage gate meetings | Integration Management | Executing | False | "20"
In a construction project, concrete is unable to be used because heavy rain affected its consistency. This possibility and its estimated costs were already identified in the risk register. How should the project manager fund the additional costs? | Apply the budget reserve | Request reserves from the client | Use the management reserve | Access the contingency reserve | In a construction project, concrete is unable to be used because heavy rain affected its consistency. This possibility and its estimated costs were already identified in the risk register. How should the project manager fund the additional costs? | Apply the budget reserve | Request reserves from the client | Use the management reserve | Access the contingency reserve | Cost Management | Planning | False | "20"
You have recently been assigned as the project manager for a company that has a history of implementing system integration projects and you don't have prior experience. What should you do? | Meet with the sponsor | Review the project charter | Refer to the project statement of work (SOW). | Seek expert judgment | You have recently been assigned as the project manager for a company that has a history of implementing system integration projects and you don't have prior experience. What should you do? | Meet with the sponsor | Review the project charter | Refer to the project statement of work (SOW). | Seek expert judgment | Integration Management | Executing | False | "18"
A long term project for a company that is increasing its infrastructure is running . In month 13 of the project, the client escalates an issue that an expected delivery from a contracted third-party vendor wasn't received. Upon investigation, the project manager discovers that the vendor was unaware of this. Where should the project manager verify the delivery schedule? | Requirements traceability matrix. | Assumptions log. | Requirements management plan | Milestone list | A long term project for a company that is increasing its infrastructure is running . In month 13 of the project, the client escalates an issue that an expected delivery from a contracted third-party vendor wasn't received. Upon investigation, the project manager discovers that the vendor was unaware of this. Where should the project manager verify the delivery schedule? | Requirements traceability matrix. | Assumptions log. | Requirements management plan | Milestone list | Schedule Management | Planning | False | "16"
A stakeholder refuses to accept delivery of a project that has passed the acceptance criteria, and provides a new set of acceptance criteria. What should the project manager do to enable project completion? | Escalate the issue to the stakeholder's manager. | Rework the project deliverables to meet the new acceptance criteria. | Execute the change control process to accommodate the new acceptance criteria. | Negotiate with the stakeholder to accept the project in its current state. | A stakeholder refuses to accept delivery of a project that has passed the acceptance criteria, and provides a new set of acceptance criteria. What should the project manager do to enable project completion? | Escalate the issue to the stakeholder's manager. | Rework the project deliverables to meet the new acceptance criteria. | Execute the change control process to accommodate the new acceptance criteria. | Negotiate with the stakeholder to accept the project in its current state. | Scope Management | Monitoring and Controlling | False | "20"
There are several communication methods used to share and distribute information to stakeholders, team members, and management. Which of the following communication methods is used when you notify the public about environmental effects from your project after implementation by posting reports on the project's website? | Interactive communication | Informal communication | Push communication | Pull communication | There are several communication methods used to share and distribute information to stakeholders, team members, and management. Which of the following communication methods is used when you notify the public about environmental effects from your project after implementation by posting reports on the project's website? | Interactive communication | Informal communication | Push communication | Pull communication | Communication Management | Planning | False | "16"
You are a project manager constructing a new railway. The rainy season in the area prevents on-site work for three months of each year. In which of the following should this information be documented initially? | Risk register. | Communication management plan. | Project schedule. | Project charter. | You are a project manager constructing a new railway. The rainy season in the area prevents on-site work for three months of each year. In which of the following should this information be documented initially? | Risk register. | Communication management plan. | Project schedule. | Project charter. | Integration Management | Initiating | False | "19"
A project manager joins a new project for an organization that does not have a lessons learned repository. How should the project manager establish the project baselines? | Identify and map the benefits and outcomes of the project. | Ask stakeholders to provide their recommendations for the project. | Develop a business case to document project objectives. | Perform a data gathering analysis and review the organizational process assets | A project manager joins a new project for an organization that does not have a lessons learned repository. How should the project manager establish the project baselines? | Identify and map the benefits and outcomes of the project. | Ask stakeholders to provide their recommendations for the project. | Develop a business case to document project objectives. | Perform a data gathering analysis and review the organizational process assets | Integration Management | Planning | False | "19"
The project manager is in the initiation phase of his project. What area should he consider when developing the business case? | Business benefits and portfolio analysis . | Expected resource performance to the strategic portfolio objectives. | Expected resource performance and cost-benefit analysis | Business benefits and the organizational strategy. | The project manager is in the initiation phase of his project. What area should he consider when developing the business case? | Business benefits and portfolio analysis . | Expected resource performance to the strategic portfolio objectives. | Expected resource performance and cost-benefit analysis | Business benefits and the organizational strategy. | Integration Management | Initiating | False | "20"
Sony is so good at assembling those types of equipment, that if someone with no experience is hired, it would take two years to match his skill. This type of knowledge is known as: | Explicit knowledge | Embedded knowledge | Experience knowledge | Tacit knowledge | Sony is so good at assembling those types of equipment, that if someone with no experience is hired, it would take two years to match his skill. This type of knowledge is known as: | Explicit knowledge | Embedded knowledge | Experience knowledge | Tacit knowledge | Integration Management | Executing | False | "19"
You are managing a project that requires an environmental permit to do work. The approval is in the final stages when a confidential, reliable report is brought to your notice. The report indicates there is a high risk of an environmental hazard due to the project. Your manager tells you it is better to keep quiet at this stage since losses from terminating the project might be very high. You must: | Send an email to your manager documenting the matter and disclaimer ownership of the project. | Wait for the project to start and see if the information in the report is true. | Keep quiet about the matter since you will follow your man instructions. | Inform the necessary authorities of the hazard, even if it means canceled the project. | You are managing a project that requires an environmental permit to do work. The approval is in the final stages when a confidential, reliable report is brought to your notice. The report indicates there is a high risk of an environmental hazard due to the project. Your manager tells you it is better to keep quiet at this stage since losses from terminating the project might be very high. You must: | Send an email to your manager documenting the matter and disclaimer ownership of the project. | Wait for the project to start and see if the information in the report is true. | Keep quiet about the matter since you will follow your man instructions. | Inform the necessary authorities of the hazard, even if it means canceled the project. | Integration Management | Executing | False | "20"
As a project manager for your company, two team members come to you with a dispute regarding who will perform and report the status of a particular task. To resolve the conflict, which document will you refer to? | Stakeholder register | Project sponsor. | Functional manager | Responsible, accountable, consult, and inform (RACI) matrix. | As a project manager for your company, two team members come to you with a dispute regarding who will perform and report the status of a particular task. To resolve the conflict, which document will you refer to? | Stakeholder register | Project sponsor. | Functional manager | Responsible, accountable, consult, and inform (RACI) matrix. | Resources Management | Planning | False | "16"
You are a certified PMP, and the PMI has contacted you as part of an investigation it is conducting into allegations of improper conduct by your manager, who is also a PMP. A complaint has been filed stating your manager has received bribes related to a large procurement contract on another project. PMI has asked whether you could provide information regarding this situation. What should you do? | Confront your manager | Send PMI project documentation and emails related to the allegations to assist with their investigation | Do nothing, citing a conflict of interest | Notify the appropriate management immediately | You are a certified PMP, and the PMI has contacted you as part of an investigation it is conducting into allegations of improper conduct by your manager, who is also a PMP. A complaint has been filed stating your manager has received bribes related to a large procurement contract on another project. PMI has asked whether you could provide information regarding this situation. What should you do? | Confront your manager | Send PMI project documentation and emails related to the allegations to assist with their investigation | Do nothing, citing a conflict of interest | Notify the appropriate management immediately | Procurement Management | Executing | False | "18"
A project team is in the process of obtaining supplier responses, selecting a supplier, and awarding a contract. For this purpose, the team is using some predefined selection criteria to evaluate the bids and select the most appropriate supplier. Which process of project management is the project team working on? | Plan Procurement Management | Control Procurements | Proposal Evaluation | Conduct Procurements | A project team is in the process of obtaining supplier responses, selecting a supplier, and awarding a contract. For this purpose, the team is using some predefined selection criteria to evaluate the bids and select the most appropriate supplier. Which process of project management is the project team working on? | Plan Procurement Management | Control Procurements | Proposal Evaluation | Conduct Procurements | Procurement Management | Executing | False | "19"
During regular team meetings, you notices that there are clear signs of conflict and issues related to unclear task assignments and ownership. What should you as a project manager do to address this? | Change the structure of the regular project meetings to improve communication. | Investigate possible ways to improve team collaboration and morale. | Meet individually with team members to understand the conflicts and issues. | Define and obtain agreement on a responsible accountable, consult, and inform RACI Matrix. | During regular team meetings, you notices that there are clear signs of conflict and issues related to unclear task assignments and ownership. What should you as a project manager do to address this? | Change the structure of the regular project meetings to improve communication. | Investigate possible ways to improve team collaboration and morale. | Meet individually with team members to understand the conflicts and issues. | Define and obtain agreement on a responsible accountable, consult, and inform RACI Matrix. | Resources Management | Planning | False | "17"
Jessi is the project manager for a mobile application development project. At the end of the project kick-off meeting, what is the next phase? | Monitoring and Controlling | Closing | Planning | Executing | Jessi is the project manager for a mobile application development project. At the end of the project kick-off meeting, what is the next phase? | Monitoring and Controlling | Closing | Planning | Executing | Integration Management | Planning | False | "20"
Project manager is in the process of obtaining seller responses, selecting a seller and awarding a contract. Which of the following is most likely to include a procurement statement of work (SOW) and request for proposal (RFP)? | Project Management plan | Procurement management | plan Quality reports | Procurement documentation | Project manager is in the process of obtaining seller responses, selecting a seller and awarding a contract. Which of the following is most likely to include a procurement statement of work (SOW) and request for proposal (RFP)? | Project Management plan | Procurement management | plan Quality reports | Procurement documentation | Procurement Management | Executing | False | "20"
A client approaches a design team member requesting that a current task be stopped and a new concept be developed. This will significantly change the design, and impact the project budget and schedule. The team member asks the project manager for the next course of action. What should the project manager do? | Hold a team meeting to discuss the request. | Accept the request and make the changes. | Ask the client to refrain from directly contacting team members. | Refer to the perform integrated change control process. | A client approaches a design team member requesting that a current task be stopped and a new concept be developed. This will significantly change the design, and impact the project budget and schedule. The team member asks the project manager for the next course of action. What should the project manager do? | Hold a team meeting to discuss the request. | Accept the request and make the changes. | Ask the client to refrain from directly contacting team members. | Refer to the perform integrated change control process. | Integration Management | Monitoring and Controlling | False | "18"
A project manager notices an unusually high rate of risks, but has limited resources to address them. To what should the project manager refer to determine risk priorities? | Risk breakdown structure (PBS) | Risk management plan | Risk mitigation strategy | Risk probability and impact matrix | A project manager notices an unusually high rate of risks, but has limited resources to address them. To what should the project manager refer to determine risk priorities? | Risk breakdown structure (PBS) | Risk management plan | Risk mitigation strategy | Risk probability and impact matrix | Risk Management | Planning | False | "19"
Lisa has only a short timeframe in which to complete a project's cost estimation. What estimating technique should Lisa use? | Bottom up | Three point | Critical Path Method | Analogous | Lisa has only a short timeframe in which to complete a project's cost estimation. What estimating technique should Lisa use? | Bottom up | Three point | Critical Path Method | Analogous | Cost Management | Planning | False | "18"
You are a project manager in the telecom project for your organization. Due to the lateness of workers' payments, the workers made a strike, causing delays in an important component delivery. What could have been done differently to prevent this type of situation? | Fast-Tracking | Crashing | Change management plan | What-If Scenario Analysis | You are a project manager in the telecom project for your organization. Due to the lateness of workers' payments, the workers made a strike, causing delays in an important component delivery. What could have been done differently to prevent this type of situation? | Fast-Tracking | Crashing | Change management plan | What-If Scenario Analysis | Schedule Management | Planning | False | "17"
Sara is a project manager for a small project periodically engages resources for tasks in the project management plan. However, due to current budget, the resources can't be retained for the full project life cycle. According to project stakeholders, there is no additional budget available, so Sara must carefully plan how resources will be used to execute the project. What should Sara do to ensure effective project delivery while utilizing resources within budgeted limits? | Move budgeted funds from other project areas to mitigate any risk of gaps in assignments. | Create a budget change request for stakeholders before presenting project progress. | Identify those resources who can likely perform all necessary project tasks, and remove resources that are specialized. | Schedule similar tasks around the same time to limit the duration of resources' engagement. | Sara is a project manager for a small project periodically engages resources for tasks in the project management plan. However, due to current budget, the resources can't be retained for the full project life cycle. According to project stakeholders, there is no additional budget available, so Sara must carefully plan how resources will be used to execute the project. What should Sara do to ensure effective project delivery while utilizing resources within budgeted limits? | Move budgeted funds from other project areas to mitigate any risk of gaps in assignments. | Create a budget change request for stakeholders before presenting project progress. | Identify those resources who can likely perform all necessary project tasks, and remove resources that are specialized. | Schedule similar tasks around the same time to limit the duration of resources' engagement. | Schedule Management | Planning | False | "18"
You are managing a software development project. You want to determine who are the individuals or groups might participate in identifying risks to the project, as well as those who are available to act as risk owners. Which of the following documents should you review? | Risk breakdown structure (RBS) | RACI chart | Stakeholder engagement plan | Stakeholder register | You are managing a software development project. You want to determine who are the individuals or groups might participate in identifying risks to the project, as well as those who are available to act as risk owners. Which of the following documents should you review? | Risk breakdown structure (RBS) | RACI chart | Stakeholder engagement plan | Stakeholder register | Risk Management | Planning | False | "20"
A project manager has two projects of equal strategic importance. However, due to budget constraints, only one can be keep ongoing. There are uncertainties and risks associated with both projects. What tool or technique should the project manager use to decide which project to keep running? | Influence diagram | Simulations | Sensitivity analysis | Decision tree analysis | A project manager has two projects of equal strategic importance. However, due to budget constraints, only one can be keep ongoing. There are uncertainties and risks associated with both projects. What tool or technique should the project manager use to decide which project to keep running? | Influence diagram | Simulations | Sensitivity analysis | Decision tree analysis | Risk Management | Planning | False | "18"
All the following activities are performed in the Close Project or Phase process except: | Activities that fulfill the exit criteria of the project | Activities that are needed to transfer the completed products to operations | Documenting the reasons for terminating the projects early | Sending the deliverables to the customer for acceptance | All the following activities are performed in the Close Project or Phase process except: | Activities that fulfill the exit criteria of the project | Activities that are needed to transfer the completed products to operations | Documenting the reasons for terminating the projects early | Sending the deliverables to the customer for acceptance | Integration Management | Closing | False | "17"
As a project manager in a communication project. The project is ahead of schedule and under budget. The sponsor then suggests a change to include a value-added feature that wouldn't impact project schedule and cost. What should you do next? | Advise the stakeholder that changes shouldn't be implemented when a project is behind schedule. | Update the project management plan to include the new feature. | Advise the stakeholder that, since the project is under budget, the feature will be added | Evaluate the change's impact with the team. | As a project manager in a communication project. The project is ahead of schedule and under budget. The sponsor then suggests a change to include a value-added feature that wouldn't impact project schedule and cost. What should you do next? | Advise the stakeholder that changes shouldn't be implemented when a project is behind schedule. | Update the project management plan to include the new feature. | Advise the stakeholder that, since the project is under budget, the feature will be added | Evaluate the change's impact with the team. | Integration Management | Monitoring and Controlling | False | "19"
The method used in the Manage Quality process to identify the factors that may influence specific characteristics of a product under development is: | The forecasting technique | The control chart | The statistical sampling | Design for X | The method used in the Manage Quality process to identify the factors that may influence specific characteristics of a product under development is: | The forecasting technique | The control chart | The statistical sampling | Design for X | Quality Management | Executing | False | "16"
A project needed to monitor the technical performance of the project and capture data related to how many errors or defects had been identified and how many remained uncorrected. Which of the following techniques should the project use? | Scatter diagram | Flowchart | Control chart | Histogram | A project needed to monitor the technical performance of the project and capture data related to how many errors or defects had been identified and how many remained uncorrected. Which of the following techniques should the project use? | Scatter diagram | Flowchart | Control chart | Histogram | Quality Management | Executing | False | "17"
Which of the following techniques focuses on identifying non-value-added activities in a project? | Pareto charting | Root cause analysis | Affinity diagrams | Process analysis | Which of the following techniques focuses on identifying non-value-added activities in a project? | Pareto charting | Root cause analysis | Affinity diagrams | Process analysis | Quality Management | Executing | False | "18"
You are managing a program and the sponsor asks you to submit CPI and TCPI numbers for your projects. You provided CPI = 1 for project A, CPI = 1.2 for project B, TCPI = 0.9 for project C and TCPI = 1.2 for project D. Which project do you think the sponsor might terminate based on this data? | Project A | Project C | Project B | Project D | You are managing a program and the sponsor asks you to submit CPI and TCPI numbers for your projects. You provided CPI = 1 for project A, CPI = 1.2 for project B, TCPI = 0.9 for project C and TCPI = 1.2 for project D. Which project do you think the sponsor might terminate based on this data? | Project A | Project C | Project B | Project D | Cost Management | Monitoring and Controlling | False | "19"
During benefit analysis, the project sponsor requires that you submit a proposal for an implementation strategy. What should you do next? | Review the SOW | Invite the stakeholder for discussions | Identify the key deliverable | Identify high level risk, constrains and assumptions | During benefit analysis, the project sponsor requires that you submit a proposal for an implementation strategy. What should you do next? | Review the SOW | Invite the stakeholder for discussions | Identify the key deliverable | Identify high level risk, constrains and assumptions | Integration Management | Initiating | False | "19"
You are managing very critical project, some groups of stakeholders appear to have low product expectations. As a result, they are not performing as expected. This may put project objectives at risk . What should the you as a project manager do? | Ask the project sponsor to intervene and motivate the underperforming stakeholders. | Speak with the problematic stakeholders to increase their performance. | Submit a change request. | Follow the stakeholder engagement plan. | You are managing very critical project, some groups of stakeholders appear to have low product expectations. As a result, they are not performing as expected. This may put project objectives at risk . What should the you as a project manager do? | Ask the project sponsor to intervene and motivate the underperforming stakeholders. | Speak with the problematic stakeholders to increase their performance. | Submit a change request. | Follow the stakeholder engagement plan. | Stakeholder Management | Planning | False | "18"
A vendor delayed in supplying some resources even the accounting system by an hourly rate. What should you refer for resolving this issue as a Project Manager? | Arbitration | Procurement documents | Procurement management plan | Agreement | A vendor delayed in supplying some resources even the accounting system by an hourly rate. What should you refer for resolving this issue as a Project Manager? | Arbitration | Procurement documents | Procurement management plan | Agreement | Procurement Management | Monitoring and Controlling | False | "17"
A project manager is aware of a high risk item prior to starting a project. The project manager has completed a risk analysis and concluded that the risk is positive, high impact, and low probability. What should the project manager do? | Conduct cost-benefit analysis | Conduct a strengths, weaknesses, opportunities, and threats (SOWT) analysis | Facilitate a risk brainstorming session | Take action to capture the positive effect of uncertainty | A project manager is aware of a high risk item prior to starting a project. The project manager has completed a risk analysis and concluded that the risk is positive, high impact, and low probability. What should the project manager do? | Conduct cost-benefit analysis | Conduct a strengths, weaknesses, opportunities, and threats (SOWT) analysis | Facilitate a risk brainstorming session | Take action to capture the positive effect of uncertainty | Risk Management | Planning | False | "19"
Which of the following Manage Quality techniques examines problems, constraints, and non-value-added activities that occur during project work? | Reserve Analysis | Earned Value Analysis | Expected monetary value analysis | Process Analysis | Which of the following Manage Quality techniques examines problems, constraints, and non-value-added activities that occur during project work? | Reserve Analysis | Earned Value Analysis | Expected monetary value analysis | Process Analysis | Quality Management | Executing | False | "16"
You are managing a one year duration project. During the middle of the project, it is found that the quality standards require a major change because of the project quality is not effective. As a project manager, what should you do next? | Follow the risk management plan | Follow the Communication management plan | Follow the scope management plan | Follow the change management plan | You are managing a one year duration project. During the middle of the project, it is found that the quality standards require a major change because of the project quality is not effective. As a project manager, what should you do next? | Follow the risk management plan | Follow the Communication management plan | Follow the scope management plan | Follow the change management plan | Quality Management | Executing | False | "17"
A global technology company invested in an infrastructure upgrade project as a part of its business strategy. During the planning phase, the project team works with stakeholders to identify project requirements. The project manager is having difficulty engaging stakeholders who work internationally in different time zones. The stakeholders are unable to participate in regularly scheduled planning meetings, and often don't provide timely responses to emails and other requests for information. What should the project manager do next to minimize the impact this issue may have on the project? | Arrange a meeting to discuss the issue. | Alert senior management. | Create a resource management plan. | Create a communication management plan. | A global technology company invested in an infrastructure upgrade project as a part of its business strategy. During the planning phase, the project team works with stakeholders to identify project requirements. The project manager is having difficulty engaging stakeholders who work internationally in different time zones. The stakeholders are unable to participate in regularly scheduled planning meetings, and often don't provide timely responses to emails and other requests for information. What should the project manager do next to minimize the impact this issue may have on the project? | Arrange a meeting to discuss the issue. | Alert senior management. | Create a resource management plan. | Create a communication management plan. | Communication Management | Planning | False | "17"
During project execution, a high-performing team member leaves. Following this loss, a planned quality audit is conducted that indicates the work product's quality standards are unmet. What should the project manager do next? | Perform a reserve analysis of the work performance. | Crash the schedule. | Consult the resource management plan. | Create a cause and effect diagram. | During project execution, a high-performing team member leaves. Following this loss, a planned quality audit is conducted that indicates the work product's quality standards are unmet. What should the project manager do next? | Perform a reserve analysis of the work performance. | Crash the schedule. | Consult the resource management plan. | Create a cause and effect diagram. | Quality Management | Executing | False | "18"
The CFO has become supportive after he was resistant. As a project manager, what should you do next? | Update Issue log | Update Risk Register | Update Communications Management plan | Update Stakeholder engagement assessment matrix | The CFO has become supportive after he was resistant. As a project manager, what should you do next? | Update Issue log | Update Risk Register | Update Communications Management plan | Update Stakeholder engagement assessment matrix | Stakeholder Management | Planning | False | "19"
During a group activity to identify an input to the plan procurement management process, some participants disagree with the ranking of compliance-related items. What tool or technique should the project manager use to resolve this? | Brainstorming. | Affinity diagram multi-criteria | Decision analysis. | Nominal group technique. | During a group activity to identify an input to the plan procurement management process, some participants disagree with the ranking of compliance-related items. What tool or technique should the project manager use to resolve this? | Brainstorming. | Affinity diagram multi-criteria | Decision analysis. | Nominal group technique. | Scope Management | Planning | False | "19"
You are working on a project for which some requirements have not been clearly defined. The customer insist that this should not be considered a problem and the project should continue without delay. What should you do as the project manager? | Accept the risk and start project work. | Meet with the team to discuss the concerns | Speak with the customer to avoid the risk. | Log the risk in the risk register. | You are working on a project for which some requirements have not been clearly defined. The customer insist that this should not be considered a problem and the project should continue without delay. What should you do as the project manager? | Accept the risk and start project work. | Meet with the team to discuss the concerns | Speak with the customer to avoid the risk. | Log the risk in the risk register. | Risk Management | Planning | False | "20"
Calculate the expected activity duration based on the following three-point estimates: Optimistic =18 days, Most Likely = 22days, Pessimistic = 27days. Using a triangular distribution formula. | 21.33 | 22.11 | 23.2 | 22.33 | Calculate the expected activity duration based on the following three-point estimates: Optimistic =18 days, Most Likely = 22days, Pessimistic = 27days. Using a triangular distribution formula. | 21.33 | 22.11 | 23.2 | 22.33 | Schedule Management | Planning | False | "19"
A project manager is managing a project with a major deliverable that failed its final acceptance test. The project is now behind schedule and over budget because a replacement must be created. What process should the project manager use to determine why the failure occurred? | Critical path method. | Alternative analysis. | Decomposition. | Root cause analysis. | A project manager is managing a project with a major deliverable that failed its final acceptance test. The project is now behind schedule and over budget because a replacement must be created. What process should the project manager use to determine why the failure occurred? | Critical path method. | Alternative analysis. | Decomposition. | Root cause analysis. | Quality Management | Executing | False | "19"
You are estimating the number of work periods needed to complete individual activities with estimated resources. One of the documents you are using contains information on categories of labor, material, and equipment required to complete your project. What is this document known as: | Resource Calendars | Organization breakdown structure (OBS) | RACI Chart | Resource breakdown structure ( RBS ) | You are estimating the number of work periods needed to complete individual activities with estimated resources. One of the documents you are using contains information on categories of labor, material, and equipment required to complete your project. What is this document known as: | Resource Calendars | Organization breakdown structure (OBS) | RACI Chart | Resource breakdown structure ( RBS ) | Schedule Management | Planning | False | "20"
During developing a quality management plan for your project. During the planning process, one of your team members tells you that, in the past, the organization has completed a similar project. You start to review the old project and find that some of its quality metrics can be used in your project as well. This technique is known as: | Process analysis | Prototyping | Reviewing organization process assets | Benchmarking | During developing a quality management plan for your project. During the planning process, one of your team members tells you that, in the past, the organization has completed a similar project. You start to review the old project and find that some of its quality metrics can be used in your project as well. This technique is known as: | Process analysis | Prototyping | Reviewing organization process assets | Benchmarking | Quality Management | Planning | False | "20"
A project is terminated early, and you sends the final project report to relevant stakeholders. A senior manager is interested in understanding the impact and requests a copy of the report. What should you do? | Send the report to the finance manager. | Don't send the report since the project was prematurely terminated. | Review the stakeholder engagement plan and act accordingly. | Check the communication management plan and act accordingly. | A project is terminated early, and you sends the final project report to relevant stakeholders. A senior manager is interested in understanding the impact and requests a copy of the report. What should you do? | Send the report to the finance manager. | Don't send the report since the project was prematurely terminated. | Review the stakeholder engagement plan and act accordingly. | Check the communication management plan and act accordingly. | Communication Management | Planning | False | "18"
You work for Yory's, a food equipment manufacturer. Your organization is installing some new manufacturing equipment, and you are managing the project. Your project sponsor has asked for an EAC and has told you that he wants you to use ETC work considering CPI and SPI factors. If EV = 145, PV = 162, AC = 148, and BAC = 200, what is EAC? | 58 | 207 | 63 | 210 | You work for Yory's, a food equipment manufacturer. Your organization is installing some new manufacturing equipment, and you are managing the project. Your project sponsor has asked for an EAC and has told you that he wants you to use ETC work considering CPI and SPI factors. If EV = 145, PV = 162, AC = 148, and BAC = 200, what is EAC? | 58 | 207 | 63 | 210 | Cost Management | Monitoring and Controlling | False | "20"
John the project manager, discovers a significant flaw in a major project deliverable. Which project management process is being performed? | Manage quality. | Plan quality management. | Statistical sampling. | Control quality. | John the project manager, discovers a significant flaw in a major project deliverable. Which project management process is being performed? | Manage quality. | Plan quality management. | Statistical sampling. | Control quality. | Quality Management | Monitoring and Controlling | False | "18"
After analyzing risk with the project team, the project manager, decides to establish a contingency reserve to handle the threat if it occurs. What type of strategy is this? | Passive acceptance | Passive transference | Active mitigation | Active acceptance | After analyzing risk with the project team, the project manager, decides to establish a contingency reserve to handle the threat if it occurs. What type of strategy is this? | Passive acceptance | Passive transference | Active mitigation | Active acceptance | Risk Management | Planning | False | "18"
The building of a Stadium has been stopped for four months due to region-specific prohibition. What should the project manager have done to avoid this issue? | Document all assumptions. | Made a prioritized list of the project constraints. | Crashed the project schedule. | Identified this as a risk in the risk register. | The building of a Stadium has been stopped for four months due to region-specific prohibition. What should the project manager have done to avoid this issue? | Document all assumptions. | Made a prioritized list of the project constraints. | Crashed the project schedule. | Identified this as a risk in the risk register. | Risk Management | Planning | False | "19"
Why is it necessary to manage changes to the project by following the change management plan, while monitoring and controlling the projects, ? | To satisfy the customer | To satisfy project requirements | To satisfy the sponsor | To align project goals with business needs | Why is it necessary to manage changes to the project by following the change management plan, while monitoring and controlling the projects, ? | To satisfy the customer | To satisfy project requirements | To satisfy the sponsor | To align project goals with business needs | Integration Management | Monitoring and Controlling | False | "20"
A project manager was assigned to a project when the project charter was in development. Which of the following is an input that the project manager will use to develop the project charter? | Enterprise environmental factors and Project Acceptance Criteria | Agreements and Make-or-Buy analysis | Organizational Process Assets and Project Scope Statement | Cost Benefit Analysis and organizational strategies | A project manager was assigned to a project when the project charter was in development. Which of the following is an input that the project manager will use to develop the project charter? | Enterprise environmental factors and Project Acceptance Criteria | Agreements and Make-or-Buy analysis | Organizational Process Assets and Project Scope Statement | Cost Benefit Analysis and organizational strategies | Integration Management | Initiating | False | "20"
The building of a commercial mall has been stopped for four months due to region-specific prohibitions. What should the project manager have done to avoid this issue? | Documented all assumptions | Crashed the project schedule | Made a prioritized list of the project constraints | Identified this as a risk in the risk register | The building of a commercial mall has been stopped for four months due to region-specific prohibitions. What should the project manager have done to avoid this issue? | Documented all assumptions | Crashed the project schedule | Made a prioritized list of the project constraints | Identified this as a risk in the risk register | Risk Management | Planning | False | "20"
As part of a joint venture, a project manager working with another company needs to share some confidential information related to intellectual property rights. He wants to know the person responsible for authorizing the release of this confidential information. Which project document should he refer to? | Stakeholder Management Plan | Organizational Breakdown Structure | Project Charter | Project Communication Management Plan | As part of a joint venture, a project manager working with another company needs to share some confidential information related to intellectual property rights. He wants to know the person responsible for authorizing the release of this confidential information. Which project document should he refer to? | Stakeholder Management Plan | Organizational Breakdown Structure | Project Charter | Project Communication Management Plan | Communication Management | Planning | False | "19"
A key stakeholder of your project particularly wants to understand which work packages, or activities each team member is responsible to complete. As a project manager, you should direct the key stakeholder of the project to which of the following Charts? | Project Charter | Resource calendars | Stakeholder's engagement assessment matrix | RACI Chart | A key stakeholder of your project particularly wants to understand which work packages, or activities each team member is responsible to complete. As a project manager, you should direct the key stakeholder of the project to which of the following Charts? | Project Charter | Resource calendars | Stakeholder's engagement assessment matrix | RACI Chart | Resources Management | Planning | False | "18"
A pilot project is ready to close and the project team wants to capture the challenges that were overcome and the opportunities for future work. Where will they document this information? | Organizational process Assets updates. | Project management plan | Work performance reports. | Lessons learned register. | A pilot project is ready to close and the project team wants to capture the challenges that were overcome and the opportunities for future work. Where will they document this information? | Organizational process Assets updates. | Project management plan | Work performance reports. | Lessons learned register. | Integration Management | Closing | False | "18"
To improve the quality of project deliverables, you decides to involve the project team in defining project standards, policies, and guidelines. The team thinks that this a waste of effort, and would like to continue to execute the project as planned. What should you do next? | Produce the quality management plan, and distribute it to stakeholders. | Meet with individual team members, and force them to comply. | Log an issue with the team and discuss it with the human resources department. | Organize a project team meeting to create a shared vision. | To improve the quality of project deliverables, you decides to involve the project team in defining project standards, policies, and guidelines. The team thinks that this a waste of effort, and would like to continue to execute the project as planned. What should you do next? | Produce the quality management plan, and distribute it to stakeholders. | Meet with individual team members, and force them to comply. | Log an issue with the team and discuss it with the human resources department. | Organize a project team meeting to create a shared vision. | Quality Management | Executing | False | "20"
A project manager is gathering formal project requirements. After conducting stakeholder interviews, the project manager realizes that some objectives are inconsistent with those in the project charter. Based on information learned during the initiation phase, this project must be highly focused to stay within budget limits. To manage requirements and meet stakeholder expectations, what should the project manager do? | Disregard stakeholders' objectives that may be outside the scope detailed in the project charter. | Expand the project charter to include the newly identified objectives. | Remove objectives in the project charter that are not aligned with the stakeholders' objectives. | Realign the stakeholders' expectations with the objectives in the project charter. | A project manager is gathering formal project requirements. After conducting stakeholder interviews, the project manager realizes that some objectives are inconsistent with those in the project charter. Based on information learned during the initiation phase, this project must be highly focused to stay within budget limits. To manage requirements and meet stakeholder expectations, what should the project manager do? | Disregard stakeholders' objectives that may be outside the scope detailed in the project charter. | Expand the project charter to include the newly identified objectives. | Remove objectives in the project charter that are not aligned with the stakeholders' objectives. | Realign the stakeholders' expectations with the objectives in the project charter. | Scope Management | Planning | False | "20"
You are a project manager of a project that was originally estimated to be completed in 12 months. During the testing phase, a higher- than- expected failure rate is reported. What should you do? | Create a product flowchart. | Initiate perform integrated change control. | Create Scatter diagram. | Create a fishbone diagram. | You are a project manager of a project that was originally estimated to be completed in 12 months. During the testing phase, a higher- than- expected failure rate is reported. What should you do? | Create a product flowchart. | Initiate perform integrated change control. | Create Scatter diagram. | Create a fishbone diagram. | Quality Management | Executing | False | "19"
The customer rejects some type of deliverables, although many of the requirements are met. After conducting a root cause analysis, the project manager learns that a specific quality control process was not performed due to a lack of resources. What should the project manager have done to avoid this? | Created quality checklists. | Held quality control process meetings. | Requested more resources for quality control activity | Ensured that quality was managed | The customer rejects some type of deliverables, although many of the requirements are met. After conducting a root cause analysis, the project manager learns that a specific quality control process was not performed due to a lack of resources. What should the project manager have done to avoid this? | Created quality checklists. | Held quality control process meetings. | Requested more resources for quality control activity | Ensured that quality was managed | Quality Management | Executing | False | "20"
Organizations evaluate whether to buy products or make the items themselves. Which of the following is not a factor that influences make-or-buy decisions: | Core capabilities of the organization | Value delivered by vendors meeting the need | Risk associated with meeting the need in a cost-effective manner | Total duration of the project | Organizations evaluate whether to buy products or make the items themselves. Which of the following is not a factor that influences make-or-buy decisions: | Core capabilities of the organization | Value delivered by vendors meeting the need | Risk associated with meeting the need in a cost-effective manner | Total duration of the project | Procurement Management | Planning | False | "16"
You are managing a process improvement project for your company. You need to analyze over 20 of the company's processes to identify weaknesses and give your recommendations for improvement. Which of the following techniques can you use to analyze these processes? | Cost-Benefit Analysis | Reserve Analysis | EMV Analysis | Process Analysis | You are managing a process improvement project for your company. You need to analyze over 20 of the company's processes to identify weaknesses and give your recommendations for improvement. Which of the following techniques can you use to analyze these processes? | Cost-Benefit Analysis | Reserve Analysis | EMV Analysis | Process Analysis | Quality Management | Executing | False | "19"
To documents a configuration management system, which of the following Project Scope Management processes is used? | Verify Scope | Define Scope | Control Scope | Plan Scope Management | To documents a configuration management system, which of the following Project Scope Management processes is used? | Verify Scope | Define Scope | Control Scope | Plan Scope Management | Scope Management | Planning | False | "18"
One month after project deployment, a project manager unsuccessfully tries to resolve an issue on their own. The project manager failed to inform stakeholders, which resulted in their frustration. To avoid stakeholders frustration, what should the project manager have done? | Referenced the lessons learned repository. | Updated the issue log. | Referred to the stakeholder engagement plan. | Adhere to the communication management plan. | One month after project deployment, a project manager unsuccessfully tries to resolve an issue on their own. The project manager failed to inform stakeholders, which resulted in their frustration. To avoid stakeholders frustration, what should the project manager have done? | Referenced the lessons learned repository. | Updated the issue log. | Referred to the stakeholder engagement plan. | Adhere to the communication management plan. | Communication Management | Planning | False | "20"
While Estimating costs - the PM expecting some rework in deliverables. However, the amount of rework is not known. This is an example of: | Management reserves | Three-Point Estimation | Betters-Up Estimation | Contingency Reserves | While Estimating costs - the PM expecting some rework in deliverables. However, the amount of rework is not known. This is an example of: | Management reserves | Three-Point Estimation | Betters-Up Estimation | Contingency Reserves | Cost Management | Planning | False | "19"
Tid is a project manager in an IT project. During the deployment of a new system, an unexpected power outage occurs. What should the Tid do? | Risk categorization | Risk probability and impact assessment | Perform a qualitative risk analysis | Refer to the risk register and inform key stakeholders | Tid is a project manager in an IT project. During the deployment of a new system, an unexpected power outage occurs. What should the Tid do? | Risk categorization | Risk probability and impact assessment | Perform a qualitative risk analysis | Refer to the risk register and inform key stakeholders | Risk Management | Planning | False | "16"
You was asked to create a business case for a company's new business in the Cyber Security sector. There is little expertise available within the company as these types of projects have not been done before. What should you as the project manager do? | Conduct a market analysis and finalize project requirements. | Identify key stakeholders and meet with them to discuss the new business endeavors. | Suggest that management doesn't pursue this business endeavors since there is a lack of experience. | Consult with subject matter experts. SMEs | You was asked to create a business case for a company's new business in the Cyber Security sector. There is little expertise available within the company as these types of projects have not been done before. What should you as the project manager do? | Conduct a market analysis and finalize project requirements. | Identify key stakeholders and meet with them to discuss the new business endeavors. | Suggest that management doesn't pursue this business endeavors since there is a lack of experience. | Consult with subject matter experts. SMEs | Scope Management | Planning | False | "19"
Jessy, a project team member identifies a simple change that will improve product quality without impacting the project budget. What should you do as the project manager? | Have team members include it in their assignments as quickly as possible. | After reviewing the change, include it in the quality management plan. | Ask the sponsor for their advice regarding the suggested change. | Meet with the team member to assess the impact, and follow the change control process | Jessy, a project team member identifies a simple change that will improve product quality without impacting the project budget. What should you do as the project manager? | Have team members include it in their assignments as quickly as possible. | After reviewing the change, include it in the quality management plan. | Ask the sponsor for their advice regarding the suggested change. | Meet with the team member to assess the impact, and follow the change control process | Integration Management | Monitoring and Controlling | False | "18"
You have just been assigned as the project manager for an ongoing project in your organization. You have discovered there is no Project Charter that describes the responsibilities and authorities of the project manager. When you talked to your project sponsor about this issue, he told you that your organization has executed many projects in the past without ever using a Project Charter. What will you do? | Create a draft project charter and submit to your supervisor | Create the project charter and inform project team members to ensure common understanding of the key deliverables and their roles and responsibilities | Conduct the project kick-off meeting and inform everyone that the project has started | Discuss the need to have a project charter with the sponsor | You have just been assigned as the project manager for an ongoing project in your organization. You have discovered there is no Project Charter that describes the responsibilities and authorities of the project manager. When you talked to your project sponsor about this issue, he told you that your organization has executed many projects in the past without ever using a Project Charter. What will you do? | Create a draft project charter and submit to your supervisor | Create the project charter and inform project team members to ensure common understanding of the key deliverables and their roles and responsibilities | Conduct the project kick-off meeting and inform everyone that the project has started | Discuss the need to have a project charter with the sponsor | Integration Management | Initiating | False | "19"
Mayra is a project manager who is deep into project execution. Currently, she is looking for information about the quality management issues that have been escalated by the team, as well as recommendations for process, project, and product improvements. What should she do? | Review the issue log | Review the quality management plan | Review the Risk register | Review the quality reports | Mayra is a project manager who is deep into project execution. Currently, she is looking for information about the quality management issues that have been escalated by the team, as well as recommendations for process, project, and product improvements. What should she do? | Review the issue log | Review the quality management plan | Review the Risk register | Review the quality reports | Quality Management | Executing | False | "20"
Levi is meeting with the seller's project manager to review their construction work. In this review Levi's focus is on the deliverables and a site walkthrough. What is this known as? | Performance review | Earned value analysis | Audit | Inspection | Levi is meeting with the seller's project manager to review their construction work. In this review Levi's focus is on the deliverables and a site walkthrough. What is this known as? | Performance review | Earned value analysis | Audit | Inspection | Quality Management | Monitoring and Controlling | False | "20"
You are a project manager of the civil Project. Your project is behind Schedule and the sponsor suggests reducing the time for quality assurance testing. What should you do first? | Perform quality audit. | Perform quality control measurements. | Change the quality requirements. | Follow the Quality Management Plan | You are a project manager of the civil Project. Your project is behind Schedule and the sponsor suggests reducing the time for quality assurance testing. What should you do first? | Perform quality audit. | Perform quality control measurements. | Change the quality requirements. | Follow the Quality Management Plan | Quality Management | Planning | False | "18"
Robin is a project manager on a large civil project. Robin had originally planned to use both of the company's tower crane simultaneously for a project but has just learned that one of them will be unavailable. Robin adjusts the schedule so that the components are created sequentially using the one remaining tower crane. Unfortunately, this action affects the critical path and delays the planned finish date of the project. Which of the following techniques has been used by Robin in this situation? | Fast tracking | Reserve analysis | Critical path method | Resource leveling | Robin is a project manager on a large civil project. Robin had originally planned to use both of the company's tower crane simultaneously for a project but has just learned that one of them will be unavailable. Robin adjusts the schedule so that the components are created sequentially using the one remaining tower crane. Unfortunately, this action affects the critical path and delays the planned finish date of the project. Which of the following techniques has been used by Robin in this situation? | Fast tracking | Reserve analysis | Critical path method | Resource leveling | Schedule Management | Planning | False | "18"
You are leading a construction new commercial project to install new door frames in an office building. Currently, you are about to start the development of the assumption log for the project. What should you do first? | Review the project scope statement | Start the Identify Stakeholders process as the assumption log is an output of this process | Review the project management plan | Read the project business case | You are leading a construction new commercial project to install new door frames in an office building. Currently, you are about to start the development of the assumption log for the project. What should you do first? | Review the project scope statement | Start the Identify Stakeholders process as the assumption log is an output of this process | Review the project management plan | Read the project business case | Integration Management | Initiating | False | "20"
As part of the initiation process, what should the project manager do prior to the planning stage? | Define the project sign-off criteria and create a risk register. | Start gathering requirements and plan the kick-off meeting. | Acquire the resources and determine the budget. | Develop the project charter and identify the stakeholders. | As part of the initiation process, what should the project manager do prior to the planning stage? | Define the project sign-off criteria and create a risk register. | Start gathering requirements and plan the kick-off meeting. | Acquire the resources and determine the budget. | Develop the project charter and identify the stakeholders. | Integration Management | Initiating | False | "19"
A project manager needed to monitor the technical performance of the project and capture data related to how many errors or defects had been identified and how many remained uncorrected. Which of the following techniques should he use? | Control chart | Flowchart | Scatter diagram | Histogram | A project manager needed to monitor the technical performance of the project and capture data related to how many errors or defects had been identified and how many remained uncorrected. Which of the following techniques should he use? | Control chart | Flowchart | Scatter diagram | Histogram | Quality Management | Executing | False | "19"
The customer insist on using an alternative execution methodology, which is expected to increase project costs. What should the project manager do? | Explain to the stakeholders why the execution methodology cannot be changed. | Ignore the request, and continue with the planned execution methodology. | Assess the stakeholder's methodology see if their expectations can be met. | Escalate the potential methodology change to the project sponsor for approval. | The customer insist on using an alternative execution methodology, which is expected to increase project costs. What should the project manager do? | Explain to the stakeholders why the execution methodology cannot be changed. | Ignore the request, and continue with the planned execution methodology. | Assess the stakeholder's methodology see if their expectations can be met. | Escalate the potential methodology change to the project sponsor for approval. | Risk Management | Planning | False | "17"
While browsing a local archive, a new project manager finds the previous project's lessons learned notes. They observe that the notes have not yet been stored in the project management information system PMIS. What should the project manager do with the notes? | As the notes are already available, no further action is required. | Store a local copy on their hard drive for future use. | Disregard the notes since they are not in the PMIS. | Ask the previous project manager to archive the notes in the PMIS. | While browsing a local archive, a new project manager finds the previous project's lessons learned notes. They observe that the notes have not yet been stored in the project management information system PMIS. What should the project manager do with the notes? | As the notes are already available, no further action is required. | Store a local copy on their hard drive for future use. | Disregard the notes since they are not in the PMIS. | Ask the previous project manager to archive the notes in the PMIS. | Integration Management | Closing | False | "19"
During testing, a team member escalates a quality defect to you "the project manager". While brainstorming with the team, you realizes there is more than one cause of the problem. What should you use to identify the primary cause? | Qualitative risk analysis | Statistical sampling | Scatter diagram | Ishikawa diagram | During testing, a team member escalates a quality defect to you "the project manager". While brainstorming with the team, you realizes there is more than one cause of the problem. What should you use to identify the primary cause? | Qualitative risk analysis | Statistical sampling | Scatter diagram | Ishikawa diagram | Quality Management | Executing | False | "20"
Liza is managing a civil project . During the implementation phase, a team member has told her that one of the risks previously identified has occurred. As a project manager, what should Liza do next? | Update the risk management plan | Implement a workaround plan | Update the change log | Update Risk Register | Liza is managing a civil project . During the implementation phase, a team member has told her that one of the risks previously identified has occurred. As a project manager, what should Liza do next? | Update the risk management plan | Implement a workaround plan | Update the change log | Update Risk Register | Risk Management | Planning | False | "18"
Your project planner has just started working with your project and has produced defective reports for the past three accounting cycles. You are now checking your company policies before moving to the next step with the corrective actions. In which process are you now: | Control Scope | Validate Scope | Perform Quality Audit | Manage Quality | Your project planner has just started working with your project and has produced defective reports for the past three accounting cycles. You are now checking your company policies before moving to the next step with the corrective actions. In which process are you now: | Control Scope | Validate Scope | Perform Quality Audit | Manage Quality | Quality Management | Executing | False | "18"
You are working as a research studying the growth of bacteria under different environmental conditions. Based on your experiments, you conclude that the immortality of bacteria increases as the temperature increases. What type of diagram can you use to illustrate your observation? | Control chart | Run Chart | Histogram | Scatter diagram | You are working as a research studying the growth of bacteria under different environmental conditions. Based on your experiments, you conclude that the immortality of bacteria increases as the temperature increases. What type of diagram can you use to illustrate your observation? | Control chart | Run Chart | Histogram | Scatter diagram | Quality Management | Executing | False | "18"
You are a project manager, your company would like to outsource the landscaping works to the subcontractor to complete within 2 months. The budget of the works is SAR 40,000 and the scope is well defined. What type of contract preferred to be used: | Cost plus incentive fee | Cost-reimbursable | Time and material | Fixed-price | You are a project manager, your company would like to outsource the landscaping works to the subcontractor to complete within 2 months. The budget of the works is SAR 40,000 and the scope is well defined. What type of contract preferred to be used: | Cost plus incentive fee | Cost-reimbursable | Time and material | Fixed-price | Procurement Management | Planning | False | "17"
While working on the project in the Manage Quality process, The project manager is determining the factors that may influence specific characteristics of a product under development and can improve the product's final characteristics. What technique is the PM using? | Analogous estimating | Benchmarking | Cost of quality | Design for X (Daft) | While working on the project in the Manage Quality process, The project manager is determining the factors that may influence specific characteristics of a product under development and can improve the product's final characteristics. What technique is the PM using? | Analogous estimating | Benchmarking | Cost of quality | Design for X (Daft) | Quality Management | Executing | False | "19"
A quality control member informs a you about a one-week schedule delay to complete the testing phase. What should you do next? | Crash the schedule. | Negotiate with the customer for a change in the schedule. | Take corrective action to minimize the impact of delay | Check whether this task is on the critical path. | A quality control member informs a you about a one-week schedule delay to complete the testing phase. What should you do next? | Crash the schedule. | Negotiate with the customer for a change in the schedule. | Take corrective action to minimize the impact of delay | Check whether this task is on the critical path. | Schedule Management | Monitoring and Controlling | False | "20"
You are managing a large project approaching its completion. You have to send the final project report to all stakeholders but receives an email from an executive manager in the company asking about the status of the project. How should you handle this request? | Review the risk register to find a response for the executive. | Ask the executive to join the next progress meeting | Send the project milestones to the executive. | Ensure the executive manager is in the communications management plan. | You are managing a large project approaching its completion. You have to send the final project report to all stakeholders but receives an email from an executive manager in the company asking about the status of the project. How should you handle this request? | Review the risk register to find a response for the executive. | Ask the executive to join the next progress meeting | Send the project milestones to the executive. | Ensure the executive manager is in the communications management plan. | Communication Management | Planning | False | "19"
A Project Manager is working on a project to create high-efficiency electric motors for a company introducing a new electric golf cart. The company's president is keenly interested in the project and requests a chart that shows the number of defects per deliverable and ranking of the causes of defects. Which type of chart would BEST meet this request? | Control chart | Statistical sampling | Scatter diagram | Histograms | A Project Manager is working on a project to create high-efficiency electric motors for a company introducing a new electric golf cart. The company's president is keenly interested in the project and requests a chart that shows the number of defects per deliverable and ranking of the causes of defects. Which type of chart would BEST meet this request? | Control chart | Statistical sampling | Scatter diagram | Histograms | Quality Management | Executing | False | "20"
The sponsor complains about the quality of some deliverables. The project manager believes that these deliverables meet the project's quality standards. What tool or technique should the project manager use to support this? | Scatter diagrams | Cause-and-effect diagrams | Histograms | Control charts | The sponsor complains about the quality of some deliverables. The project manager believes that these deliverables meet the project's quality standards. What tool or technique should the project manager use to support this? | Scatter diagrams | Cause-and-effect diagrams | Histograms | Control charts | Quality Management | Monitoring and Controlling | False | "19"
A methods in the Control Schedule process is used to compute different scenarios to get the project realigned with the Project Management Plan. What is this method called? | Corrective Action | Delphi Technique | Pareto Chart | What if Scenario analysis | A methods in the Control Schedule process is used to compute different scenarios to get the project realigned with the Project Management Plan. What is this method called? | Corrective Action | Delphi Technique | Pareto Chart | What if Scenario analysis | Schedule Management | Monitoring and Controlling | False | "19"
You are estimating activity durations for a project. Which of the following is the best to help the project manager to estimate duration? | Project sponsor | All Stakeholders | HR manger | Subject matter expert (SME) | You are estimating activity durations for a project. Which of the following is the best to help the project manager to estimate duration? | Project sponsor | All Stakeholders | HR manger | Subject matter expert (SME) | Schedule Management | Planning | False | "19"
Nada is managing a complex industrial process reengineering project. She has identified all her key project stakeholders and has conducted individual interviews with them to identify other project stakeholders, as well. However, Nada is still not satisfied with her project?s stakeholders list; she believes there may be more key external stakeholders missing from the list. What can help Nada in this situation? | Use stakeholder register templates from the organizational process assets | Conduct more meetings with the key stakeholders | Get over her fear and finalize the project stakeholder register | Seek expert judgment from subject matter experts | Nada is managing a complex industrial process reengineering project. She has identified all her key project stakeholders and has conducted individual interviews with them to identify other project stakeholders, as well. However, Nada is still not satisfied with her project?s stakeholders list; she believes there may be more key external stakeholders missing from the list. What can help Nada in this situation? | Use stakeholder register templates from the organizational process assets | Conduct more meetings with the key stakeholders | Get over her fear and finalize the project stakeholder register | Seek expert judgment from subject matter experts | Stakeholder Management | Initiating | False | "16"
You want to confirm that the project team implemented best practices for the requirements-gathering process. What should you as the project manager do? | Examine the lessons learned repository | Review quality control reports | Evaluate the work performance reports | Perform a quality audit | You want to confirm that the project team implemented best practices for the requirements-gathering process. What should you as the project manager do? | Examine the lessons learned repository | Review quality control reports | Evaluate the work performance reports | Perform a quality audit | Quality Management | Executing | False | "19"
During initial project scheduling, an internal key stakeholder announces that they already agreed on some delivery dates with a vendor. What technique should you as the project manager use to ensure that all prerequisites are fulfilled for those deliverables to meet the agreed dates? | Discretionary dependencies. | Internal dependencies. | Finish-to-finish dependencies. | Mandatory dependencies. | During initial project scheduling, an internal key stakeholder announces that they already agreed on some delivery dates with a vendor. What technique should you as the project manager use to ensure that all prerequisites are fulfilled for those deliverables to meet the agreed dates? | Discretionary dependencies. | Internal dependencies. | Finish-to-finish dependencies. | Mandatory dependencies. | Schedule Management | Planning | False | "20"
After finalizing some activities for the project, the customer is not satisfied and complains that his requirements are not being met. in which of the following processes should the project manager have involved him to ensure approval? | Collect requirements | Develop Project charter | Close project or phase | Validate scope | After finalizing some activities for the project, the customer is not satisfied and complains that his requirements are not being met. in which of the following processes should the project manager have involved him to ensure approval? | Collect requirements | Develop Project charter | Close project or phase | Validate scope | Scope Management | Monitoring and Controlling | False | "19"
All the following are true regarding resource calendars, except ? | Resource calendars are an output of the Acquire Resources process. | Resource calendars consider quantity, capability, and availability of equipment and material resources. | Resource calendars show the resources' vacation time | Resource calendars are an output of the Develop Schedule process. | All the following are true regarding resource calendars, except ? | Resource calendars are an output of the Acquire Resources process. | Resource calendars consider quantity, capability, and availability of equipment and material resources. | Resource calendars show the resources' vacation time | Resource calendars are an output of the Develop Schedule process. | Schedule Management | Planning | False | "18"
Tom is a project manager joins a project with cross-functional stakeholders and a fixed go-live date. He wants to quickly gather requirements and ensure all stakeholders are aligned so that any conflicts are flagged as early as possible. What should Tom do? | Send a questionnaire to all stakeholders. | Conduct individual interviews with each stakeholder. | Set up job-shadowing sessions for all stakeholders. | Use facilitation techniques with all stakeholders. | Tom is a project manager joins a project with cross-functional stakeholders and a fixed go-live date. He wants to quickly gather requirements and ensure all stakeholders are aligned so that any conflicts are flagged as early as possible. What should Tom do? | Send a questionnaire to all stakeholders. | Conduct individual interviews with each stakeholder. | Set up job-shadowing sessions for all stakeholders. | Use facilitation techniques with all stakeholders. | Scope Management | Planning | False | "20"
Tom is in the executing phase of his project and stakeholders are escalating issues to management directly without involving him. Which of the following would have prevented this from happening if well documented and communicated? | Project Charter | Issues log | Risk register | Communications Management Plan | Tom is in the executing phase of his project and stakeholders are escalating issues to management directly without involving him. Which of the following would have prevented this from happening if well documented and communicated? | Project Charter | Issues log | Risk register | Communications Management Plan | Communication Management | Planning | False | "20"
You receive an email requesting modification to a project's baseline. From whom should the project manager request formal approval to implement this change? | Project sponsor | Project customer | Project management office (PMO) | Change control board (CCB) | You receive an email requesting modification to a project's baseline. From whom should the project manager request formal approval to implement this change? | Project sponsor | Project customer | Project management office (PMO) | Change control board (CCB) | Integration Management | Monitoring and Controlling | False | "19"
The change control board (CCB) has rejected a change request made by a key stakeholder. What should the project manager do? | Ask the CCB to reconsider and review the change request again. | Ask the sponsor to review and approve the change request. | Implement the change that the key stakeholder has requested. | Notify the key stakeholder about the decision made by the CCB. | The change control board (CCB) has rejected a change request made by a key stakeholder. What should the project manager do? | Ask the CCB to reconsider and review the change request again. | Ask the sponsor to review and approve the change request. | Implement the change that the key stakeholder has requested. | Notify the key stakeholder about the decision made by the CCB. | Integration Management | Monitoring and Controlling | False | "20"
You are a project manager. One of your team members identifies a risk for which new requirements may be needed for a project. This risk has a high impact but a low chance of occurrence. As a project manager, what should you do? | Assess and monitor the risk, and develop a risk response strategy. | Update the Risk register and scope baseline | Issue a change request and get it approved through Integrated Change Control process | Accept the risk and plan to use the contingency reserve. | You are a project manager. One of your team members identifies a risk for which new requirements may be needed for a project. This risk has a high impact but a low chance of occurrence. As a project manager, what should you do? | Assess and monitor the risk, and develop a risk response strategy. | Update the Risk register and scope baseline | Issue a change request and get it approved through Integrated Change Control process | Accept the risk and plan to use the contingency reserve. | Risk Management | Planning | False | "18"
A new government regulation requires financial resources to be added to a project, the CEO request to add another project activity. What should the project manager do? | Update the schedule to include the new activity because it was requested by the CEO. | Execute the new activity because it was requested by the CEO. | Use funding allocated to other activities to execute the CEO's request. | Document the request from the CEO and perform the change request procedure | A new government regulation requires financial resources to be added to a project, the CEO request to add another project activity. What should the project manager do? | Update the schedule to include the new activity because it was requested by the CEO. | Execute the new activity because it was requested by the CEO. | Use funding allocated to other activities to execute the CEO's request. | Document the request from the CEO and perform the change request procedure | Integration Management | Monitoring and Controlling | False | "18"
At the end of project execution, Michel the project manager has retained some team members. What should the team be primarily focused on doing at this point? | Providing support as part of the warranty period associated with the handover | Operating the newly completed facilities until the owners are fully competent | Assisting with clean up, site restoration, commissioning, and personnel training | Supporting administrative project closure procedures as per company policies | At the end of project execution, Michel the project manager has retained some team members. What should the team be primarily focused on doing at this point? | Providing support as part of the warranty period associated with the handover | Operating the newly completed facilities until the owners are fully competent | Assisting with clean up, site restoration, commissioning, and personnel training | Supporting administrative project closure procedures as per company policies | Integration Management | Closing | False | "20"
Your CEO asked you what the Estimate at Completion (EAC) will be for a small project you are working on. You were given a budget of $30,000, and to date, you have spent $20,000 but only completed $10,000 worth of work. You are sure the future work will be accomplished at the planned rate. What is the EAC? | $30,000 as Planned Rate | $60,000 as CPI is expected to be the same | $10,000 as CPI is expected to be the same | $40,000 as Planned Rate | Your CEO asked you what the Estimate at Completion (EAC) will be for a small project you are working on. You were given a budget of $30,000, and to date, you have spent $20,000 but only completed $10,000 worth of work. You are sure the future work will be accomplished at the planned rate. What is the EAC? | $30,000 as Planned Rate | $60,000 as CPI is expected to be the same | $10,000 as CPI is expected to be the same | $40,000 as Planned Rate | Cost Management | Monitoring and Controlling | False | "19"
You are managing a project which will provide web- base solutions to your customer. The requirements of this project are not clearly defined in the beginning and there will be modifications based on customer feedback as the project evolves. You plan as much as you can and work based on that. You continue the planning as you learn more about the project. Which techniques will be most helpful to define activities on the project? | Templates | WBS | Scope management | Rolling wave planning | You are managing a project which will provide web- base solutions to your customer. The requirements of this project are not clearly defined in the beginning and there will be modifications based on customer feedback as the project evolves. You plan as much as you can and work based on that. You continue the planning as you learn more about the project. Which techniques will be most helpful to define activities on the project? | Templates | WBS | Scope management | Rolling wave planning | Schedule Management | Planning | False | "19"
You are the project manager for a mobile application development project. An issue has occurred and one of the team members identifies a workaround, but fails to inform you. After a few weeks, a similar issue appeared again that impact the project. What should have done to prevent this situation? | Escalate the problem to the sponsor | Updating the risk register | Revising the responsibility assignments matrix (RAM). | Performing a root cause analysis | You are the project manager for a mobile application development project. An issue has occurred and one of the team members identifies a workaround, but fails to inform you. After a few weeks, a similar issue appeared again that impact the project. What should have done to prevent this situation? | Escalate the problem to the sponsor | Updating the risk register | Revising the responsibility assignments matrix (RAM). | Performing a root cause analysis | Quality Management | Executing | False | "20"
Which data representation techniques helps to categorize stakeholders and combine the grid elements into a three-dimensional model that can be useful to project managers and teams in identifying and engaging their stakeholder community and assists with the development of communication strategies? | Probability and impact matrix | Power/interest grid | Power/influence grid | Stakeholder cube | Which data representation techniques helps to categorize stakeholders and combine the grid elements into a three-dimensional model that can be useful to project managers and teams in identifying and engaging their stakeholder community and assists with the development of communication strategies? | Probability and impact matrix | Power/interest grid | Power/influence grid | Stakeholder cube | Stakeholder Management | Initiating | False | "17"
Ben is the new project manager who has never managed a project before. He has been asked to plan a new project. Which of the following will help him to improve his chance of choices? | Configuration management. | Stakeholder analysis. | Your intuition and training. | Historical information. | Ben is the new project manager who has never managed a project before. He has been asked to plan a new project. Which of the following will help him to improve his chance of choices? | Configuration management. | Stakeholder analysis. | Your intuition and training. | Historical information. | Integration Management | Planning | False | "18"
In order to determine the target fuel efficiency for a hybrid car being designed, you are looking at published statistics for similar models in the industry. The technique being used is called: | Brainstorming | Statistical sampling | Scatter diagrams | Benchmarking | In order to determine the target fuel efficiency for a hybrid car being designed, you are looking at published statistics for similar models in the industry. The technique being used is called: | Brainstorming | Statistical sampling | Scatter diagrams | Benchmarking | Quality Management | Planning | False | "19"
During a review meeting, you observe that one team member performed tasks beyond the scope of work. What should you as the project manager do? | Crash the project to accommodate the additional scope that was performed. | Advice the team member to keep all work within project scope. | Inform the client of additional cost implications due to the extra work completed. | Review the impact on the baseline and initiate changes control procedures. | During a review meeting, you observe that one team member performed tasks beyond the scope of work. What should you as the project manager do? | Crash the project to accommodate the additional scope that was performed. | Advice the team member to keep all work within project scope. | Inform the client of additional cost implications due to the extra work completed. | Review the impact on the baseline and initiate changes control procedures. | Scope Management | Monitoring and Controlling | False | "17"
A security team notifies you of a change in security procedures. you use the change control process to update the project management plan. After seeing the change, a stakeholder complains that it was unnecessary because the project is almost complete. What should you as the project manager do? | Create a change request to reverse the change until a consensus is reached. | Add a risk to the risk register to track the impact of stakeholder disagreement. | Ignore the stakeholder's concern and follow the new procedures. | Convince the stakeholder of the benefits resulting from the change. | A security team notifies you of a change in security procedures. you use the change control process to update the project management plan. After seeing the change, a stakeholder complains that it was unnecessary because the project is almost complete. What should you as the project manager do? | Create a change request to reverse the change until a consensus is reached. | Add a risk to the risk register to track the impact of stakeholder disagreement. | Ignore the stakeholder's concern and follow the new procedures. | Convince the stakeholder of the benefits resulting from the change. | Stakeholder Management | Monitoring and Controlling | False | "19"
John finds that a specific work package was not delivered on time and will be delayed by an additional three weeks. He worries that this might impact project completion. What should John do first? | Determine if the work package is on the critical path. | Adjust the Gantt chart for the work package. | Use schedule compression to get the project back on track. | Calculate the amount of total float for the work package. | John finds that a specific work package was not delivered on time and will be delayed by an additional three weeks. He worries that this might impact project completion. What should John do first? | Determine if the work package is on the critical path. | Adjust the Gantt chart for the work package. | Use schedule compression to get the project back on track. | Calculate the amount of total float for the work package. | Schedule Management | Monitoring and Controlling | False | "20"
The collect requirements team has generated a large number of ideas during sessions to gather product and project requirements. Which of the following techniques is best suited to generate, organize information and allows large numbers of ideas to be classified into groups for review and analysis? | Idea/mind mapping | Nominal group technique | Brainstorming | Affinity diagram | The collect requirements team has generated a large number of ideas during sessions to gather product and project requirements. Which of the following techniques is best suited to generate, organize information and allows large numbers of ideas to be classified into groups for review and analysis? | Idea/mind mapping | Nominal group technique | Brainstorming | Affinity diagram | Scope Management | Planning | False | "18"
You have been appointed as a project manager for a project which involves more than 2,000 stakeholders. One of the key stakeholders does not have authority regarding project decisions, but you recently discovered that he has much interest in your project. What stakeholder management strategy should you use with this key stakeholder? | Keep him satisfied | Monitor his actions | Manage him closely | Keep him informed | You have been appointed as a project manager for a project which involves more than 2,000 stakeholders. One of the key stakeholders does not have authority regarding project decisions, but you recently discovered that he has much interest in your project. What stakeholder management strategy should you use with this key stakeholder? | Keep him satisfied | Monitor his actions | Manage him closely | Keep him informed | Stakeholder Management | Initiating | False | "18"
Six Sigma methodology incorporates many powerful tools to use in continuous improvement projects and programs. Six Sigma are tools in which of the following processes? | Plan Scope management | Close project or phase | Define Scope | Manage Quality | Six Sigma methodology incorporates many powerful tools to use in continuous improvement projects and programs. Six Sigma are tools in which of the following processes? | Plan Scope management | Close project or phase | Define Scope | Manage Quality | Quality Management | Executing | False | "19"
Ali have been assigned as a project manager for a project. Ali and his team members start to identify individual project risks as well as sources of overall project risk and documenting their characteristics. Which of the following Data analysis techniques can be used for this process? | Interviews | Probability and impact matrix | Brainstorming | Root cause analysis | Ali have been assigned as a project manager for a project. Ali and his team members start to identify individual project risks as well as sources of overall project risk and documenting their characteristics. Which of the following Data analysis techniques can be used for this process? | Interviews | Probability and impact matrix | Brainstorming | Root cause analysis | Risk Management | Planning | False | "19"
You are the project manager of a project to solve customer service problems in your marketing company. During the execution phase, several quality defects have been discovered, causing customer concern. You would like to create a chart showing the frequency of problems and the causes that have the largest number of defects. Which tool shows defects by volume from greatest to least? | Flowchart | Matrix diagrams | Ishikawa Diagram | Pareto Chart | You are the project manager of a project to solve customer service problems in your marketing company. During the execution phase, several quality defects have been discovered, causing customer concern. You would like to create a chart showing the frequency of problems and the causes that have the largest number of defects. Which tool shows defects by volume from greatest to least? | Flowchart | Matrix diagrams | Ishikawa Diagram | Pareto Chart | Quality Management | Executing | False | "20"
You are in the process of analyzing the stakeholders on your project. You have grouped them based on their authority and their degree of active involvement in the project. Which of the following would you use to document this information? | Model Power/Interest Grid | Influence/Impact Grid | Salience | Power/Influence Grid | You are in the process of analyzing the stakeholders on your project. You have grouped them based on their authority and their degree of active involvement in the project. Which of the following would you use to document this information? | Model Power/Interest Grid | Influence/Impact Grid | Salience | Power/Influence Grid | Stakeholder Management | Initiating | False | "19"
You are estimating the duration of your project activities using a triangular distribution formula. For a particular project activity, your Optimistic estimate is 14 days, Pessimistic estimate is 49 days, and Most Likely estimate is 27 days. What is the expected duration of this activity? | 50 | 25 | 32 | 30 | You are estimating the duration of your project activities using a triangular distribution formula. For a particular project activity, your Optimistic estimate is 14 days, Pessimistic estimate is 49 days, and Most Likely estimate is 27 days. What is the expected duration of this activity? | 50 | 25 | 32 | 30 | Schedule Management | Planning | False | "20"
You want to establish benchmark for comparing actual project performance with the project management plan. What process should you complete to generate this model? | Develop schedule | Sequence activities | Develop project Charter | Create WBS | You want to establish benchmark for comparing actual project performance with the project management plan. What process should you complete to generate this model? | Develop schedule | Sequence activities | Develop project Charter | Create WBS | Scope Management | Planning | False | "19"
During the testing phase, your testing team implemented a solution to correct a defect they discovered. The solution didn't have an impact on cost or time. You know the case now; as a Project manager your action should be: | Update management plans | Escalate the team member who did the action without letting you know | Issue a change request to CCB | Add the corrective action to a Lessons learned register | During the testing phase, your testing team implemented a solution to correct a defect they discovered. The solution didn't have an impact on cost or time. You know the case now; as a Project manager your action should be: | Update management plans | Escalate the team member who did the action without letting you know | Issue a change request to CCB | Add the corrective action to a Lessons learned register | Quality Management | Monitoring and Controlling | False | "20"
During the planning phase of a project, you learn that the sponsor has eliminated some important deliverables in other projects over the past three years, producing a negative cost variance. What should the you as a project manager do next? | Document the lessons learned. | Define the scope baseline correctly. | Document the issue in the issue log. | Include the risk in the risk register. | During the planning phase of a project, you learn that the sponsor has eliminated some important deliverables in other projects over the past three years, producing a negative cost variance. What should the you as a project manager do next? | Document the lessons learned. | Define the scope baseline correctly. | Document the issue in the issue log. | Include the risk in the risk register. | Risk Management | Planning | False | "20"
Nada has been assigned to establish a PMO in her organization. Nada believes this project cannot succeed unless all the key project stakeholders support the project. She also believes she needs to pay special attention to stakeholder management to ensure the success of this project. First, she needs to develop her stakeholder register. To produce the project stakeholder register, which of the following processes must Nada start? | Plan Stakeholder Engagement | Manage Stakeholder Engagement | Monitor Stakeholder Engagement | Identify Stakeholders | Nada has been assigned to establish a PMO in her organization. Nada believes this project cannot succeed unless all the key project stakeholders support the project. She also believes she needs to pay special attention to stakeholder management to ensure the success of this project. First, she needs to develop her stakeholder register. To produce the project stakeholder register, which of the following processes must Nada start? | Plan Stakeholder Engagement | Manage Stakeholder Engagement | Monitor Stakeholder Engagement | Identify Stakeholders | Stakeholder Management | Initiating | False | "20"
Which of the following statements most accurately describes a project scenario? | Changes in project scope during the initial phases of the project are very expensive | The influence of the stakeholders is the same all through the project | The next phase of a project should never start until the deliverables for the previous phase are completely reviewed and approved | Staffing peaks are in the execution phase of a project | Which of the following statements most accurately describes a project scenario? | Changes in project scope during the initial phases of the project are very expensive | The influence of the stakeholders is the same all through the project | The next phase of a project should never start until the deliverables for the previous phase are completely reviewed and approved | Staffing peaks are in the execution phase of a project | Resources Management | Executing | False | "16"
Which of the following is a tool or technique of the Develop Team process? | Organizational charts | Acquisition | Influence diagrams | Co-location | Which of the following is a tool or technique of the Develop Team process? | Organizational charts | Acquisition | Influence diagrams | Co-location | Resources Management | Executing | False | "17"
A project manager in a multinational company has assigned to implement new software that will impact several departments. To guarantee alignment of stakeholder expectations with the final product, what should the PM develop? | Business case | Stakeholder engagement assessment matrix. | Risk Breakdown structure (RBS) | Stakeholder engagement plan. | A project manager in a multinational company has assigned to implement new software that will impact several departments. To guarantee alignment of stakeholder expectations with the final product, what should the PM develop? | Business case | Stakeholder engagement assessment matrix. | Risk Breakdown structure (RBS) | Stakeholder engagement plan. | Stakeholder Management | Planning | False | "20"
Your are managing a project which needs a few vendors to finish the work. One of the vendors before signing asked you to first get a part of payment before he makes the first shipment. As a Project manager, you will review: | Contract and agreement | Project Charter | Company process and conditions | Procurement Management Plan | Your are managing a project which needs a few vendors to finish the work. One of the vendors before signing asked you to first get a part of payment before he makes the first shipment. As a Project manager, you will review: | Contract and agreement | Project Charter | Company process and conditions | Procurement Management Plan | Procurement Management | Planning | False | "18"
A team member in your project is constantly providing incomplete deliverables and not performing well. What should you do first? | Discuss the issue with the team member in the presence of the project sponsor | Discuss the issue with the team member in the presence of other team members | Discuss the issue with the team member in the presence of the company's HR manager | Discuss the issue with the team member in private | A team member in your project is constantly providing incomplete deliverables and not performing well. What should you do first? | Discuss the issue with the team member in the presence of the project sponsor | Discuss the issue with the team member in the presence of other team members | Discuss the issue with the team member in the presence of the company's HR manager | Discuss the issue with the team member in private | Resources Management | Executing | False | "18"
During execution phase, a project manager learns that a team member's line manager believes they shouldn't execute a certain task. What document should the project manager review to resolve this? | Organizational chart | Work breakdown structure (WBS) | Resource management plan | RACI (responsible, accountable, consult, and inform) chart | During execution phase, a project manager learns that a team member's line manager believes they shouldn't execute a certain task. What document should the project manager review to resolve this? | Organizational chart | Work breakdown structure (WBS) | Resource management plan | RACI (responsible, accountable, consult, and inform) chart | Resources Management | Planning | False | "19"
The project team learns from a key stakeholders that some deliverables have been forwarded for approval without their knowledge. What should you have done to prevent this situation? | Notified the project team. | Scheduled a meeting with the customer and the project team | Consulted the most recent meeting minutes related to deliverable | Verified the communication management plan. | The project team learns from a key stakeholders that some deliverables have been forwarded for approval without their knowledge. What should you have done to prevent this situation? | Notified the project team. | Scheduled a meeting with the customer and the project team | Consulted the most recent meeting minutes related to deliverable | Verified the communication management plan. | Communication Management | Planning | False | "18"
A large, publicly funded civil project regulatory requirements specify that the contractor's project work be visually monitored on a continuous basis. Which method is suitable for meeting this compliance obligation'? | Video feedback using a drone | Photographs by an onsite photographer | Photographs attached to documentation submitted on a weekly basis | Video feedback through onsite web cameras | A large, publicly funded civil project regulatory requirements specify that the contractor's project work be visually monitored on a continuous basis. Which method is suitable for meeting this compliance obligation'? | Video feedback using a drone | Photographs by an onsite photographer | Photographs attached to documentation submitted on a weekly basis | Video feedback through onsite web cameras | Procurement Management | Planning | False | "19"
You have just taken over a project from another project manager about six months into a 12-month project. As you get to know the staff on the project, you become aware that five staff members are relatives of the previous project manager. What do you do? | Check recruitment records of all employees | Report the HR manager to PMI | Interview these five employees | Notify your project stakeholders there is a possibility that nepotism was behind some of the staffing decisions made on your project | You have just taken over a project from another project manager about six months into a 12-month project. As you get to know the staff on the project, you become aware that five staff members are relatives of the previous project manager. What do you do? | Check recruitment records of all employees | Report the HR manager to PMI | Interview these five employees | Notify your project stakeholders there is a possibility that nepotism was behind some of the staffing decisions made on your project | Resources Management | Executing | False | "19"
During the execution of the project, the project manager had to manage a change request. He evaluated the impact of the change on the other constraints of the project then he got the change request approved by CCB. The next step a project manager should do is: | Implement the Approved change. | Update Project Management plan. | Update the Issue Log. | Ask the Sponsor for authorization. | During the execution of the project, the project manager had to manage a change request. He evaluated the impact of the change on the other constraints of the project then he got the change request approved by CCB. The next step a project manager should do is: | Implement the Approved change. | Update Project Management plan. | Update the Issue Log. | Ask the Sponsor for authorization. | Integration Management | Monitoring and Controlling | False | "19"
The project manager forgot to archive the project document at the closing process. What is the benefit of the archive project document? | Collecting lessons learned | Update the organization's knowledge base. | Update the OPA | For potential use in future projects and audits. | The project manager forgot to archive the project document at the closing process. What is the benefit of the archive project document? | Collecting lessons learned | Update the organization's knowledge base. | Update the OPA | For potential use in future projects and audits. | Integration Management | Closing | False | "19"
The CTO identified a problem with one of the features of a software application your team was working on and submitted a change request. Even though it was out of the project's scope, the change control board approved the change. The BEST action to take next is: | Inform stakeholders with the new status of the project | Update Project management plan | Implement the Approved change request | Update the change log | The CTO identified a problem with one of the features of a software application your team was working on and submitted a change request. Even though it was out of the project's scope, the change control board approved the change. The BEST action to take next is: | Inform stakeholders with the new status of the project | Update Project management plan | Implement the Approved change request | Update the change log | Integration Management | Monitoring and Controlling | False | "20"
You are a project manager, and your project is currently in the execution phase. One of your project teams leave the site early at 3:00 pm Thursday and mistreats his colleagues. You would like to establish clear expectations regarding the acceptable behavior of the team member. To avoid such situations, you should create: | Team-building activities | Interpersonal skills | Management skills | Team charter | You are a project manager, and your project is currently in the execution phase. One of your project teams leave the site early at 3:00 pm Thursday and mistreats his colleagues. You would like to establish clear expectations regarding the acceptable behavior of the team member. To avoid such situations, you should create: | Team-building activities | Interpersonal skills | Management skills | Team charter | Resources Management | Executing | False | "20"
A project has a duration of three years. In the middle of the project, the project manager resigned. A new project manager was assigned, and at the first meeting, the project team told him that a flood may happen within the next few months and will affect the project equipment. What should the project manager do next? | Using a management reserves | Using a workaround | Update the risk register | Review a risk management plan | A project has a duration of three years. In the middle of the project, the project manager resigned. A new project manager was assigned, and at the first meeting, the project team told him that a flood may happen within the next few months and will affect the project equipment. What should the project manager do next? | Using a management reserves | Using a workaround | Update the risk register | Review a risk management plan | Risk Management | Planning | False | "18"
You have a project that is three months behind but is surprisingly markedly under budget. You have decided to try to make up time, but needs to minimize the project risk. What is the best thing to do? | Fast track the project | Redefine the scope | Perform resource levelling | Crash the project | You have a project that is three months behind but is surprisingly markedly under budget. You have decided to try to make up time, but needs to minimize the project risk. What is the best thing to do? | Fast track the project | Redefine the scope | Perform resource levelling | Crash the project | Schedule Management | Planning | False | "18"
During the planning stage of a project, a company goes under an organizational structure change. The project manager believes most of the stakeholders have changed. Which tool or technique should the project manager uses to verify whether the stakeholders have changed? | Mind mapping. | Decision-making matrix. | Fishbone diagram. | Questionnaires and surveys. | During the planning stage of a project, a company goes under an organizational structure change. The project manager believes most of the stakeholders have changed. Which tool or technique should the project manager uses to verify whether the stakeholders have changed? | Mind mapping. | Decision-making matrix. | Fishbone diagram. | Questionnaires and surveys. | Stakeholder Management | Initiating | False | "16"
Fixed Price Contract is a form of which risk? | Avoiding | Mitigating | Working around | Transferring | Fixed Price Contract is a form of which risk? | Avoiding | Mitigating | Working around | Transferring | Risk Management | Planning | False | "19"
The customer always asks for a lot of changes in scope and product features during the project execution. You accept all changes to meet customer satisfaction. After a period of implementation, you noticed inflation in the budget. What should you have done to prevent this situation? | Control scope | Cost management plan | Scope management plan | Change management plan | The customer always asks for a lot of changes in scope and product features during the project execution. You accept all changes to meet customer satisfaction. After a period of implementation, you noticed inflation in the budget. What should you have done to prevent this situation? | Control scope | Cost management plan | Scope management plan | Change management plan | Integration Management | Planning | False | "19"
A lead business analyst on a large project has consistently been working late to finalize requirements for the next sprint. In the weekly team lead meeting. The project manager learns there are several business analysts on the team who have free cycles. What should the project manager do to ensure an even workload? | Delay the start date of the next sprint to allow more time for gathering requirements. | Review the list of open requirements and reassign them to team members with free cycles. | Direct the business analysts with free cycles to take more ownership of the project. | Facilitate a discussion within the team to redistribute the work within the project team. | A lead business analyst on a large project has consistently been working late to finalize requirements for the next sprint. In the weekly team lead meeting. The project manager learns there are several business analysts on the team who have free cycles. What should the project manager do to ensure an even workload? | Delay the start date of the next sprint to allow more time for gathering requirements. | Review the list of open requirements and reassign them to team members with free cycles. | Direct the business analysts with free cycles to take more ownership of the project. | Facilitate a discussion within the team to redistribute the work within the project team. | Resources Management | Executing | False | "17"
Using quantitative risk analysis and modeling technique that helps to determine which risks have the most impact on a project. Your goal is to find whether the occurrence of a particular threat would be merely an inconvenience or would ruin the project. Which of the following tools will be most appropriate for your analysis? | Control chart | Expected monetary value | SWOT analysis | Tornado Diagram | Using quantitative risk analysis and modeling technique that helps to determine which risks have the most impact on a project. Your goal is to find whether the occurrence of a particular threat would be merely an inconvenience or would ruin the project. Which of the following tools will be most appropriate for your analysis? | Control chart | Expected monetary value | SWOT analysis | Tornado Diagram | Risk Management | Planning | False | "20"
A supplier delivers equipment that fails to meet customer requirements in your project. After investigation, you determined that the supplier misunderstood the requirements and make incorrect assumptions without clarifying them with the customer. What type of communication methods should the project manager have used to avoid this? | Push communication | Pull communication | Manual communication | Interactive communication | A supplier delivers equipment that fails to meet customer requirements in your project. After investigation, you determined that the supplier misunderstood the requirements and make incorrect assumptions without clarifying them with the customer. What type of communication methods should the project manager have used to avoid this? | Push communication | Pull communication | Manual communication | Interactive communication | Communication Management | Planning | False | "19"
During the design for a new laptop project, one of your team members discovers an approach for increasing the storage area for the laptop without increasing the expenses of the project. What is the best risk response to plan? | Mitigate | Accept | Transfer | Exploit | During the design for a new laptop project, one of your team members discovers an approach for increasing the storage area for the laptop without increasing the expenses of the project. What is the best risk response to plan? | Mitigate | Accept | Transfer | Exploit | Risk Management | Planning | False | "19"
The Project team members and the subject matter expert (SME) are working on a design development project. You discover an enhancement that will improve the design. What should you as the project manager do? | Ask the subject matter expert (SME) to implement the enhancement. | Document this discovery, and present it to all stakeholders. | Ignore the enhancement, as no changes are allowed. | Ask the change control board (CCB) to review the enhancement. | The Project team members and the subject matter expert (SME) are working on a design development project. You discover an enhancement that will improve the design. What should you as the project manager do? | Ask the subject matter expert (SME) to implement the enhancement. | Document this discovery, and present it to all stakeholders. | Ignore the enhancement, as no changes are allowed. | Ask the change control board (CCB) to review the enhancement. | Integration Management | Monitoring and Controlling | False | "19"
Two team members who have conflicting opinions. One team member explains her side of the conflict. The other team member responds by saying, "I know you'll never really listen to my side, so let's just go with her opinion and get back to work." The team member used which of the following techniques for resolving conflict? | Forcing | Smoothing | Compromise | Withdrawal | Two team members who have conflicting opinions. One team member explains her side of the conflict. The other team member responds by saying, "I know you'll never really listen to my side, so let's just go with her opinion and get back to work." The team member used which of the following techniques for resolving conflict? | Forcing | Smoothing | Compromise | Withdrawal | Resources Management | Executing | False | "18"
Ann is a member of a software team, she identified a potential nonconformance in some recently developed software The person who wrote the software disagrees. How should the project manager respond? | Wait until the next automated test which will identify if the defect exists. | Ask the member who discovered the problem to rectify it urgently so it is available in the next release. | Record the disagreement for discussion at the next retrospective. | Bring both resources together to discuss and resolve the issue immediately. | Ann is a member of a software team, she identified a potential nonconformance in some recently developed software The person who wrote the software disagrees. How should the project manager respond? | Wait until the next automated test which will identify if the defect exists. | Ask the member who discovered the problem to rectify it urgently so it is available in the next release. | Record the disagreement for discussion at the next retrospective. | Bring both resources together to discuss and resolve the issue immediately. | Resources Management | Executing | False | "19"
You receives an email from a vendor that a key deliverables will be delayed by a month. What should you as the project manager do first? | Call the vendor to obtain a justification for the delay. | Update the management and obtain their advice. | Meet with the team identify ways to absorb this delay. | Assess the impact of the delay on the project plan. | You receives an email from a vendor that a key deliverables will be delayed by a month. What should you as the project manager do first? | Call the vendor to obtain a justification for the delay. | Update the management and obtain their advice. | Meet with the team identify ways to absorb this delay. | Assess the impact of the delay on the project plan. | Risk Management | Planning | False | "20"
You have only completed the project charter and is working on the project management plan. What should you as the project manager do next to build a detailed scope description? | Develop the scope statement with stakeholder input. | List all concerns in the stakeholder engagement plan. | Create the work breakdown structure. WBS | Implement the plan scope management process. | You have only completed the project charter and is working on the project management plan. What should you as the project manager do next to build a detailed scope description? | Develop the scope statement with stakeholder input. | List all concerns in the stakeholder engagement plan. | Create the work breakdown structure. WBS | Implement the plan scope management process. | Scope Management | Planning | False | "20"
You are working in a matrix organization. A team members indicate that they are also assigned to work on other initiatives and can no longer devote any time to their assigned activities. As a project manager, what should you do first to resolve this issue? | Evaluate the impact and use optimizations techniques to compensate for the delay. | Escalate the problem to the sponsor who can assign more staff to work on the project. | Implement the change control process and reduce the project scope to include less deliverables. | Speak to the functional manager and determine alternatives to address these activities. | You are working in a matrix organization. A team members indicate that they are also assigned to work on other initiatives and can no longer devote any time to their assigned activities. As a project manager, what should you do first to resolve this issue? | Evaluate the impact and use optimizations techniques to compensate for the delay. | Escalate the problem to the sponsor who can assign more staff to work on the project. | Implement the change control process and reduce the project scope to include less deliverables. | Speak to the functional manager and determine alternatives to address these activities. | Resources Management | Executing | False | "20"
You want to recruit another team member to replace an architect who resigned from your project. What document should capture this change? | Organizational process Assets. | Project management plan. | Ground rules | Responsibility assignments matrix (RAM) | You want to recruit another team member to replace an architect who resigned from your project. What document should capture this change? | Organizational process Assets. | Project management plan. | Ground rules | Responsibility assignments matrix (RAM) | Resources Management | Planning | False | "20"
In a project to develop a new product, The project has fallen behind schedule because team members are lacking motivation. What should the project manager do to motivate the project team? | Use coaching and monitoring skills. | Delegates the responsibilities. | Apply creative problem solving. | Offer recognition and rewards. | In a project to develop a new product, The project has fallen behind schedule because team members are lacking motivation. What should the project manager do to motivate the project team? | Use coaching and monitoring skills. | Delegates the responsibilities. | Apply creative problem solving. | Offer recognition and rewards. | Resources Management | Executing | False | "18"
You notice that a process has 3 points between mean and lower control limit and 4 points between upper control limit and specification limit during the review of a control chart. How will you evaluate this process? | Cannot be determined | In control | Customer only can take decision for this process | Need solution | You notice that a process has 3 points between mean and lower control limit and 4 points between upper control limit and specification limit during the review of a control chart. How will you evaluate this process? | Cannot be determined | In control | Customer only can take decision for this process | Need solution | Quality Management | Monitoring and Controlling | False | "18"
Now, you wish to track the performance of individual members and optimize the team's performance. After you have completed resource planning and acquired resources and improved the team competency and performance. Which process will you perform? | Control Resources | Develop Team | Team building | Manage Team | Now, you wish to track the performance of individual members and optimize the team's performance. After you have completed resource planning and acquired resources and improved the team competency and performance. Which process will you perform? | Control Resources | Develop Team | Team building | Manage Team | Resources Management | Executing | False | "19"
A project manager decides to procure the full amount of a required project material to exploit a price-volume discount. There months later, the price for that material drops by 50 percent due to over- production and change in technology. What should the project manager have done differently? | Purchased the material from two or more vendors. | Purchased the minimum amount of the material. | Negotiated with the vendor to adjust the price. | Properly identified the risks. | A project manager decides to procure the full amount of a required project material to exploit a price-volume discount. There months later, the price for that material drops by 50 percent due to over- production and change in technology. What should the project manager have done differently? | Purchased the material from two or more vendors. | Purchased the minimum amount of the material. | Negotiated with the vendor to adjust the price. | Properly identified the risks. | Risk Management | Planning | False | "19"
During sequencing activities, your team defines that: ? Activity A has a duration of three weeks. ? Activity C with a duration of four weeks, will start first. ? Activity B with a duration of two weeks, will start after completion of activity A ? Activity D, with a duration of four weeks, will start with a lead time of one week upon completion of activity B ? Activity E with a duration of five weeks, will start after the completion of activity C ? Activity F, with a duration of three weeks, will have a start to start dependency with activity E, with a lag time of three weeks What is the project's critical path? | 8 weeks. | 12 weeks. | 9 weeks. | 10 weeks. | During sequencing activities, your team defines that: ? Activity A has a duration of three weeks. ? Activity C with a duration of four weeks, will start first. ? Activity B with a duration of two weeks, will start after completion of activity A ? Activity D, with a duration of four weeks, will start with a lead time of one week upon completion of activity B ? Activity E with a duration of five weeks, will start after the completion of activity C ? Activity F, with a duration of three weeks, will have a start to start dependency with activity E, with a lag time of three weeks What is the project's critical path? | 8 weeks. | 12 weeks. | 9 weeks. | 10 weeks. | Schedule Management | Planning | False | "19"
One day before the launch of the new product, the project was terminated due to important distribution needs that were not identified. What should the PM developed to prevent this? | Stakeholder engagement plan | Risk management plan | Resource management plan | Communication management plan | One day before the launch of the new product, the project was terminated due to important distribution needs that were not identified. What should the PM developed to prevent this? | Stakeholder engagement plan | Risk management plan | Resource management plan | Communication management plan | Communication Management | Planning | False | "20"
The GM keeps asking for changes to the project scope that are not consistent with the original project requirements. One of the changes was requested one month before the project launch date. This change is projected to cause significant project delays. What should the project manager do? | Continue with the launch date as per the approved project management plan. | Update the change management document. | Inform the project steering committee about the project delay risk. | Submit a change request to the change control board (CCB). | The GM keeps asking for changes to the project scope that are not consistent with the original project requirements. One of the changes was requested one month before the project launch date. This change is projected to cause significant project delays. What should the project manager do? | Continue with the launch date as per the approved project management plan. | Update the change management document. | Inform the project steering committee about the project delay risk. | Submit a change request to the change control board (CCB). | Scope Management | Monitoring and Controlling | False | "16"
During a unique product development project, you notice that the requirements are conceptual and that it is difficult to obtain a shared understanding by all stakeholders. What can you do to obtain a shared understanding of the project's requirements? | Benchmark with the other organizations. | Conduct a requirements walkthrough. | Hold brainstorming sessions with the stakeholders. | Build a prototype. | During a unique product development project, you notice that the requirements are conceptual and that it is difficult to obtain a shared understanding by all stakeholders. What can you do to obtain a shared understanding of the project's requirements? | Benchmark with the other organizations. | Conduct a requirements walkthrough. | Hold brainstorming sessions with the stakeholders. | Build a prototype. | Scope Management | Planning | False | "19"
You are the project manager of the Mega IT Project. Before the implementation of a system upgrade, one of the team members discovers a critical defect in the current system that must be fixed. What should the project manager do? | Implement the fix | No action taken because the project scope has been finalized | Update the Risk register | Inform the project sponsor and follow the perform integrated change control process. | You are the project manager of the Mega IT Project. Before the implementation of a system upgrade, one of the team members discovers a critical defect in the current system that must be fixed. What should the project manager do? | Implement the fix | No action taken because the project scope has been finalized | Update the Risk register | Inform the project sponsor and follow the perform integrated change control process. | Integration Management | Monitoring and Controlling | False | "20"
Suzi is a new project manager on a project with a very tight budget, she is struggling as they have no experience working on this type of project. What can the project manager do to mitigate the lack of experience? | Ask for support from more senior project managers. | Review the lessons learned repository of similar projects. | Request reassignment to a different type of project. | Seek external training | Suzi is a new project manager on a project with a very tight budget, she is struggling as they have no experience working on this type of project. What can the project manager do to mitigate the lack of experience? | Ask for support from more senior project managers. | Review the lessons learned repository of similar projects. | Request reassignment to a different type of project. | Seek external training | Resources Management | Executing | False | "20"
You are a project manager for a IT project. During the implementation phase, you found the budget of one of the supplied software packages became much more than you expected. What should you have been done to prevent this situation? | Procurement audit | Inspection and audit | Performance Review | Make or buy decision | You are a project manager for a IT project. During the implementation phase, you found the budget of one of the supplied software packages became much more than you expected. What should you have been done to prevent this situation? | Procurement audit | Inspection and audit | Performance Review | Make or buy decision | Procurement Management | Planning | False | "20"
As a project manager, you notice one of your team members doesn't finish his tasks on time. What should you do next? | Meeting with the project team members and evaluate the impact on the project. | Schedule training sessions for the team member to optimize his performance. | Release a team member | Conduct One-on-One Meeting with the team member | As a project manager, you notice one of your team members doesn't finish his tasks on time. What should you do next? | Meeting with the project team members and evaluate the impact on the project. | Schedule training sessions for the team member to optimize his performance. | Release a team member | Conduct One-on-One Meeting with the team member | Resources Management | Executing | False | "18"
A project manager has signed a multi-year contract with a customer to complete a project for a fixed price. Since the duration of the contract is long, the PM has added a provision to adjust the price of the contract according to the market inflation. What kind of contract is this? | Cost plus fixed fee | Firm fixed price | Time and materials | Fixed price with economic price adjustment | A project manager has signed a multi-year contract with a customer to complete a project for a fixed price. Since the duration of the contract is long, the PM has added a provision to adjust the price of the contract according to the market inflation. What kind of contract is this? | Cost plus fixed fee | Firm fixed price | Time and materials | Fixed price with economic price adjustment | Procurement Management | Planning | False | "16"
After conducting a data analysis, John determines the cause and degree of variance relatives to the approved scope. What should the project manager do next? | Change the performance measurement baseline. | Revise the scope baseline. | Updates the scope management plan. | Decide if a corrective or preventative action is required | After conducting a data analysis, John determines the cause and degree of variance relatives to the approved scope. What should the project manager do next? | Change the performance measurement baseline. | Revise the scope baseline. | Updates the scope management plan. | Decide if a corrective or preventative action is required | Scope Management | Monitoring and Controlling | False | "20"
Kim is a project manager for a big project. He want to outsource some of the works. The project schedule is very tight and the scope not well defined. What type of contract should Kim sign? | Firm fixed price contract (FFP) | Cost Plus Fixed Fee Contracts (CPFF) | Fixed Price Incentive Fee Contracts (FPIF) | Cost Plus Incentive Fee Contracts (CPIF) | Kim is a project manager for a big project. He want to outsource some of the works. The project schedule is very tight and the scope not well defined. What type of contract should Kim sign? | Firm fixed price contract (FFP) | Cost Plus Fixed Fee Contracts (CPFF) | Fixed Price Incentive Fee Contracts (FPIF) | Cost Plus Incentive Fee Contracts (CPIF) | Procurement Management | Planning | False | "18"
The construction company is signing contract with consultant agent to finalize the project requirement. Which of the following estimating technique would be best in order to estimate the activity cost? | Three Point Estimating | Parametric Estimating | Analogous Estimating | Bottom-up-Estimating | The construction company is signing contract with consultant agent to finalize the project requirement. Which of the following estimating technique would be best in order to estimate the activity cost? | Three Point Estimating | Parametric Estimating | Analogous Estimating | Bottom-up-Estimating | Cost Management | Planning | False | "20"
You are project manager responsible for executing houses construction project. The key stakeholders and the Project sponsor approved the project management plan. What is the next step? | Identify Stakeholders | Direct and Manage Project Work | Update Business Case | Conduct the project kick-off meeting | You are project manager responsible for executing houses construction project. The key stakeholders and the Project sponsor approved the project management plan. What is the next step? | Identify Stakeholders | Direct and Manage Project Work | Update Business Case | Conduct the project kick-off meeting | Integration Management | Planning | False | "20"
Liza is a project manager in the execution stage of the project. Her team members are conducting a meeting to examine and document the effectiveness of risk responses in dealing with overall project risk and with identified individual project risk. What is the project team doing? | Reserve analysis | Risk reassessment | Status meeting | Risk review meeting | Liza is a project manager in the execution stage of the project. Her team members are conducting a meeting to examine and document the effectiveness of risk responses in dealing with overall project risk and with identified individual project risk. What is the project team doing? | Reserve analysis | Risk reassessment | Status meeting | Risk review meeting | Risk Management | Monitoring and Controlling | False | "19"
You are the project manager of a project near completion. After sending a follow-up report to the stakeholders, some stakeholders comment that some unresolved issues have been excluded from the report. What should you have done to prevent this? | Conducted the monitor Stakeholder Engagement process. | Followed the change control process. | Better controlled project documents. | Conducted the monitor communication process. | You are the project manager of a project near completion. After sending a follow-up report to the stakeholders, some stakeholders comment that some unresolved issues have been excluded from the report. What should you have done to prevent this? | Conducted the monitor Stakeholder Engagement process. | Followed the change control process. | Better controlled project documents. | Conducted the monitor communication process. | Communication Management | Monitoring and Controlling | False | "19"
A project is initiated, and planned. As a project manager, you are about to conduct the kick-off meeting with all stakeholders, and you feel that the strategic directions for the project need to be presented first. Who should present this topic? | customer | Project manager | Functional manager | Project sponsor | A project is initiated, and planned. As a project manager, you are about to conduct the kick-off meeting with all stakeholders, and you feel that the strategic directions for the project need to be presented first. Who should present this topic? | customer | Project manager | Functional manager | Project sponsor | Communication Management | Planning | False | "18"
You are the project manager of the Telecom Project and are working with the project stakeholders to determine the project requirements. You and the stakeholders are brainstorming privately to come up with as many solutions to the project as possible. After the brainstorming session, a recorder documents all the solutions on a white board so everyone can see the ideas and how they may be related. After the solutions have been documented, you lead the group through a voting process to discuss and rank each idea and requirement that has been proposed. What is this technique called? | Affinity diagram | Brainstorming | Mind mapping | Nominal group technique | You are the project manager of the Telecom Project and are working with the project stakeholders to determine the project requirements. You and the stakeholders are brainstorming privately to come up with as many solutions to the project as possible. After the brainstorming session, a recorder documents all the solutions on a white board so everyone can see the ideas and how they may be related. After the solutions have been documented, you lead the group through a voting process to discuss and rank each idea and requirement that has been proposed. What is this technique called? | Affinity diagram | Brainstorming | Mind mapping | Nominal group technique | Scope Management | Planning | False | "20"
The project and product requirements have been identified by the project team members during the planning phase of your project. Which of the following were used to accomplish this? | Mind mapping, affinity diagram and Brainstorming | Observations conversations, trend analysis and work breakdown structure (WBS) | Network diagram, Benchmarking, and project scope statement. | Observations conversations, benchmarking and affinity diagram | The project and product requirements have been identified by the project team members during the planning phase of your project. Which of the following were used to accomplish this? | Mind mapping, affinity diagram and Brainstorming | Observations conversations, trend analysis and work breakdown structure (WBS) | Network diagram, Benchmarking, and project scope statement. | Observations conversations, benchmarking and affinity diagram | Scope Management | Planning | False | "19"
You are at the end of your civil project when the PMO head called you asking to ensure the transfer of liability of the buildings to the operation department. What should you do to achieve a PMO request? | Obtain Formal Acceptance from customer | Collect lessons learned and update knowledge base | Prepare and share the final project report | Obtain financial, legal, and administrative closure | You are at the end of your civil project when the PMO head called you asking to ensure the transfer of liability of the buildings to the operation department. What should you do to achieve a PMO request? | Obtain Formal Acceptance from customer | Collect lessons learned and update knowledge base | Prepare and share the final project report | Obtain financial, legal, and administrative closure | Integration Management | Closing | False | "18"
John is a project manager of a construction project. While doing the estimation, he realize that he will need 8 resources for 6 months. John can get only 3 resources after negotiating with the functional manager and as per the organizational policy, he can hire 3 more every 6 months. What will be his next step? | Work with virtual team | Negotiate with the functional manager to get more two resources | Request your project Customer to get more resources | Negotiate with External organizations and suppliers | John is a project manager of a construction project. While doing the estimation, he realize that he will need 8 resources for 6 months. John can get only 3 resources after negotiating with the functional manager and as per the organizational policy, he can hire 3 more every 6 months. What will be his next step? | Work with virtual team | Negotiate with the functional manager to get more two resources | Request your project Customer to get more resources | Negotiate with External organizations and suppliers | Resources Management | Executing | False | "19"
You joined a project during it's initial planning phase. The project involves various local government institutions. While interviewing the project sponsor, you learn the importance of keeping the security officers of two of these institutions satisfied, since project development will be affected without their involvement. What should you use to record and monitor this information? | Communication management plan | Risk register. | Responsibility assignments matrix RAM. | Power /interest grid | You joined a project during it's initial planning phase. The project involves various local government institutions. While interviewing the project sponsor, you learn the importance of keeping the security officers of two of these institutions satisfied, since project development will be affected without their involvement. What should you use to record and monitor this information? | Communication management plan | Risk register. | Responsibility assignments matrix RAM. | Power /interest grid | Stakeholder Management | Initiating | False | "17"
Based on the following table, which of the following activities will be within the budget and behind schedule? | Activity C | Activity B | Activity D | Activity A | Based on the following table, which of the following activities will be within the budget and behind schedule? | Activity C | Activity B | Activity D | Activity A | Cost Management | Monitoring and Controlling | False | "19"
The customer and hardware engineering team disagree about the limits on the control chart being used to measure quality. You meet with both stakeholders and listens to their opinions. In order to proceed with the project, you decides to use an average of their opinions. What is this an example of? | Problem solving | Collaboration | Smoothing | Compromise | The customer and hardware engineering team disagree about the limits on the control chart being used to measure quality. You meet with both stakeholders and listens to their opinions. In order to proceed with the project, you decides to use an average of their opinions. What is this an example of? | Problem solving | Collaboration | Smoothing | Compromise | Resources Management | Executing | False | "20"
You want to compare the baseline to the actual results and determine if the variance is within the threshold amount or if corrective or preventive action is appropriate during the implementation phase. Which of the following techniques can help you? | Trend analysis | Decomposition | Control chart | Variance Analysis | You want to compare the baseline to the actual results and determine if the variance is within the threshold amount or if corrective or preventive action is appropriate during the implementation phase. Which of the following techniques can help you? | Trend analysis | Decomposition | Control chart | Variance Analysis | Scope Management | Monitoring and Controlling | False | "19"
You are informed that one of the suppliers who is working on your project has taken another project during the implementation phase. As a project manager, what should you do next? | Change management plan | Procurement review | Remove the supplier from your project. | Performance review | You are informed that one of the suppliers who is working on your project has taken another project during the implementation phase. As a project manager, what should you do next? | Change management plan | Procurement review | Remove the supplier from your project. | Performance review | Procurement Management | Monitoring and Controlling | False | "18"
A techniques help to identify and analyze risks. Which of below? | Probability and impact matrix. | SWOT Analysis | Monte Carol | Expert judgment | A techniques help to identify and analyze risks. Which of below? | Probability and impact matrix. | SWOT Analysis | Monte Carol | Expert judgment | Risk Management | Monitoring and Controlling | False | "20"
The project charter has been signed, and a project management plan is in place. What should you as the project manager do next? | Develop the project schedule | Team-building activities | Meet with the project sponsor | Assign the project team. | The project charter has been signed, and a project management plan is in place. What should you as the project manager do next? | Develop the project schedule | Team-building activities | Meet with the project sponsor | Assign the project team. | Resources Management | Executing | False | "19"
Which of the following analysis techniques is recommended when you need to analyze project stakeholders based on their power, urgency, and legitimacy and usefulness for large complex communities of stakeholders or where there are complex networks of relationships within the community? | Power/interest grid | Power/influence grid | Influence/impact grid | Salience model | Which of the following analysis techniques is recommended when you need to analyze project stakeholders based on their power, urgency, and legitimacy and usefulness for large complex communities of stakeholders or where there are complex networks of relationships within the community? | Power/interest grid | Power/influence grid | Influence/impact grid | Salience model | Stakeholder Management | Initiating | False | "18"
The customer comes to you during the project execution and tells you about a minor requirement that he forgot during the collect requirement process. He assures you that there will be no effect on the cost if you implement his request. What will your next step be? | You will deny his request | Update Scope Baseline | Implement the change | Evaluate the impact with team members | The customer comes to you during the project execution and tells you about a minor requirement that he forgot during the collect requirement process. He assures you that there will be no effect on the cost if you implement his request. What will your next step be? | You will deny his request | Update Scope Baseline | Implement the change | Evaluate the impact with team members | Scope Management | Monitoring and Controlling | False | "18"
The customer sent an urgent change request. You review the request and find that it might cost a lot if you implement this change request. What will be your next step? | Implement the change | You will not allow any change request | Since it increases the cost, reject it | Discuss the cost impact with the client | The customer sent an urgent change request. You review the request and find that it might cost a lot if you implement this change request. What will be your next step? | Implement the change | You will not allow any change request | Since it increases the cost, reject it | Discuss the cost impact with the client | Cost Management | Monitoring and Controlling | False | "20"
During the team review, the project manager learns that the schedule performance index (SPI) is 0.6 and the cost performance index (CPI) is 0.8. The project manager asks team members to work overtime. How will this effect the ( CPI ) ? | It will increase. | It will return to 1.0 | It will remain the same. | It will decrease. | During the team review, the project manager learns that the schedule performance index (SPI) is 0.6 and the cost performance index (CPI) is 0.8. The project manager asks team members to work overtime. How will this effect the ( CPI ) ? | It will increase. | It will return to 1.0 | It will remain the same. | It will decrease. | Cost Management | Monitoring and Controlling | False | "19"
You identify that three leaders in the organization have three different expectations about what should be implemented in a project. What did you use to identify this? | Root cause analysis | Communication requirements analysis | Bidder conferences | Stakeholder analysis. | You identify that three leaders in the organization have three different expectations about what should be implemented in a project. What did you use to identify this? | Root cause analysis | Communication requirements analysis | Bidder conferences | Stakeholder analysis. | Stakeholder Management | Initiating | False | "19"
During the execution phase. A risk management plan has been implemented and risk analysis is ongoing. How should the impacts of identified risks be communicated to the stakeholder? | Show the reasons for upcoming risks using either an affinity diagram or a matrix diagram. | Engage in opportunity management on the identified risks for added value. | Calculate the necessary contingency funding and time buffers needed for the risk response. | Draw a probability and impact matrix to prioritize risks. | During the execution phase. A risk management plan has been implemented and risk analysis is ongoing. How should the impacts of identified risks be communicated to the stakeholder? | Show the reasons for upcoming risks using either an affinity diagram or a matrix diagram. | Engage in opportunity management on the identified risks for added value. | Calculate the necessary contingency funding and time buffers needed for the risk response. | Draw a probability and impact matrix to prioritize risks. | Risk Management | Planning | False | "20"
A project manager leading constructing dams and must provide cost estimates to stakeholders. What should the project manager present to avoid unreasonable cuts in the budget that will undermine the project? | High-level costs summarized by resource. | Cost estimates as per historical data and other variables. | Cost estimates using expert judgment. | Bottom-up cost as the basis for the estimate. | A project manager leading constructing dams and must provide cost estimates to stakeholders. What should the project manager present to avoid unreasonable cuts in the budget that will undermine the project? | High-level costs summarized by resource. | Cost estimates as per historical data and other variables. | Cost estimates using expert judgment. | Bottom-up cost as the basis for the estimate. | Cost Management | Planning | False | "18"
What is the key purpose of the Monitoring and Controlling process group? | Perform preventive actions so that no variances ever occur in the project lifecycle | Conduct daily status meetings | None of the above | Measure project performance in order to identify and quantify any variances and perform approved corrective actions | What is the key purpose of the Monitoring and Controlling process group? | Perform preventive actions so that no variances ever occur in the project lifecycle | Conduct daily status meetings | None of the above | Measure project performance in order to identify and quantify any variances and perform approved corrective actions | Integration Management | Monitoring and Controlling | False | "19"
You are working on a project to construct four buildings complex. The project management plan calls for completion of one building per year at a cost of US$ 100 Million each. At the end of year three, 1st Building was completed at a cost of US$100 million & 2nd Building completed at a cost of US$120 million & 3rd Building only 50% completed at a cost of US$ 60 million To meet the original project management plan, what monthly performance is needed until the end of year four? | 120 percent | 110 percent | 115 percent | 125 percent | You are working on a project to construct four buildings complex. The project management plan calls for completion of one building per year at a cost of US$ 100 Million each. At the end of year three, 1st Building was completed at a cost of US$100 million & 2nd Building completed at a cost of US$120 million & 3rd Building only 50% completed at a cost of US$ 60 million To meet the original project management plan, what monthly performance is needed until the end of year four? | 120 percent | 110 percent | 115 percent | 125 percent | Cost Management | Monitoring and Controlling | False | "20"
You are a project manager in a infrastructure project. During a review, the project team member identifies a quality issue that may cause the product to be rejected by the customer. However, the project sponsor wants to deliver the product. As a project manager, what should you do? | Ensure that the product meets customer requirements. | Deliver the product. | Update the issue log. | Review the quality checklist. | You are a project manager in a infrastructure project. During a review, the project team member identifies a quality issue that may cause the product to be rejected by the customer. However, the project sponsor wants to deliver the product. As a project manager, what should you do? | Ensure that the product meets customer requirements. | Deliver the product. | Update the issue log. | Review the quality checklist. | Quality Management | Monitoring and Controlling | False | "19"
Your project has been progressing well so far. Due to an unexpected increase in the cost of raw materials which was not factored as project risk, you are in need of some management reserve. The management reserve is available but the sponsor asks you to do something to obtain it. What is the sponsor asking you to do? | There is no need for a management reserve as the risk was not factored, and therefore it may be funded from the contingency reserve | To put in a request to the sponsor for the management reserve | To first move the required funds from the contingency reserve to the management reserve | To follow the change approval process to move the required management reserve funds to the cost baseline | Your project has been progressing well so far. Due to an unexpected increase in the cost of raw materials which was not factored as project risk, you are in need of some management reserve. The management reserve is available but the sponsor asks you to do something to obtain it. What is the sponsor asking you to do? | There is no need for a management reserve as the risk was not factored, and therefore it may be funded from the contingency reserve | To put in a request to the sponsor for the management reserve | To first move the required funds from the contingency reserve to the management reserve | To follow the change approval process to move the required management reserve funds to the cost baseline | Cost Management | Monitoring and Controlling | False | "20"
You have just been assigned as the project manager of a project to construct a hospital. During a planning meeting, the team decides to conduct a site survey to determine the ground conditions before engineering the design. Which of the following risk management processes is the team implementing? | Plan Risk Management process | Perform Qualitative Risk Analysis process | Plan risk response process | Identify Risks process | You have just been assigned as the project manager of a project to construct a hospital. During a planning meeting, the team decides to conduct a site survey to determine the ground conditions before engineering the design. Which of the following risk management processes is the team implementing? | Plan Risk Management process | Perform Qualitative Risk Analysis process | Plan risk response process | Identify Risks process | Risk Management | Planning | False | "19"
A new resource has been assigned to a project team. He used to a different delivery method that is less productive and does not enforce deadline. The new delivery method is integrated so low productivity personnel have larger impact on the overall productivity of team performance. What strategy can the project manager apply to resolve the conflict with the new resource? | Force/direct. | Compromise/reconcile . | Smooth/accommodate. | Collaborate/problem solve. | A new resource has been assigned to a project team. He used to a different delivery method that is less productive and does not enforce deadline. The new delivery method is integrated so low productivity personnel have larger impact on the overall productivity of team performance. What strategy can the project manager apply to resolve the conflict with the new resource? | Force/direct. | Compromise/reconcile . | Smooth/accommodate. | Collaborate/problem solve. | Resources Management | Executing | False | "20"
You are managing very complex project and due to a scope change, you need a few additional experts, which you did not think of earlier. You request that your company provide you with some experts for consultancy work. Although your company has provided you with those experts, they are located in a different geographical location. In this situation, how will you get their input? | None of the above | Recruit new members with same skills | Ask management to bring them to you | Create a virtual team | You are managing very complex project and due to a scope change, you need a few additional experts, which you did not think of earlier. You request that your company provide you with some experts for consultancy work. Although your company has provided you with those experts, they are located in a different geographical location. In this situation, how will you get their input? | None of the above | Recruit new members with same skills | Ask management to bring them to you | Create a virtual team | Resources Management | Executing | False | "19"
During having a coffee with the CEO that you have a good relationship with, he was surprised that you do not have the information that your project will be canceled due to future changes in company plans, and your team members will be released. As a Project manager, what should you do? | Hold a meeting with your team and inform them about what will happen. | Hold a meeting with stakeholders and discuss this information openly with them | Hold a meeting with the sponsor and discuss this info with him. | Review the communication management plan and validate why you did not get this information through it. | During having a coffee with the CEO that you have a good relationship with, he was surprised that you do not have the information that your project will be canceled due to future changes in company plans, and your team members will be released. As a Project manager, what should you do? | Hold a meeting with your team and inform them about what will happen. | Hold a meeting with stakeholders and discuss this information openly with them | Hold a meeting with the sponsor and discuss this info with him. | Review the communication management plan and validate why you did not get this information through it. | Communication Management | Planning | False | "19"
A key stakeholder has removed a key team resource from a project. The activities on the critical path will be negatively affected by this action. What should the project manager do? | Analyze the impact to the project management plan and submit a change request. | Engage the sponsor to discuss the importance of the resource with the functional leader. | Negotiate with and influence the functional leader to reverse their decision. | Acquire a replacement resource by following the resource management plan. | A key stakeholder has removed a key team resource from a project. The activities on the critical path will be negatively affected by this action. What should the project manager do? | Analyze the impact to the project management plan and submit a change request. | Engage the sponsor to discuss the importance of the resource with the functional leader. | Negotiate with and influence the functional leader to reverse their decision. | Acquire a replacement resource by following the resource management plan. | Resources Management | Executing | False | "20"
You are in the first meetings for your new project that you have been assigned to, two team members were discussing new ideas that each one thinks is correct and their opinion is the best for the project. You didn't interact or cut the discussion, as you know this is a normal discussion in this phase, which is? | Norming | Performing | Supporting | Storming | You are in the first meetings for your new project that you have been assigned to, two team members were discussing new ideas that each one thinks is correct and their opinion is the best for the project. You didn't interact or cut the discussion, as you know this is a normal discussion in this phase, which is? | Norming | Performing | Supporting | Storming | Resources Management | Executing | False | "19"
As a project manager, in which document will you find information about the acceptable level of project and product quality and how to ensure this level of quality in its deliverables and processes? | The Scope Management | Plan Work Performance data | Project Charter | The project management plan | As a project manager, in which document will you find information about the acceptable level of project and product quality and how to ensure this level of quality in its deliverables and processes? | The Scope Management | Plan Work Performance data | Project Charter | The project management plan | Quality Management | Planning | False | "20"
You are managing a project with a budget of 9,000, and 1,500 has been spent. However, you only completed $1000 worth of work. Your schedule says that you should have completed 50% of the work. What is the estimate at completion (EAC)? | US$ 9000 ( Based on original project Budget ) | US$ 9000 ( Based on performance data ) | US$13500 ( Based on original project Budget ) | US$13500 ( Based on performance data ) | You are managing a project with a budget of 9,000, and 1,500 has been spent. However, you only completed $1000 worth of work. Your schedule says that you should have completed 50% of the work. What is the estimate at completion (EAC)? | US$ 9000 ( Based on original project Budget ) | US$ 9000 ( Based on performance data ) | US$13500 ( Based on original project Budget ) | US$13500 ( Based on performance data ) | Cost Management | Monitoring and Controlling | False | "16"
On a virtual project status meeting, there is a team member who consistently has issues with the technology being used to join the meeting. These issues are preventing this team member from being actively engaged in the meetings. What should the project manager do? | Ask another team member to follow up and provide updates to the team member. | Call this team member separately to communicate the project status. | Replace the team member with someone who has more technology experience. | Have a separate meeting with the team member to find a solution together. | On a virtual project status meeting, there is a team member who consistently has issues with the technology being used to join the meeting. These issues are preventing this team member from being actively engaged in the meetings. What should the project manager do? | Ask another team member to follow up and provide updates to the team member. | Call this team member separately to communicate the project status. | Replace the team member with someone who has more technology experience. | Have a separate meeting with the team member to find a solution together. | Resources Management | Executing | False | "20"
On your project, two team members often disagree. You need a long-term conflict resolution method. You decide to use which one of the following approaches? | Withdrawal | Smoothing | Compromise | Problem solving | On your project, two team members often disagree. You need a long-term conflict resolution method. You decide to use which one of the following approaches? | Withdrawal | Smoothing | Compromise | Problem solving | Resources Management | Executing | False | "19"
During the execution of the project, you had to manage a change request. You evaluated the impact of the change on the other constraints of the project, then you got the change request approved by CCB. The next step a project manager should do is: | Implement the Approved change. | Inform stakeholders with new status of the project. | Update the Issue Log. | Update Project Management plan. | During the execution of the project, you had to manage a change request. You evaluated the impact of the change on the other constraints of the project, then you got the change request approved by CCB. The next step a project manager should do is: | Implement the Approved change. | Inform stakeholders with new status of the project. | Update the Issue Log. | Update Project Management plan. | Integration Management | Monitoring and Controlling | False | "20"
You are managing a project in which your team members all work in the same location and have worked together on many projects. You have seniors and junior team members. Senior team members feel that they are always overloaded and junior team members are not learning that fast. As a Project manager, what should you do? | Focus on decreasing sources of conflicts Team | Team-building activities | A kick-off meeting | Recognition and Rewards throughout the project | You are managing a project in which your team members all work in the same location and have worked together on many projects. You have seniors and junior team members. Senior team members feel that they are always overloaded and junior team members are not learning that fast. As a Project manager, what should you do? | Focus on decreasing sources of conflicts Team | Team-building activities | A kick-off meeting | Recognition and Rewards throughout the project | Resources Management | Executing | False | "20"
Project stakeholders are concerned that the project changes may have an unplanned impact on the business documents. They want to understand these changes before they occur. What should the project manager do? | Update the change management plan to track and communicate change. | Escalate all changes to key stakeholders to obtain agreement before implementation. | Ensure that all potential changes are part of the risk mitigation plan. | Review the project plan to handle upcoming change requests. | Project stakeholders are concerned that the project changes may have an unplanned impact on the business documents. They want to understand these changes before they occur. What should the project manager do? | Update the change management plan to track and communicate change. | Escalate all changes to key stakeholders to obtain agreement before implementation. | Ensure that all potential changes are part of the risk mitigation plan. | Review the project plan to handle upcoming change requests. | Integration Management | Monitoring and Controlling | False | "19"
The change control board (CCB) recently approved two change requests. 1st was a delay in activity on the critical path due to insufficient resources. 2nd was due to sending late communications to stakeholders. What should you do FIRST as a project manager? | Implement change request #2 | Hire additional resources to do both at the same time | Implement change request #1 | Ask CCB for further clarifications/explanations | The change control board (CCB) recently approved two change requests. 1st was a delay in activity on the critical path due to insufficient resources. 2nd was due to sending late communications to stakeholders. What should you do FIRST as a project manager? | Implement change request #2 | Hire additional resources to do both at the same time | Implement change request #1 | Ask CCB for further clarifications/explanations | Integration Management | Closing | False | "20"
A project manager analyzed the project's communication requirements and decided that 15 out of the 30 stakeholders in the project would only need voicemail updates of certain information. This type of communication method is called: | Pull communication | Interactive communication | On-demand communication | Push communication | A project manager analyzed the project's communication requirements and decided that 15 out of the 30 stakeholders in the project would only need voicemail updates of certain information. This type of communication method is called: | Pull communication | Interactive communication | On-demand communication | Push communication | Communication Management | Planning | False | "20"
You are managing a houses project, your cost performance is not as planned and your Project is over budget. Therefore, you again estimate the cost of the project and find that you will require more funding to complete the project. This will require an update of the cost baseline. What will you do? | Update the cost baseline. | Update Change Log. | Terminate the Project. | Issue the change request. | You are managing a houses project, your cost performance is not as planned and your Project is over budget. Therefore, you again estimate the cost of the project and find that you will require more funding to complete the project. This will require an update of the cost baseline. What will you do? | Update the cost baseline. | Update Change Log. | Terminate the Project. | Issue the change request. | Cost Management | Monitoring and Controlling | False | "18"
In Critical Project for your organization, Your project is behind schedule and over budget. Therefore, the Project Sponsor asks you if the team members may work on weekends. As a Project manager, what should you do to persuade the team members to work during their weekends? | Ask the Management what should you do | Ignore the Sponsor | Update Issue Log | Recognition and rewards | In Critical Project for your organization, Your project is behind schedule and over budget. Therefore, the Project Sponsor asks you if the team members may work on weekends. As a Project manager, what should you do to persuade the team members to work during their weekends? | Ask the Management what should you do | Ignore the Sponsor | Update Issue Log | Recognition and rewards | Resources Management | Executing | False | "19"
You are a project manager to construct a new industries in a typhoon prone area and may impact the schedule and quality. As a project manager, what should you do? | Establish a contingency reserve | Perform Quantitative Risk Analysis, and plan risk response | Develop the risk management plan and establish a management reserve | Outsource the project and transfer the risk | You are a project manager to construct a new industries in a typhoon prone area and may impact the schedule and quality. As a project manager, what should you do? | Establish a contingency reserve | Perform Quantitative Risk Analysis, and plan risk response | Develop the risk management plan and establish a management reserve | Outsource the project and transfer the risk | Risk Management | Planning | False | "20"
A project team is staffed with experienced subject matter experts. The project is going well and there are no known quality issues. Team members believe that the quality control process is unnecessary for this project. What should the project manager do? | Review the risk management plan to update risks. | Create a cause and effect diagram to quantify impact. | Remove the process from the quality management plan. | Create a team culture that is committed to quality | A project team is staffed with experienced subject matter experts. The project is going well and there are no known quality issues. Team members believe that the quality control process is unnecessary for this project. What should the project manager do? | Review the risk management plan to update risks. | Create a cause and effect diagram to quantify impact. | Remove the process from the quality management plan. | Create a team culture that is committed to quality | Resources Management | Executing | False | "20"
You are a project manager and have received an acceptance of project deliverables and held the lessons learned session. What should you do next to close the project? | Validate the scope. | Release the resources. | Conduct performance evaluation. | Update the organizational process Assets. | You are a project manager and have received an acceptance of project deliverables and held the lessons learned session. What should you do next to close the project? | Validate the scope. | Release the resources. | Conduct performance evaluation. | Update the organizational process Assets. | Integration Management | Closing | False | "19"
The project manager reviews the issue log at the end of each day. One issue she recorded in the issue log stems from delays in the delivery of resources from a contracted supplier. What tool should the project manager use to determine if corrective action is necessary? | Inspection | Independent estimate | Claims administration | Audit | The project manager reviews the issue log at the end of each day. One issue she recorded in the issue log stems from delays in the delivery of resources from a contracted supplier. What tool should the project manager use to determine if corrective action is necessary? | Inspection | Independent estimate | Claims administration | Audit | Procurement Management | Monitoring and Controlling | False | "19"
You are a project manager of a company and your project is currently in the execution phase. In your project there is an issue requires the execution of the contingency plan, which impacts the cost baseline. As a project manager, what should you do? | Perform risk audit. | Review the cost impact. | Do nothing as this would cause changes to the baselines | Issue a change request. | You are a project manager of a company and your project is currently in the execution phase. In your project there is an issue requires the execution of the contingency plan, which impacts the cost baseline. As a project manager, what should you do? | Perform risk audit. | Review the cost impact. | Do nothing as this would cause changes to the baselines | Issue a change request. | Integration Management | Monitoring and Controlling | False | "20"
The project manager hired a team to check the quality, but the project manager cannot obtain stakeholder consensus on the team's composition. What selection criteria can the project manager present to influence consensus? | Knowledge of stakeholder expectations, market landscape, and project scope statement. | Knowledge of the product benchmark, business case and quality assurance. | Knowledge of the stakeholder engagement plan, approval criteria and document specifications. | Knowledge of customer requirements, organizational policies and industry standards and project metrics. | The project manager hired a team to check the quality, but the project manager cannot obtain stakeholder consensus on the team's composition. What selection criteria can the project manager present to influence consensus? | Knowledge of stakeholder expectations, market landscape, and project scope statement. | Knowledge of the product benchmark, business case and quality assurance. | Knowledge of the stakeholder engagement plan, approval criteria and document specifications. | Knowledge of customer requirements, organizational policies and industry standards and project metrics. | Resources Management | Executing | False | "19"
What should the project manager refer to evaluate the resources that assign by the project management office (PMO)? | Resource Breakdown Structure (RBS). | Responsibility Assignment Matrix (RAM) | Expert judgment. | Resource management plan. | What should the project manager refer to evaluate the resources that assign by the project management office (PMO)? | Resource Breakdown Structure (RBS). | Responsibility Assignment Matrix (RAM) | Expert judgment. | Resource management plan. | Resources Management | Planning | False | "19"
You are a project manager in an Manufacturing project. You and key stakeholders start conducting a project benefit analysis. Because of the solutions that have not been identified, an engineer from another department has informed you that there are affected systems. As a project manager, what should you do? | Identify all stakeholders | Review the project benefit analysis to consider the additional impact | Update the risk register | Document the issue in the issue log | You are a project manager in an Manufacturing project. You and key stakeholders start conducting a project benefit analysis. Because of the solutions that have not been identified, an engineer from another department has informed you that there are affected systems. As a project manager, what should you do? | Identify all stakeholders | Review the project benefit analysis to consider the additional impact | Update the risk register | Document the issue in the issue log | Quality Management | Monitoring and Controlling | False | "20"
You are responsible for leading the HR Project. The customer has requested a change in the scope which you have processed through a change request and it is approved from CCB, and the team members Updated the Scope and Schedule baselines to reflect the approved changes. What should you do next? | Inform the sponsor about the approved change request | Implement the approved change request | Update the change log | Inform the impacted stakeholders about the approved change request | You are responsible for leading the HR Project. The customer has requested a change in the scope which you have processed through a change request and it is approved from CCB, and the team members Updated the Scope and Schedule baselines to reflect the approved changes. What should you do next? | Inform the sponsor about the approved change request | Implement the approved change request | Update the change log | Inform the impacted stakeholders about the approved change request | Integration Management | Monitoring and Controlling | False | "19"
You have identified a risk that will negatively affect your security project. You and your team have decided to use an older encryption technology because of the high risk associated with the new technology. What type of risk strategy are you using? | Transfer | Exploitation | Mitigation | Avoidance | You have identified a risk that will negatively affect your security project. You and your team have decided to use an older encryption technology because of the high risk associated with the new technology. What type of risk strategy are you using? | Transfer | Exploitation | Mitigation | Avoidance | Risk Management | Planning | False | "19"
A quality defect on project deliverables. In Which Category are these risks included? | External Risk | Commercial | Risk Management Risk | Technical Risk | A quality defect on project deliverables. In Which Category are these risks included? | External Risk | Commercial | Risk Management Risk | Technical Risk | Risk Management | Planning | False | "20"
The project manager works in risk management and creating a risk register. The risk register records details of all the risks identified at the beginning and during the life of the project. What tool or technique should the project manager use to generate a list of all possible project risks? | Monte Carlo | Tornado diagram | Probability and impact matrix | Brainstorming | The project manager works in risk management and creating a risk register. The risk register records details of all the risks identified at the beginning and during the life of the project. What tool or technique should the project manager use to generate a list of all possible project risks? | Monte Carlo | Tornado diagram | Probability and impact matrix | Brainstorming | Risk Management | Planning | False | "19"
You are the project manager of a large IT project. During the implementation phase, you sign a contract to rent an additional server from a local company because of the possibility that the main server may fail due to constant, local-area electrical outages. As a project manager, what strategy are you using? | Transfer | Avoid | Escalate | Mitigate | You are the project manager of a large IT project. During the implementation phase, you sign a contract to rent an additional server from a local company because of the possibility that the main server may fail due to constant, local-area electrical outages. As a project manager, what strategy are you using? | Transfer | Avoid | Escalate | Mitigate | Risk Management | Planning | False | "20"
As a project manager, you discover that the concrete's composition is incorrect. What document should the project manager reviews to verify the concrete's performance and quality requirements? | Request for proposal REF. | Procurement management plan. | Quality management plan. | Procurement statement of work SOW. | As a project manager, you discover that the concrete's composition is incorrect. What document should the project manager reviews to verify the concrete's performance and quality requirements? | Request for proposal REF. | Procurement management plan. | Quality management plan. | Procurement statement of work SOW. | Procurement Management | Planning | False | "19"
You are is a project manager leading huge project with 100 million dollars. Various teams from different countries are involved in this project and the teams need to work cohesively and seamlessly for the success of the project. The task of one team member is highly dependent on that of other team members. Which of the following is important for the overall success of project integration? | Change management | Adherence to professional code of conduct | Detailed definition of the work packages | Communications management plan | You are is a project manager leading huge project with 100 million dollars. Various teams from different countries are involved in this project and the teams need to work cohesively and seamlessly for the success of the project. The task of one team member is highly dependent on that of other team members. Which of the following is important for the overall success of project integration? | Change management | Adherence to professional code of conduct | Detailed definition of the work packages | Communications management plan | Communication Management | Planning | False | "19"
Your project team works in two different cities across the country. The team has been struggling to perform effectively, morale is low and has a difficult time resolving problems. What would be the BEST team development technique to resolve this issue? | Training | Rewards | Mediation | Co-location | Your project team works in two different cities across the country. The team has been struggling to perform effectively, morale is low and has a difficult time resolving problems. What would be the BEST team development technique to resolve this issue? | Training | Rewards | Mediation | Co-location | Resources Management | Executing | False | "20"
A multiphase project that has been executed with internal resources has reached a phase gate. The key project stakeholders want to determine if the phase has met its success criteria, and whether or not the project should progress to the next phase. In addition to the project management plan, which documents will be required? | Agreements including procurement contracts | Lessons learned register and lessons learned repository | Risk register and risk report | Business documents and project charter | A multiphase project that has been executed with internal resources has reached a phase gate. The key project stakeholders want to determine if the phase has met its success criteria, and whether or not the project should progress to the next phase. In addition to the project management plan, which documents will be required? | Agreements including procurement contracts | Lessons learned register and lessons learned repository | Risk register and risk report | Business documents and project charter | Integration Management | Planning | False | "19"
As the project manager of a constructing hospitals project, you are determining the accuracy of the deliverables before closing a project. What process should be used to determine this and is an input to formalizing acceptance? | Manage quality. | Control scope. | Accepted deliverables | Control Quality | As the project manager of a constructing hospitals project, you are determining the accuracy of the deliverables before closing a project. What process should be used to determine this and is an input to formalizing acceptance? | Manage quality. | Control scope. | Accepted deliverables | Control Quality | Quality Management | Monitoring and Controlling | False | "19"
You are managing a project to construct commercial buildings. During the project kick-off meeting, one project team members had a disagreement around whether to include a specific test within testing scenarios for the new product or not. As the project manager, what should you do? | Reject adding the new test | Add the suggested scenario | Ask each one of them to explain the logic behind his opinion | Postpone the discussion for a later time | You are managing a project to construct commercial buildings. During the project kick-off meeting, one project team members had a disagreement around whether to include a specific test within testing scenarios for the new product or not. As the project manager, what should you do? | Reject adding the new test | Add the suggested scenario | Ask each one of them to explain the logic behind his opinion | Postpone the discussion for a later time | Resources Management | Executing | False | "19"
Tom is the project manager of a project that is halfway through its execution. Jack realizes that the scope of the project should be changed due to a new government regulation affects the current project. What tool or technique should the project manager have considered before this issue occurred? | Stakeholder register. | Multicriteria decision analysis | Presentations | Stakeholder analysis. | Tom is the project manager of a project that is halfway through its execution. Jack realizes that the scope of the project should be changed due to a new government regulation affects the current project. What tool or technique should the project manager have considered before this issue occurred? | Stakeholder register. | Multicriteria decision analysis | Presentations | Stakeholder analysis. | Stakeholder Management | Initiating | False | "20"
You are working on a project to construct villa in your city, and you are about to start project planning. As a starting point for initial project planning, what is the first thing you should do? | Conduct a project kick-off meeting to inform and engage stakeholders and gain commitment. | Begin the process of identifying stakeholders so they can be engaged as necessary for project planning. | Develop the project schedule to manage timely completion of the project | Review the project charter to understand the high-level information about the project. | You are working on a project to construct villa in your city, and you are about to start project planning. As a starting point for initial project planning, what is the first thing you should do? | Conduct a project kick-off meeting to inform and engage stakeholders and gain commitment. | Begin the process of identifying stakeholders so they can be engaged as necessary for project planning. | Develop the project schedule to manage timely completion of the project | Review the project charter to understand the high-level information about the project. | Integration Management | Planning | False | "20"
You are managing a large engineering project. Your project team works in two different industries across the city. You want to communicate the vision and inspire the project team to achieve high performance. Which of the following skills help the project manager? | Political awareness | Emotional intelligence | Feedback | Leadership | You are managing a large engineering project. Your project team works in two different industries across the city. You want to communicate the vision and inspire the project team to achieve high performance. Which of the following skills help the project manager? | Political awareness | Emotional intelligence | Feedback | Leadership | Resources Management | Executing | False | "20"
You are the project manager of the HDM Project. Your project must be completed by September 10 and cannot exceed $12,000. $12,000 is an example of which one of the following? | Management reserve | Scheduled completion date | Assumption | Constraint | You are the project manager of the HDM Project. Your project must be completed by September 10 and cannot exceed $12,000. $12,000 is an example of which one of the following? | Management reserve | Scheduled completion date | Assumption | Constraint | Cost Management | Monitoring and Controlling | False | "19"
Situational Awareness is a key interpersonal skill for all effective project managers and means knowing what is going on around you and being able to quickly switch your focus. What another skill is often used in conjunction with Situational Awareness where you the project manager, have to be persuasive in expressing your point and position in order for your project team and stakeholders to react quickly to changing project priorities? | Leadership | Negotiation | Conflict Management | Influencing | Situational Awareness is a key interpersonal skill for all effective project managers and means knowing what is going on around you and being able to quickly switch your focus. What another skill is often used in conjunction with Situational Awareness where you the project manager, have to be persuasive in expressing your point and position in order for your project team and stakeholders to react quickly to changing project priorities? | Leadership | Negotiation | Conflict Management | Influencing | Resources Management | Executing | False | "19"
You has been assigned as a project manager, you are managing a software development project as a result of observation and conversation, you notice some of the team members need to improve their skills. What should you do FIRST? | Update Cost Baseline | Schedule training sessions for the team member to optimize his performance. | Acquire new members | Review the Resource Management Plan | You has been assigned as a project manager, you are managing a software development project as a result of observation and conversation, you notice some of the team members need to improve their skills. What should you do FIRST? | Update Cost Baseline | Schedule training sessions for the team member to optimize his performance. | Acquire new members | Review the Resource Management Plan | Resources Management | Planning | False | "20"
A vendor has a contract to deliver products for a project on the first week of each month. An inspection reveals that some product components are not meeting design requirements. What should the project manager do next? | Conduct an audit of all deliverables and hire another vendor. | Demand the necessary corrections from the vendor and update the progress report. | Request an audit of all deliverables and apply penalties to the vendors. | Insist that the vendor make all necessary corrections and update the risk register. | A vendor has a contract to deliver products for a project on the first week of each month. An inspection reveals that some product components are not meeting design requirements. What should the project manager do next? | Conduct an audit of all deliverables and hire another vendor. | Demand the necessary corrections from the vendor and update the progress report. | Request an audit of all deliverables and apply penalties to the vendors. | Insist that the vendor make all necessary corrections and update the risk register. | Procurement Management | Monitoring and Controlling | False | "20"
While reviewing the statement of work (SOW) for the project, four stakeholders not agree on what the project should include. As a project manager, What should you do? | Document the conflict in the issue log before participating in the development of the project charter. | Include the stakeholders' comments for future reference in the project charter. | Document the stakeholders' points but include the remaining stakeholders' input in final decision making. | Hold a meeting with the four stakeholders to resolve the conflict and reach agreement. | While reviewing the statement of work (SOW) for the project, four stakeholders not agree on what the project should include. As a project manager, What should you do? | Document the conflict in the issue log before participating in the development of the project charter. | Include the stakeholders' comments for future reference in the project charter. | Document the stakeholders' points but include the remaining stakeholders' input in final decision making. | Hold a meeting with the four stakeholders to resolve the conflict and reach agreement. | Resources Management | Executing | False | "20"
One of the key stakeholders requested additional features to be added to the product without changing the scope, budget, or schedule. The project manager believes that these features will add great value to the end product. However, these additions will increase project costs and impact the project schedule. Which process should the project manager have followed before including the additional project feature? | Schedule and cost management | Scope and cost management | Collect requirement | Change management | One of the key stakeholders requested additional features to be added to the product without changing the scope, budget, or schedule. The project manager believes that these features will add great value to the end product. However, these additions will increase project costs and impact the project schedule. Which process should the project manager have followed before including the additional project feature? | Schedule and cost management | Scope and cost management | Collect requirement | Change management | Integration Management | Monitoring and Controlling | False | "20"
The completion date for a critical milestone is approaching, but a shared team is unable to commit to achieving it on schedule. What should the project manager do to meet the milestone date? | Ask the client to change the milestone date. | Request the additional resources. | Remind the shared team about the milestone's importance. | Approach the shared team's functional manager to request additional support. | The completion date for a critical milestone is approaching, but a shared team is unable to commit to achieving it on schedule. What should the project manager do to meet the milestone date? | Ask the client to change the milestone date. | Request the additional resources. | Remind the shared team about the milestone's importance. | Approach the shared team's functional manager to request additional support. | Schedule Management | Monitoring and Controlling | False | "19"
A project manager is asked to contribute to a document to describe what is intended to be achieved with a project once it is successfully finished, and how this will be measured. What could be the name of that document? | Project management plan | Change management plan | Statement of work | Benefits management plan | A project manager is asked to contribute to a document to describe what is intended to be achieved with a project once it is successfully finished, and how this will be measured. What could be the name of that document? | Project management plan | Change management plan | Statement of work | Benefits management plan | Integration Management | Closing | False | "20"
Which of the following data representation technique helps the project manager to classify the identified stakeholders? | Focus groups | Stakeholders assessment grid | Stakeholders register | Power/ interest grid | Which of the following data representation technique helps the project manager to classify the identified stakeholders? | Focus groups | Stakeholders assessment grid | Stakeholders register | Power/ interest grid | Stakeholder Management | Initiating | False | "18"
the program manager of a project that is halfway through the execution. Because of the increased volatility of prices, one of the vendors asks the program manager to make a price change that will affect the project contract. As a program manager, what should you do next? | Ask the CCB for approval | Implement the approved change | Analyze the impact and Update the Project management plan | Submit a change request and analyze the impact | the program manager of a project that is halfway through the execution. Because of the increased volatility of prices, one of the vendors asks the program manager to make a price change that will affect the project contract. As a program manager, what should you do next? | Ask the CCB for approval | Implement the approved change | Analyze the impact and Update the Project management plan | Submit a change request and analyze the impact | Integration Management | Monitoring and Controlling | False | "19"
During project closure and transferring of the completed project deliverables to the operations department, the construction manager discovers that an audit report from an early project phase is missing. What should the construction manager do? | Ask the operations group to accept the project without the audit report. | Complete project closure and Update the OPA | Remove the audit report from the required project documents and update the project management plan | Inform the operations group about the missing audit report. | During project closure and transferring of the completed project deliverables to the operations department, the construction manager discovers that an audit report from an early project phase is missing. What should the construction manager do? | Ask the operations group to accept the project without the audit report. | Complete project closure and Update the OPA | Remove the audit report from the required project documents and update the project management plan | Inform the operations group about the missing audit report. | Integration Management | Closing | False | "19"
Without consulting the project manager, a operational manager relocate the key project resources in order to assign them operational tasks. Since these resources are now focused on operational tasks rather than deliverables, the deliverables run late. What should the project manager do first? | Ask to have the resources replaced immediately. | Escalate the functional manager's actions to the sponsor. | Extend the project timeline. | Negotiate time allocation to prioritize the resources' workload. | Without consulting the project manager, a operational manager relocate the key project resources in order to assign them operational tasks. Since these resources are now focused on operational tasks rather than deliverables, the deliverables run late. What should the project manager do first? | Ask to have the resources replaced immediately. | Escalate the functional manager's actions to the sponsor. | Extend the project timeline. | Negotiate time allocation to prioritize the resources' workload. | Resources Management | Executing | False | "16"
As you are project manager in the final closing project phase. Which of the following should you as the project manager refer to ensure that requirements approved in the requirements documentation are delivered? | Stakeholder Engagement Assessment Matrix | Scope Management Plan | Project Management Plan | Requirement Traceability Matrix | As you are project manager in the final closing project phase. Which of the following should you as the project manager refer to ensure that requirements approved in the requirements documentation are delivered? | Stakeholder Engagement Assessment Matrix | Scope Management Plan | Project Management Plan | Requirement Traceability Matrix | Integration Management | Closing | False | "20"
A new team member has been assigned to a project team. This resource is used to a different delivery method that is less productive and does not enforce the deadline. The new delivery method is integrated so low productivity personnel have larger impact on the overall productivity of team performance. What strategy can the project manager apply to resolve the conflict with the new resource? | Force / Direct | compromise / Reconcile | Smooth / Accommodate | Collaborate / Problem solve | A new team member has been assigned to a project team. This resource is used to a different delivery method that is less productive and does not enforce the deadline. The new delivery method is integrated so low productivity personnel have larger impact on the overall productivity of team performance. What strategy can the project manager apply to resolve the conflict with the new resource? | Force / Direct | compromise / Reconcile | Smooth / Accommodate | Collaborate / Problem solve | Resources Management | Executing | False | "17"
You and your team have done extensive brainstorming and discussions. You have also looked up the Organizations process assets and have come up with an exhaustive list of risks. You and your team members feel fairly confident now that you know all the risks. You decide to prioritize the risks and only focus on the high priority ones. A team member indicates that a large number of risks have very low priority. What should you do next? | These risks can be dismissed | Perform Quantitative Risk Analysis | These risks can be accepted | Update risk register | You and your team have done extensive brainstorming and discussions. You have also looked up the Organizations process assets and have come up with an exhaustive list of risks. You and your team members feel fairly confident now that you know all the risks. You decide to prioritize the risks and only focus on the high priority ones. A team member indicates that a large number of risks have very low priority. What should you do next? | These risks can be dismissed | Perform Quantitative Risk Analysis | These risks can be accepted | Update risk register | Risk Management | Planning | False | "19"
After completing some work required to develop your project team members, such as training and improving competencies. What will you do next? | foam building activities | Staff assignments | WBS dictionary elements | Team performance assessments | After completing some work required to develop your project team members, such as training and improving competencies. What will you do next? | foam building activities | Staff assignments | WBS dictionary elements | Team performance assessments | Resources Management | Executing | False | "18"
You are a project manager in an IT project. During the deployment of a new system, an unexpected power outage occurs. What should the project manager do? | Risk categorization | Risk probability and impact assessment | Perform a qualitative risk analysis | Refer to the risk register and inform key stakeholder, | You are a project manager in an IT project. During the deployment of a new system, an unexpected power outage occurs. What should the project manager do? | Risk categorization | Risk probability and impact assessment | Perform a qualitative risk analysis | Refer to the risk register and inform key stakeholder, | Risk Management | Monitoring and Controlling | False | "18"
You are a construction manager assigned to a new seaport construction project. You want to Create WBS but the project is new to your company and there is no previous experience and documentation as a reference. Which of the following tools will help the project manager? | Organizational process assets | Brainstorming | Lessons learned register | Subject matter experts | You are a construction manager assigned to a new seaport construction project. You want to Create WBS but the project is new to your company and there is no previous experience and documentation as a reference. Which of the following tools will help the project manager? | Organizational process assets | Brainstorming | Lessons learned register | Subject matter experts | Scope Management | Planning | False | "20"
Using the following values, calculate the Management reserve: Project Budget = 100,000 EAC = 120,000 AC = 5,500 BAC=70,000 | 70000 | 40000 | 100000 | 30000 | Using the following values, calculate the Management reserve: Project Budget = 100,000 EAC = 120,000 AC = 5,500 BAC=70,000 | 70000 | 40000 | 100000 | 30000 | Cost Management | Monitoring and Controlling | False | "17"
Within your project team, you notice that emotions are at a high due to competition among the team members. People are quick to react rather than understanding each other's needs and responding appropriately. Due to this, team members you are struggling to meet your project goals and results. You are also disturbed about this and speak to your sponsor who advises you to attend a certain training. What training is this likely to be? | Active listening | Team building | Goal setting and results management | Emotional Intelligence | Within your project team, you notice that emotions are at a high due to competition among the team members. People are quick to react rather than understanding each other's needs and responding appropriately. Due to this, team members you are struggling to meet your project goals and results. You are also disturbed about this and speak to your sponsor who advises you to attend a certain training. What training is this likely to be? | Active listening | Team building | Goal setting and results management | Emotional Intelligence | Resources Management | Executing | False | "18"
You have completed resource planning and acquired resources. You have improved the team competency and performance. Now you wish to track the performance of individual members and optimize the team's performance. Which process will you perform? | Team building | Develop Team | Control Resources | Manage Team | You have completed resource planning and acquired resources. You have improved the team competency and performance. Now you wish to track the performance of individual members and optimize the team's performance. Which process will you perform? | Team building | Develop Team | Control Resources | Manage Team | Resources Management | Executing | False | "18"
Your project manager has advised that you need to protect the organization from financial risk. In planning a new project, you realize there is a limited scope definition related to the work required to fulfill the contract. What is the best type of contract to choose? | Time and material (T&M) | Cost plus fixed fee (CPFF) | Fixed price incentive fee (FPIF). | Cost plus incentive fee (CPIF). | Your project manager has advised that you need to protect the organization from financial risk. In planning a new project, you realize there is a limited scope definition related to the work required to fulfill the contract. What is the best type of contract to choose? | Time and material (T&M) | Cost plus fixed fee (CPFF) | Fixed price incentive fee (FPIF). | Cost plus incentive fee (CPIF). | Procurement Management | Planning | False | "20"
Creating a network diagram for your project, Activity A (5 days ) can start immediately. Activity B ( 3 days ) can start after Activity A is complete. Activity C ( 2 days ) can start after Activity B is complete. Activity D (4 days ) can start after Activity A and B are complete. Activity E ( 3 days ) can start after Activity C and D are complete. While having all Activities as FS relation, what is the Float of Activity D? | 2 Day | 3 Day | 1 Day | 0 Day | Creating a network diagram for your project, Activity A (5 days ) can start immediately. Activity B ( 3 days ) can start after Activity A is complete. Activity C ( 2 days ) can start after Activity B is complete. Activity D (4 days ) can start after Activity A and B are complete. Activity E ( 3 days ) can start after Activity C and D are complete. While having all Activities as FS relation, what is the Float of Activity D? | 2 Day | 3 Day | 1 Day | 0 Day | Schedule Management | Planning | False | "20"
A tool that provides a visual representation of human resource allocation to a project, number of working hours, and availability on the project over a series of time periods is a: | Resource Breakdown Structure (RBS) | Organization Breakdown Structure (OBS) | Stakeholder Register | Resource Histogram | A tool that provides a visual representation of human resource allocation to a project, number of working hours, and availability on the project over a series of time periods is a: | Resource Breakdown Structure (RBS) | Organization Breakdown Structure (OBS) | Stakeholder Register | Resource Histogram | Resources Management | Planning | False | "20"
A project manager notices that there is limited participation and contribution from a new team member. What should the project manager do? | Review the roles and responsibilities of each team member. | Discuss the situation with the project sponsor | Write a complaint to the human resources department. | Discipline the new team member. | A project manager notices that there is limited participation and contribution from a new team member. What should the project manager do? | Review the roles and responsibilities of each team member. | Discuss the situation with the project sponsor | Write a complaint to the human resources department. | Discipline the new team member. | Resources Management | Executing | False | "19"
The project in closure phase now, what is the activity necessary to transfer the project's products, services, or results to production and/or operations group? | Perform Quality Audit | Complete the preventive and corrective actions | Monitoring implementation of approved changes as they occur | Determine summary budget | The project in closure phase now, what is the activity necessary to transfer the project's products, services, or results to production and/or operations group? | Perform Quality Audit | Complete the preventive and corrective actions | Monitoring implementation of approved changes as they occur | Determine summary budget | Integration Management | Closing | False | "19"
In the planning process of your project, you realize that your schedule requires more resources in certain months of the project than what are available to you. Your senior management has clearly instructed that you will not be able to obtain additional resources for the project. So, you instruct your planner to adjust the schedule to accommodate these constraints. What are you instructing the planner to do? | Crashing | Fast tracking | Evaluation and Review Technique | Resource leveling | In the planning process of your project, you realize that your schedule requires more resources in certain months of the project than what are available to you. Your senior management has clearly instructed that you will not be able to obtain additional resources for the project. So, you instruct your planner to adjust the schedule to accommodate these constraints. What are you instructing the planner to do? | Crashing | Fast tracking | Evaluation and Review Technique | Resource leveling | Schedule Management | Planning | False | "19"
The project manager got information that a very powerful stakeholder who was not identified in his stakeholder list isn't happy with his project performance. He asked for some updates to be done in the project. What is the first action project manager should do? | Implement the change. | Issue a change request to CCB. | Analyze the impact of the request on the project. | Update Stakeholder register. | The project manager got information that a very powerful stakeholder who was not identified in his stakeholder list isn't happy with his project performance. He asked for some updates to be done in the project. What is the first action project manager should do? | Implement the change. | Issue a change request to CCB. | Analyze the impact of the request on the project. | Update Stakeholder register. | Stakeholder Management | Initiating | False | "19"
The project you are managing is large, when you starting to get approval for management reserve to use for unforeseen work happen in the execution phase, you were dealing with an interested stakeholder who has no authority. How can you handle that? | Monitor | Keep satisfied | Manage closely | Inform the stakeholder | The project you are managing is large, when you starting to get approval for management reserve to use for unforeseen work happen in the execution phase, you were dealing with an interested stakeholder who has no authority. How can you handle that? | Monitor | Keep satisfied | Manage closely | Inform the stakeholder | Stakeholder Management | Initiating | False | "20"
A company has recurring quality issues with one of its sole source suppliers. A new project will incur significant penalties from the end users if deliverables are late What should the project manager do? | Escalate the issue to top management | Negotiate with other vendors with better quality-control methods. | Review incoming inspection reports and quality logs | Identify high- level risks prior to developing contingency plans | A company has recurring quality issues with one of its sole source suppliers. A new project will incur significant penalties from the end users if deliverables are late What should the project manager do? | Escalate the issue to top management | Negotiate with other vendors with better quality-control methods. | Review incoming inspection reports and quality logs | Identify high- level risks prior to developing contingency plans | Risk Management | Monitoring and Controlling | False | "19"
During the control quality process, the quality inspectors have discovered a many number of defects on the deliverables. The project owner told the project manager go proceed to validate scope process for approval. As a project manager, What should you do next? | Validate Scope Process | Ignore the sponsor and direct team to complete the deliverables | Request training for the team members and rework | Evaluate the impact of defects on the project and inform the sponsor | During the control quality process, the quality inspectors have discovered a many number of defects on the deliverables. The project owner told the project manager go proceed to validate scope process for approval. As a project manager, What should you do next? | Validate Scope Process | Ignore the sponsor and direct team to complete the deliverables | Request training for the team members and rework | Evaluate the impact of defects on the project and inform the sponsor | Quality Management | Monitoring and Controlling | False | "20"
As project manager managing project, A conflict between the requirements is best resolved in favor of the: | Sponsor | Team members | Project manager's boss | Customer | As project manager managing project, A conflict between the requirements is best resolved in favor of the: | Sponsor | Team members | Project manager's boss | Customer | Resources Management | Executing | False | "19"
The project manager is trying to get hand over for a series of marketing materials. The work is rejected by the key stakeholders responsible for sign off because of incorrect use of marketing standards and specification. What should the project manager do before sending materials to the key stakeholders again? | Validate the scope before performing quality control | Create a work breakdown structure before validating the scope | Validate scope before communicating the project status | Perform quality control checks before validating the scope | The project manager is trying to get hand over for a series of marketing materials. The work is rejected by the key stakeholders responsible for sign off because of incorrect use of marketing standards and specification. What should the project manager do before sending materials to the key stakeholders again? | Validate the scope before performing quality control | Create a work breakdown structure before validating the scope | Validate scope before communicating the project status | Perform quality control checks before validating the scope | Quality Management | Monitoring and Controlling | False | "19"
You are a project manager in a infrastructure project. What should you do to ensure the successful delivery of the project? | Meet with stakeholders to communicate the schedule budget, and cost impact in the event of a project delay. | Establish a management reserve to handle the unknown risks when occurs | Conduct a team-building activity | Identify the project's risks and necessary success criteria. | You are a project manager in a infrastructure project. What should you do to ensure the successful delivery of the project? | Meet with stakeholders to communicate the schedule budget, and cost impact in the event of a project delay. | Establish a management reserve to handle the unknown risks when occurs | Conduct a team-building activity | Identify the project's risks and necessary success criteria. | Risk Management | Planning | False | "20"
You are managing a critical project with frequent changes in requirement. You are in the testing phase of the project, and the customer has requested the addition of a new feature. You have assessed the impact of the change on the triple constraints with your team. What should be your NEXT step? | Update the project management plans and other project documents including project baselines | Look for alternative options including schedule compression techniques like crashing and fast tracking | Raise a change request form and send it for approval to change control board | Analyze the impact of the change on the project's quality objectives and quality planning | You are managing a critical project with frequent changes in requirement. You are in the testing phase of the project, and the customer has requested the addition of a new feature. You have assessed the impact of the change on the triple constraints with your team. What should be your NEXT step? | Update the project management plans and other project documents including project baselines | Look for alternative options including schedule compression techniques like crashing and fast tracking | Raise a change request form and send it for approval to change control board | Analyze the impact of the change on the project's quality objectives and quality planning | Quality Management | Monitoring and Controlling | False | "20"
A project is initiated, and the planning is complete. As a project manager, you are about to conduct the kick-off meeting with all stakeholders before start execution phase, and you feel that the strategic directions for the project need to be presented first. Who should present this topic? | customer | Project manager | Functional manager | Project sponsor | A project is initiated, and the planning is complete. As a project manager, you are about to conduct the kick-off meeting with all stakeholders before start execution phase, and you feel that the strategic directions for the project need to be presented first. Who should present this topic? | customer | Project manager | Functional manager | Project sponsor | Integration Management | Planning | False | "19"
During the review of a control chart, you notice that the process has 3 points between mean and lower control limit and 4 points between upper control limit and specification limit. How will you consider this process? | Cannot be determined | In control | The customer only can take a decision for this process | Unstable | During the review of a control chart, you notice that the process has 3 points between mean and lower control limit and 4 points between upper control limit and specification limit. How will you consider this process? | Cannot be determined | In control | The customer only can take a decision for this process | Unstable | Quality Management | Monitoring and Controlling | False | "19"
You are a project manager managing a small project for the company XY. A company's financial year-end is coming. A seller delivers most of a project's deliverables but a few defects require correction before the contracted payment can be made. What should the project manager do? | Arrange an extended financial project close until contract closure is completed | Claim penalties for the value of the outstanding payment. | Terminate seller contract | Pay to the seller with a formal written commitment to complete the work | You are a project manager managing a small project for the company XY. A company's financial year-end is coming. A seller delivers most of a project's deliverables but a few defects require correction before the contracted payment can be made. What should the project manager do? | Arrange an extended financial project close until contract closure is completed | Claim penalties for the value of the outstanding payment. | Terminate seller contract | Pay to the seller with a formal written commitment to complete the work | Procurement Management | Monitoring and Controlling | False | "18"
As you are a project manager of the construct infrastructure Project. Your project is behind Schedule and the sponsor suggests reducing the time for quality assurance testing. What should the project manager do first? | Perform quality audit | Perform quality control measurements. | Change the quality requirements | Follow the Quality Management Plan | As you are a project manager of the construct infrastructure Project. Your project is behind Schedule and the sponsor suggests reducing the time for quality assurance testing. What should the project manager do first? | Perform quality audit | Perform quality control measurements. | Change the quality requirements | Follow the Quality Management Plan | Quality Management | Monitoring and Controlling | False | "20"
You are managing a complex construction project and you request a seven-year schedule for this project. Although multiple brainstorming sessions with your project team, you struggle to provide detail for the project management plan. This causes a delay in obtaining the project management plan approvals. As a project manager, what should you have done to avoid this situation? | Used decomposition techniques | Used subject matter expert to develop the detailed schedule. | Created a high level Gantt chart to represent the milestone only | Used the rolling wave planning technique for activity planning | You are managing a complex construction project and you request a seven-year schedule for this project. Although multiple brainstorming sessions with your project team, you struggle to provide detail for the project management plan. This causes a delay in obtaining the project management plan approvals. As a project manager, what should you have done to avoid this situation? | Used decomposition techniques | Used subject matter expert to develop the detailed schedule. | Created a high level Gantt chart to represent the milestone only | Used the rolling wave planning technique for activity planning | Schedule Management | Planning | False | "19"
The change control board (CCB) is evaluating a recently submitted change request. The project sponsor wants to deferring the request until a later date. Another stakeholder is in favor of denying. The project manager and other stakeholders feel to approve the request. The Project manager is unsure how to proceed since there is disagreement among the stakeholders what should the project manager do? | Approve the request as the project manager has authority to decide for the group | Approve the request as the project sponsor has the final say | Defer the request until all of the stakeholders are in agreement | Consult the project management plan | The change control board (CCB) is evaluating a recently submitted change request. The project sponsor wants to deferring the request until a later date. Another stakeholder is in favor of denying. The project manager and other stakeholders feel to approve the request. The Project manager is unsure how to proceed since there is disagreement among the stakeholders what should the project manager do? | Approve the request as the project manager has authority to decide for the group | Approve the request as the project sponsor has the final say | Defer the request until all of the stakeholders are in agreement | Consult the project management plan | Integration Management | Monitoring and Controlling | False | "20"
As a project manager for a huge project, you conduct a kick-off meeting to inform and engage stakeholders and gain commitment to the project. In which process group are you currently? | Executing | Monitoring and Controlling | Closing | Planning | As a project manager for a huge project, you conduct a kick-off meeting to inform and engage stakeholders and gain commitment to the project. In which process group are you currently? | Executing | Monitoring and Controlling | Closing | Planning | Integration Management | Planning | False | "20"
The Project team members and the professional experts are working on a design development project. A project manager discovers an enhancement that will improve the design. What should the project manager do? | Document this discovery, and present it to an stakeholders | Ask the subject matter expert (SME) to implement the enhancement | Ignore the enhancement as no changes are allowed | Ask the change control board (CCB) to review the enhancement. | The Project team members and the professional experts are working on a design development project. A project manager discovers an enhancement that will improve the design. What should the project manager do? | Document this discovery, and present it to an stakeholders | Ask the subject matter expert (SME) to implement the enhancement | Ignore the enhancement as no changes are allowed | Ask the change control board (CCB) to review the enhancement. | Integration Management | Monitoring and Controlling | False | "19"
An approved change request adds an incentive to a lump sum contract if the contractor is able to maintain the current baseline schedule. What should now be updated? | Schedule baseline. | Scope baseline. | Project management plan. | Cost baseline. | An approved change request adds an incentive to a lump sum contract if the contractor is able to maintain the current baseline schedule. What should now be updated? | Schedule baseline. | Scope baseline. | Project management plan. | Cost baseline. | Integration Management | Monitoring and Controlling | False | "20"
A project manager uses the schedule from a similar project to estimate the cost of the project activities for a new project. Which method was used to derive the estimates? | Bottom-up estimating. | Parametric estimating. | Expert judgment | Analogous estimating. | A project manager uses the schedule from a similar project to estimate the cost of the project activities for a new project. Which method was used to derive the estimates? | Bottom-up estimating. | Parametric estimating. | Expert judgment | Analogous estimating. | Cost Management | Planning | False | "19"
You are a project manager in a construction project. During a review, the project team member identifies a quality issue that may cause the product to be rejected by the customer. However, the project sponsor wants to deliver the product. As a project manager, what should you do? | Ensure that the product meets customer requirements | Deliver the product | Update the issue log | Review the quality checklist | You are a project manager in a construction project. During a review, the project team member identifies a quality issue that may cause the product to be rejected by the customer. However, the project sponsor wants to deliver the product. As a project manager, what should you do? | Ensure that the product meets customer requirements | Deliver the product | Update the issue log | Review the quality checklist | Quality Management | Monitoring and Controlling | False | "19"
During the implementation phase, the project manager identifies a new project activity that will not affect the project deadline. What should the project manager do next step? | Ask the sponsor to approve the new activity. | Update the schedule baseline and Begin working on the new task immediately | Update the change log and update the schedule baseline | Create a change request. | During the implementation phase, the project manager identifies a new project activity that will not affect the project deadline. What should the project manager do next step? | Ask the sponsor to approve the new activity. | Update the schedule baseline and Begin working on the new task immediately | Update the change log and update the schedule baseline | Create a change request. | Integration Management | Monitoring and Controlling | False | "19"
Which of the following risk analysis techniques can help you to investigate the likelihood that each specific risk will occur? | Monte Carlo | Risk categorization | Probability and Impact matrix | Risk Probability and Impact Assessment | Which of the following risk analysis techniques can help you to investigate the likelihood that each specific risk will occur? | Monte Carlo | Risk categorization | Probability and Impact matrix | Risk Probability and Impact Assessment | Risk Management | Planning | False | "19"
Two of your expert team members have been in a heated argument over the use of a new software product for your research project. Recently, you noticed that the argument, instead of increasing creativity, is causing conflict between the team members. To prevent the conflict from escalating, you want to resolve it by open dialogue and evaluating alternatives. All the following statements about conflict are false except: | Scarce resources cannot be a source of a conflict. | Personal work style cannot be a source of a conflict. | Reducing the amount of conflict is not desirable. | Conflict is inevitable in a project environment. | Two of your expert team members have been in a heated argument over the use of a new software product for your research project. Recently, you noticed that the argument, instead of increasing creativity, is causing conflict between the team members. To prevent the conflict from escalating, you want to resolve it by open dialogue and evaluating alternatives. All the following statements about conflict are false except: | Scarce resources cannot be a source of a conflict. | Personal work style cannot be a source of a conflict. | Reducing the amount of conflict is not desirable. | Conflict is inevitable in a project environment. | Resources Management | Executing | False | "19"
A project status report shows that: The earned value (EV) is 30 The schedule performance index (SPI) is .93. The cost performance index (CPI) is 1.05. In what area should the project manager implement corrective actions? | Project cost. | Resource management. | Communication management | Project schedule. | A project status report shows that: The earned value (EV) is 30 The schedule performance index (SPI) is .93. The cost performance index (CPI) is 1.05. In what area should the project manager implement corrective actions? | Project cost. | Resource management. | Communication management | Project schedule. | Cost Management | Monitoring and Controlling | False | "18"
A buyer sent the quotation (RFQ) to the potential sellers. After a certain days, some potential sellers have questions about the terms and conditions. As a project manager, to ensure that all vendors have a clear and common understanding, what should you do? | Resubmit the RFP. | Send a clarification to the vendors via email. | Conduct one- to-one meeting with vendors. | Conduct a bidder conferences | A buyer sent the quotation (RFQ) to the potential sellers. After a certain days, some potential sellers have questions about the terms and conditions. As a project manager, to ensure that all vendors have a clear and common understanding, what should you do? | Resubmit the RFP. | Send a clarification to the vendors via email. | Conduct one- to-one meeting with vendors. | Conduct a bidder conferences | Procurement Management | Planning | False | "19"
As part of a strategy to handle negative risk, a project manager decided to do less complex processes, add more tests, and deal with more stable supplier. What strategy would this be classified as? | Acceptance | Avoidance | Transference | Mitigation | As part of a strategy to handle negative risk, a project manager decided to do less complex processes, add more tests, and deal with more stable supplier. What strategy would this be classified as? | Acceptance | Avoidance | Transference | Mitigation | Risk Management | Executing | False | "18"
You are managing a project a local government project which has BAC $120,000 and supposes to finish in 6 months. After four months, the project manager confirmed that the project is 55 % complete . To date,US$90,000 has been spent. What is the EV, SV, and CV? | EV=US$60,000. SV=- US$14,000 CV=- US$24,000 | EV= US$60,00 SV=US$24,000 CV=US$14.000 | EV=US$66,000 SV=-US$24,000 CC=-US$14,000 | EV=US$66,000 SV= - US$14,000 CV= - US$24,000 | You are managing a project a local government project which has BAC $120,000 and supposes to finish in 6 months. After four months, the project manager confirmed that the project is 55 % complete . To date,US$90,000 has been spent. What is the EV, SV, and CV? | EV=US$60,000. SV=- US$14,000 CV=- US$24,000 | EV= US$60,00 SV=US$24,000 CV=US$14.000 | EV=US$66,000 SV=-US$24,000 CC=-US$14,000 | EV=US$66,000 SV= - US$14,000 CV= - US$24,000 | Cost Management | Monitoring and Controlling | False | "19"
You are a project manager who is in charge of an important project for your company. When the SPI=0.85 and CPI=1.15. How is the project performing? | The project is on schedule and under budget | The project is ahead of schedule and under budget | The project is behind schedule and over budget | The project is behind schedule and within budget | You are a project manager who is in charge of an important project for your company. When the SPI=0.85 and CPI=1.15. How is the project performing? | The project is on schedule and under budget | The project is ahead of schedule and under budget | The project is behind schedule and over budget | The project is behind schedule and within budget | Cost Management | Monitoring and Controlling | False | "20"
At the beginning of the project, you and your team would like to address all the strengths, weaknesses, opportunities, and threats the project is facing. What tool should be used? | Cause and effect diagram | Interviewing | Delphi Technique | SWOT Analysis | At the beginning of the project, you and your team would like to address all the strengths, weaknesses, opportunities, and threats the project is facing. What tool should be used? | Cause and effect diagram | Interviewing | Delphi Technique | SWOT Analysis | Risk Management | Executing | False | "19"
As a project manager for a huge construction project, the project is being fast-tracked because the stakeholders committed to the schedule baseline. Some construction activities must be initiated before all basic scope specifications are completely developed. What type of contract should the procurement manager negotiate? | Cost plus foxed fee (CPFF). | Firm fixed price (FFP). | Fixed price incentive fee (FPIF) | Cost plus incentive fee (CPIF). | As a project manager for a huge construction project, the project is being fast-tracked because the stakeholders committed to the schedule baseline. Some construction activities must be initiated before all basic scope specifications are completely developed. What type of contract should the procurement manager negotiate? | Cost plus foxed fee (CPFF). | Firm fixed price (FFP). | Fixed price incentive fee (FPIF) | Cost plus incentive fee (CPIF). | Procurement Management | Planning | False | "20"
You need a public opinion as part of the requirements gathering process for your project. You selected a wide variety of people for your study and want to use a requirements gathering technique that can produce results quickly. Which technique is best suited for this scenario? | Observations | Brainstorming | Group Creativity Techniques | Questionnaires and Surveys | You need a public opinion as part of the requirements gathering process for your project. You selected a wide variety of people for your study and want to use a requirements gathering technique that can produce results quickly. Which technique is best suited for this scenario? | Observations | Brainstorming | Group Creativity Techniques | Questionnaires and Surveys | Scope Management | Planning | False | "19"
project manager is creating a program evaluation and review technique (PERT) diagram. As per the following data, what is the activity's expected time? - Optimistic time (O ) is three weeks. - Pessimistic time ( P) is seven weeks. - Most likely time ( M) is five weeks. | 7 weeks. | 6 weeks | 3 weeks. | 5 weeks | project manager is creating a program evaluation and review technique (PERT) diagram. As per the following data, what is the activity's expected time? - Optimistic time (O ) is three weeks. - Pessimistic time ( P) is seven weeks. - Most likely time ( M) is five weeks. | 7 weeks. | 6 weeks | 3 weeks. | 5 weeks | Schedule Management | Planning | False | "20"
Your project is in execution, and you identify a new important stakeholder with a high level of influence. As a project manager, what should you do? | Update the Project management plan | Update the Stakeholder engagement plan | Update the requirements traceability matrix | Update the Stakeholder register | Your project is in execution, and you identify a new important stakeholder with a high level of influence. As a project manager, what should you do? | Update the Project management plan | Update the Stakeholder engagement plan | Update the requirements traceability matrix | Update the Stakeholder register | Risk Management | Executing | False | "20"
A program manager informs the project manager that their project was terminated. The project manager want to inform the stakeholders and team members about this. To what document should the project manager refer? | Change Management Plan | Responsibility assignment matrix (RAM) | Resources Management Plan | Communication management plan | A program manager informs the project manager that their project was terminated. The project manager want to inform the stakeholders and team members about this. To what document should the project manager refer? | Change Management Plan | Responsibility assignment matrix (RAM) | Resources Management Plan | Communication management plan | Communication Management | Monitoring and Controlling | False | "20"
As a project manager, what should you do FIRST if the project sponsor decided to conduct certain changes to the project scope without consulting you? | Update the project management plan to involve the changes. | Negotiate with the project sponsor to make the changes in the next phase of the project | Identify this as a risk and implement risk response strategies | Assess the impact of the change in the project scope. | As a project manager, what should you do FIRST if the project sponsor decided to conduct certain changes to the project scope without consulting you? | Update the project management plan to involve the changes. | Negotiate with the project sponsor to make the changes in the next phase of the project | Identify this as a risk and implement risk response strategies | Assess the impact of the change in the project scope. | Scope Management | Monitoring and Controlling | False | "16"
After finishing the planning phase of a project, but before execution, the project manager needs to communicate and gain commitment on project objectives. What should the project manager do next? | Send the project management plan to all stakeholders via email. | Call each stakeholder to explain their roles and responsibilities. | Ask the project sponsor to communicate the plan to all stakeholders. | Conduct a kick-off meeting with all stakeholders. | After finishing the planning phase of a project, but before execution, the project manager needs to communicate and gain commitment on project objectives. What should the project manager do next? | Send the project management plan to all stakeholders via email. | Call each stakeholder to explain their roles and responsibilities. | Ask the project sponsor to communicate the plan to all stakeholders. | Conduct a kick-off meeting with all stakeholders. | Integration Management | Planning | False | "20"
A project task involves the procurement of a specific raw materials at regular intervals. Price fluctuations was identified as a risk during planning. The risk response is to exploit a price drop if it occurs. The price of the raw material has now reduced drastically. What should the project manager do? | Purchase the raw material at the existing price. | Wait for the prices to further reduce. | Ask the management for advice. | Review the risk register for the recommended responses. | A project task involves the procurement of a specific raw materials at regular intervals. Price fluctuations was identified as a risk during planning. The risk response is to exploit a price drop if it occurs. The price of the raw material has now reduced drastically. What should the project manager do? | Purchase the raw material at the existing price. | Wait for the prices to further reduce. | Ask the management for advice. | Review the risk register for the recommended responses. | Risk Management | Executing | False | "20"
A quality control member informs a project manager about a one-week schedule delay to complete the testing phase. What should the project manager do next? | Crash the schedule. | Negotiate with the customer for a change in the schedule. | Take corrective action to minimize the impact of delay | Check whether this task is on the critical path. | A quality control member informs a project manager about a one-week schedule delay to complete the testing phase. What should the project manager do next? | Crash the schedule. | Negotiate with the customer for a change in the schedule. | Take corrective action to minimize the impact of delay | Check whether this task is on the critical path. | Schedule Management | Monitoring and Controlling | False | "20"
You are a Project Manager in a Engineering company. the sponsor of project has just developed the project charter, and has also provided you with a list of the project's key stakeholders that he has identified. He then asks you to immediately gather the requirements. What should be your next step as the project manager? | Develop a stakeholder engagement plan | Prepare a power/interest matrix for key stakeholders | Start working on define activities | Conduct the stakeholder identification process to identify all stakeholder's | You are a Project Manager in a Engineering company. the sponsor of project has just developed the project charter, and has also provided you with a list of the project's key stakeholders that he has identified. He then asks you to immediately gather the requirements. What should be your next step as the project manager? | Develop a stakeholder engagement plan | Prepare a power/interest matrix for key stakeholders | Start working on define activities | Conduct the stakeholder identification process to identify all stakeholder's | Stakeholder Management | Initiating | False | "18"
You are a project manager in a critical project for your organization. You have a project with a budget of 200,000 SR. The duration of the project is 30 months, and the work is evenly distributed throughout the duration. After 15 months, you review the project's progress and you find that 60% of the work is completed and 110,000 SR has been spent. Determine the estimate at completion assuming the future cost performance is the same as the past cost performance. | 100,000 SR | 190,000 SR | 120,000 SR | 183,486 SR | You are a project manager in a critical project for your organization. You have a project with a budget of 200,000 SR. The duration of the project is 30 months, and the work is evenly distributed throughout the duration. After 15 months, you review the project's progress and you find that 60% of the work is completed and 110,000 SR has been spent. Determine the estimate at completion assuming the future cost performance is the same as the past cost performance. | 100,000 SR | 190,000 SR | 120,000 SR | 183,486 SR | Cost Management | Monitoring and Controlling | False | "20"
The procurement manager of a civil project has emailed the project manager stating that the cost of the cement may exceed the amount budgeted. The project must have a cement delivery in the next two weeks. What should the project manager do first? | Request a quote from another supplier. | Negotiate with the item supplier. | Contact the project sponsor to get more money. | Perform the risk response. | The procurement manager of a civil project has emailed the project manager stating that the cost of the cement may exceed the amount budgeted. The project must have a cement delivery in the next two weeks. What should the project manager do first? | Request a quote from another supplier. | Negotiate with the item supplier. | Contact the project sponsor to get more money. | Perform the risk response. | Risk Management | Executing | False | "19"
You have been asked to begin writing the project scope management plan. You are gathering the necessary documents to begin this process. Which of the following is required to do this? | Focus groups | Risk management plan | Requirement traceability chart | Quality management plan | You have been asked to begin writing the project scope management plan. You are gathering the necessary documents to begin this process. Which of the following is required to do this? | Focus groups | Risk management plan | Requirement traceability chart | Quality management plan | Scope Management | Planning | False | "20"
The project has reached a stage where work is being done in seven countries. Project team members need to know in which currency they are to report their cost data. Which of the following should they reference? | Cost baseline | Cost estimates | Cost breakdown structure | Cost management plan | The project has reached a stage where work is being done in seven countries. Project team members need to know in which currency they are to report their cost data. Which of the following should they reference? | Cost baseline | Cost estimates | Cost breakdown structure | Cost management plan | Cost Management | Planning | False | "20"
You, as a project manager, are in the process of midway review at the end of the first year of a $50K project. The earned value analysis shows that the PV is $25K, the EV is $20K, and the AC is $30K. What can be determined from these figures? | The project should be terminated as there is no solution to fix it. | The project is under budget but ahead of schedule. | The project is going normally, and it will be managed and closed normally. | The project is going slower than planned. | You, as a project manager, are in the process of midway review at the end of the first year of a $50K project. The earned value analysis shows that the PV is $25K, the EV is $20K, and the AC is $30K. What can be determined from these figures? | The project should be terminated as there is no solution to fix it. | The project is under budget but ahead of schedule. | The project is going normally, and it will be managed and closed normally. | The project is going slower than planned. | Cost Management | Monitoring and Controlling | False | "18"
You are the project manager of a large communication project. During the implementation phase, you sign a contract to rent an additional server from a local company because of the possibility that the main server may fail due to constant, local-area electrical outages. As a project manager, what strategy are you using? | Transfer | Avoid | Escalate | Mitigate | You are the project manager of a large communication project. During the implementation phase, you sign a contract to rent an additional server from a local company because of the possibility that the main server may fail due to constant, local-area electrical outages. As a project manager, what strategy are you using? | Transfer | Avoid | Escalate | Mitigate | Risk Management | Executing | False | "20"
You are managing a project which has BAC 90.000 $ and supposes to finish in 9 months. Five months have passed; however, four months of the work have been completed. To date, you have spent 60% of the budget. What are the EV, CPI, and SPI? | EV= 30,000 & CPI = 0.74 & SPI = 0.9 | EV= 35,000 & CPI = 0.74 & SPI = 0.9 | EV= 35,000 & CPI = 0.74 & SPI = 2 | EV= 40,000 & CR = 0.74 & SPI = 0.8 | You are managing a project which has BAC 90.000 $ and supposes to finish in 9 months. Five months have passed; however, four months of the work have been completed. To date, you have spent 60% of the budget. What are the EV, CPI, and SPI? | EV= 30,000 & CPI = 0.74 & SPI = 0.9 | EV= 35,000 & CPI = 0.74 & SPI = 0.9 | EV= 35,000 & CPI = 0.74 & SPI = 2 | EV= 40,000 & CR = 0.74 & SPI = 0.8 | Cost Management | Monitoring and Controlling | False | "20"
A project manager has just learned that his project's sole equipment supplier has gone out of business. It is an unanticipated risk and will cause a delay in the project until a new vendor can be selected and contracts put in place. What do the PM do? | Continue working on non-critical path tasks. | Put out into RFP for new vendors. | Consult with legal counsel. | Notify the project stakeholders. | A project manager has just learned that his project's sole equipment supplier has gone out of business. It is an unanticipated risk and will cause a delay in the project until a new vendor can be selected and contracts put in place. What do the PM do? | Continue working on non-critical path tasks. | Put out into RFP for new vendors. | Consult with legal counsel. | Notify the project stakeholders. | Risk Management | Executing | False | "19"
During the middle of the project, the project manager has been exposed to an accident, and a new project manager has been assigned. What should the new project manager do next? | Update Organizational process assets ( OPA ) | Update resource calendar | Update project charter | Update project management plan | During the middle of the project, the project manager has been exposed to an accident, and a new project manager has been assigned. What should the new project manager do next? | Update Organizational process assets ( OPA ) | Update resource calendar | Update project charter | Update project management plan | Risk Management | Executing | False | "20"
You are project manager and working with your customers on completing deliverables in seaport project. Which of the following stakeholders can modify and make changes in the project charter? | The project customer | All stakeholders | The team members | The project sponsor | You are project manager and working with your customers on completing deliverables in seaport project. Which of the following stakeholders can modify and make changes in the project charter? | The project customer | All stakeholders | The team members | The project sponsor | Integration Management | Closing | False | "20"
A project manager is in the process of identifying the likely stakeholders on a project and their interests in the project. The project manager has just compiled a list of potential stakeholders' names. What should the project manager do next? | Conduct kick-off meeting to inform and engage stakeholders and gain commitment | Develop the scope management plan | Develop the stakeholder engagement plan | Conduct stakeholder analysis | A project manager is in the process of identifying the likely stakeholders on a project and their interests in the project. The project manager has just compiled a list of potential stakeholders' names. What should the project manager do next? | Conduct kick-off meeting to inform and engage stakeholders and gain commitment | Develop the scope management plan | Develop the stakeholder engagement plan | Conduct stakeholder analysis | Stakeholder Management | Initiating | False | "19"
A project consists of 5 activities, A, B, C, D, and E. Task A begins on day 1 and will take two days to complete. Task B will take 6 days to complete and can not begin until task A is finished. Task C will take 4 days to complete, cannot begin before task A is finished, and must be completed before task D begins. Task D will take 8 days to complete and cannot begin until task B is finished. Task E will take 1 day to complete and cannot begin until task D is finished. What is the duration of the critical path? | 19 days. | 20 days. | 15 days. | 17 days | A project consists of 5 activities, A, B, C, D, and E. Task A begins on day 1 and will take two days to complete. Task B will take 6 days to complete and can not begin until task A is finished. Task C will take 4 days to complete, cannot begin before task A is finished, and must be completed before task D begins. Task D will take 8 days to complete and cannot begin until task B is finished. Task E will take 1 day to complete and cannot begin until task D is finished. What is the duration of the critical path? | 19 days. | 20 days. | 15 days. | 17 days | Schedule Management | Planning | False | "19"
In your project, your project team starts testing an mechanical component created during a project, the test failed. The cost of such testing is usually classified as: | Appraisal cost | Internal failure cost | External failure cost | Appraisal and internal failure costs | In your project, your project team starts testing an mechanical component created during a project, the test failed. The cost of such testing is usually classified as: | Appraisal cost | Internal failure cost | External failure cost | Appraisal and internal failure costs | Quality Management | Monitoring and Controlling | False | "20"
During the initiation phase, the project manager classifying a list of project stakeholders and discovers an interested stakeholder with little authority. How should manage this stakeholder? | Keep satisfied | Manage Closely | Monitor | Keep informed | During the initiation phase, the project manager classifying a list of project stakeholders and discovers an interested stakeholder with little authority. How should manage this stakeholder? | Keep satisfied | Manage Closely | Monitor | Keep informed | Stakeholder Management | Initiating | False | "20"
You are a project manager in a manufacturing company. You want to analyze the output of a production line which manufactures piston rings. You want to determine whether the variations in the jobs are inherent to the process or if the process is in need of adjustment. Which of the following tools would be most useful? | Trend analysis | Pareto charts | Statistical sampling | Control charts | You are a project manager in a manufacturing company. You want to analyze the output of a production line which manufactures piston rings. You want to determine whether the variations in the jobs are inherent to the process or if the process is in need of adjustment. Which of the following tools would be most useful? | Trend analysis | Pareto charts | Statistical sampling | Control charts | Quality Management | Monitoring and Controlling | False | "19"
After identifying and analyzing risks you and your team start to risk response process, you find a risk which would be difficult for you to manage. You discuss the issue with management and a decision is taken to transfer the management of this risk to your Program manager. What risk response strategy is this? | Transfer | Mitigate | Workaround | Escalate | After identifying and analyzing risks you and your team start to risk response process, you find a risk which would be difficult for you to manage. You discuss the issue with management and a decision is taken to transfer the management of this risk to your Program manager. What risk response strategy is this? | Transfer | Mitigate | Workaround | Escalate | Risk Management | Executing | False | "19"
One of the key stakeholder asks the project manager for a new product feature. The project manager is unsure who have the authority to approve this request. To what document should the project manager refer? | RACI Matrix | Change Log | Organizational process assets ( OPA ) | Change Management Plan | One of the key stakeholder asks the project manager for a new product feature. The project manager is unsure who have the authority to approve this request. To what document should the project manager refer? | RACI Matrix | Change Log | Organizational process assets ( OPA ) | Change Management Plan | Integration Management | Monitoring and Controlling | False | "20"
You are developing a budget for your airport project. You don't want to use indirect costs in determining the budget. Where should you specify the information regarding indirect costs? | Activity Cost Estimates | Project schedule | Scope baseline | Basis of Estimates | You are developing a budget for your airport project. You don't want to use indirect costs in determining the budget. Where should you specify the information regarding indirect costs? | Activity Cost Estimates | Project schedule | Scope baseline | Basis of Estimates | Cost Management | Planning | False | "20"
You are in the process of executing a project that deals with laying out fiber cables connecting two cities. You have been reporting progress on a monthly basis. This month, due to unplanned vacations, many of the staff have not turned up at work. This has caused a delay in the schedule. You decide to check if the schedule variance is within the allowable threshold. What document should you refer to? | Project Management Plan | Project Schedule Network Diagram | Activity Definition | Schedule Management Plan | You are in the process of executing a project that deals with laying out fiber cables connecting two cities. You have been reporting progress on a monthly basis. This month, due to unplanned vacations, many of the staff have not turned up at work. This has caused a delay in the schedule. You decide to check if the schedule variance is within the allowable threshold. What document should you refer to? | Project Management Plan | Project Schedule Network Diagram | Activity Definition | Schedule Management Plan | Schedule Management | Planning | False | "20"
This tool of the Control Quality process is used to aid organize data when performing inspections and collecting information on defects: | Histogram | Cause and effect diagram | Scatter diagrams | Check sheets | This tool of the Control Quality process is used to aid organize data when performing inspections and collecting information on defects: | Histogram | Cause and effect diagram | Scatter diagrams | Check sheets | Quality Management | Monitoring and Controlling | False | "20"
As you work to prepare your quality management plan for your project. Which of the following can help you to have an overview of the tests required to verify requirements? | Use a checklist | Review the Quality metrics | Review project scope statement | Review the requirements traceability matrix | As you work to prepare your quality management plan for your project. Which of the following can help you to have an overview of the tests required to verify requirements? | Use a checklist | Review the Quality metrics | Review project scope statement | Review the requirements traceability matrix | Quality Management | Planning | False | "19"
Which of the following Processes should be used to implement agreed-upon risk response plans. The benefit of this process is that it ensures that agreed-upon risk responses are executed as planned? | Plan Risk management | Identify Risk | Monitor Risk | Implement Risk Responses | Which of the following Processes should be used to implement agreed-upon risk response plans. The benefit of this process is that it ensures that agreed-upon risk responses are executed as planned? | Plan Risk management | Identify Risk | Monitor Risk | Implement Risk Responses | Risk Management | Executing | False | "20"
Which process ensures that the assigned physical resources are available to the project at the right time and in the right place? | Plan Resource Management | Acquire Resources | Manage Tears | Control resources | Which process ensures that the assigned physical resources are available to the project at the right time and in the right place? | Plan Resource Management | Acquire Resources | Manage Tears | Control resources | Resources Management | Monitoring and Controlling | False | "20"
The business case documents the business needs and the cost-benefit analysis that justify the project. The summary of how the project has achieved the business needs identified in the business case is documented in the: | Project WBS | Project Scope Statement | Project charter | Project final report | The business case documents the business needs and the cost-benefit analysis that justify the project. The summary of how the project has achieved the business needs identified in the business case is documented in the: | Project WBS | Project Scope Statement | Project charter | Project final report | Integration Management | Closing | False | "19"
During a presentation to CEO you want to display the project schedule with only the key deliverables displayed. What is the best tool help you with this? | Critical chain diagram | Control chart | Critical path method | Milestone chart | During a presentation to CEO you want to display the project schedule with only the key deliverables displayed. What is the best tool help you with this? | Critical chain diagram | Control chart | Critical path method | Milestone chart | Schedule Management | Executing | False | "20"
A project manager is spending most of the project funding in the current phase of the project. The manager is also managing various resources in the project. What is the stakeholder influence on the project now compared to earlier phases? | Cannot be determined | More | Same | Less | A project manager is spending most of the project funding in the current phase of the project. The manager is also managing various resources in the project. What is the stakeholder influence on the project now compared to earlier phases? | Cannot be determined | More | Same | Less | Stakeholder Management | Executing | False | "20"
You are construction manager and meeting with the seller's project manager to review their construction work. In this review, your focus is on the deliverables and a site walkthrough. What is this known as? | Performance review | Earned value analysis | Audit | Inspection | You are construction manager and meeting with the seller's project manager to review their construction work. In this review, your focus is on the deliverables and a site walkthrough. What is this known as? | Performance review | Earned value analysis | Audit | Inspection | Procurement Management | Monitoring and Controlling | False | "19"
You are project manager managing a heavy equipment manufacturing project. During the execution phase, an unexpected issue occurred and need to procure a new piece of machinery. As a project manager, from where may the necessary funds be obtained? | Contingency reserve. | Project sponsor. | Cost Baseline. | Management reserve. | You are project manager managing a heavy equipment manufacturing project. During the execution phase, an unexpected issue occurred and need to procure a new piece of machinery. As a project manager, from where may the necessary funds be obtained? | Contingency reserve. | Project sponsor. | Cost Baseline. | Management reserve. | Cost Management | Planning | False | "19"
The director of PMO requests from the project managers to start calculating the cost contingency reserve for the project works. As a project manager, how should you calculate contingency reserves? | Trend analysis | What-if scenario analysis | Earned value analysis | Percentage of the estimated cost | The director of PMO requests from the project managers to start calculating the cost contingency reserve for the project works. As a project manager, how should you calculate contingency reserves? | Trend analysis | What-if scenario analysis | Earned value analysis | Percentage of the estimated cost | Risk Management | Planning | False | "20"
You are a project manager of a project. During the preparing and planning phase, you and your team members start identify the definition of probability of events occurring and the impact. What process is this? | Perform qualitative risk analysis | Identify risks | Perform quantitative risk analysis | Plan risk management | You are a project manager of a project. During the preparing and planning phase, you and your team members start identify the definition of probability of events occurring and the impact. What process is this? | Perform qualitative risk analysis | Identify risks | Perform quantitative risk analysis | Plan risk management | Risk Management | Planning | False | "19"
As a project manager, you are in the process of confirming the formal acceptance of the seller's work, finalizing open claims, Updating records to reflect final results, and archiving lessons learned recently captured about the seller's performance. Which of the following processes are you performing? | Control Procurements | Monitor and Control Project Work | Conduct Procurements | Close Project or Phase | As a project manager, you are in the process of confirming the formal acceptance of the seller's work, finalizing open claims, Updating records to reflect final results, and archiving lessons learned recently captured about the seller's performance. Which of the following processes are you performing? | Control Procurements | Monitor and Control Project Work | Conduct Procurements | Close Project or Phase | Integration Management | Closing | False | "20"
As a project manager, in which document will you find information about Project Scope Description, Project Deliverables, and Project Exclusions? | Stakeholder register | Change log | Project charter | Scope baseline | As a project manager, in which document will you find information about Project Scope Description, Project Deliverables, and Project Exclusions? | Stakeholder register | Change log | Project charter | Scope baseline | Scope Management | Planning | False | "19"
In which of the following types of contracts does the buyer have the maximum cost risk? | Fixed Price | Time and Material | Cost Plus Incentive Fee | Cost Reimbursable, | In which of the following types of contracts does the buyer have the maximum cost risk? | Fixed Price | Time and Material | Cost Plus Incentive Fee | Cost Reimbursable, | Procurement Management | Planning | False | "19"
A project manager begins working for a project that is already in progress. The project manager will be meeting with the project sponsor very shortly to review the project's overall scope and expected deliverables. How should the project manager prepare for the meeting? | Review the schedule forecast | Interview project team members | Examine the Gantt chart | Review the project charter | A project manager begins working for a project that is already in progress. The project manager will be meeting with the project sponsor very shortly to review the project's overall scope and expected deliverables. How should the project manager prepare for the meeting? | Review the schedule forecast | Interview project team members | Examine the Gantt chart | Review the project charter | Stakeholder Management | Executing | False | "16"
In a project with a tight time frame, the project manager needs continuous stakeholder buy-in and input to avoid errors. Inevitably, changes occur as the project progresses. What should the project manager do? | Speak with management about stakeholders involvement to initiate a change in schedule expectations. | Provide increased project updates to stakeholders and deliver accurate change management documentation. | Stop work before The changes cause a schedule delay and update the project schedule to reflect this. | Monitor and update stakeholder relationships and tailor strategies for engaging stakeholders through changes. | In a project with a tight time frame, the project manager needs continuous stakeholder buy-in and input to avoid errors. Inevitably, changes occur as the project progresses. What should the project manager do? | Speak with management about stakeholders involvement to initiate a change in schedule expectations. | Provide increased project updates to stakeholders and deliver accurate change management documentation. | Stop work before The changes cause a schedule delay and update the project schedule to reflect this. | Monitor and update stakeholder relationships and tailor strategies for engaging stakeholders through changes. | Stakeholder Management | Executing | False | "17"
Four team members have just joined the project you are leading. The project is medium and involves many stakeholders. You want to get the new team members up to speed with the overall dynamics of the project and engage effectively with the project stakeholders. What should you do? | Schedule a meeting with the new team members and all project stakeholders | Submit a change request to update the stakeholder engagement plan | Ask the team members to record any issues they encounter into the issue log | Review the stakeholder register with the new team members | Four team members have just joined the project you are leading. The project is medium and involves many stakeholders. You want to get the new team members up to speed with the overall dynamics of the project and engage effectively with the project stakeholders. What should you do? | Schedule a meeting with the new team members and all project stakeholders | Submit a change request to update the stakeholder engagement plan | Ask the team members to record any issues they encounter into the issue log | Review the stakeholder register with the new team members | Stakeholder Management | Executing | False | "18"
As project manager managing project, You are in the process of finalizing all activities for the project, phase, or contract. Which of the following documents include information about Objectives of Scope, Quality and Cost and the criteria used to evaluate them? | Risk Register | Project Charter | Scope Management Plan | Final Report | As project manager managing project, You are in the process of finalizing all activities for the project, phase, or contract. Which of the following documents include information about Objectives of Scope, Quality and Cost and the criteria used to evaluate them? | Risk Register | Project Charter | Scope Management Plan | Final Report | Integration Management | Closing | False | "19"
As project manager managing project, in which of the following estimating technique that uses a statistical relationship between historical data and project parameters to calculate the activity duration? | Three-Point estimating | Bottom-up estimating | Top-down estimating | Parametric estimating | As project manager managing project, in which of the following estimating technique that uses a statistical relationship between historical data and project parameters to calculate the activity duration? | Three-Point estimating | Bottom-up estimating | Top-down estimating | Parametric estimating | Schedule Management | Planning | False | "19"
A project manager for a application development project has collected the work performance data and used the requirements documentation and requirements traceability matrix to generate the work performance information regarding variances in the project work compared to the baseline. What process is the project manager performing? | Validate Scope | Manage Quality | Direct and Manage Project Work | Control Scope | A project manager for a application development project has collected the work performance data and used the requirements documentation and requirements traceability matrix to generate the work performance information regarding variances in the project work compared to the baseline. What process is the project manager performing? | Validate Scope | Manage Quality | Direct and Manage Project Work | Control Scope | Scope Management | Monitoring and Controlling | False | "18"
Your project sponsor has specified that you have to consider the external limitations during the develop schedule process. This is an example of: | Assumptions | Regulations | Standards | Constraints | Your project sponsor has specified that you have to consider the external limitations during the develop schedule process. This is an example of: | Assumptions | Regulations | Standards | Constraints | Schedule Management | Planning | False | "20"
You are a project manager of a company and you are in the implementation phase. The commercial authorities sent a notice to the project manager to stop work. What should the project manager have done to avoid this? | Identified project risks | Defined a detailed scope of work. | Developed a detailed project management plan. | Identified stakeholders. | You are a project manager of a company and you are in the implementation phase. The commercial authorities sent a notice to the project manager to stop work. What should the project manager have done to avoid this? | Identified project risks | Defined a detailed scope of work. | Developed a detailed project management plan. | Identified stakeholders. | Stakeholder Management | Executing | False | "19"
A Project Manager is in the process of preparing a plan that documents how the procurement process will be managed: from developing procurement documents to contract closure. She is also going through project requirements and scope documents with the team and discussing different contract types to decide the one most suitable for the project. According to you, which process of procurement management is the Project Manager in? | Conduct Procurements | Control Procurements | Close Procurements | Plan Procurement Management | A Project Manager is in the process of preparing a plan that documents how the procurement process will be managed: from developing procurement documents to contract closure. She is also going through project requirements and scope documents with the team and discussing different contract types to decide the one most suitable for the project. According to you, which process of procurement management is the Project Manager in? | Conduct Procurements | Control Procurements | Close Procurements | Plan Procurement Management | Procurement Management | Planning | False | "20"
You are a project manager for a application design project. Which of the following data representation techniques that can be used in understanding and estimating the cost of quality for a process? | Logical data model | Matrix diagrams | Prioritization matrix | Process maps | You are a project manager for a application design project. Which of the following data representation techniques that can be used in understanding and estimating the cost of quality for a process? | Logical data model | Matrix diagrams | Prioritization matrix | Process maps | Quality Management | Planning | False | "20"
During the development phase of an IT implementation project, the client refuses to grant the project team access to their database. Since this is essential for configuration of the application, the project deliverables could be impacted. What should the project manager do next? | Discuss it with the project team and update the project schedule. | Review the project statement of work (SOW) | Log it in the risk register. | Update the issue log and meet with the client to review. | During the development phase of an IT implementation project, the client refuses to grant the project team access to their database. Since this is essential for configuration of the application, the project deliverables could be impacted. What should the project manager do next? | Discuss it with the project team and update the project schedule. | Review the project statement of work (SOW) | Log it in the risk register. | Update the issue log and meet with the client to review. | Stakeholder Management | Executing | False | "20"
A large construction project for a logistics company will require the expenditure of a large amount of capital. The finance group works with the project manager to project set limits when expenses will be incurred in a given project and to determine whether there are ways to smooth out or level the spending to avoid a single large expenditure in one quarter and none in the next. This is an example of: | Levelized Billing | A financial review | Rescheduling | Funding Limit Reconciliation | A large construction project for a logistics company will require the expenditure of a large amount of capital. The finance group works with the project manager to project set limits when expenses will be incurred in a given project and to determine whether there are ways to smooth out or level the spending to avoid a single large expenditure in one quarter and none in the next. This is an example of: | Levelized Billing | A financial review | Rescheduling | Funding Limit Reconciliation | Cost Management | Planning | False | "20"
Calculation of late finish dates and late start dates for the uncompleted portion of the project is called. | Schedule compression | An arrow diagram | A forward pass | A backward pass | Calculation of late finish dates and late start dates for the uncompleted portion of the project is called. | Schedule compression | An arrow diagram | A forward pass | A backward pass | Schedule Management | Planning | False | "19"
While rating a proposal, one of the requirements was: "The proposed project manager needs to be a certified Project Management Professional, PMP?" This is an example of: | Constraints | Assumptions | Good practice | Source Selection Criteria | While rating a proposal, one of the requirements was: "The proposed project manager needs to be a certified Project Management Professional, PMP?" This is an example of: | Constraints | Assumptions | Good practice | Source Selection Criteria | Procurement Management | Planning | False | "19"
A decision tree is a Perform Quantitative Risk Analysis technique. A decision tree is represented by a Decision Tree Diagram. The decision tree describes a situation under consideration, the implications of each of the available choices, and the possible scenarios. A Decision Tree Diagram shows how to make a decision among alternative capital strategies known as: | Alternative nodes | Question points | Checkpoints | Decision nodes | A decision tree is a Perform Quantitative Risk Analysis technique. A decision tree is represented by a Decision Tree Diagram. The decision tree describes a situation under consideration, the implications of each of the available choices, and the possible scenarios. A Decision Tree Diagram shows how to make a decision among alternative capital strategies known as: | Alternative nodes | Question points | Checkpoints | Decision nodes | Risk Management | Planning | False | "20"
Which of the following processes deals with maintaining the integrity of baselines by releasing only approved changes for incorporation into the project management plan? | Direct and Manage Project Work | Develop Project Management Plan | Monitor and Control Project Work | Perform Integrated Change Control | Which of the following processes deals with maintaining the integrity of baselines by releasing only approved changes for incorporation into the project management plan? | Direct and Manage Project Work | Develop Project Management Plan | Monitor and Control Project Work | Perform Integrated Change Control | Integration Management | Monitoring and Controlling | False | "19"
During the execution phase, the project owner left the project and a new sponsor has been assigned. What should you do next? | Update RACI Chart | Update the Project Management Plan | Update Stakeholder Engagement Plan | Update the stakeholder register | During the execution phase, the project owner left the project and a new sponsor has been assigned. What should you do next? | Update RACI Chart | Update the Project Management Plan | Update Stakeholder Engagement Plan | Update the stakeholder register | Stakeholder Management | Executing | False | "16"
In projects where there is a gap between the real business requirements and the stated business requirements, agile methods are extremely helpful. Agile methods provide a solution to this problem by: | Completing the project quickly so that gap is significantly reduced. | Replacing the project manager with a Scrum master in order to ex the project. | Eliminating the documentation altogether from the project manage approach. | Purposefully building and reviewing prototypes and release version refine requirements. | In projects where there is a gap between the real business requirements and the stated business requirements, agile methods are extremely helpful. Agile methods provide a solution to this problem by: | Completing the project quickly so that gap is significantly reduced. | Replacing the project manager with a Scrum master in order to ex the project. | Eliminating the documentation altogether from the project manage approach. | Purposefully building and reviewing prototypes and release version refine requirements. | Scope Management | Planning | False | "20"
Ahmad is the project manager for a shopping mall construction project which is in its fourth month of execution. According to the project contract, Ahmad can only issue project invoices when the project is 25%, 50%, 75% and 100% complete in terms of the approved project schedule. Recently the 25% milestone has been reached and Ahmad is ready to issue his first invoice. According to the contract, the project must be completed in 12 months. What is the project?s SPI? | 0.25 | 0.33 | 1.33 | 0.75 | Ahmad is the project manager for a shopping mall construction project which is in its fourth month of execution. According to the project contract, Ahmad can only issue project invoices when the project is 25%, 50%, 75% and 100% complete in terms of the approved project schedule. Recently the 25% milestone has been reached and Ahmad is ready to issue his first invoice. According to the contract, the project must be completed in 12 months. What is the project?s SPI? | 0.25 | 0.33 | 1.33 | 0.75 | Schedule Management | Monitoring and Controlling | False | "20"
Visiting a construction site to ensure the completed work is the same work specified in the requirements is: | Milestone | Variance Analysis | Requirements traceability | Scope validation | Visiting a construction site to ensure the completed work is the same work specified in the requirements is: | Milestone | Variance Analysis | Requirements traceability | Scope validation | Scope Management | Monitoring and Controlling | False | "20"
While reviewing project procurement and accounting records for your project, you discover there is a pattern of unauthorized expenses by a specific resource. These expenses are not within the scope of the project and were somewhat camouflaged within a number of large and complicated expense reports. What do you do? | If the total expenses are less than 1% of the project budget do nothing | Fire the resource | Confront the resource | Notify the appropriate management immediately | While reviewing project procurement and accounting records for your project, you discover there is a pattern of unauthorized expenses by a specific resource. These expenses are not within the scope of the project and were somewhat camouflaged within a number of large and complicated expense reports. What do you do? | If the total expenses are less than 1% of the project budget do nothing | Fire the resource | Confront the resource | Notify the appropriate management immediately | Procurement Management | Monitoring and Controlling | False | "20"
A project to design and build a new building is canceled after the project has been underway for some time. What process is employed to document what work was done and to what extent it was completed? | Validate Scope | Control Scope | Control Quality | Close Project or Phase | A project to design and build a new building is canceled after the project has been underway for some time. What process is employed to document what work was done and to what extent it was completed? | Validate Scope | Control Scope | Control Quality | Close Project or Phase | Integration Management | Closing | False | "20"
During the initiation phase, the project manager classifying a list of project stakeholders and discovers an interested stakeholder with certain authority. How should the project manager manage this stakeholder? | Keep satisfied | Manage Closely | Monitor | Keep informed | During the initiation phase, the project manager classifying a list of project stakeholders and discovers an interested stakeholder with certain authority. How should the project manager manage this stakeholder? | Keep satisfied | Manage Closely | Monitor | Keep informed | Stakeholder Management | Executing | False | "20"
A Work Breakdown Structure is a hierarchical illustration of all the work to be done in a project. A WBS component does not represent: | Products | Results | Services | Project activities | A Work Breakdown Structure is a hierarchical illustration of all the work to be done in a project. A WBS component does not represent: | Products | Results | Services | Project activities | Scope Management | Planning | False | "19"
Which of the following is not a Risk Diagramming technique? | Influence diagrams | Decision trees | Tornado diagram | Control charts | Which of the following is not a Risk Diagramming technique? | Influence diagrams | Decision trees | Tornado diagram | Control charts | Risk Management | Planning | False | "19"
The Cost of Quality principle includes: | The costs involved when changes are made to the requirements | The cost of deploying a project Configuration Management System | The costs associated with eliminating requirements | The costs of ensuring conformance to requirements | The Cost of Quality principle includes: | The costs involved when changes are made to the requirements | The cost of deploying a project Configuration Management System | The costs associated with eliminating requirements | The costs of ensuring conformance to requirements | Cost Management | Planning | False | "19"
You are in the middle of a risk assessment meeting with key stakeholders, customers and project team leaders. While identifying and assessing risks, you realize that two key stakeholders are overemphasizing the impact of a risk. What is the best step to take to avoid unfairness or bias when assessing risks? | Implement assumptions analysis to explore the validity of assumptions. | Develop a risk response strategy to eliminate threats. | Perform sensitivity analysis to establish which risks have the most impact on the project. | Engage a neutral facilitator to support the Perform Qualitative Risk Analysis process. | You are in the middle of a risk assessment meeting with key stakeholders, customers and project team leaders. While identifying and assessing risks, you realize that two key stakeholders are overemphasizing the impact of a risk. What is the best step to take to avoid unfairness or bias when assessing risks? | Implement assumptions analysis to explore the validity of assumptions. | Develop a risk response strategy to eliminate threats. | Perform sensitivity analysis to establish which risks have the most impact on the project. | Engage a neutral facilitator to support the Perform Qualitative Risk Analysis process. | Risk Management | Planning | False | "20"
You are working on a complex project which involves multiple team members and sponsors. As a project manager, what should you do before obtaining the project approval and buy-in? | Meet with the stakeholders | Perform a Qualitative and Quantitative risk analysis | Conduct Sensitivity analysis | Complete a stakeholder analysis | You are working on a complex project which involves multiple team members and sponsors. As a project manager, what should you do before obtaining the project approval and buy-in? | Meet with the stakeholders | Perform a Qualitative and Quantitative risk analysis | Conduct Sensitivity analysis | Complete a stakeholder analysis | Stakeholder Management | Initiating | False | "20"
Jared is in the execution phase of a residential housing construction project. He has been informed of major scope changes from stakeholders in the middle of the project. These changes involve regulatory requirements from local authorities that may affect not only the scope but also the cost and duration of the project. What is the first step that Jared should take in considering these changes? | Meet with the change control board to solicit some ideas on the new project plan | Add new tasks to the project plan and assign resources to account for regulatory changes | Escalate the scope changes to the sponsor and steering committee for their decision | Create a report detailing the impact of scope changes on project parameters such as cost, quality, and schedule | Jared is in the execution phase of a residential housing construction project. He has been informed of major scope changes from stakeholders in the middle of the project. These changes involve regulatory requirements from local authorities that may affect not only the scope but also the cost and duration of the project. What is the first step that Jared should take in considering these changes? | Meet with the change control board to solicit some ideas on the new project plan | Add new tasks to the project plan and assign resources to account for regulatory changes | Escalate the scope changes to the sponsor and steering committee for their decision | Create a report detailing the impact of scope changes on project parameters such as cost, quality, and schedule | Integration Management | Monitoring and Controlling | False | "19"
Jane is worried about her project because many of her tasks are moving slowly, and two critical tasks may slip. She conducts a thorough resource analysis and finds out that there are five people who will be free next week. She would like to assign those people to finish her tasks early and prevent the project completion date from slipping. This is an example of: | Management reserves | Resource leveling | Fast tracking | Crashing | Jane is worried about her project because many of her tasks are moving slowly, and two critical tasks may slip. She conducts a thorough resource analysis and finds out that there are five people who will be free next week. She would like to assign those people to finish her tasks early and prevent the project completion date from slipping. This is an example of: | Management reserves | Resource leveling | Fast tracking | Crashing | Schedule Management | Planning | False | "20"
You have overheard two functional managers arguing about the impacts that your project will have on their departments. What is your best response? | Do nothing | Inform the managers that the project sponsors already consider impact when they decided to implement the project | Put in advance requests for resources from each department | Analyze and report to each manager the impact your project will have on their departments in terms of time and resources required and the enterprise priority of your project. | You have overheard two functional managers arguing about the impacts that your project will have on their departments. What is your best response? | Do nothing | Inform the managers that the project sponsors already consider impact when they decided to implement the project | Put in advance requests for resources from each department | Analyze and report to each manager the impact your project will have on their departments in terms of time and resources required and the enterprise priority of your project. | Stakeholder Management | Executing | False | "18"
The Manage Stakeholder Engagement process is a very important project management process. An ineffective effort in this process can sabotage the whole project. Which of the following is the key benefit of this process? | It makes the Manage Communications process redundant. | It produces the stakeholder engagement plan. | Lessons learned are documented during this process. | It increases support and minimizes resistance from stakeholders. | The Manage Stakeholder Engagement process is a very important project management process. An ineffective effort in this process can sabotage the whole project. Which of the following is the key benefit of this process? | It makes the Manage Communications process redundant. | It produces the stakeholder engagement plan. | Lessons learned are documented during this process. | It increases support and minimizes resistance from stakeholders. | Stakeholder Management | Executing | False | "19"
Andrew is managing a construction project. He is using his communication, interpersonal and management skills to keep the key project stakeholders engaged with the project. Which of the following activities is not related to the Manage Stakeholder Engagement process? | Addressing and resolving issues | Confirming the stakeholders' continued commitment | Negotiating and communicating with the stakeholders | Developing the stakeholder engagement plan | Andrew is managing a construction project. He is using his communication, interpersonal and management skills to keep the key project stakeholders engaged with the project. Which of the following activities is not related to the Manage Stakeholder Engagement process? | Addressing and resolving issues | Confirming the stakeholders' continued commitment | Negotiating and communicating with the stakeholders | Developing the stakeholder engagement plan | Stakeholder Management | Executing | False | "20"
Changes in projects are inevitable. Therefore, project managers must develop or use a system to manage and control changes. There are four types of changes that need to be controlled in a project: Project changes, deliverable changes, process changes, and baseline changes. The impact of each of these changes must be evaluated, and approved or rejected changes must be communicated to all stakeholders, as and when required. Which of the following helps control these changes? | Configuration control and Control chart | Control chart and Cost control | Change control and Control chart | Configuration control and Change control | Changes in projects are inevitable. Therefore, project managers must develop or use a system to manage and control changes. There are four types of changes that need to be controlled in a project: Project changes, deliverable changes, process changes, and baseline changes. The impact of each of these changes must be evaluated, and approved or rejected changes must be communicated to all stakeholders, as and when required. Which of the following helps control these changes? | Configuration control and Control chart | Control chart and Cost control | Change control and Control chart | Configuration control and Change control | Integration Management | Monitoring and Controlling | False | "20"
You are working on a waste management project that, upon completion, will be turned over to the local municipality for steady-state operation. Parking of trucks and other vehicles has become a serious problem because no parking area was allotted to you on the main dumping site. As a result, your trucks are parked on nearby roadsides. One of the fleet supervisors informs you that close to the main site, there is a large tract of land a local charity owns. Many locals park their cars on this tract of land. What should you do? | Since the piece of land is already used as parking, you can park your trucks over there. | Don?t park the trucks on that piece of land because it will be a violation of other?s property rights. | Check the local parking laws. | Ask the supervisor to get contact information of the local charity. | You are working on a waste management project that, upon completion, will be turned over to the local municipality for steady-state operation. Parking of trucks and other vehicles has become a serious problem because no parking area was allotted to you on the main dumping site. As a result, your trucks are parked on nearby roadsides. One of the fleet supervisors informs you that close to the main site, there is a large tract of land a local charity owns. Many locals park their cars on this tract of land. What should you do? | Since the piece of land is already used as parking, you can park your trucks over there. | Don?t park the trucks on that piece of land because it will be a violation of other?s property rights. | Check the local parking laws. | Ask the supervisor to get contact information of the local charity. | Stakeholder Management | Executing | False | "17"
The customer requests a change to the project that would increase the project risk. Which of the following should you do first? | Talk to the customer about the impact of the change | Change the risk management plan | Include the expected monetary value of the risk in the new cost estimate | Analyze the change?s impact of the change with the team | The customer requests a change to the project that would increase the project risk. Which of the following should you do first? | Talk to the customer about the impact of the change | Change the risk management plan | Include the expected monetary value of the risk in the new cost estimate | Analyze the change?s impact of the change with the team | Integration Management | Monitoring and Controlling | False | "19"
After stakeholders in a company's sales department examined all the deliverables, they state that there has been a change in the company strategy. Therefore, important changes must be made to the requirements. The project manager believes that these changes make the deliverables unstable. What should the project manager do? | Evaluate and incorporate the changes to the project management plan to start executing them. | Request the details about the new requirements. evaluate them with the project team. and recommend whether to continue or close the project. | Evaluate the impact on the project. coordinate with the sponsor and close the project. | Request that the stakeholders specify the new requirements and present them to the change control board (CCB). | . | . | . | . | . | Scope Management | Monitoring and Controlling | False | "18"
Task B is dependent upon task A which is delayed. Resource for task B have limited availability and you must begin task B on time. What should the you do to replan the schedule so that the deadline not changed? | Fast track task A and move task B's start date. | Fast track task B and immediately begin work. | Replan task B start date so it begins after the completion of task A | Crash task A and start task B at the planned time. | . | . | . | . | . | Schedule Management | Planning | False | "16"
A project manager needs to communicate the start of the project, key milestones, and other relevant information to stakeholders, and then gain their commitment. What should the project manager do? | Review and assess detailed project requirements, constraints, and assumptions with stakeholders. | Develop the project charter | Develop the communication management plan. | Conduct a kick-off meeting. | . | . | . | . | . | Integration Management | Planning | False | "18"
A contractor is currently constructing a new building for your organization on a cost-plus-incentive contract. You just received the project status report from the contractor’s project manager. According to the report, the project’s CPI is 1.5. You are shocked because you believe the project costs are out of control. Upon investigation, you learn the $1 million advance payment (20 percent of the estimated project cost) given to the contractor at the start of the project was included in the project’s earned value. Further, the cost of the inventory at the project site was excluded from the total actual costs. According to the contract, your company reimburses only the costs for the completed deliverables and not for the supplies in the project’s inventory. In this scenario, the reported project’s CPI is incorrect because: | Actual cost is understated | Earned value is overstated, and actual cost is understated | Both the earned value and the actual cost are overstated | Earned value is overstated. | . | . | . | . | . | Cost Management | Monitoring and Controlling | False | "20"
A project to develop a new product contains many stakeholders who are trying to influence the project but have conflicting interests. The project manager has just completed the project charter and is working on the project management plan, which only gives a high-level view of both the product specifications and the project scope. What should the project manager do next to build a detailed scope description? | List all concerns in the stakeholder engagement plan | Create the work breakdown structure. WBS | Develop the scope statement with stakeholder input. | Implement the plan scope management process. | . | . | . | . | . | Scope Management | Planning | False | "19"
You have managed a federal highway construction project, which is intended to improve transportation between north and south regions of the country. In the execution phase, you received many complaints from stakeholders, including the highway transportation agency. At least half these complaints were regarding the quality of the micro texture of the road, and the nonconformance to the quality levels incorporated in the project quality management plan. So far, you have successfully fixed all the reported issues, but you are concerned by this recurrent event. What should you do to avoid future similar issues? | Initiate a defect repair to repair the road or completely pave a new road | Initiate a change request to update the project quality management plan | Initiate a corrective action to bring the future quality of the road in line with the project management plan | Initiate a preventive action to reduce the probability of negative consequences associated with the poor quality of the road | . | . | . | . | . | Integration Management | Executing | False | "20"
There is a heavy demand for new houses in your city's expensive neighborhood. RECON, a construction company, has employed you as a project manager to assess the benefit of building new energy-efficient houses in that neighborhood, even though it takes more expensive technology to build such houses. You have started gathering data to perform a detailed payback analysis to submit a report to your management. Since the full financial impact of building energy-efficient houses is difficult to estimate, you would like to prepare a rough cost benefit analysis and include it with the report. Which of the following describes the effort you are undertaking in this scenario? | You are developing a cost management plan to provide as an input to the Estimate Costs process. | You are developing a risk management plan to provide as an input to the Perform Quantitative Risk Analysis process. | You are developing a cost-benefit analysis to provide as an input to the Plan Risk Management process. | You are developing a business case to provide as an input to the Develop Project Charter process. | . | . | . | . | . | Integration Management | Initiating | False | "20"
A project is behind schedule and over budget. As a result of increased stakeholder pressure, the project team has been placed under serious pressure. This causes a conflict between the quality and production managers, with each blaming the other for the delay and cost overruns. What should the project manager do? | Meet with both managers, and ask them to immediately end the conflict to avoid negatively impacting the project. | Meet with the managers' supervisors to discuss possible actions. | Discuss the situation with the stakeholders, and follow their suggestions for dealing with the conflict. | Refer to the team charter for guidelines on how to deal with this conflict. | . | . | . | . | . | Resources Management | Executing | False | "16"
You have been recently assigned as a project manager in a big infrastructure project. A strike by local workers occurs due to the lateness workers' payments. That leads to delays in a major component delivery. What is the process the project manager could have been done differently to prevent this type of situation? | Monitor Risk | Identify Stakeholder | Control Scope | Develop Schedule | . | . | . | . | . | Schedule Management | Planning | False | "20"
As you project manager, you have submitted the cost baseline to the sponsor. After a review, the sponsor tells you that the amount you have estimated for a certain month is more than the funds the sponsor can disburse you for that month. What do you think the sponsor will advise you to do next? | To remove some of the work scope for that month | To motivate the project team to do the work of that month without being fully paid for it | To reduce the cost estimates of the activities for that month | To reschedule the work of that month | . | . | . | . | . | Cost Management | Monitoring and Controlling | False | "19"
You have been asked to provide Cost estimates for a project which would be responsible for the complete plumber installation in building. As a project manager, you have had past experience in similar projects in your previous organization. The organization you have joined also has recently done a similar project. There is an urgency in providing the estimate as mandated by executive management. What estimation technique would you adopt? | Use Bottom-up Estimating | Use Parametric Estimating technique | Ask your previous organization for the estimates | Use Analogous Estimating | . | . | . | . | . | Cost Management | Planning | False | "19"
A project has been initiated that has several project stakeholders from various departments. Some stakeholders are unavailable for the facilitation meeting to discuss end-to-end processes. To satisfy their own personal agenda, the project owner requests that the meeting take place without all stakeholder's present. What should the project manager do? | Discuss stakeholder availability with the sponsor. | Hold a separate meeting with those stakeholders who are unavailable. | Reschedule the meeting to accommodate all stakeholders. | Set up a facilitation meeting without all stakeholders to obtain initial requirements. | . | . | . | . | . | Stakeholder Management | Initiating | False | "19"
Ali is in the execution phase of his project. He is getting unexpected requests from his stakeholders about the project’s progress. Ali can use all the following to respond to their requests except: | Communications management plan | Organizational process assets | Work performance reports | Business case | . | . | . | . | . | Communication Management | Executing | False | "18"
You are working for a large project organization with several project managers working on 15 projects. All project managers submit their status reports at month’s end. One of your fellow project managers, Jane, has reported an error in the past two months. From discussions with one of her project’s team members who is also working on one of your projects, you realize Jane is deliberately misreporting the project’s status to inflate her performance for the annual performance appraisal next month. The month end review meeting is in two days, and you are preparing your own presentation for it. What should you say about her status report? | Since there is no direct relationship between your project and hers, there is no need to intervene in this issue. | Prepare a brief of what you have discussed with her team member and report the inconsistency in the meeting. | Send an email to her boss asking to check the contents of her report. | Investigate and verify the blame before reporting the incorrect status to the appropriate management. | . | . | . | . | . | Integration Management | Monitoring and Controlling | False | "20"

## Sheet1
140 | Integration Management
141 | Scope Management
142 | Schedule Management
143 | Cost Management
144 | Quality Management
145 | Resources Management
146 | Communication Management
147 | Risk Management
148 | Procurement Management
149 | Stakeholder Management
2;"Initiating";"2019-04-30 15:27:33";"2019-04-30 15:27:33"
3;"Planning";"2019-04-30 15:27:40";"2019-04-30 15:27:40"
4;"Executing";"2019-04-30 15:27:46";"2019-04-30 15:27:46"
5;"Monitoring and Controlling";"2019-04-30 15:27:52";"2019-04-30 15:27:52"
6;"Closing";"2019-04-30 15:27:59";"2019-04-30 15:27:59"